## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [6 empty] | Document # ITP-026
Revision : 1
Client: |  | Wyndham City Council |  | Construction Process: | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | K Rd |  | GR Shelter | Name: | Jarvis Gleeson | Name: |  |  | Name:
Contract No: |  | N400378 |  | Specifications:
|  |  |  | Structure / Component: | Signed : | J.GLEESON | Signed : |  |  | Signed :
|  |  |  | Location: | Date : | 2024-11-08 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | Date
1.1 | Pre-Construction Site Preparation |  | Prior to Excavation | Site cleared, leveled, and marked; utilities checked to avoid conflicts | Confirm site setup and marking before foundation work begins. | Signed ITP | IP | Site Engineer | N/A
1.2 | Foundation Excavation |  | During Excavation | Excavation follows design dimensions for depth and width, with stable trench walls. | Inspect excavation before formwork and reinforcement. | Signed ITP | IP | Site Engineer | N/A
1.3 | Formwork and Reinforcement Placement |  | During Excavation | Formwork set to correct dimensions and alignment; reinforcement placed per design with correct spacings. | Verify formwork and reinforcement placement before concrete pour. | Signed ITP | IP | Building Surveyor
1.4 | Concrete Pouring and and Compaction |  | During Excavation | Concrete mix complies with specifications; poured and compacted without air pockets. | Check concrete pour and compaction during placement. | Signed ITP | IP | Site Engineer | N/A
1.5 | Shelter Column and Beam Installation |  | During Excavation | Columns and beams installed to design specifications; securely fixed withh appropriate connections. | Inspect connections and alignment before proceeding with roofing. | Signed ITP | IP | Site Engineer | N/A
1.6 | Roofing Installation |  | During Excavation | Roofing material installed per design; all fastenings secure, with water drainage measures in place. | Check roofing installation and drainage setup. | Signed ITP | IP | Site Engineer | N/A
1.7 | Finishing and Surface Protection |  | During Excavation | Apply protective coatings to steel/timber as specified; ensure all surfaces are weather-protected. | Verify surface finishes before final inspection. | Signed ITP | IP | Site Engineer | N/A
1.8 | Final Inspection and Safety Check |  | Post Excavation | Conduct a final inspection to ensure structural stability and compliance; check for safety hazards. | Complete safety inspection before site handover. | Signed ITP | IP | Building Surveyor
COMMENTS |  | _______________________________________________________________________________________________________________________________________________________________________________________ _______________________________________________________________________________________________________________________________________________________________________________________
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: | [5 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent