## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 1.15 - Civil - Kerb & Channel | itp |  |  |  |  | 1.15 - Civil - Kerb & Channel
section | Kerb & Channel
checkpoint | 1.1 - Pre-Construction Site Preperation
label | FREQUENCY - Prior to Construction
label | ACCEPTANCE CRITERIA - Site cleared and graded as per design; kerb line marked, and utilities identified to avoid conflicts.
label | INSPECTION / TEST METHOD - Confrim site setup and markings before formwork installation
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.2 - Formwork Installation
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Formwork set to specified alignment and profile, with correct height and level, secure and free of movement
label | INSPECTION / TEST METHOD - Inspect formwork for stability and alignment before reinforcement.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.3 - Reinforcement Placement
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Reinforcement placed as per design, with correct cover, spacing, and securely fixed in position.
label | INSPECTION / TEST METHOD - Verify reinforcement placement before concrete pour.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.4 - Concrete Mixing and Delivery
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Concrete mix complies with design specifications (e.g., strength, slump, and mix ratio); verify batching records.
label | INSPECTION / TEST METHOD - Check concrete mix quality upon delivery.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.5 - Concrete Pouring and Compaction
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Concrete poured continuously and compacted to avoid air pockets; proper finish achieved on kerb face.
label | INSPECTION / TEST METHOD - Inspect pour for consistent compaction and surface finish.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.6 - Surface Finishing
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Kerb surface finished to specified texture and profile; edges clean and sharp as per design.
label | INSPECTION / TEST METHOD - Verify surface finish before initial curing.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.7 - Curing Application
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Apply curing compound or cover with moist material; ensure curing process follows project specifications.
label | INSPECTION / TEST METHOD - Inspect curing method and ensure it is maintained for the specified period.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.8 - Expansion and Control Joints
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Expansion and control joints installed at specified intervals and filled as per design.
label | INSPECTION / TEST METHOD - Check joint placement and filling before final inspection.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.9 - Final inspection and Tolerance Check
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Verify kerb alignment, elevation, and surface finish against design tolerances; no visible cracks or defects.
label | INSPECTION / TEST METHOD - Final inspection before project sign off.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | 1.22 - Civil - General Paving | itp |  |  |  |  | 1.22 - Civil - General Paving
section | Construction Works
checkpoint | Pre-Construction Site Preparation
label | FREQUENCY - Prior to Construction
label | ACCEPTANCE CRITERIA - Site cleared, graded, and free from debris; utilities marked to avoid conflicts; area prepared as per design.
label | INSPECTION / TEST METHOD - Confirm site setup and grading complete before formwork installation.
label | RECORD OF CONFORMITY - Signed ITP
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Formwork Installation
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Formwork set to correct alignment and elevation, secured, and checked for stability.
label | INSPECTION / TEST METHOD - Inspect formwork for stability and dimension before reinforcement.
label | RECORD OF CONFORMITY - Signed ITP
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Reinforcement Placement
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Reinforcement placed per design specifications, with correct cover, spacing, and securely fixed in place.
label | INSPECTION / TEST METHOD - Verify reinforcement placement before concrete pour.
label | RECORD OF CONFORMITY - Signed ITP
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Concrete Mix Verification
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Concrete mix complies with design specifications for strenght, slump, and mix ratio. Batch records verified.
label | INSPECTION / TEST METHOD - Inspect concrete mix and batch record upon delivery.
label | RECORD OF CONFORMITY - Signed ITP
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Concrete Pouring and Compaction
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Concrete poured in sections and compacted to avoid air pockets and achieve uniform density.
label | INSPECTION / TEST METHOD - Check compaction and placement during pour.
label | RECORD OF CONFORMITY - Signed ITP
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Surface finishing
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Finish applied as specified (e.g., broomed or troweled); edges cleaned and straight.
label | INSPECTION / TEST METHOD - Inspect surface finish before curing.
label | RECORD OF CONFORMITY - Signed ITP
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Curing Application
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Curing applied (e.g., curing compound or covering) per specification, and maintained for the required period.
label | INSPECTION / TEST METHOD - Check curing application and maintenance for specified period.
label | RECORD OF CONFORMITY - Signed ITP
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Joint Placement and Sealing
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Expansion and control joints placed at specified intervals; joints cleaned and sealed per design.
label | INSPECTION / TEST METHOD - Verify joint placement and sealing before final inspection.
label | RECORD OF CONFORMITY - Signed ITP
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection and Tolerance Check
label | FREQUENCY - Post Construction
label | ACCEPTANCE CRITERIA - Confirm alignment, elevation, surface smoothness, and joint placement within design tolerances; no visible cracks or defects.
label | INSPECTION / TEST METHOD - Conduct final inspection before project sign-off.
label | RECORD OF CONFORMITY - Signed ITP
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | 1.26 - Landscape - Decking | itp |  |  |  |  | 1.26 - Landscape - Decking
section | Decking
checkpoint | 1.1 - Pre-Construction Site Preperation
label | FREQUENCY - Prior To Construction
label | ACCEPTANCE CRITERIA - Site is cleared, pile locations are marked, and access for materials and equipmet is confirmed.
label | INSPECTION / TEST METHOD - Confirm all setup tasks are completed before pile installation.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.2 - Pile Installation
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Proprietary piles installed to specific depths and load ratings.
label | INSPECTION / TEST METHOD - Inspect piles for correct installation depth and load bearing capacity.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Building Surveyor
date | Date Completed:
checkpoint | 1.3 - Verification of Pile Load Capacity
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Piles meet load capacities of 100 kN or 200 kN as specified.
label | INSPECTION / TEST METHOD - Testing required before further assembly
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.4 - Beam and Frame Placement
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Position beam and frames according to layout in S010 and S011; confirm alignment and level.
label | INSPECTION / TEST METHOD - Verify alignment and secure placement of primary beams before fising
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.5 - Sub Floor Inspection
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Sub floor area is free of debris, properly leveled and complies with with design tolerances and specifications.
label | INSPECTION / TEST METHOD - Confirm sub floor condition before continueing with flooring
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Building Surveyor
date | Date Completed:
checkpoint | 1.6 - Connection Assembly
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Connections use specified bolts and welds (e.g., 6CFW); Alignment meets drawings on S020 and S021.
label | INSPECTION / TEST METHOD - Inspect each connection for compliance with spacing and alignment.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.7 - Decking Installation
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Install decking panels securely with no gaps or misalignment; confirm all dimentions per design.
label | INSPECTION / TEST METHOD - Final check of decking placement before apllying finishes.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.8 - Balustrate and Handrail Installation.
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Balustrate and handrails installed per design specifications; stanchion spacing does not exceed 2500mm.
label | INSPECTION / TEST METHOD - Verify spacing and stability of balustrate and handrails.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.9 - Welding and Structural Integrity Check
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Welds inspected per design and safety standards; no signs of defects (e.g cracks, undercuts).
label | INSPECTION / TEST METHOD - Welding inspection required before load application.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.10 - Finishing and Surface Protection
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Apply protective coatings and finishes; ensure decking and handrails are sealed as per specifications.
label | INSPECTION / TEST METHOD - Check final finished before handover.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.11 - Final Inspection and Load Testing
label | FREQUENCY - Post Construction
label | ACCEPTANCE CRITERIA - Complete a final inspection and load testing to confirm structural integrity and design compliance.
label | INSPECTION / TEST METHOD - Final load test and safety checks required before comissioning.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Building Surveyor
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | 1.30 - Landscape - Boardwalk | itp |  |  |  |  | 1.30 - Landscape - Boardwalk
section | Boardwalk
checkpoint | 1.1 - Pre-Construction Site Preperation
label | FREQUENCY - Prior To Construction
label | ACCEPTANCE CRITERIA - Site is cleared, pile locations are marked, and access for materials and equipmet is confirmed.
label | INSPECTION / TEST METHOD - Confirm all setup tasks are completed before pile installation.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.2 - Pile Installation
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Proprietary piles installed to specific depths and load ratings.
label | INSPECTION / TEST METHOD - Inspect piles for correct installation depth and load bearing capacity.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Building Surveyor
date | Date Completed:
checkpoint | 1.3 - Verification of Pile Load Capacity
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Piles meet load capacities as specified for the boardwalk structure.
label | INSPECTION / TEST METHOD - Testing required before Structural assembly of the boardwalk begins.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.4 - Beam and Frame Placement
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Position beam and frames according to layout in S010 and S011; confirm alignment and level.
label | INSPECTION / TEST METHOD - Verify alignment and secure placement of primary beams before fising
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.5 - Sub Floor Inspection
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Sub floor area is free of debris, properly leveled and complies with with design tolerances and specifications.
label | INSPECTION / TEST METHOD - Confirm sub floor condition before continueing with flooring
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Building Surveyor
date | Date Completed:
checkpoint | 1.6 - Connection Assembly
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Connections use specified bolts and welds (e.g., 6CFW); Alignment meets drawings on S020 and S021.
label | INSPECTION / TEST METHOD - Inspect each connection for compliance with spacing and alignment.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.7 - Installation of Decking and Treads
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Decking and treads installed securely with no gaps; match dimensions and alignment per design.
label | INSPECTION / TEST METHOD - Final check of decking and tread placement before apllying finishes.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.8 - Balustrate and Handrail Installation.
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Balustrate and handrails installed per design specifications; stanchion spacing does not exceed 2500mm.
label | INSPECTION / TEST METHOD - Verify spacing and stability of balustrate and handrails.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.9 - Welding and Structural Integrity Check
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Welds inspected per design and safety standards; no signs of defects (e.g cracks, undercuts).
label | INSPECTION / TEST METHOD - Welding inspection required before load application.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.10 - Finishing and Surface Protection
label | FREQUENCY - During Construction
label | ACCEPTANCE CRITERIA - Apply protective coatings and finishes; ensure decking and handrails are sealed as per specifications.
label | INSPECTION / TEST METHOD - Check final finished before handover.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.11 - Final Inspection and Load Testing
label | FREQUENCY - Post Construction
label | ACCEPTANCE CRITERIA - Complete a final inspection and load testing to confirm structural integrity and design compliance.
label | INSPECTION / TEST METHOD - Final load test and safety checks required before comissioning.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Building Surveyor
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | 1.31 - Landscape - Shelter | itp |  |  |  |  | 1.31 - Landscape - Shelter
section | Shelter
checkpoint | 1.1 - Pre-Construction Site Preparation
label | FREQUENCY - Prior to Excavation
label | ACCEPTANCE CRITERIA - Site cleared, leveled, and marked; utilities checked to avoid conflicts
label | INSPECTION / TEST METHOD - Confirm site setup and marking before foundation work begins.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.2 - Foundation Excavation
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - Excavation follows design dimensions for depth and width, with stable trench walls.
label | INSPECTION / TEST METHOD - Inspect excavation before formwork and reinforcement.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.3 - Formwork and Reinforcement Placement
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - Formwork set to correct dimensions and alignment; reinforcement placed per design with correct spacings.
label | INSPECTION / TEST METHOD - Verify formwork and reinforcement placement before concrete pour.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Building Surveyor
date | Date Completed:
checkpoint | 1.4 - Concrete Pouring and and Compaction
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - Concrete mix complies with specifications; poured and compacted without air pockets.
label | INSPECTION / TEST METHOD - Check concrete pour and compaction during placement.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.5 - Shelter Column and Beam Installation
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - Columns and beams installed to design specifications; securely fixed withh appropriate connections.
label | INSPECTION / TEST METHOD - Inspect connections and alignment before proceeding with roofing.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.6 - Roofing Installation
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - Roofing material installed per design; all fastenings secure, with water drainage measures in place.
label | INSPECTION / TEST METHOD - Check roofing installation and drainage setup.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.7 - Finishing and Surface Protection
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - Apply protective coatings to steel/timber as specified; ensure all surfaces are weather-protected.
label | INSPECTION / TEST METHOD - Verify surface finishes before final inspection.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.8 - Final Inspection and Safety Check
label | FREQUENCY - Post Excavation
label | ACCEPTANCE CRITERIA - Conduct a final inspection to ensure structural stability and compliance; check for safety hazards.
label | INSPECTION / TEST METHOD - Complete safety inspection before site handover.
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Building Surveyor
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP