## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Accessways | itp |  |  |  |  | ITP - Accessways
section | Preconstruction
checkpoint | Design
label | Issued For Construction Drawings:
label | MSF-EN-CIV-DRG-510
label | MSF-EN-CIV-DRG-511
label | MSF-EN-CIV-DRG-512
label | MSF-EN-CIV-DRG-590
label | KDC EES2011
checkpoint | Survey & Setout
label | Issued For Construction Drawings
label | KDC EES2011
section | Material Procurement
checkpoint | Granular Fill Material for subgrade improvement (If Required)
label | Issued For Construction Drawings
label | Delivery Dockets if Imported Granular Fill from Offsite is Used
label | Photos if sourced from Onsite Quarry or Delivery Dockets if Sourced Offsite
checkpoint | Drainage Pipe
label | IFC Drawings
label | Manufacturers Specifications
label | KDC EES2011
label | Delivery Dockets
label | Visual Inspections
checkpoint | Drainage Bedding Material
label | IFC Drawings
label | KDC EES2011
label | Delivery Dockets
checkpoint | Gap 65 Subbase Material
label | Issued For Construction Drawings
label | MSF-EN-CIV-DRG-020
label | Delivery Dockets
checkpoint | Gap40 Basecourse Material
label | Issued for Construction Drawings
section | Construction
checkpoint | Inspect Subgrade layer and Check Subgrade Strength
label | Issued for Construction Drawings
label | Visual Inspection
label | Scalar Penetrometer with results recorded of No of blows per 100mm on ITC
checkpoint | Drainage Culvert Installation
label | IFC Drawings:
label | MSF-EN-CIV-DRG-310
label | MSF-EN-CIV-DRG-311
label | MSF-EN-CIV-DRG-312
label | MSF-EN-CIV-DRG-313
label | KDC EES2011 S06
label | Visual Inspection
label | Meets requirements of Issued For Construction Drawings & KDC EES2011 S06
label | ITC - QF008 Pipelines
checkpoint | 300mm Granular Material
label | IFC Drawings
label | KDC EES2011
label | Check granular layer is minimum of 300 thick. Take photos and measurements
checkpoint | Gap 40 Basecourse Construction
label | IFC Drawings
label | KDC EES2011
label | Visual Inspection
label | Clegg hammer reading of >25 recorded onto QF022 Clegg Hammer Test Report
section | Close-Out
checkpoint | Non-Conformance-Reports
label | Non-Conformances Closed Out
checkpoint | Handover
label | At completion of works QA/QC Pack is handed to client
label | Client Verifies Work has been completed correctly and all quality documents are in order
holdpoint | HOLD POINT
checklist | Laydowns | itp |  |  |  |  | ITP - Laydowns
section | Preconstruction
checkpoint | Design
label | Issued For Construction Drawings
checkpoint | Survey & Setout
label | Issued For Construction Drawings
label | Agree and Confirm Locations and Areas Onsite
section | Material Procurement
checkpoint | Granular Fill Material for subgrade improvement (If Required)
label | Issued For Construction Drawings
label | Delivery Dockets if Imported Granular Fill from Offsite is Used
label | Photos if sourced from Onsite Quarry or Delivery Dockets if Sourced Offsite
checkpoint | Gap 65
label | Issued For Construction Drawings
label | MSF-EN-CIV-DRG-020
label | Delivery Dockets
section | Construction
checkpoint | Inspect Subgrade layer and Check Subgrade Strength
label | Issued for Construction Drawings
label | Visual Inspection
label | Scalar Penetrometer with results recorded of No of blows per 100mm on ITC
checkpoint | Granular Fill Construction As Required
label | IFC Drawings
label | Visual Inspection of completed Gap65 after light rolling
checkpoint | Gap 65 Construction
label | IFC Drawings
label | Visual Inspection
label | Proof Rolling
holdpoint | HOLD POINT
section | Close-Out
checkpoint | Non-Conformance-Reports
label | Non-Conformances Closed Out
checkpoint | Handover
label | At completion of works QA/QC Pack is handed to client
label | Client Verifies Work has been completed correctly and all quality documents are in order
holdpoint | HOLD POINT