## Cover Page
Inspection and Test Plan
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL details
Project Name: | State Highway 58 Safety Improvements | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | DS2681 | [5 empty] | A | Action | Role Key |  | Name | Initial
Customer: | NZTA | [5 empty] | B | Report by Breach | PM | Project Manager | Gordon Lemon | GL
Contract Number: | 10687 | [5 empty] | C | Check | SPE | Senior Project Engineer | Jamie Nisbet | JN
Area/ Sub-System: | Piled Retaining Walls |  |  | Lot ID Number: | JWL-001 |  | D | Dimension Inspection | PE | Project Engineer | Natalia Jimenez | NJ
[7 empty] | E | Examine | SE | Site Engineer | Livingstone Lameko | LL
ITP Number: | DS2681-SH58-ITP-C-025 |  |  | Version: | 1 |  | H | Hold Point | SV | Surveyor | Jim Robins | JR
ITP Description: | H-Piles (Retaining Wall) | [5 empty] | I | Inspection | QM | QA Manager | Diliban Sengottian | DS
Discipline: | Retaining Wall | [5 empty] | M | Monitor on Random Basis | ST | Superintendent | Nick Talbot | NT
Specification: | Project Specification, SH58 Safety Improvements - M2TG | [5 empty] | O | Operation | PS | Project Supervisor | Disco | D
[7 empty] | R | Review | SR | Stantec Representative | Sam parkinson | SP
Drawings: | 80510096-02B-315-S001 - 80510096-02B-315-S003 80510096-02B-315-S100 - 80510096-02B-315-S108 80510096-02B-1100-S001 - 80510096-02B-1100-S002 80510096-02B-1100-S101 - 80510096-02B-1100-S106 | [5 empty] | S | Subcontractor
[7 empty] | V | Visual Verification
Prepared By: (Name) | Livingstone Lameko |  |  | Date: | 2025-07-31 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Jamie Nisbet |  |  | Signature: |  | #VALUE! |  |  | Date: | 2025-08-19
Downer Approval |  | Name: | Diliban Sengottian |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: | Sam Parkinson |  |  | Signature: |  |  |  |  | Date:

## Materials & Piling
Inspection and Test Plan
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Specification/Drg Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  |  | Inspection Point/ Signature & Date
[7 empty] | Key | Inspection By (Role Key) |  | Downer Signature | Date | Customer Requirements Verification Record / Location
MATERIALS
4.01 | Pile casing / sleeves / liners | PS Cl. 24.5.3, 24.5.4 | All steelwork shall comply with the requirements of NZS 3404. The steel casings / sleeves / liners must have an inside diameter not less than the specified diameter of the pile. | Delivery Dockets | Once | Witness Point | W | PE
4.02 | Concrete Mix Design | Specification Cl 26.1.11 | The concrete mix design must be submitted and approved prior to pouring. | Mix Design | Min 10 days prior to works | Hold Point | H | SR
4.03 | Structural Steel | Specification Cl 26.3 | All steel shall be in accordance with the appropriate standard as outlined in NZS 3404. | Delivery Dockets, Mill certs, Galvanising certs | Once | Witness Point | W | PE
PILING WORKS
4.04 | Method Statement | PS Cl. 24.5.2 | Piling methodology to be approved by Engineer. | Method Statement | Min 10 days prior to works | Hold Point | H | SR
4.05 | Pile Setout | Drg 80510096-02B-315-S003 | All pile locations have been set out as required by the drawings, and agreed upon with the engineer. Piles shall be set out in accordance with the SESOC/NZGS construction specification bored and driven piles 2022. Pile Setout coordinates are attached in 80510096-02B-315-S105 | ConQA Sign-off | After setout | Hold Point | H | SR
4.06 | Pile Card | Drg 80510096-02B-315-S003 | A Pile Construction Record Card shall be completed for each pile constructed on site, in accordance with AS 2159:2009. | Pile Card | Continuous | Witness Point | W | PE
4.07 | Excavation of Pile Foundation | Drg 80510096-02B-315-S003 | Each pile foundation shall be excavated to the depth shown on the drawings. The contractor shall arrange for the engineer to inspect each excavated shaft upon completion. Tolerances for Pile: Diameter - Not less than specified Position - Tops of piles shall not vary by more than 75mm in horizontal and 25mm in vertical Verticality - Max permitted deviation not more than 1:75 (horizontal:vertical) Engineer Acceptance | ConQA Sign-off / Photos | Post drilling | Hold Point | H | SR
4.08 | Pre-Pour Inspection | PS Cl 24.1.17 | Provide a minimum of 24 hours notice of each initial intention to place concrete to the engineer. A Pre-pour Inspection must verify that the pile hole dimensions (600 mm Ø), steel profile (250UC89) and hole cleanliness comply with design requirements. The concrete mix must meet specifications, and safety measures should be in place before proceeding with the pour. Engineer Acceptance prior to pour | Pre-Pour Inspection Sheet | Prior to Concrete Pouring | Hold Point | H | SR
4.09 | Concrete Pour - Docket | PS Cl 24.1.3 | Confirm correct mix design brought to site Concrete Docket Showing: • Mix Design Item Code • 28 day specified strength • concrete placement method that the mix was designed for - Pump Mix • type of supplementary cementitious materials (if used); • slump (target and actual slump when measured); • Order and Delivery Quantity • Load Time out of plant • To site time • Unload Time • Associated Products e.g. cement and additives | Concrete Docket | Each truckload | Witness Point | W | SE | SE
4.1 | Concrete Pour - Placement | AS/NZS 4671: 2001, 'NZS 3109, 26.1.16 Handling and Placing | Concreting to be a continous operation between ends of members and/or properly formed construction joints. Concrete should be placed as close to its final position as practical and drop height shall not exceed 2m. | Pre-Pour Inspection | Per Pour | Witness Point | W | SE | SE
4.11 | Concrete Pour - Test Cylinders | PS Cl.24.1.14 | A set of specimens for compression tests shall consist of 3 specimens from each sample of concrete. 1no. tested at 7 days and 2no. tested at 28 days. Strength of concrete = Dependent on Mix Design. | Lab Report | Per batch | Witness Point | W | SE | SE
4.12 | Concrete Pour - Slump | PS Table 9.1 | Slump tests shall be taken for each truckload of concrete and when compressive testing samples are taken. Slump spread test if slump could exceed 210mm. Slump test tolerances: | Visual/Photos | Each truckload | Witness Point | W | SE | SE
4.13 | Concrete Pour - Time Limits | PS Cl 24.1.17 | Incorporated in the works within 90minutes of batching. Incorporated in the works within 30minutes of discharge from concrete truck/agitator | Dockets & pour sheet | Each truckload | Witness Point | W | SE | SE
4.14 | Concrete Pour - Vibration | Clause 7.6 of NZS 3109 | All compaction of concrete shall be carried out in accordance with Clause 7.6 of NZS 3109 as further modified by the following provisions: - All concrete shall be thoroughly compacted during and immediately after depositing, by means of power driven immersion vibrators of a size suitable for the section being poured. At least the top 2m of pile shall be vibrated unless noted otherwise. | Visual / Photos | Per Pour | Witness Point | W | SE | SE
4.15 | Survey As Built | PS Cl 24.5.4 | Tolerances: Diameter - Not less than specified Position - Tops of piles shall not vary by more than 75mm in horizontal and 25mm in vertical Verticality - Max permitted deviation not more than 1:75 (horizontal:vertical) Pile Head Level - Overcast by min 0.3m and siphoned/pumped off down to finished level. 25mm tolerance | As-built / Measurements | Per pile | Witness Point | W | SE
Note on D10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do we have Reo for the wall? Should this reference the UC instead? Reply: We have REO for the bored piles at Judgeford. Reply: We’ll need a separate ITP for Bored piles. Too many references to the UC in this ITP and it is called H-Piles
Note on H16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Only Hold or Witness