## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DS2681-SH58-ITP-C-025 Plunged H-Piles (Retaining Wall) | itp |  |  |  |  | DS2681-SH58-ITP-C-025 Plunged H-Piles (Retaining Wall)
section | SECTION 4 – IN-PROCESS INSPECTIONS (MATERIALS)
checkpoint | 4.01 - Pile casing / sleeves / liners
label | Specification/Drg Reference - PS Cl. 24.5.3, 24.5.4
label | Acceptance Criteria - All steelwork shall comply with the requirements of NZS 3404.
label | ○ The steel casings / sleeves / liners must have an inside diameter not less than the specified diameter of the pile.
label | Verifying Document - Delivery Dockets
label | Frequency - Once
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - PE
checkpoint | 4.02 - Concrete Mix Design
label | Specification/Drg Reference - Specification Cl 26.1.11
label | Acceptance Criteria - The concrete mix design must be submitted and approved prior to pouring.
label | Verifying Document - Mix Design
label | Frequency - Min 10 days prior to works
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - SR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.03 - Structural Steel
label | Specification/Drg Reference - Specification Cl 26.3
label | Acceptance Criteria - All steel shall be in accordance with the appropriate standard as outlined in NZS 3404.
label | Verifying Document - Delivery Dockets, Mill certs, Galvanising certs
label | Frequency - Once
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - PE
section | SECTION 4 – IN-PROCESS INSPECTIONS (PILING WORKS)
checkpoint | 4.04 - Method Statement
label | Specification/Drg Reference - PS Cl. 24.5.2
label | Acceptance Criteria - Piling methodology to be approved by Engineer.
label | Verifying Document - Method Statement
label | Frequency - Min 10 days prior to works
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - SR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.05 - Pile Setout
label | Specification/Drg Reference - Drg 80510096-02B-315-S003
label | Acceptance Criteria - All pile locations have been set out as required by the drawings, and agreed upon with the engineer. Piles shall be set out in accordance with the SESOC/NZGS construction specification bored and driven piles 2022. Pile Setout coordinates are attached in 80510096-02B-315-S105
label | Verifying Document - ConQA Sign-off
label | Frequency - After setout
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - SR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.06 - Pile Card
label | Specification/Drg Reference - Drg 80510096-02B-315-S003
label | Acceptance Criteria - A Pile Construction Record Card shall be completed for each pile constructed on site, in accordance with AS 2159:2009.
label | Verifying Document - Pile Card
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - PE
checkpoint | 4.07 - Excavation of Pile Foundation
label | Specification/Drg Reference - Drg 80510096-02B-315-S003
label | Acceptance Criteria - Each pile foundation shall be excavated to the depth shown on the drawings. The contractor shall arrange for the engineer to inspect each excavated shaft upon completion.
label | Tolerances for Pile:
label | — Diameter - Not less than specified
label | — Position - Tops of piles shall not vary by more than 75mm in horizontal and 25mm in vertical
label | — Verticality - Max permitted deviation not more than 1:75 (horizontal:vertical)
label | ○ Engineer Acceptance
label | Verifying Document - ConQA Sign-off / Photos
label | Frequency - Post drilling
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - SR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.08 - Pre-Pour Inspection
label | Specification/Drg Reference - PS Cl 24.1.17
label | Acceptance Criteria - Provide a minimum of 24 hours notice of each initial intention to place concrete to the engineer. A Pre-pour Inspection must verify that the pile hole dimensions (600 mm Ø), steel profile (250UC89) and hole cleanliness comply with design requirements. The concrete mix must meet specifications, and safety measures should be in place before proceeding with the pour.
label | ○ Engineer Acceptance prior to pour
label | Verifying Document - Pre-Pour Inspection Sheet
label | Frequency - Prior to Concrete Pouring
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - SR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.09 - Concrete Pour - Docket
label | Specification/Drg Reference - PS Cl 24.1.3
label | Acceptance Criteria - Confirm correct mix design brought to site
label | Concrete Docket Showing:
label | ○ Mix Design Item Code
label | ○ 28 day specified strength
label | ○ concrete placement method that the mix was designed for - Pump Mix
label | ○ type of supplementary cementitious materials (if used);
label | ○ slump (target and actual slump when measured);
label | ○ Order and Delivery Quantity
label | ○ Load Time out of plant
label | ○ To site time
label | ○ Unload Time
label | ○ Associated Products e.g. cement and additives
label | Verifying Document - Concrete Docket
label | Frequency - Each truckload
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.10 - Concrete Pour - Placement
label | Specification/Drg Reference - AS/NZS 4671: 2001, 'NZS 3109, 26.1.16 Handling and Placing
label | Acceptance Criteria - Concreting to be a continous operation between ends of members and/or properly formed construction joints.
label | ○ Concrete should be placed as close to its final position as practical and drop height shall not exceed 2m.
label | Verifying Document - Pre-Pour Inspection
label | Frequency - Per Pour
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.11 - Concrete Pour - Test Cylinders
label | Specification/Drg Reference - PS Cl.24.1.14
label | Acceptance Criteria - A set of specimens for compression tests shall consist of 3 specimens from each sample of concrete. 1no. tested at 7 days and 2no. tested at 28 days.
label | ○ Strength of concrete = Dependent on Mix Design.
label | Verifying Document - Lab Report
label | Frequency - Per batch
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.12 - Concrete Pour - Slump
label | Specification/Drg Reference - PS Table 9.1
label | Acceptance Criteria - Slump tests shall be taken for each truckload of concrete and when compressive testing samples are taken. Slump spread test if slump could exceed 210mm. Slump test tolerances:
label | — — — — — — — — — — —
label | Nominated slump (mm) ¦¦ Tolerance for snatch sample (mm)
label | — — — — — — — — — — —
label | 60 or less ¦¦ ±20
label | 70 — 110 ¦¦ ±30
label | Greater than 110 ¦¦ ±40
label | — — — — — — — — — — —
label | Verifying Document - Visual/Photos
label | Frequency - Each truckload
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.13 - Concrete Pour - Time Limits
label | Specification/Drg Reference - PS Cl 24.1.17
label | Acceptance Criteria - Incorporated in the works within 90minutes of batching.
label | ○ Incorporated in the works within 30minutes of discharge from concrete truck/agitator
label | Verifying Document - Dockets & pour sheet
label | Frequency - Each truckload
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.14 - Concrete Pour - Vibration
label | Specification/Drg Reference - Clause 7.6 of NZS 3109
label | Acceptance Criteria - All compaction of concrete shall be carried out in accordance with Clause 7.6 of NZS 3109 as further modified by the following provisions: -
label | ○ All concrete shall be thoroughly compacted during and immediately after depositing, by means of power driven immersion vibrators of a size suitable for the section being poured. At least the top 2m of pile shall be vibrated unless noted otherwise.
label | Verifying Document - Visual / Photos
label | Frequency - Per Pour
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.15 - Survey As Built
label | Specification/Drg Reference - PS Cl 24.5.4
label | Acceptance Criteria - Tolerances:
label | ○ Diameter - Not less than specified
label | ○ Position - Tops of piles shall not vary by more than 75mm in horizontal and 25mm in vertical
label | ○ Verticality - Max permitted deviation not more than 1:75 (horizontal:vertical)
label | ○ Pile Head Level - Overcast by min 0.3m and siphoned/pumped off down to finished level. 25mm tolerance
label | Verifying Document - As-built / Measurements
label | Frequency - Per pile
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE