## Abutment Base Type A
Checkers Checklist - Abutment Base -Type A
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type AA | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules - Position, Size, Orientation -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Edge Lifters Correct - Position, Size, Orientation-as per the site requirement | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Grout Tube to form VOIDS - Position, Size -50mm Dia ,300mm | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double check ferrules are firmly positioned & Fixed with Reo | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check minimum 30mm | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel length check, alignment check | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Diagonal length check, alignment check | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Photo Taken | Pass/Fail/NA | attachments/photos/Comments
Installers Checklist - Abutment Base - Type A
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Complete Material "Bucket List" | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate | Pass/Fail/NA | attachments/photos/Comments | Repeating items
text box |  |  |  | Base-A9
section | Pre-Pour Check Approvals | Pass/Fail/NA | attachments/photos/Comments | Base-A10
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments | Base-A11
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/Comments | Base-A12
checkpoint | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/Comments | Base-A13
checkpoint | Double Check the Ferrule placement -Type AA | Pass/Fail/NA | attachments/photos/Comments | Base-A14
checkpoint | Reinforcement Check - Reo as-per Shop Drawing | Pass/Fail/NA | attachments/photos/Comments | Base-A15
checkpoint | Embeded Items - Fixed Firm & aligned -Check | Pass/Fail/NA | attachments/photos/Comments | Base-A16
tick box | Ferrules - Position, Size, Orientation -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments | Base-A17
tick box | Ferrules for Dowels - Position, Size -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments | Base-A18
tick box | Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) | Pass/Fail/NA | attachments/photos/Comments | Base-A19
checkpoint | Concrete cover Check - minimum 30mm | Pass/Fail/NA | attachments/photos/Comments | Base-A20
section | Quality Assurance |  |  | Base-A21
checkpoint | QA - Final Check of ALL measurements | Pass/Fail/NA | attachments/photos/Comments | Base-A22
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments | Base-A23
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments | Base-A24
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments | Base-A25
date | Pour Date |  |  | Base-A26
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments | Base-A27
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments | Base-A28
section | Other Arrangements |  |  | Base-A29
checkpoint | Concrete surface Finish Requirement arranged | Pass/Fail/NA | attachments/photos/Comments | Base-A30
dropdown | Fine finish |  |  | Base-A31
dropdown | Broom finish |  |  | Base-A32
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments | Base-A33
Base-A34
Base-A35
Base-A36
Base-A37
Base-A38
Base-A39
Base-A40

## Abutment Base Type B
Checkers Checklist - Abutment Base -Type B
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type BB | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules - Position, Size, Orientation -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Edge Lifters Correct - Position, Size, Orientation-as per the site requirement | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Grout Tube to form VOIDS - Position, Size -50mm Dia ,300mm | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double check ferrules are firmly positioned & Fixed with Reo | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check minimum 30mm | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel length check, alignment check | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Diagonal length check, alignment check | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Photo Taken | Pass/Fail/NA | attachments/photos/Comments
Installers Checklist - Abutment Base - Type B
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Complete Material "Bucket List" | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate | Pass/Fail/NA | attachments/photos/Comments | Repeating items
text box |  |  |  | Base-B7
section | Pre-Pour Check Approvals | Pass/Fail/NA | attachments/photos/Comments | Base-B8
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments | Base-B9
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/Comments | Base-B10
checkpoint | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/Comments | Base-B11
checkpoint | Double Check the Ferrule placement -Type BB | Pass/Fail/NA | attachments/photos/Comments | Base-B12
checkpoint | Reinforcement Check - Reo as-per Shop Drawing | Pass/Fail/NA | attachments/photos/Comments | Base-B13
checkpoint | Embedded Items - Fixed Firm & aligned -Check | Pass/Fail/NA | attachments/photos/Comments | Base-B14
tick box | Ferrules - Position, Size, Orientation -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments | Base-B15
tick box | Ferrules for Dowels - Position, Size -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments | Base-B16
tick box | Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) | Pass/Fail/NA | attachments/photos/Comments | Base-B17
checkpoint | Concrete cover Check - minimum 30mm | Pass/Fail/NA | attachments/photos/Comments | Base-B18
section | Quality Assurance |  |  | Base-B19
checkpoint | QA - Final Check of ALL measurements | Pass/Fail/NA | attachments/photos/Comments | Base-B20
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments | Base-B21
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments | Base-B22
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments | Base-B23
date | Pour Date |  |  | Base-B24
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments | Base-B25
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments | Base-B26
section | Other Arrangements |  |  | Base-B27
checkpoint | Concrete surface Finish Requirement arranged | Pass/Fail/NA | attachments/photos/Comments | Base-B28
dropdown | Fine finish |  |  | Base-B29
dropdown | Broom finish |  |  | Base-B30
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments | Base-B31
Base-B32
Base-B33
Base-B34
Base-B35
Base-B36
Base-B37
Base-B38
Base-B39
Base-B40

## Bridge Plank Type AB
checklist | Checkers Checklist
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Void - Position, Size, Orientation |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules - - Position, Size, Orientation - NS / FS |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position, Size, Orientation |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Fillet / Chamfer installation |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel Thickness check |  | Pass/Fail/NA | attachments/photos/Comments
dropdown |  | 150mm
dropdown |  | 200mm
checkpoint | Panel length check |  | Pass/Fail/NA | attachments/photos/Comments
dropdown |  | 15m
dropdown |  | 16m
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Panel is clean |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) arrangement |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photos/Comments
Installers Checklist - Type AB - Bridge Plank
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List" |  |  | attachments/photos/Comments
checkpoint | Eye Anchor - 2.5T |  |  | attachments/photos/Comments
text box
checkpoint | Ferrules - M20 x 96mm |  |  | attachments/photos/Comments
text box
checkpoint | ID Plate |  |  | attachments/photos/Comments
text box
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
add this drawing to each repeating items
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photos/Comments | Repeating items | P-1
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photos/Comments |  | P-2
checkpoint | Double Check the Ferrule placement -Type AB |  | Pass/Fail/NA | attachments/photos/Comments |  | P-3
checkpoint | Reinforcement Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photos/Comments |  | P-4
checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check |  | Pass/Fail/NA | attachments/photos/Comments |  | P-5
checkpoint | Concrete cover Check - minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments |  | P-6
section | Quality Assurance |  |  |  |  | P-7
checkpoint | QA - Final Check of ALL measurements |  | Pass/Fail/NA | attachments/photos/Comments |  | P-8
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photos/Comments |  | P-9
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time |  | Pass/Fail/NA | attachments/photos/Comments |  | P-10
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments |  | P-11
date | Pour Date |  |  |  |  | P-12
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photos/Comments |  | P-13
checkpoint | APPROVAL FROM ENGINEER |  |  |  |  | P-14
section | Other Arrangements |  |  |  |  | P-15
checkpoint | Concrete surface Finish Requirement arranged |  | Pass/Fail/NA | attachments/photos/Comments |  | P-16
dropdown | Fine finish |  |  |  |  | P-17
dropdown | Broom finish |  |  |  |  | P-18
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments |  | P-19
P-20
| Checkers Checklist - Type AB - Bridge Plank |  |  |  |  | P-21
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photos |  | P-22
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photos | add this drawing to each repeating items | P-23
P-24
P-25
P-26
P-27
P-28
P-29
P-30
P-31
P-32
P-33
P-34
P-35
P-36
P-37
P-38
P-39
P-40
P-41
P-42
checkpoint | Double Check the Ferrule placement -Type AB |  | Pass/Fail/NA | attachments/photos |  | P-43
checkpoint | Overall Measurements of construction Element |  | Pass/Fail/NA | attachments/photos |  | P-44
checkpoint | Embedded Item - Ferrules - Position, Size, Orientation -M20 (96mm) |  | Pass/Fail/NA | attachments/photos |  | P-45
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal |  | Pass/Fail/NA | attachments/photos |  | P-46
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photos |  | P-47
checkpoint | Panel Thickness check, allignment check |  | Pass/Fail/NA | attachments/photos |  | P-48
checkpoint | Panel length check, alignment check |  | Pass/Fail/NA | attachments/photos |  | P-49
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing |  | Pass/Fail/NA | attachments/photos |  | P-50
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean |  | Pass/Fail/NA | attachments/photos |  | P-51
checkpoint | Reinforcement (Reo) placed, cleaned, tightened |  | Pass/Fail/NA | attachments/photos |  | P-52
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos |  | P-53
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photos |  | P-54
P-55
P-56
P-57
P-58
P-59
P-60

## Sheet5 (hidden)
Repeating items | FFBP-A1 | FFBP-B1
| FFBP-A2 | FFBP-B2
| FFBP-A3 | FFBP-B3
| FFBP-A4 | FFBP-B4
| FFBP-A5 | FFBP-B5
| FFBP-A6 | FFBP-B6
| FFBP-A7 | FFBP-B7
| FFBP-A8 | FFBP-B8
| FFBP-A9 | FFBP-B9
| FFBP-A10 | FFBP-B10
| FFBP-A11 | FFBP-B11
| FFBP-A12 | FFBP-B12
| FFBP-A13 | FFBP-B13
| FFBP-A14 | FFBP-B14
| FFBP-A15 | FFBP-B15
| FFBP-A16 | FFBP-B16
FFBP-B17
FFBP-B18
FFBP-B19
FFBP-B20
FFBP-B21
FFBP-B22
FFBP-B23
FFBP-B24
FFBP-B25
FFBP-B26
FFBP-B27
FFBP-B28
FFBP-B29
FFBP-B30
FFBP-B31
FFBP-B32