## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Checkers Checklist - Abutment Base - Type A
section | Details
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Double Check the Ferrule placement -Type AA
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item - Ferrules - Position, Size, Orientation -M24 (96mm)
checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm)
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
checkpoint | Embedded Item - Edge Lifters Correct - Position, Size, Orientation-as per the site requirement
checkpoint | Embedded Item - Grout Tube to form VOIDS - Position, Size -50mm Dia ,300mm
checkpoint | Double check ferrules are firmly positioned & Fixed with Reo
checkpoint | Concrete cover check minimum 30mm
checkpoint | Panel length check, alignment check
checkpoint | Diagonal length check, alignment check
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist - Abutment Base - Type A
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing
checkpoint | Complete Material "Bucket List"
checkpoint | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Double Check the Ferrule placement -Type AA
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Embeded Items - Fixed Firm & aligned -Check
bool | Ferrules - Position, Size, Orientation -M24 (96mm)
bool | Ferrules for Dowels - Position, Size -M24 (96mm)
bool | Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
checkpoint | Concrete cover Check - minimum 30mm
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged
dropdown | Finish: | Fine finish,Broom finish
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist - Abutment Base - Type B
section | Details
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Double Check the Ferrule placement -Type BB
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item - Ferrules - Position, Size, Orientation -M24 (96mm)
checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm)
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
checkpoint | Embedded Item - Edge Lifters Correct - Position, Size, Orientation-as per the site requirement
checkpoint | Embedded Item - Grout Tube to form VOIDS - Position, Size -50mm Dia ,300mm
checkpoint | Double check ferrules are firmly positioned & Fixed with Reo
checkpoint | Concrete cover check minimum 30mm
checkpoint | Panel length check, alignment check
checkpoint | Diagonal length check, alignment check
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist - Abutment Base - Type B
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing
checkpoint | Complete Material "Bucket List"
checkpoint | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Double Check the Ferrule placement -Type BB
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Embedded Items - Fixed Firm & aligned -Check
bool | Ferrules - Position, Size, Orientation -M24 (96mm)
bool | Ferrules for Dowels - Position, Size -M24 (96mm)
bool | Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
checkpoint | Concrete cover Check - minimum 30mm
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged
dropdown | Finish: | Fine finish,Broom finish
checkpoint | Curing Procedure arranged
checklist | Installers Checklist - Type AB - Bridge Plank
section | Job Approval Documents/Construction Documents
checkpoint-no-status | Complete Material "Bucket List"
checkpoint-no-status | Eye Anchor - 2.5T
textbox | Eye Anchor:
checkpoint-no-status | Ferrules - M20 x 96mm
textbox | Ferrules:
checkpoint-no-status | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Double Check the Ferrule placement -Type AB
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
checkpoint | Concrete cover Check - minimum 30mm
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged
dropdown | Finish: | Fine finish,Broom finish
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist - Type AB - Bridge Plank
section | Details
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Double Check the Ferrule placement -Type AB
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item - Ferrules - Position, Size, Orientation -M20 (96mm)
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
checkpoint | Concrete cover check minimum 30mm
checkpoint | Panel Thickness check, allignment check
checkpoint | Panel length check, alignment check
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken