## ITP Summary
Job | 2025-35 - Mt Allyn 15M Bridge - Mifsud | values | Check list | options
checklist-sectioned | Precast Components ITP
section | Documentations
checkpoint | Special Instructions |  |  | attachments/photos/Sign
checkpoint | approved Shop Drawings |  |  | attachments/photos/Sign
tick Box | 4.5m Wide Deck Panels x 15
tick Box | Abutment Base - Type B x 2
tick Box | Upper Wall - 800mm x 2
checkpoint | Other |  |  | attachments/photos/Sign
section | Job Approval Documents/Construction Documents
checkpoint | Shop drawings repaired, reviewed and updated. Issued "As For Construction" |  | Pass/Fail/NA | attachments/photos
All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint | Formwork |  |  | attachments/photos/Sign
checkpoint | Reinforcement(Reo) |  |  | attachments/photos/Sign
checkpoint | Embedded Items and their placement |  |  | attachments/photos/Sign
checkpoint | Lift Procedure
checkpoint | Concreting (mix design) |  |  | attachments/photos/Sign
section | Test on Concrete (requests and approvals)
checkpoint | Request From Client |  |  | attachments/photos/Sign
checkpoint | Test schedule and Test Results |  |  | attachments/photos/Sign
section | Transport
Sub section 01 | Transport 01
| Any Lifting, Loading, Transport Instructions from Client |  | Pass/Fail/NA | attachments/photos/Sign | Repeating items
| Transport Vehicle Approvals |  | Pass/Fail/NA | attachments/photos/Sign
| Ensure loads are glutted correctly and chains are over gluts. |  | Pass/Fail/NA | attachments/photos/Sign
Sub section 02 | Transport 02
| Any Lifting, Loading, Transport Instructions from Client |  | Pass/Fail/NA | attachments/photos/Sign
| Transport Vehicle Approvals |  | Pass/Fail/NA | attachments/photos/Sign
| Ensure loads are glutted correctly and chains are over gluts. |  | Pass/Fail/NA | attachments/photos/Sign
Sub section 01 | Transport 03
| Any Lifting, Loading, Transport Instructions from Client |  | Pass/Fail/NA | attachments/photos/Sign
| Transport Vehicle Approvals |  | Pass/Fail/NA | attachments/photos/Sign
| Ensure loads are glutted correctly and chains are over gluts. |  | Pass/Fail/NA | attachments/photos/Sign
Sub section 02 | Transport 04
| Any Lifting, Loading, Transport Instructions from Client |  | Pass/Fail/NA | attachments/photos/Sign
| Transport Vehicle Approvals |  | Pass/Fail/NA | attachments/photos/Sign
| Ensure loads are glutted correctly and chains are over gluts. |  | Pass/Fail/NA | attachments/photos/Sign
section | Other Documentations
checkpoint | Special Instructions |  | Pass/Fail/NA | attachments/photos/Sign
checkpoint | Other |  | Pass/Fail/NA | attachments/photos/Sign
section | Final Inspection
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected. |  | Pass/Fail/NA | attachments/photos/Sign
This is a General Section
No repeating Items

## Upper Wall Type B-15M
Job: | 2025-35 - Mt Allyn 15M Bridge - Mifsud
Checkers Checklist - Upper Wall -Type B-15M
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type BB Wall Height - |  | Pass/Fail/NA | attachments/photos/Comments
dropdown |  | Other
dropdown |  | 800mm
checkpoint | Overall Measurements of construction Element |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -75x75x8EA galvanized Edge strip - Position, Size, Orientation |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Edge Lifters Correct - Position, Size, Orientation-as per the site requirement |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double check ferrules are firmly positioned & Fixed with Reo |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel Thickness check, allignment check -200mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel length check, alignment check -5000x800mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Diagonal length check, alignment check (5034 mm or close to this) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photos/Comments
Installers Checklist - Upper Wall l -Type B-15M
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Complete Material "Bucket List" |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Eye Anchor - 2.5T(170mm) - 04 |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate |  | Pass/Fail/NA | attachments/photos/Comments | Repeating items
text box |  |  |  |  | UW800-1
section | Pre-Pour Check Approvals |  |  |  | UW800-2
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type BB Wall Height - |  | Pass/Fail/NA | attachments/photos/Comments
dropdown |  | Other
dropdown |  | 800mm
checkpoint | Reinforcement Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters, Ferrules Fixed Firm & aligned -Check |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
tick box | Embedded Item - Edge Lifters Correct - Position, Size, Orientation-as per the site requirement |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover Check - minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER |  | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged |  | Pass/Fail/NA | attachments/photos/Comments
dropdown | Fine finish
dropdown | Broom finish
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments

## Sheet5 (hidden)
Repeating items | FFBP-A1 | FFBP-B1
| FFBP-A2 | FFBP-B2
| FFBP-A3 | FFBP-B3
| FFBP-A4 | FFBP-B4
| FFBP-A5 | FFBP-B5
| FFBP-A6 | FFBP-B6
| FFBP-A7 | FFBP-B7
| FFBP-A8 | FFBP-B8
| FFBP-A9 | FFBP-B9
| FFBP-A10 | FFBP-B10
| FFBP-A11 | FFBP-B11
| FFBP-A12 | FFBP-B12
| FFBP-A13 | FFBP-B13
| FFBP-A14 | FFBP-B14
| FFBP-A15 | FFBP-B15
| FFBP-A16 | FFBP-B16
FFBP-B17
FFBP-B18
FFBP-B19
FFBP-B20
FFBP-B21
FFBP-B22
FFBP-B23
FFBP-B24
FFBP-B25
FFBP-B26
FFBP-B27
FFBP-B28
FFBP-B29
FFBP-B30
FFBP-B31
FFBP-B32