## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Precast Components ITP
section | Documentations
checkpoint-no-status | Special Instructions
checkpoint-no-status | approved Shop Drawings
bool | 4.5m Wide Deck Panels x 15
bool | Abutment Base - Type B x 2
bool | Upper Wall - 800mm x 2
checkpoint-no-status | Other
section | Job Approval Documents/Construction Documents
checkpoint | Shop drawings repaired, reviewed and updated. Issued "As For Construction"
label | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint-no-status | Formwork
checkpoint-no-status | Reinforcement (Reo)
checkpoint-no-status | Embedded Items and their placement
checkpoint-no-status | Lift Procedure
checkpoint-no-status | Concreting (mix design)
section | Test on Concrete (requests and approvals)
checkpoint-no-status | Request From Client
checkpoint-no-status | Test schedule and Test Results
section | Transport 01
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 02
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 03
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 04
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Other Documentations
checkpoint | Special Instructions
checkpoint | Other
section | Final Inspection
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
checklist | Checkers Checklist - Upper Wall -Type B-15M
section | Details
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Double Check the Ferrule placement -Type BB Wall Height -
dropdown | Height: | Other,800mm
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item -75x75x8EA galvanized Edge strip - Position, Size, Orientation
checkpoint | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
checkpoint | Embedded Item - Edge Lifters Correct - Position, Size, Orientation-as per the site requirement
checkpoint | Double check ferrules are firmly positioned & Fixed with Reo
checkpoint | Concrete cover check minimum 30mm
checkpoint | Panel Thickness check, allignment check -200mm
checkpoint | Panel length check, alignment check -5000x800mm
checkpoint | Diagonal length check, alignment check (5034 mm or close to this)
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist - Upper Wall l -Type B-15M
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing
checkpoint | Complete Material "Bucket List"
checkpoint | Eye Anchor - 2.5T(170mm) - 04
checkpoint | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Double Check the Ferrule placement -Type BB Wall Height -
dropdown | Height: | Other,800mm
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Embedded Item - Lifters, Ferrules Fixed Firm & aligned -Check
bool | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm
bool | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
bool | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
bool | Embedded Item - Edge Lifters Correct - Position, Size, Orientation-as per the site requirement
checkpoint | Concrete cover Check - minimum 30mm
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged
dropdown | Finish: | Fine finish,Broom finish
checkpoint | Curing Procedure arranged