## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | ITP-001
Revision : 1 17/06/2022
Client: |  | DTP |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | WGT Project |  | West Gate Closure Works |  | Name: | Bunnarith BY | Name: | Cameron Beattie |  | Name: | Cameron Beattie
Contract No: |  |  |  | Specifications: VicRoads Specification Section 100, Section 100
|  |  |  | Structure / Component: Intersection remodelling |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | 2025-08-18 |  | Date : | 2025-08-18 |  | Date : | 2025-08-18
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Project Engineer / Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP | QMP, TMP, SWMS, ITP | Visual Inspection | This ITP signed off | HP* | Project Engineer / Site Foreman | N/A |  | N/A
1.3 | Approval of Klemm fix material |  | Prior to ordering | Stantec IFC TAP Traffic Network Plans | IFC Drawings | Visual Inspection | This ITP signed off | WP | DTP / Project Engineer |  |  | N/A
1.4 | Approval of Rubber Kerb |  | Prior to ordering | Stantec IFC TAP Traffic Network Plans | IFC Drawings | Visual Inspection | This ITP signed off | WP | DTP / Project Engineer |  |  | N/A
1.5 | Approval for special order signs |  | Prior to ordering | Stantec IFC TAP Traffic Network Plans | IFC Drawings | Visual Inspection | This ITP signed off | WP | DTP / Project Engineer |  |  | N/A
1.6 | Bollards / Planter box approval |  | Prior to ordering | Stantec IFC TAP Traffic Network Plans | IFC Drawings | Visual Inspection | This ITP signed off | WP | DTP / Project Engineer |  |  | N/A
1.7 | Pre installation Setout Traffic Signals |  | Prior to any electrical works | Stantec IFC TAP Traffic Network Plans | IFC Drawings | Visual Inspection | This ITP signed off | WP | DTP / Project Engineer |  |  | N/A
1.7 | VMS boards Delivered 2 weeks Prior |  | Prior to any electrical works | MOA + TGS | MOA detours Plan | Approval point | This ITP signed off | HP | DTP / Project Engineer |  |  | N/A
1.8 | Communication to Business owners and Local residents |  | 2 weeks prior to works | Section 100 | Section 100 | Approval point | This ITP signed off | HP | DTP / Project Engineer |  |  | N/A
2 | Construction Works
2.0 | MOA Approval |  | Each lot | Traffic management plan approved | Section 100 | Approval point | This ITP signed off | HP* | Project Engineer | N/A |  | N/A
2.1 | Excavation Permit |  | Each lot | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | PSP | Approval point | This ITP signed off | WP | Project Engineer | N/A |  | N/A
2.2 | Set out of kerb works |  | Each Lot | Kerb Works to be marked on site with paint prior to installation | IFC Drawings | Witness Point | This ITP signed off | WP | Engineer / Forman & Superintendent | N/A |  | N/A
2.3 | Set out of Klem fix |  | Each Lot | Klem fix Works to be marked on site with paint prior to installation | IFC Drawings | Witness Point | This ITP signed off | WP | Engineer / Forman & Superintendent | N/A |  | N/A
2.4 | Set out of Bollards |  | Each Lot | Bollard works to be marked on site with paint prior to installation | IFC Drawings | Witness Point | This ITP signed off | WP | Engineer / Forman & Superintendent | N/A |  | N/A
2.5 | Set out line marking removal |  | Each Lot | Redundant line marking to be marked on site with paint prior to removal | IFC Drawings | Witness Point | This ITP signed off | WP | Engineer / Forman & Superintendent | N/A |  | N/A
2.6 | Set out line marking |  | Each Lot | 1. Line marking Works to be marked on site with paint prior to installation. 2. Painting/application of material shall not commence until the Superintendent has inspected the setout and given consent to proceed. | IFC Drawings Section 721.B05 | Witness Point | This ITP signed off | HP | Engineer / Forman & Superintendent |  |  | N/A
2.7 | Set out of signage |  | Each lot | The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences | Section 714.06 | Hold Point | This ITP signed off | HP | Engineer / Forman & Superintendent |  |  | N/A
2.8 | Installation of signage |  | Each lot | 1. Sign post socket should prortrude 50mm above an earth surface or 25mm above a paved surface. 2. Sign post must penetrate a minimum 450mm into the socket. | Section 714.06(d) | Inspection | This ITP signed off | IP | Engineer / Forman | N/A |  | N/A
2.9 | Set out location of pedestal |  | Each lot | Confirm the locations of all pedestals are suitable | Section 700 | Witness Point | This ITP signed off | WP | Engineer / Forman & Superintendent |  |  | N/A
2.10 | Standing traffic signal poles |  | Each lot | All foundations have cured for a minimum of 3 days plus reached a minimum compression strength of 40MPa before standing any poles. | Section 730.132 | Hold Point | This ITP signed off | HP | Engineer / Forman & Superintendent |  |  | N/A
3 | Testing & Completion
3.1 | Flash Test |  | Each intersection Prior to opening intersection | To be agreed approved on site with DTP | Section 730 | Hold Point | This ITP signed off | HP | Project Engineer / Site Foreman
3.2 | Traffic Signal pre commissioning report |  | Each intersection Prior to opening intersection | To be agreed approved on site with DTP | Section 730 | Hold Point | This ITP signed off | Hp | Site Engineer / Site Foreman
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent