## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-001 - West Gate Tunnel | itp |  |  |  |  | ITP-001 - West Gate Tunnel Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
label | REFERENCE DOCUMENTS: QMP, TMP, SWMS, ITP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Approval of Klemm fix material
label | FREQUENCY: Prior to ordering
label | ACCEPTANCE CRITERIA: Stantec IFC TAP Traffic Network Plans
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: DTP / Project Engineer
date | Date Completed:
checkpoint | 1.4 - Approval of Rubber Kerb
label | FREQUENCY: Prior to ordering
label | ACCEPTANCE CRITERIA: Stantec IFC TAP Traffic Network Plans
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: DTP / Project Engineer
date | Date Completed:
checkpoint | 1.5 - Approval for special order signs
label | FREQUENCY: Prior to ordering
label | ACCEPTANCE CRITERIA: Stantec IFC TAP Traffic Network Plans
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: DTP / Project Engineer
date | Date Completed:
checkpoint | 1.6 - Bollards / Planter box approval
label | FREQUENCY: Prior to ordering
label | ACCEPTANCE CRITERIA: Stantec IFC TAP Traffic Network Plans
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: DTP / Project Engineer
date | Date Completed:
checkpoint | 1.7 - Pre installation Setout Traffic Signals
label | FREQUENCY: Prior to any electrical works
label | ACCEPTANCE CRITERIA: Stantec IFC TAP Traffic Network Plans
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: DTP / Project Engineer
date | Date Completed:
checkpoint | 1.7 - VMS boards Delivered 2 weeks Prior
label | FREQUENCY: Prior to any electrical works
label | ACCEPTANCE CRITERIA: MOA + TGS
label | REFERENCE DOCUMENTS: MOA detours Plan
label | INSPECTION/TEST METHOD: Approval point
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: DTP / Project Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Communication to Business owners and Local residents
label | FREQUENCY: 2 weeks prior to works
label | ACCEPTANCE CRITERIA: Section 100
label | REFERENCE DOCUMENTS: Section 100
label | INSPECTION/TEST METHOD: Approval point
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: DTP / Project Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.0 - MOA Approval
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Traffic management plan approved
label | REFERENCE DOCUMENTS: Section 100
label | INSPECTION/TEST METHOD: Approval point
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.1 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: PSP
label | INSPECTION/TEST METHOD: Approval point
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.2 - Set out of kerb works
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Kerb Works to be marked on site with paint prior to installation
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Witness Point
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
checkpoint | 2.3 - Set out of Klem fix
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Klem fix Works to be marked on site with paint prior to installation
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Witness Point
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
checkpoint | 2.4 - Set out of Bollards
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bollard works to be marked on site with paint prior to installation
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Witness Point
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
checkpoint | 2.5 - Set out line marking removal
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Redundant line marking to be marked on site with paint prior to removal
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Witness Point
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
checkpoint | 2.6 - Set out line marking
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: 1. Line marking Works to be marked on site with paint prior to installation.
label | 2. Painting/application of material shall not commence until the Superintendent has inspected the setout and given consent to proceed.
label | REFERENCE DOCUMENTS: IFC Drawings Section 721.B05
label | INSPECTION/TEST METHOD: Witness Point
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Set out of signage
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences
label | REFERENCE DOCUMENTS: Section 714.06
label | INSPECTION/TEST METHOD: Hold Point
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Installation of signage
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: 1. Sign post socket should prortrude 50mm above an earth surface or 25mm above a paved surface.
label | 2. Sign post must penetrate a minimum 450mm into the socket.
label | REFERENCE DOCUMENTS: Section 714.06(d)
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Engineer / Forman
date | Date Completed:
checkpoint | 2.9 - Set out location of pedestal
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Confirm the locations of all pedestals are suitable
label | REFERENCE DOCUMENTS: Section 700
label | INSPECTION/TEST METHOD: Witness Point
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
checkpoint | 2.1 - Standing traffic signal poles
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: All foundations have cured for a minimum of 3 days plus reached a minimum compression strength of 40MPa before standing any poles.
label | REFERENCE DOCUMENTS: Section 730.132
label | INSPECTION/TEST METHOD: Hold Point
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing & Completion
checkpoint | 3.1 - Flash Test
label | FREQUENCY: Each intersection Prior to opening intersection
label | ACCEPTANCE CRITERIA: To be agreed approved on site with DTP
label | REFERENCE DOCUMENTS: Section 730
label | INSPECTION/TEST METHOD: Hold Point
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Traffic Signal pre commissioning report
label | FREQUENCY: Each intersection Prior to opening intersection
label | ACCEPTANCE CRITERIA: To be agreed approved on site with DTP
label | REFERENCE DOCUMENTS: Section 730
label | INSPECTION/TEST METHOD: Hold Point
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: