## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
f5d6cf74-3858-4133-bdd5-7bb57813e537 | checklist | ITC - (1) Drawing Register (For Construction) |  | Drawing Register (For Construction)
aad4b87d-4b7b-46c8-a823-ccc7d9e67e7b | section | Details
2541882c-79d9-418f-bd3b-9db024ea6ba7 | checkpoint-no-value | DRAWING REGISTER
250789a4-9776-5e5f-9b2f-519ed4d4eca7 | date | Date:
db63807a-c4ba-5c96-b76e-77f3a3fe1209 | textbox | DRAWING No.
27c39b8a-a946-545c-8c20-7d123495383e | textbox | DRAWING TITLE
a3bbe8be-e311-5012-a638-270d16970d96 | textbox | REVISION / ISSUE
01421f78-c2d5-4611-b4ff-28f6d7e34437 | checkpoint-no-value | DISTRIBUTION:
50fe52e9-2c59-5557-af8e-d6bc432aed5e | textbox | SITE OFFICE
2b420d1a-6e26-5132-920b-4b1c1c940bbe | textbox | SITE
cac145de-7aba-5283-b665-535ce1d9c27d | textbox | NCR No:
250cc4cb-dda0-456a-8471-e9f9a243c797 | checkpoint | FINAL ACCEPTANCE:
a4401c9d-ac06-58c0-96de-e7ebc3f629e6 | textbox | HEYDAY GROUP (REPRESENTATIVE)
6f94610e-9668-5ebc-b558-767516745105 | textbox | CLIENT (REPRESENTATIVE)
95121fa7-cb8f-5402-b46a-404cfa74072d | textbox | AUTHORITY (IF APPLICABLE)
56bda5b1-60af-4989-9c12-de6a6183393e | signoff | Signoff
f813d2a6-3065-45f0-aa92-6085eaee1bca | checklist | ITC - (2) Temporary Wiring-Temporary DB's |  | Level / Area:
88e15ede-d00d-42b9-a4dd-b98f49ff0da8 | section | Details
12f4cb67-4cce-4336-b94c-05dc018f0722 | checkpoint | EQUIPMENT LOCATED CORRECTLY
6349a484-251b-4323-a955-3c875323cc85 | checkpoint | EQUIPMENT SECURE/BOLTED DOWN
ba41abc7-49c9-4326-94d8-1f40fe3401f3 | checkpoint | WIRING INSTALLED CORRECTLY
b7c3ca9e-aff5-4e4b-bbbd-5d285dec49d3 | checkpoint | WIRING MECHANICALLY PROTECTED
48ab3d59-5030-4027-9809-3fb0778f9de2 | checkpoint | POLE FILLERS INSTALLED
cbc1ce9f-f1dd-4bb2-a320-f8bb42a65d30 | checkpoint | ESCUTCHEON / COVERS CHECKED
c056966f-e438-4d1a-bb9a-8b15ae9fb2f9 | checkpoint | LOCKABLE COVERS AND PADLOCKS
a85f4fe2-0158-41b6-9866-d19be8371c12 | checkpoint | EQUIPMENT TESTED AND TAGGED
4b4b9dca-b831-411c-8743-6012c0dbbf27 | checkpoint | TEMPORARY BOARD NUMBERED
12685319-e003-4ac9-a859-10c0bed277f1 | checkpoint | BOARD LABELLED FOR SOURCE OF SUPPLY
308dce2c-5cc7-401d-a771-b7f65ffa691b | checkpoint | FINAL ACCEPTANCE:
b8876a58-fc97-5412-8616-56bf087c8ab7 | textbox | HEYDAY GROUP (REPRESENTATIVE)
fbcbd81c-7867-579d-aac8-8e9922a32a99 | textbox | CLIENT (REPRESENTATIVE)
51f315c0-2ffa-553f-9a3a-6336e0f09047 | textbox | AUTHORITY (IF APPLICABLE)
7d72b4ae-6d3d-4dbf-b25e-588ac811cb0e | signoff | Signoff
2ccddc3f-79bf-440f-b556-c4fa8a88f0c8 | checklist | ITC - (3) Main and Distribution Panels |  | Board Type or Number or Area:
d13b06d5-0bb4-46eb-a890-fa07d2edff4e | section | Details
6d8b72e4-8de4-4f0b-9a8d-818be71a288e | checkpoint | ACCEPTANCE CRITERIA
776674ea-da15-4be1-9dca-ac286fb2db38 | checkpoint | MFG QA
65239a86-5aa0-4d98-97f9-4a28cd3f7014 | checkpoint | DAMAGE
27389368-a35e-4146-9f98-ffd5185ab488 | checkpoint | LOCATION TO DRAWING
080d76a1-370f-4b4d-97a3-bb126ce77637 | checkpoint | EQUIPMENT TO DRAWING
aee47c2d-a7a5-4ee7-b9cf-69b80db54d72 | checkpoint | NEUTRAL CONNECTIONS CORRESPOND
b38bf6e1-24e1-4a8d-8d9b-abe2da8eff22 | checkpoint | CORRECT EARTHING AND SOLIDLY FIXED
6bf77064-bd1f-4217-86f7-d72dc37b77de | checkpoint | POLE FILLERS INSTALLED
45b9463c-676a-482f-9bbe-b26f7804c2a8 | checkpoint | ALL CABLE ENTRIES WITH ESCUTCHEON PLATES AND SEALS FITTED
21dde43c-8c10-432b-b1b3-8ab688d8b159 | checkpoint | BOARD SEALED AND LOCKED FOR SAFETY INC: FRONT AND REAR PANELS
257d49d9-cc96-49ae-96a3-c88fad88083d | checkpoint | LABELS AND SCHEDULE LIST CORRECT AND INSTALLED
8b87a991-cfed-449d-ad40-d84f18ea73de | checkpoint | FINAL ACCEPTANCE:
970145da-a808-5850-881d-b2389fcee499 | textbox | HEYDAY GROUP (REPRESENTATIVE)
f6e48934-8047-501b-8646-eae05fef8b42 | textbox | CLIENT (REPRESENTATIVE)
8c8b9863-38df-5541-b49c-7cab4edfd17a | textbox | AUTHORITY (IF APPLICABLE)
c85d0212-7388-4961-87e9-8a08c686aa34 | signoff | Signoff
43258ed2-e290-449b-8ddf-d4c94a5596ee | checklist | ITC - (3A) MSB and DB's TEST Sheet V3 | itp | ITC - (3A) MSB and DB's TEST Sheet V3
97e7daa1-30a5-4f04-8a05-54e6d358d078 | section | 1 - Visual Checks
c59ba759-533e-41b3-ac3b-2fe439f90615 | checkpoint | Approved Factory Acceptance Test completed
26db2c24-b34b-4ad6-83af-5603a18fcb20 | checkpoint | Switchboard is secure and ready for Consumer Main/Submain Installation
dd2988c3-b58c-4976-94b6-f981a0825cfc | checkpoint | Consumer Main/Submain Installed?
bc05e29a-7b59-4966-b0c2-2f8b8172ffae | checkpoint | Verify C/B Trip Settings are Correct.
619911e2-9016-4fab-932d-b6b4d651598b | checkpoint | Are the connections tight, correct tension and marked?
53485dba-2601-4c06-ba59-9c239cf6a3be | checkpoint | Switchboard is ready to be energised?
d05d16b5-d95e-4238-aac9-397b771c2e53 | section | 2 - Pre Energisation Checks (AS/NZS 3000)
e6c074dc-f5e2-403f-9ae5-9d958c5b6601 | checkpoint | Earth Continuity (Value must be less than 0.5 ohms)
52e3632c-1c1e-5e39-a08c-870e3d98492a | textbox | Earth Size:
3fe8fb4e-6fb4-5b66-8003-4874bfcb4e70 | textbox | FROM:
de8f512f-12f2-5ecc-b1dc-fe8e5ac15592 | textbox | TO:
b56a539f-ecb0-584b-8d70-06ade44dd3eb | textbox | Point to Point Reading:
c3c2b629-356a-4201-b903-c8d142bc3bc0 | checkpoint | BUSBAR Insulation Resistance Test - RED TO WHITE >1MOhm
7b6f22e8-4282-4610-a4c1-e78add9c86c6 | checkpoint | BUSBAR Insulation Resistance Test - RED TO BLACK >1MOhm
ec98b820-c27c-4446-bc24-2e837c9e400f | checkpoint | BUSBAR Insulation Resistance Test - RED TO EARTH >1MOhm
1eeed3b2-fb8f-49e5-93dd-5236f34ea89e | checkpoint | BUSBAR Insulation Resistance Test - WHITE TO BLUE >1MOhm
91bd0348-0c45-43d2-8992-5d357f5ae747 | checkpoint | BUSBAR Insulation Resistance Test - WHITE TO BLACK >1MOhm
d5dd669b-184f-49ca-8c98-f911d9dab4d4 | checkpoint | BUSBAR Insulation Resistance Test - WHITE TO EARTH >1MOhm
8210758c-6e5d-47bf-9b3a-cabf74b57236 | checkpoint | BUSBAR Insulation Resistance Test - BLUE TO RED >1MOhm
a5aa4b61-910d-4f14-8c46-2af4ab392494 | checkpoint | BUSBAR Insulation Resistance Test - BLUE TO BLACK >1MOhm
bc23938d-d2a1-44b8-b900-0a33cf990987 | checkpoint | BUSBAR Insulation Resistance Test - BLUE TO EARTH >1MOhm
6ad47da4-0258-4d99-85bb-f1c5757a5049 | section | 3 - Post Energisation Checks (AS/NZS 3000)
fd149068-de64-4803-a0e7-a6384a6362d6 | checkpoint | Phase Rotation
e4645303-0f2e-5bc4-bcdd-44749bf88d73 | tickbox | Clockwise →
8de32f56-0fa9-557a-af70-b80c4fa4c481 | tickbox | Anti Clockwise ←
766e84a9-9d5a-4dc7-a512-15f6c8050683 | checkpoint | Voltage Check - RED TO WHITE
8ae6f921-6b5f-52f1-8155-d292cdaf8265 | textbox | Voltage
b397058f-2d4e-410b-8383-d4dd2f92caf3 | checkpoint | Voltage Check - RED TO BLACK
1f4238be-15e0-5896-8f52-7030badeb553 | textbox | Voltage
5076a8dc-27a6-4748-919f-1e0a3f143f67 | checkpoint | Voltage Check - RED TO EARTH
fd34f255-6c2e-59fe-be4a-4c7ef500aa45 | textbox | Voltage
41fd3424-6659-4737-ae82-6009f668a5ae | checkpoint | Voltage Check - WHITE TO BLUE
f1832108-d433-57f1-854e-374df66fabd6 | textbox | Voltage
32386c00-9508-4b8c-8537-0dab03173117 | checkpoint | Voltage Check - WHITE TO BLACK
56a410dd-1c05-52c0-9b64-567049d3e61b | textbox | Voltage
067542e5-fd19-47a5-8374-a12b71b9b7a7 | checkpoint | Voltage Check - WHITE TO EARTH
37e167fd-0dab-5dad-ad89-d50fce1ec6b5 | textbox | Voltage
0f6c7e6d-8384-4387-833d-0bc61c569e5d | checkpoint | Voltage Check - BLUE TO RED
9df2bc0a-a1fc-56ab-a02d-0c63980d0a2b | textbox | Voltage
31d30f09-e310-4162-ae36-9198af30b661 | checkpoint | Voltage Check - BLUE TO BLACK
8a401fb3-25aa-5cf0-8292-058ed54ef9df | textbox | Voltage
d539e0bd-e819-42b7-83ea-db03ab535136 | checkpoint | Voltage Check - BLUE TO EARTH
86b34f4c-e57e-58bf-b5bd-0647910dc2a6 | textbox | Voltage
4fc8c6bd-4578-435d-8283-91c9cd27d655 | checklist | ITC - (4) Main and Submain |  | MAINS AND SUBMAINS
beb1c845-04eb-4218-8e1a-b06b922f0875 | section | Details
638ba9c3-3fc6-4903-a6b6-c450ddcb7216 | checkpoint-no-value | Details
9bfc2647-9994-5677-943d-8857704d1750 | textbox | FED FROM
0f1dda67-789c-551c-87f5-71e4dd564e58 | textbox | TO DB No
3fff7e7e-e1d9-49d9-b2bc-6213cb0d124e | checkpoint | COMPLIES TO SPEC AND LATEST DRG
a9a8cdfb-cde0-4d85-ba89-3f51a58f9cfd | checkpoint | SIZE CORRECT
e7a0603e-ab1c-4d85-a2a7-46ef2c6c214b | checkpoint | INSTALLED CORRECT
39532773-cafb-49f4-bd9d-1757274049ee | checkpoint | TERMINATED
d9989836-b366-48c5-a36e-88e2de64052f | checkpoint | ARE CONNECTIONS TIGHT, CORRECT TENSION AND MARKED
eaa54dd8-5ab3-4d01-b5c3-4cf63231884d | checkpoint | IS THE CABLE FREE OF DAMAGE?
c1f5c738-d11f-409b-8ed5-62a0cc3e5d77 | checkpoint | CABLE AND TERMINATIONS CORRECTLY LABELLED?
52d84b74-b36d-4497-8d11-de85e5e6e0ec | checkpoint | NOEW SUBMITTED TO COUNCIL
4bbf6621-9e06-406a-97a8-776a9cf9c235 | checkpoint | FINAL ACCEPTANCE:
fecc5fd7-962c-55cc-9ce3-4788228ace0f | textbox | HEYDAY GROUP (REPRESENTATIVE)
304b5f76-76f2-5a9d-8fd6-f1113295313d | textbox | CLIENT (REPRESENTATIVE)
f3e13d85-87a9-5ce2-bdd0-67a2d6cf001e | textbox | AUTHORITY (IF APPLICABLE)
20326dc3-a95a-4288-8b3a-a61734c82681 | signoff | Signoff
fef975bc-524b-4ca3-9b4c-aac8f241bdd7 | checklist | ITC - (4A) Mains and Submains Test Results |  | ITC - (4A) Mains and Submains Test Results
82f150d2-bf2b-455f-a0a0-b888077cb6f8 | section | Details
57d6f350-c086-4bf2-8ef7-f52f557f11d7 | checkpoint-no-value | Details
648ee359-7797-512f-b43b-2b101de338eb | textbox | Area
ba6047db-927e-5cfb-a543-4109a6fb33ea | textbox | From
feb5ca1b-9878-5a9f-be55-ae426d9e219e | textbox | Cable No.
f193658b-43bb-5da3-920a-752eba3e1f32 | textbox | MCCB Model
b95e8d15-15aa-5017-8858-e949bac1190b | textbox | Cable Type
18aa6ecf-a264-5f90-846c-713220b769c9 | textbox | Rating (A)
51cb65b5-b829-5a9d-927a-60cc1f9cd57a | textbox | Drawing No.
4a43fa00-c36a-51e0-8905-cea9592203ed | textbox | To
90557bc5-89fd-57f5-bb90-28ed37d8ec10 | textbox | Cable Size
e6eb31f1-e1bb-5da0-ad0a-7fb8e365726a | textbox | Trip Unit
c9186110-0e87-55aa-843e-762d702b7324 | textbox | Length
56a1e761-c090-5b4f-bfa1-1242b204b455 | textbox | Trip Setting (A)
366b1ec8-f18a-52b8-9342-0ebcd23f1d5f | textbox | Cores
1bab087d-4950-4b65-804a-e573d2f696e9 | section | 1 - Pre Energisation Checks (AS/NZS 3000)
1588bbb0-68f1-40eb-ac5e-cdf118d49e45 | checkpoint | Bolt Tension Check/Bolt Lined and Tension noted?
201db8f5-27e3-5c3d-b831-560cd9c67f4c | textbox | NM
c16abd11-bd98-47b5-92b2-0cd0e43f9fb4 | checkpoint | Earth Continuity (Value must be less than 0.5 ohms)
22a434f5-4d8c-56ed-bf14-6373af22fd7f | textbox | Resistance (target <0.5ohms)
a7b12246-8c61-4fd2-97cc-ed11e7cddecf | checkpoint | Insulation Resistance Test - RED TO WHITE >1 MOhm
7e127cae-5463-49a9-bb10-6f7c32b826cd | checkpoint | Insulation Resistance Test - RED TO BLACK >1 MOhm
d3f0b351-dc82-45d7-90e3-af641994d5b6 | checkpoint | Insulation Resistance Test - RED TO EARTH >1 MOhm
bb93eda6-3377-4b2c-bd68-4220f4b836cd | checkpoint | Insulation Resistance Test - WHITE TO BLUE >1 MOhm
60f6ba2d-d8e4-49e3-99dd-48ca1dfc2b6c | checkpoint | Insulation Resistance Test - WHITE TO BLACK >1 MOhm
0e2f0106-661f-4da8-9a89-13b9e79ef2eb | checkpoint | Insulation Resistance Test - WHITE TO EARTH >1 MOhm
446213e7-8180-4cc8-b62e-7ec216b24ca7 | checkpoint | Insulation Resistance Test - BLUE TO RED >1 MOhm
d6002a81-7bbb-4130-8d42-4fa81b62a20f | checkpoint | Insulation Resistance Test - BLUE TO BLACK >1 MOhm
2535a1b3-71b8-4353-9eb8-011093624733 | checkpoint | Insulation Resistance Test - BLUE TO EARTH >1 MOhm
ce8b2dc3-d8f1-4f89-af48-4fc2835c2588 | section | 2 - Polarity Test
7a37b59e-9908-4abc-b09b-85ee2f50d99c | checkpoint | RED TO RED
59235388-35a1-51d2-82f2-8f5c2eb4d82a | textbox | RED TO RED:
de146485-9396-407d-bd07-f3fe4e7d4dca | checkpoint | WHITE TO WHITE
8f2a614c-1ecc-53fb-b197-55dbc6465954 | textbox | WHITE TO WHITE:
052b1df7-87ce-424f-a242-012be3a7d4bd | checkpoint | BLUE TO BLUE
5b944cb8-e172-589c-969c-66521c337174 | textbox | BLUE TO BLUE:
125ddc90-51b9-4e21-b192-3ee19b5af396 | checkpoint | BLACK TO BLACK
6437b325-2f8f-54d7-9b55-b178810e0078 | textbox | BLACK TO BLACK:
36d40662-fa41-4129-99d1-d20972d8761a | section | 4 - Post Energisation Checks (AS/NZS 3000) - Phase Rotation
7ff2f963-ee18-4255-872d-1587491e7c8b | checkpoint | Phase Rotation
03f09519-24ce-568f-97df-1debf2b9c15e | tickbox | Clockwise →
ce3eea71-aa1d-5109-98cf-66cc82712637 | tickbox | Anti Clockwise ←
6ead16e2-09da-4ab9-be1f-739a4fd867b0 | checkpoint | Voltage Check - RED TO WHITE
cdba07ed-82ed-5a77-a71f-d395f63c0d14 | textbox | Voltage
2d6a9615-b40e-405d-ad4c-2ed7b206e631 | checkpoint | Voltage Check - RED TO BLACK
30088395-2e6f-5981-b188-6a53fdfb094a | textbox | Voltage
1f33f3f6-86f6-4b60-a565-21c912baf4ce | checkpoint | Voltage Check - RED TO EARTH
08075cd3-d130-56b6-a8d8-f32beb23206a | textbox | Voltage
06ad9dc4-5626-4d80-9d8e-9788cf11c02e | checkpoint | Voltage Check - WHITE TO BLUE
c3c98ce1-8ce4-5072-9b88-b2653e1c5bc1 | textbox | Voltage
970f3875-d07d-4e1f-a517-3eb9ed12ce7a | checkpoint | Voltage Check - WHITE TO BLACK
b23ce394-6e9a-5503-a890-9dc8dfb80839 | textbox | Voltage
874ec785-bfe8-4746-88b4-8430653589c3 | checkpoint | Voltage Check - WHITE TO EARTH
7af94a2e-179b-5487-a0e5-74bd52dd56b6 | textbox | Voltage
008c2844-ddde-4f26-bcd7-cfb49140a664 | checkpoint | Voltage Check - BLUE TO RED
68b4ac59-3bd3-5749-97e1-5a6a159bedb8 | textbox | Voltage
236b8ae6-a432-471e-b7bd-d58e193066f7 | checkpoint | Voltage Check - BLUE TO BLACK
25fa6154-42af-5d51-89ff-6671bd6bb4b4 | textbox | Voltage
0591c157-2db4-4471-87fb-e2e00b1c0fbe | checkpoint | Voltage Check - BLUE TO EARTH
bb175cfe-08f2-5ee2-a943-d2741af9ac6d | textbox | Voltage
66d6a0ea-494b-4bce-b653-80a756998450 | checkpoint | Fault Loop Impedance (If Applicable) - Cables have been installed as per design calculations.
d1da70aa-c06b-53db-b814-559a659aef6f | note | Note, if FAIL seek design clarification to adjust circuit breaker tripping curve characteristics.
f2ebf1ac-1626-484c-abc8-5bcfe8099685 | checklist | ITC - (5) Cable Tray-Ladder-Trenching |  | Level / Area:
920611f6-3a6f-4240-b900-109da4fda7cd | section | Details
bba4f696-0c04-4b6c-8217-41e60e53d572 | checkpoint | AREA/LOCATION TO DRAWING
a1ec429e-da12-4acf-a6fa-41aa3a2043ff | checkpoint | CORRECT SIZE, TYPE & SPARE CAPACITY
bef8cdbf-0216-4063-bc1f-abe324135a80 | checkpoint | GALVANISED / PAINTED
474bc696-080a-43d6-be18-e10e899c7f81 | checkpoint | CORRECT SPACING
12697dfe-901e-4bcb-b4f5-9962a793bb43 | checkpoint | CORRECT ALIGNMENT
48850c21-dac9-4b65-a4b5-a2c8151f122f | checkpoint | CORRECT BRACKETS AND SAFE FIXING
69d802cf-ab5d-41a9-a817-43682858afbc | checkpoint | CLEAR TO OTHER SERVICES
c771ce99-7f2b-4e16-84ea-261ef4aec66b | checkpoint | FINAL ACCEPTANCE:
4126777a-b4a4-50f2-94a4-81beb0af6a2d | textbox | HEYDAY GROUP (REPRESENTATIVE)
5e17ad88-e91a-56d7-9803-06b67869f7da | textbox | CLIENT (REPRESENTATIVE)
6ffd2f0d-cb4f-539b-a1d2-b5c5ce6809f1 | textbox | AUTHORITY (IF APPLICABLE)
62525a6d-8b61-40a2-9fa9-beff73978b8d | signoff | Signoff
6edae76c-923d-469c-a87b-6a757e2f7e4e | checklist | ITC - (6) Conduit |  | Level / Area:
c8380545-b8df-4e8a-91b5-bb6a3506a157 | section | Details
7cfb0b11-d20e-4085-afe6-71b7e2af14bf | checkpoint | CORRECT LOCATION TO DRAWING
eb28fcf5-bda2-4081-8c34-e5f3a38d678f | checkpoint | CORRECT SIZE AND TYPE
70570835-e05a-4498-8ceb-25c2be910385 | checkpoint | CORRECT SPACING IN SLAB
f9ecdf3a-6480-4545-8ff0-4c367e3d3213 | checkpoint | CORRECT ALIGNMENT
f4b5f9c2-09f9-4e52-9600-bf70c5f7bf8f | checkpoint | CLEAR TO OTHER SERVICES
14e8ba94-6450-4c5f-afad-e3af013ab3fd | checkpoint | CORRECT DEPTH U/GROUND
42061315-6285-4aaa-8a2c-150dd2d11ef7 | checkpoint | CORRECTLY MARKED (TAPE OR OTHER)
1756a309-3a33-4910-9760-4f37d3a48b88 | checkpoint | CORRECT FIXING AND SAFE
bce82d1d-d6b0-458d-9d59-41c9809f8483 | checkpoint | CORRECT BACKFILL AND SURFACES
d78779fe-9e2e-4cd6-b426-95f9352e59be | checkpoint | FINAL ACCEPTANCE:
261e314d-70e1-5757-aa4f-28a28d7b67c8 | textbox | HEYDAY GROUP (REPRESENTATIVE)
525b1980-8e8a-5038-a5cd-094be223278a | textbox | CLIENT (REPRESENTATIVE)
852accf6-8dd6-5bcb-895e-08a6fd83d541 | textbox | AUTHORITY (IF APPLICABLE)
5c5ed48e-2992-4f51-99ba-993e8dc8970f | signoff | Signoff
4f358674-e0ff-4d07-a793-b89762618f7d | checklist | ITC - (7) Light and Power Circuits |  | Level / Area:
bc960f86-88c4-4ad1-9b8f-18710060353f | section | Details
0891ee32-74f9-495c-9563-930a0aa519f0 | checkpoint | RETICULATION
8b2a069f-296d-4980-8048-0f45b6332a06 | checkpoint | ROUGH IN
9cb16bf8-c561-4cb0-beba-6307428003ac | checkpoint | FIT OFF
639b97b1-aab8-4db5-9a7b-9c79cc5422b6 | checkpoint | READY FOR TESTING AND COMMISSIONING AS PER ITC 7A AND 7B
ecdb577a-59f1-4503-a84b-fab138a2334b | checkpoint | FINAL ACCEPTANCE:
8897ff8f-7443-57a7-9004-3c8197087a34 | textbox | HEYDAY GROUP (REPRESENTATIVE)
1f8c7266-088e-59b2-8999-bb25af78682e | textbox | CLIENT (REPRESENTATIVE)
5fc7f560-abb7-512d-a282-72e25e2dac12 | textbox | AUTHORITY (IF APPLICABLE)
e430b7b9-078b-416d-b700-a5c4ed9268eb | signoff | Signoff
c93ff0ee-2cb1-42e5-a2b6-4a4829a4957f | checklist | ITC - (7A/B) Light and Power Circuits |  | ITC (7A/B) - LIGHT/POWER Circuits
f3eccfa8-4658-4fee-acef-73d7d419c6ab | section | Lighting/Power Circuits Field PRE
35bda9a0-3e0d-4fba-972e-9ae7cc631c1e | checkpoint | Lighting/Power Circuits Field PRE ITC
860408ee-416b-55aa-bd79-cd0bcdf8780a | textbox | C/B No.
2f637e7f-ccfe-5d59-9490-e477fd55d90f | textbox | C/B Size
897afcf4-93c9-59ef-ab4e-5b942ff1d37b | textbox | Cable Size
7da9abd5-53c5-4178-8914-e6600b1add2f | checkpoint | Earth Resistance (must be less than 0.5 ohms)
3996fcca-a363-55ce-b97d-9f4742802e3a | textbox | Resistance (target <0.5ohms)
ec76a3a2-1553-46da-b2c8-e376ea9f02da | checkpoint | Insulation Resistance ( >1MOhm)
96378376-e1fb-4150-8a60-54fbcb094def | checkpoint | Polarity
f8a3f49e-44ba-4459-b31a-4af35f15181c | checkpoint | Safe to Energise
1bfc178e-5d4f-5134-8730-bc32774150ee | textbox | Tested By
3d34005d-10e8-5182-a121-33dcb9990c02 | date | Date:
393c5b2d-664f-4e16-b283-ede4551948e9 | signoff | Sign
9cc615e1-1df8-479c-8387-d27e18292833 | checkpoint | FINAL ACCEPTANCE:
7de26fb4-dda6-532a-aa93-28b5b7566e1d | textbox | HEYDAY GROUP (REPRESENTATIVE)
c2438063-72d5-5afe-94eb-13aeae058c65 | textbox | CLIENT (REPRESENTATIVE)
2f00bd06-ccba-507a-b259-7cdcb52e3e69 | textbox | AUTHORITY (IF APPLICABLE)
82388e1e-2e73-4e2d-99f5-9968941a3c2f | signoff | Signoff
8a5d88b4-270a-4431-b4d8-d63c79a19bbc | section | Lighting/Power Circuits Field POST ITC
b51851a3-64f9-4f2a-a823-e6955afbbc12 | checkpoint | Voltage Check - RED TO WHITE
b632fa87-ab3c-54d4-9fea-ae04217e71ac | textbox | Voltage
3987d8ea-7c2a-4432-a716-fff729774bd7 | checkpoint | Voltage Check - WHITE TO BLUE
93286b25-7e63-5bcc-a975-fc3fc29f898b | textbox | Voltage
38201475-77f2-4f9a-9cc0-8d1f0ff707b6 | checkpoint | Voltage Check - BLUE TO RED
03e27eaa-69ae-5a09-a72a-9586eefe3bdc | textbox | Voltage
b968e1c0-b71f-4763-8fe5-d0e85747212a | checkpoint | Voltage Check - Active to Neutral
c85a855c-a003-5fcd-b2f0-7d3c4a88c090 | textbox | Voltage
13fce32e-c7c2-4b33-9566-37226cce7530 | checkpoint | Voltage Check - Active to Earth
ffc98cae-caaf-5175-880a-f6e88b3cf7af | textbox | Voltage
5becd56c-a617-4f90-ac4a-a0cfc54ceb01 | checkpoint | RCD-RCBO Tripping Test
3cf6e2de-f557-56bf-8359-4d3be6964369 | textbox | Trip Current (mA)
8880bfe3-cc40-501a-a495-1a3250a79667 | textbox | Trip Time (ms)
b0ed8832-2250-4217-a319-f058ab515264 | checkpoint | Fault Loop Impedance - (N/A if the circuit is RCD Protected)
5fb3056a-4ec0-5e1d-a670-b05b2761d06d | textbox | Record Inpedance (Ω)
dba0a317-7bce-560f-acf0-229791cbd5a9 | textbox | Target Impedance (Ω)
d4aacacc-c7f8-4b88-8871-db6ca060c10b | checkpoint | Energised By
a01526e0-26c4-5554-bb79-eb4c7ced9992 | textbox | Initial:
df308b60-bcd7-5963-9ed0-6082632c83da | date | Date:
e683f0bf-5093-42cc-8f19-842f158d3693 | signoff | Sign
5013b5f5-7824-451a-917c-3ae082e2ce5c | checkpoint | FINAL ACCEPTANCE:
618f109d-cbaa-555a-88a3-6a271509e609 | textbox | HEYDAY GROUP (REPRESENTATIVE)
39f1ee14-b43f-5634-bf17-5af175fb7f26 | textbox | CLIENT (REPRESENTATIVE)
fbc28a78-fccb-53b6-932b-2d920138ad97 | textbox | AUTHORITY (IF APPLICABLE)
568b14ad-bc4a-47e4-ad67-5718f26e112b | signoff | Signoff
7723fd4a-6160-40e5-9477-38082fe97946 | checklist | ITC - (8) Light Fittings |  | ITEM No:
dd317154-1b89-4384-94f9-5d511d8fd28f | section | Details
84337d3c-aecd-4f41-9ee6-47f57b6bcdd2 | checkpoint | CORRECT LOCATION TO DRAWING
7fc8963e-319b-4469-8537-91af59550659 | checkpoint | CORRECT SIZE AND TYPE
d32e13f0-235c-4006-9185-9360719c6d58 | checkpoint | DAMAGE
0fefaf87-6e9b-49f6-86fb-fc4043de50e0 | checkpoint | CORRECT LAMPS
0ff6e0ae-8c26-443b-9d24-1b4fad50e40f | checkpoint | CORRECT DIFFUSERS/ REFLECTORS
d3d24535-07eb-4ed7-bd6a-eca2729d020e | checkpoint | CORRECT OPERATION
94e81169-fcfc-4a49-ad64-221e9a5d216a | checkpoint | CORRECT CIRCUIT / DB DESTINATION
6cae9e14-cd00-42ed-acfa-616ed68a5d1e | checkpoint | CORRECT LABELLING
abfb4b98-6fac-4255-933e-51d03297be0f | checkpoint | FINAL ACCEPTANCE:
0e69ce08-3f8d-529f-9197-6819c309d3a2 | textbox | HEYDAY GROUP (REPRESENTATIVE)
2796a5fb-d963-57e5-9cb8-b070896adece | textbox | CLIENT (REPRESENTATIVE)
471e539f-c59d-55d2-8e4a-0961dfa995fd | textbox | AUTHORITY (IF APPLICABLE)
f8e0c4b3-3271-48e0-87fc-d9288bc4e5ae | signoff | Signoff
b175a565-abaa-46bd-a67f-87b206c90123 | checklist | ITC - (9) Electrical Equipment-Accessories |  | ITEM No:
fc7486b9-fd54-41fd-8f5e-30fadf8c447a | section | Details
bc256e29-ed47-4a93-be71-8bc7d8ef783f | checkpoint | CORRECT TYPE / COLOUR
c2dead83-7230-44b6-b5df-fb8b7527fed7 | checkpoint | CORRECT ALIGNMENT LOCATION
aa6639f0-3026-4bf0-843e-ad03006fb6d5 | checkpoint | CORRECT FIXING AND MADE SAFE
e3ed7d96-d988-471c-b69a-ab97bba869a9 | checkpoint | CORRECT LABELLING
3528320e-cd1b-4b8c-a68a-9b846a238012 | checkpoint | CORRECT TERMINATION
f930fd85-44b0-4e43-94d9-0d1178feba08 | checkpoint | CORRECT EARTHING
3d5ef8ca-384f-4dd6-8fb7-70f0c5652bf4 | checkpoint | CORRECT IP RATING
dfc2b502-8dff-4dcb-bfed-b01ba66d5d16 | checkpoint | CORRECT CLASSIFICATION
13421599-6b08-4a3e-9e6e-b08a4ffe6711 | checkpoint | FINAL CHECK AND NO DAMAGE
dc5b922a-513e-4b2a-9b70-c301e9e9bfe1 | checkpoint | FINAL ACCEPTANCE:
c220556c-0b2d-55bf-8185-1f5872a7438f | textbox | HEYDAY GROUP (REPRESENTATIVE)
5238c6e2-add2-5661-a098-f87ea123997e | textbox | CLIENT (REPRESENTATIVE)
b612534e-8c3d-5f4c-8cd9-9963fc913780 | textbox | AUTHORITY (IF APPLICABLE)
e53a4e22-8c4c-4b9b-a719-198deae929bd | signoff | Signoff
596fd4d9-8739-4427-b45b-968bf4d6cfb3 | checklist | ITC - (10) Cardiac Earthing |  | Cardiac Earthing
f2533806-86bf-494e-898a-cefd257a2488 | section | Details
ba89d854-7d25-4ba7-a5ad-19b097269c6d | checkpoint-no-value | Area Tested
45d9046d-beab-5c7b-807f-87f428d85934 | textbox | DESCRIPTION:
83da3d86-d4f4-5eb1-91ea-d13537369c2d | textbox | CABLE DETAILS: FROM
620adca4-fd18-5e55-bbfc-d20f1c3c46f8 | textbox | CABLE DETAILS: TO
c0b15e51-062e-428c-be4f-390ef1809d47 | checkpoint | CABLE SIZE INSTALLED AS PER AS/NZS 3003:2018 TABLE D1
ff675f7f-f6da-4995-b49c-3426f891e5e6 | checkpoint | ROUGH IN – HIGH / LOW LEVEL
4a8f9048-4e3f-4a40-8268-4b1c19eba495 | checkpoint | FIT OFF
c88b1ef6-92a8-4723-9e64-7ee16715bbee | checkpoint | POINT TO POINT TEST
d15b41ec-ead6-41fb-970f-5d10be2e5578 | checkpoint | DRAWINGS MARKED UP TO REFLECT AS-INSTALLED
53d58afe-7a74-4c26-b7bc-723d8063baf2 | checkpoint | FINAL ACCEPTANCE:
52967c5f-59f2-52f7-876e-e55d110772bb | textbox | HEYDAY GROUP (REPRESENTATIVE)
3e8d9782-0485-573f-a820-34a15bf3b1d7 | textbox | MULTIPLEX (REPRESENTATIVE)
b30f4564-1676-526a-821d-0334a03798e6 | textbox | CLIENT (IF APPLICABLE)
e4d60a7c-1b37-454f-a677-ac24b49f99d4 | signoff | Signoff
1ff82eba-0e1c-472e-ad51-5f1738de4c7c | checklist | ITC - (11) Testing and Commissioning |  | TESTING AND COMMISSIONING
193b1ff4-8ba7-4de0-956b-1422e1344d72 | section | Details
3f38af66-12a6-4220-9cf5-6af3d3cb8deb | checkpoint | EQUIPMENT/ SYSTEM TO BE COMMISSIONED
f7e4b490-3eb5-5bba-9c1d-c3c9c70bebe1 | textbox | GIVE BRIEF DESCRIPTION
0b55aceb-ddaa-50ce-8f81-cbb7d1697d21 | date | DATE OF TESTS
faba75c9-d947-58f5-b326-06e263429e39 | textbox | INSPECTION/WITNESS BY (NAME, COMPANY/DEPARTMENT)
f4809fe5-803f-5ea8-b20e-7819b08682b2 | button | ACCEPTANCE | Yes,No
605a4ce1-7e8c-5def-aa21-a2c834d6e1a1 | textbox | CONFIRMATION NAME
01281034-b652-4058-88c7-fcbdf55348b0 | signoff | SIGNATURE
d3fc98ff-2e2a-46ae-a434-d8573a9d9beb | checkpoint | FINAL ACCEPTANCE:
5ea03330-1d63-5b6e-8dee-062dc1e53cf6 | textbox | HEYDAY GROUP (REPRESENTATIVE)
75fa5730-08a1-5283-9b10-bceda323758e | textbox | CLIENT (REPRESENTATIVE)
402fec24-391d-5128-aab8-87e0be87d2a0 | textbox | AUTHORITY (IF APPLICABLE)
28ccff54-c27c-4562-9f77-d974869ecabe | signoff | Signoff
eaa1f6dc-225d-4629-bcce-ff6a6882da6d | checklist | ITC - (12) As Built Drawings-Maintenance Manuals |  | AS BUILT DRAWINGS/MAINTENANCE MANUALS
f4e5a3dc-b422-4be2-b08a-cf3cf2e263a3 | section | Details
6a2e94e9-b84d-4038-a122-a7f161ac8b9f | checkpoint | AS BUILT DRAWINGS
c85bb9ee-8545-5510-9a0a-3dd4cc091a65 | textbox | AS BUILT DRAWINGS NO:
b17d012f-e812-5d31-8086-7b4b9dee2901 | textbox | DRAWING TITLE
3d174f43-cae1-550b-89b4-05591471fb74 | textbox | FINAL REVISION AND DATE
d0ed5878-dada-560b-978f-300e764571b0 | button | MANUALS (DRAFT) ACCEPTANCE | Yes,No
45b3b6ba-d664-42e6-85ce-6a0d303c2067 | checkpoint | MANUALS AND DRAWINGS SUBMITTED
57f77736-0f30-4ea9-85e3-635c402cef04 | checkpoint | FINAL ACCEPTANCE:
5650c709-bc8d-53df-aba0-ab175b2a4861 | textbox | HEYDAY GROUP (REPRESENTATIVE)
951833b4-78b3-56a2-9d6f-d11dc90fb938 | textbox | CLIENT (REPRESENTATIVE)
7bc46153-7523-52c3-b4a5-93e7670a192f | textbox | AUTHORITY (IF APPLICABLE)
a504bf94-ff1b-4de4-bc35-d59355422521 | signoff | Signoff
41b466b6-9df0-4c8a-9a4c-10cd927a98e9 | checklist | Test Equipment |  | Test Eqipment FIC
8dcf25b6-b519-4af6-8b3c-785deeb02c7a | section | Test Equipment
c897b29e-03e1-4f06-a2b5-52d97a50b028 | checkpoint | Multimeter
e5b2096b-1b97-519c-be1c-2f4758aeccb6 | textbox | Brand/Model
147f248c-4a96-5b10-bd86-7719ff318c3e | textbox | Serial No.
11b521a9-acee-5505-9be0-678a42f2db98 | textbox | Calibration Due
29f31a0d-1564-5262-9387-ddf414f42492 | textbox | Tester
f9e85620-960e-5e3e-8ad1-31809c1b3267 | date | Date:
8837b2c9-4ac5-4837-81de-45e2d35b86dc | checkpoint | Insulation Resistance Tester
4e9d3a24-9ffa-50a9-8451-7f720463ad78 | textbox | Brand/Model
2c0c1eab-9c26-57df-a3f4-82094a7a2ebd | textbox | Serial No.
6562a621-ade2-5563-853c-2aa1c7387422 | textbox | Calibration Due
f2bb7958-efbb-5562-a282-e443ec226c1a | textbox | Tester
14921bf5-6aec-5f10-88bf-c42b4b5edc0f | date | Date:
9bdba2d5-4d9d-4709-8c9b-cc46e55641bb | checkpoint | Phase Rotation Meter
dcbd1aec-d858-52a4-bd25-1cf4059a5353 | textbox | Brand/Model
62890e49-b582-59f0-bca9-31d9288ca67c | textbox | Serial No.
fb67502f-45ba-5bc5-b93e-dbade89d6da2 | textbox | Calibration Due
bf7d4b3b-0adb-5634-b10c-634187cf9138 | textbox | Tester
807b544c-9cc5-5e60-9769-7053643f4927 | date | Date: