## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | INSPECTION & TEST PLAN (ITP) | itp |  |  |  |  | PROJ3001 - INSPECTION & TEST PLAN (ITP)
section | Details
checkpoint | 1/1A - DRAWINGS (FOR CONSTRUCTION)
label | ACCEPTANCE CRITERIA: 3,7
checkpoint | 2 - MAIN AND DISTRIBUTION PANELS
label | ACCEPTANCE CRITERIA: 1,2,3,5
checkpoint | 3 - MAINS AND SUBMAINS
label | ACCEPTANCE CRITERIA: 1,2,3,5
checkpoint | 4 - CABLE TRAY / LADDER / TRENCHING
label | ACCEPTANCE CRITERIA: 2,3
checkpoint | 5 - CONDUIT
label | ACCEPTANCE CRITERIA: 1,2,3
checkpoint | 6 - LIGHT AND POWER CIRCUITS / DETECTION & EWIS CIRCUITS
label | ACCEPTANCE CRITERIA: 1,2,3
checkpoint | 7 - LIGHT FITTINGS
label | ACCEPTANCE CRITERIA: 1,2,3,5
checkpoint | 8 - ELECTRICAL EQUIPMENT / ACCESSORIES
label | ACCEPTANCE CRITERIA: 1,2,3
checkpoint | 9/9A - TELECOM RETICULATION
label | ACCEPTANCE CRITERIA: 1,2,3,7
checkpoint | 10/10A - SKIRTING DUCT
label | ACCEPTANCE CRITERIA: 1,2,3
checkpoint | 11 - MATERIAL DELIVERY
label | ACCEPTANCE CRITERIA: ---
checkpoint | 12/12A - LIGHTNING PROTECTION
label | ACCEPTANCE CRITERIA: 2
checkpoint | 13/13A - AUDIO VISUAL RETICULATION (MATV)
label | ACCEPTANCE CRITERIA: 2
checkpoint | 14/14A - EWIS / FIRE PROTECTION RETICULATION
label | ACCEPTANCE CRITERIA: 2
checkpoint | 15/15A - SECURITY / INTERCOM / CCTV
label | ACCEPTANCE CRITERIA: 2
checkpoint | 16/16A - POWER GENERATION (CONTROL & POWER CABLING)
label | ACCEPTANCE CRITERIA: 2
checkpoint | 17 - NURSE CALL
label | ACCEPTANCE CRITERIA: 2
checkpoint | 18 - POWER FACTOR CORRECTION EQUIP
label | ACCEPTANCE CRITERIA: 1,2,3,5
checkpoint | 19 - BUSDUCT
label | ACCEPTANCE CRITERIA: 1,2
checkpoint | 20 - (DATA) MDF/IDF/TPF/BD/FD/TO
label | ACCEPTANCE CRITERIA: 1,2,3,4
checkpoint | 21 - (DATA) CABINETS
label | ACCEPTANCE CRITERIA: 1,2,3,4,5
checkpoint | 22 - (DATA) BACKBONE - FIBRE OPTIC CABLE
label | ACCEPTANCE CRITERIA: 1,3,4,5,8
checkpoint | 23 - (DATA) BACKBONE - COPPER CABLE
label | ACCEPTANCE CRITERIA: 3,4,5,8
checkpoint | 24 - (DATA) TELEX EARTH / TRL
label | ACCEPTANCE CRITERIA: 1,3,4,5,8
checkpoint | 25 - (DATA) HORIZONTAL - FIBRE OPTIC
label | ACCEPTANCE CRITERIA: 1,3,4,5,8
checkpoint | 26 - (DATA) HORIZONTAL - COPPER CABLE
label | ACCEPTANCE CRITERIA: 1,3,4,5,8
checkpoint | 27 - (DATA) EQUIPMENT - HUBS & EQUIP CABLES
label | ACCEPTANCE CRITERIA: 1,3,4,5,8
checkpoint | 28/28A - RODING, HAULING & BLOWING CABLE
label | ACCEPTANCE CRITERIA: 2,3,8,9
checkpoint | 29/29A - COPPER, FIBRE OPTIC TERMINATION
label | ACCEPTANCE CRITERIA: 2,3,8,9
checkpoint | 30/30A - TESTING / COMMISSIONING
label | ACCEPTANCE CRITERIA: 2
checkpoint | 31 - AS BUILT DRAWINGS / MANUALS
label | ACCEPTANCE CRITERIA: 2
checkpoint | 32 - WHS&R
label | ACCEPTANCE CRITERIA: 2
checkpoint | 33 - ENVIRONMENTAL MANAGEMENT (2 PAGES)
label | ACCEPTANCE CRITERIA: 2
checkpoint | 34 - COMMISSIONING OF SUBCIRCUIT
label | ACCEPTANCE CRITERIA: 1,2,3
checkpoint | 65 - TEMPORARY WIRING & DB’S
label | ACCEPTANCE CRITERIA: 2,10
checklist | DRAWING REGISTER (FOR CONSTRUCTION ONLY) | [5 empty] | PROJ3002 - ITC - (1) Drawing Register (For Construction)
section | Details
checkpoint-no-status | Details
date | Date:
textbox | DRAWING No.
textbox | DRAWING TITLE
textbox | REVISION / ISSUE
checkpoint-no-status | DISTRIBUTION:
textbox | SITE OFFICE
textbox | SITE
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | DRAWING REGISTER (FOR CONSTRUCTION ONLY) | [5 empty] | PROJ3003 - ITC - (1A) Drawing Register (For Construction)
section | Details
checkpoint-no-status | Details
date | Date:
textbox | DRAWING No.
textbox | DRAWING TITLE
textbox | REVISION / ISSUE
checkpoint-no-status | DISTRIBUTION:
textbox | SITE OFFICE
textbox | SITE
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | BOARD TYPE / NUMBER / AREA: | [5 empty] | PROJ3004 - ITC - (2) Main and Distribution Panels
section | Details
checkpoint | ACCEPTANCE CRITERIA
checkpoint | MFG QA
checkpoint | DAMAGE
checkpoint | LOCATION TO DRAWING
checkpoint | EQUIPMENT TO DRAWING
checkpoint | CONNECTIONS INCOMING & OUTGOING BY HEYDAY.
checkpoint | NEUTRAL CONNECTIONS CORRESPOND
checkpoint | CORRECT EARTHING AND SOLIDLY FIXED
checkpoint | POLE FILLERS INSTALLED
checkpoint | ALL CABLE ENTRIES WITH ESCUTCHEON PLATES AND SEALS FITTED
checkpoint | BOARD SEALED AND LOCKED FOR SAFETY INC: FRONT AND REAR PANELS
checkpoint | LABELS AND SCHEDULE LIST CORRECT AND INSTALLED
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | MAINS AND SUBMAINS | [5 empty] | PROJ3005 - ITC - (3) Main and Submain
section | Details
checkpoint-no-status | Details
textbox | LEVEL
textbox | AREA
textbox | FED FROM
textbox | TO DB No
checkpoint | COMPLIES TO SPEC AND LATEST DRG
checkpoint | SIZE CORRECT
checkpoint | INSTALLED CORRECT
checkpoint | TERMINATED
checkpoint | TESTED AS PER NOEW FORM
checkpoint | NOEW SUBMITTED TO COUNCIL
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | LEVEL / AREA: | [5 empty] | PROJ3006 - ITC - (4) Cable Tray-Ladder-Trenching
section | Details
checkpoint | AREA/LOCATION TO DRAWING
checkpoint | CORRECT SIZE, TYPE & SPARE CAPACITY
checkpoint | GALVANISED / PAINTED
checkpoint | CORRECT SPACING
checkpoint | CORRECT ALIGNMENT
checkpoint | CORRECT BRACKETS AND SAFE FIXING
checkpoint | CLEAR TO OTHER SERVICES
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | LEVEL / AREA: | [5 empty] | PROJ3007 - ITC - (5) Conduit-Catenary
section | Details
checkpoint | CORRECT LOCATION TO DRAWING
checkpoint | CORRECT SIZE AND TYPE
checkpoint | CORRECT SPACING IN SLAB
checkpoint | CORRECT ALIGNMENT
checkpoint | CLEAR TO OTHER SERVICES
checkpoint | CORRECT DEPTH U/GROUND
checkpoint | CORRECTLY MARKED (TAPE OR OTHER)
checkpoint | CORRECT FIXING AND SAFE
checkpoint | CORRECT BACKFILL AND SURFACES
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checkpoint-no-status | Details
textbox | LEVEL
textbox | AREA
textbox | D.B. No:
textbox | CCT No:
textbox | C/B No:
checkpoint | CONDUIT
checkpoint | ROUGH IN
checkpoint | FIT OFF
checkpoint | TESTED
checkpoint | NOEW SUBMITTED TO COUNCIL
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM No: | [5 empty] | PROJ3009 - ITC - (7) Light Fittings
section | Details
checkpoint | CORRECT LOCATION TO DRAWING
checkpoint | CORRECT SIZE AND TYPE
checkpoint | DAMAGE
checkpoint | CORRECT LAMPS
checkpoint | CORRECT DIFFUSERS/REFLECTORS
checkpoint | CORRECT OPERATION
checkpoint | CORRECT CIRCUIT / DB DESTINATION
checkpoint | CORRECT LABELLING
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM NO: | [5 empty] | PROJ3010 - ITC - (8) Electrical Equipment-Accessories
section | Details
checkpoint | CORRECT TYPE / COLOUR
checkpoint | CORRECT ALIGNMENT LOCATION
checkpoint | CORRECT FIXING AND MADE SAFE
checkpoint | CORRECT LABELLING
checkpoint | CORRECT TERMINATION
checkpoint | CORRECT EARTHING
checkpoint | CORRECT IP RATING
checkpoint | CORRECT CLASSIFICATION
checkpoint | FINAL CHECK AND NO DAMAGE
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM: | [5 empty] | PROJ3011 - ITC - (9) Telecommunications Reticulation
section | Details
checkpoint | QA CHECK AS PER SUPPLIER
date | DATE
textbox | DRAWING NO/SPECIFICATION CLAUSE
checkpoint | SYSTEMS / EQUIPMENT INSTALLATION
checkpoint | TEST AND COMMISSION
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM: | [5 empty] | PROJ3013 - ITC - (10) Skirting Duct
section | Details
checkpoint | QA CHECK AS PER SUPPLIER
date | DATE
textbox | DRAWING NO/SPECIFICATION CLAUSE
checkpoint | SYSTEMS / EQUIPMENT INSTALLATION
checkpoint | TEST AND COMMISSION
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | LEVEL/AREA: | [5 empty] | PROJ3014 - ITC - (10A) Skirting Duct
section | Details
checkpoint | AREA/LOCATION TO DRAWING
checkpoint | CORRECT SIZE, TYPE & SPARE CAPACITY
checkpoint | GALVANISED / PAINTED
checkpoint | CORRECT SPACING
checkpoint | CORRECT ALIGNMENT
checkpoint | CLEAR TO OTHER SERVICES
checkpoint | CORRECT FIXING AND SAFE
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM: | [5 empty] | PROJ3015 - ITC - (11) Material Delivery
section | Details
checkpoint | CHECK AGAINST ORDER/SPEC
date | DATE
textbox | MATERIAL DETAILS (BRIEF)
button | DAMAGE | Yes,No
date | DATE RETURNED TO SUPPLIER WITH NCR
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM: | [5 empty] | PROJ3016 - ITC - (12) Lightning Protection
section | Details
checkpoint | QA CHECK AS PER SUBCONTRACTOR
date | DATE
textbox | DRAWING / SPECIFICATION DETAILS
date | DATE REVISION APPROVED
textbox | ACCEPTANCE CRITERIA
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | LEVEL/AREA: | [5 empty] | PROJ3017 - ITC - (12A) Lightning Protection
section | Details
checkpoint | CORRECT LOCATION TO DRAWING
checkpoint | CORRECT SIZE AND TYPE
checkpoint | INSTALLED CORRECT
checkpoint | BONDING CONTINUITY
checkpoint | CORRECT DEPTH IN SLAB
checkpoint | CLEAR TO OTHER SERVICES
checkpoint | SYSTEM TEST
checkpoint | SYSTEM COMMISSION
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM: | [5 empty] | PROJ3018 - ITC - (13) Audio Visual Reticulation (MATV)
section | Details
checkpoint | QA CHECK AS PER SUPPLIER
date | DATE
textbox | DRAWING NO/SPECIFICATION CLAUSE
checkpoint | SYSTEMS / EQUIPMENT INSTALLATION
checkpoint | TEST AND COMMISSION
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | LEVEL/AREA: | [5 empty] | PROJ3019 - ITC - (13A) Audio Visual Reticulation (MATV)
section | Details
checkpoint | CORRECT LOCATION TO DRAWING
checkpoint | CONDUIT INSTALL TO DRAWINGS
checkpoint | CABLE INSTALL TO DRAWINGS
checkpoint | INSTALL EQUIPMENT
checkpoint | TERMINATE OUTLETS
checkpoint | TERMINATE EQUIPMENT
checkpoint | SYSTEM TEST
checkpoint | SYSTEM COMMISSION
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM: | [5 empty] | PROJ3020 - ITC - (14) Ewis-Fire Protection Reticulation
section | Details
checkpoint | QA CHECK AS PER SUBCONTRACTOR
date | DATE
textbox | DRAWING / SPECIFICATION DETAILS
date | DATE REVISION APPROVED
textbox | ACCEPTANCE CRITERIA
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | LEVEL/AREA: | [5 empty] | PROJ3021 - ITC - (14A) Ewis-Fire Protection Reticulation
section | Details
checkpoint | CORRECT LOCATION TO DRAWING
checkpoint | CONDUIT INSTALL TO DRAWINGS
checkpoint | CABLE INSTALL TO DRAWINGS
checkpoint | INSTALL EQUIPMENT
checkpoint | TERMINATE OUTLETS
checkpoint | TERMINATE EQUIPMENT
checkpoint | SYSTEM TEST
checkpoint | SYSTEM COMMISSION
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM: | [5 empty] | PROJ3022 - ITC - (15) Security-Intercom-CCTV
section | Details
checkpoint | QA CHECK AS PER SUPPLIER
date | DATE
textbox | DRAWING NO/SPECIFICATION CLAUSE
checkpoint | SYSTEMS/EQUIPMENT INSTALLATION
checkpoint | TEST AND COMMISSION
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | LEVEL/AREA: | [5 empty] | PROJ3023 - ITC - (15A) Security-Intercom-CCTV
section | Details
checkpoint | CORRECT LOCATION TO DRAWING
checkpoint | CONDUIT INSTALL TO DRAWINGS
checkpoint | CABLE INSTALL TO DRAWINGS
checkpoint | INSTALL EQUIPMENT
checkpoint | TERMINATE OUTLETS
checkpoint | TERMINATE EQUIPMENT
checkpoint | SYSTEM TEST
checkpoint | SYSTEM COMMISSION
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM: | [5 empty] | PROJ3024 - ITC - (16) Power Generation
section | Details
checkpoint | QA CHECK AS PER SUPPLIER
date | DATE
textbox | DRAWING NO/SPECIFICATION CLAUSE
checkpoint | SYSTEMS/EQUIPMENT INSTALLATION
checkpoint | TEST AND COMMISSION
checkpoint-no-status | REMARKS
label | TESTING & COMMISSIONING: REFER TO ISO STANDARD FOR POWER GENERATION TESTING & MANUFACTURERS SPECIFICATIONS/REQUIREMENTS.
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | LEVEL/AREA: | [5 empty] | PROJ3025 - ITC - (16A) Power Generation (Control Power Cabling)
section | Details
checkpoint | CORRECT LOCATION TO DRG
checkpoint | CONTROL CABLING FUEL SYSTEM
checkpoint | CONTROL CABLING DIESEL BOARD
checkpoint | CONTROL CABLING TERMINATING (TEST CABLE)
checkpoint | POWER CABLING FUEL SYSTEM
checkpoint | POWER CABLING GENSET TO BOARD
checkpoint | POWER CABLING TERMINATING (TEST CABLE)
checkpoint | ALL CONTROL & POWER CABLE LABELLED
checkpoint-no-status | REMARKS
label | TESTING & COMMISSIONING: REFER TO SPECIFIED PROGRAM & ISO STANDARDS FOR POWER GENERATION.
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM: | [5 empty] | PROJ3026 - ITC - (17) Nurse Call (Hospital Systems)
section | Details
checkpoint | QA CHECK AS PER SUPPLIER
date | DATE
textbox | DRAWING No/SPECIFICATION CLAUSE
checkpoint | INSTALLATION OF UNIT TO DRAWING
checkpoint | TEST AND COMMISSION
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM: | [5 empty] | PROJ3027 - ITC - (18) Power Factor Correction Equipment
section | Details
checkpoint-no-status | Details
textbox | ACCEPTANCE CRITERIA
textbox | MFG QA
checkpoint | EQUIPMENT TO DRAWING
checkpoint | CORRECT INSTALLATION
checkpoint | CONTROL CABLING
checkpoint | TERMINATION & TEST EQUIPMENT
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | LEVEL / AREA: | [5 empty] | PROJ3028 - ITC - (19) Busduct
section | Details
checkpoint | CORRECT LOCATION TO DRAWING
checkpoint | CORRECT SECTIONS AS PER DESIGN
checkpoint | CORRECT HANDLING EQUIPMENT USED
checkpoint | CORRECT FIXING AND STRUCTURAL CHECK
checkpoint | INSTALLED TO SUPPLIERS REQUIREMENT
checkpoint | EARTHING TO LOCAL AUTHORITY REQUIREMENT
checkpoint | TEST RESULTS AS PER SUPPLIERS REQUIREMENT
checkpoint | LABELLED
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | MDF/IDF/TPF/BD/FD/TO | [5 empty] | PROJ3029 - ITC - (20) MDF-IDF-TPF-BD-FD-TO
section | 1
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | MDF
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | 2
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | IDF
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | 3
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | IDF
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | 4
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | IDF
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | 5
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | IDF
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | 6
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | IDF
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | 7
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | IDF
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | 8
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | TPF
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | 9
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | BD
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | 10
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | FD
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | 11
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | FD
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | 12
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | FD
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | 13
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | FD
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | 14
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | TO
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | 15
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | TO
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | 16
checkpoint-no-status | LEVEL
textbox | LEVEL |  |  | TO
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | FRAMES LABELLED AND INSTALLED
checkpoint | RECORD INSTALLED
checkpoint | DRAWINGS MARKED AS INSTALLED
checkpoint-no-status | REMARKS
section | FINAL ACCEPTANCE
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | LEVEL: | [5 empty] | PROJ3030 - ITC - (21) Cabinets
section | Details
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | CABINET POSITIONING MARKED
checkpoint | CABINET CONFORMS TO SPECIFICATION
checkpoint | CABINET & ACCESSORIES INSTALLED & EARTHED
checkpoint | CABINET & ACCESSORIES LABELLED
checkpoint | DRAWINGS MARKED UP TO REFLECT AS-INSTALLED
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM NO: | [5 empty] | PROJ3031 - ITC - (22) Backbone - Fibre Optic Cable
section | Details
checkpoint-no-status | CABLE IDENTIFICATION DRG OUTLET NO:
textbox | FROM
textbox | TO
textbox | CABLE NO
textbox | DESCRIPTION
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | CABLE INSTALLED AND LABELLED
checkpoint | CABLE TERMINATED AND OUTLETS LABELLED
checkpoint | CABLE TESTED
checkpoint | DRAWINGS MARKED UP TO REFLECT AS-INSTALLED
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM NO: | [5 empty] | PROJ3032 - ITC - (23) Backbone - Copper Cable
section | Details
checkpoint-no-status | CABLE IDENTIFICATION DRAWING OUTLET NO:
textbox | FROM
textbox | TO
textbox | CABLE NO
textbox | DESCRIPTION
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | CABLE INSTALLED AND LABELLED
checkpoint | CABLE TERMINATED AND OUTLETS LABELLED
checkpoint | CABLE TESTED
checkpoint | DRAWINGS MARKED UP TO REFLECT AS-INSTALLED
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM NO: | [5 empty] | PROJ3033 - ITC - (24) Telex Earth-TRL
section | Details
checkpoint-no-status | CABLE IDENTIFICATION DRAWING OUTLET NO:
textbox | FROM
textbox | TO
textbox | CABLE NO
textbox | DESCRIPTION
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | CABLE INSTALLED AND LABELLED
checkpoint | CABLE TERMINATED AND OUTLETS LABELLED
checkpoint | CABLE TESTED
checkpoint | DRAWINGS MARKED UP TO REFLECT AS-INSTALLED
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM NO: | [5 empty] | PROJ3034 - ITC - (25) Horizontal - Fibre Optic Cable
section | Details
checkpoint-no-status | CABLE IDENTIFICATION DRAWING OUTLET NO:
textbox | FROM
textbox | TO
textbox | CABLE NO
textbox | DESCRIPTION
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | CABLE INSTALLED AND LABELLED
checkpoint | CABLE TERMINATED AND OUTLETS LABELLED
checkpoint | CABLE TESTED
checkpoint | DRAWINGS MARKED UP TO REFLECT AS-INSTALLED
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM NO: | [5 empty] | PROJ3035 - ITC - (26) Horizontal - Copper Cable
section | Details
checkpoint-no-status | CABLE IDENTIFICATION DRAWING OUTLET NO:
textbox | FROM
textbox | TO
textbox | CABLE NO
textbox | DESCRIPTION
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | MATERIALS CONFORM TO SPECIFICATION
checkpoint | CABLE INSTALLED AND LABELLED
checkpoint | CABLE TERMINATED AND OUTLETS LABELLED
checkpoint | CABLE TESTED
checkpoint | DRAWINGS MARKED UP TO REFLECT AS-INSTALLED
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM NO: | [5 empty] | PROJ3036 - ITC - (27) Equipment (ie - Hubs Equipment Cables)
section | Details
checkpoint-no-status | DESCRIPTION & LOCATION
textbox | LEVEL
textbox | AREA
textbox | TYPE
textbox | LENGTH (m)
checkpoint | CONSTRUCTION DRAWING IS LATEST REVISION
checkpoint | EQUIPMENT, MATERIALS CONFORM TO SPECIFICATION
checkpoint | EQUIPMENT INSTALLED AND LABELLED
checkpoint | LEADS INSTALLED
checkpoint | EQUIPMENT AND LEADS TESTED
checkpoint | DRAWINGS MARKED UP TO REFLECT AS-INSTALLED
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM / AREA OR ZONE: | [5 empty] | PROJ3037 - ITC - (28) Roding, Roping, Hauling and Blowing of Cable
section | Details
checkpoint | LATEST REVISION OF DRAWINGS
checkpoint | PIT LOCATION TO DRAWINGS
checkpoint | ROUTE LENGTH TO DRAWINGS
checkpoint | SAFETY BARRIERS & SIGNAGE ERECTED (PRIOR TO REMOVING PIT LIDS)
button | IS TRAFFIC MANAGEMENT REQUIRED? | Yes,No
button | IS PIT A CONFINED SPACE? | Yes,No
checkpoint | NUMBER OF CABLES, CORES AND LENGTH PER SPECIFICATION
checkpoint | NOMINATED SUB-DUCTS AND CONDUITS AS PER DRAWINGS
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM / AREA OR ZONE: | [5 empty] | PROJ3038 - ITC - (28A) Roding, Roping, Hauling and Blowing of Cable
section | Details
checkpoint | INSTALL ROPE (WHERE REQUIRED)
checkpoint | BLOW CLEAR AND LUBRICATE SUB-DUCT (WHERE REQUIRED)
checkpoint | CABLE INSTALLATION TO DRAWINGS
checkpoint | PIT ENTRY/EXIT CABLE LENGTH RECORD
checkpoint | SPECIFIED PIT CABLE LENGTH
checkpoint | CORRECT LABELLING
checkpoint | PIT LIDS REPLACED & BARRIERS REMOVED
checkpoint | CABLE DRUMS RETURNED TO SUPPLIERS/STORES
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | TERMINATION NO: | [5 empty] | PROJ3039 - ITC - (29) Termination of Copper-Fibre Cable
section | Details
checkpoint | LATEST REVISION OF DRAWINGS
checkpoint | LOCATION OF SPLICING TO DRAWINGS
checkpoint | SAFETY BARRIERS & SIGNAGE ERECTED (PRIOR TO REMOVING PIT LIDS)
button | IS TRAFFIC MANAGEMENT REQUIRED | Yes,No
button | IS PIT A CONFINED SPACE | Yes,No
checkpoint | CORRECT LABELLING
checkpoint | CABLE LAY OFF/TAILS LENGTH TO SPECIFICATION
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | TERMINATION NO: | [5 empty] | PROJ3040 - ITC - (29A) Termination of Copper-Fibre Cable
section | Details
checkpoint | LABEL & HOUSE FIBRE CABLES PREPARED (SEALS FITTED)
checkpoint | EYE PROTECTION USED FOR FIBRE SPLICING
checkpoint | LABELLING OF PANEL, TRAYS AND ENCLOSURE TO DRAWINGS
checkpoint | LOCATION/INSTALLATION OF PANEL OR ENCLOSURE TO DRAWINGS
checkpoint | MOUNTING OF FIBRE CABLE LAY OFF OR TAIL TO DRAWINGS
checkpoint | PIT LIDS REPLACED & BARRIERS REMOVED
checkpoint | RESULTS RECORDED OF TESTED CABLES
checkpoint | TEST RESULTS AND AS BUILT DRAWINGS RETURNED TO COORDINATED
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM: | [5 empty] | PROJ3041 - ITC - (30) Testing and Commissioning
section | Details
checkpoint-no-status | EQUIPMENT/SYSTEM TO BE COMMISSIONED
textbox | GIVE BRIEF DESCRIPTION
date | DATE OF TESTS
textbox | INSPECTION/WITNESS BY (NAME, COMPANY/DEPARTMENT)
checkpoint | ACCEPTANCE
holdpoint | CONFIRMATION
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM: | [5 empty] | PROJ3043 - ITC - (31) As Built Drawings-Maintenance Manuals
section | Details
checkpoint-no-status | AS BUILT DRAWINGS
textbox | AS BUILT DRAWINGS NO:
textbox | DRAWING TITLE
textbox | FINAL REVISION AND DATE
button | MANUALS (DRAFT) ACCEPTANCE | Yes,No
checkpoint | MANUALS AND DRAWINGS SUBMITTED
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | (Safety Check Personnel Register) WORK HEALTH, SAFETY AND REHABILITATION | [5 empty] | PROJ3044 - ITC - (32) WHS and R
section | Details
checkpoint-no-status | SITE PERSONNEL
textbox | SITE PERSONNEL (NAME)
textbox | HEYDAY GROUP OR SUBCONTRACTOR
checkpoint | SAFETY SHOES
checkpoint | HELMET
checkpoint | WHS CONSTRUCTION CERTIFICATE
checkpoint | SITE INDUCTION (IF REQUIRED)
holdpoint | PERSONNEL SIGNATURE
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM NO: | [5 empty] | PROJ3045 - ITC - (33) Environmental Management
section | Details
checkpoint | PACKAGING: CARDBOARD/PAPER RECYCLE/MFG
checkpoint | CABLE/COPPER WASTE: CABLE RECYCLERS
checkpoint | PYRO WASTE: CABLE RECYCLERS
checkpoint | TRAYS/LADDER STEEL WASTE: STEEL SCRAP RECYCLERS
checkpoint | SITE/OFFICE PAPER WASTE: PAPER RECYCLERS
checkpoint | SITE/OFFICE CLEAR CLEAN ALL AREAS DAILY/WEEKLY
checkpoint | SAFE AREAS FOR ALL SITE AND OFFICE WASTE
checkpoint | GENERAL WASTE FOOD WASTE ETC: AS PER LOCAL AUTHORITY
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | DISTRIBUTION BOARD NO: | [5 empty] | PROJ3046 - ITC - (34) Commissioning of Subcircuit
section | Details
checkpoint | CORRECT CB RATING
checkpoint | CABLE SIZE
checkpoint | POLARITY
checkpoint | INSULATION RES.
checkpoint | EARTH RES
checkpoint | NO OF POINTS PERMISSIBLE
checkpoint | RCD OPERATION
checkpoint | LABELLING
checkpoint | INSTALLATION WORKS AS INTENDED
holdpoint | DATE & SIGN
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | STATE RAIL MAXIMUM DEMAND AND VOLTAGE CHECKS Subcontract to Heyday Group | [5 empty] | PROJ3076 - ITC - (64) State Rail Maximum Demand and Voltage Checks
section | Details
checkpoint-no-status | LIST LIGHTING, APPLIANCES ETC IN STATION BEING ACTIVATED/USED
textbox | LIST LIGHTING, APPLIANCES ETC IN STATION BEING ACTIVATED/USED:
checkpoint | AT COMMENCEMENT
textbox | Results
textbox | Measure Current at Main Distribution Board |  |  | A
textbox | Measure Voltage at Main Distribution Board |  |  | V
textbox | Measure Voltage at Light Furthest From MDB |  |  | V
textbox | Any Other Comments
holdpoint | Supervisors Signature
checkpoint | AT COMPLETION
textbox | Results
textbox | Measure Current at Main Distribution Board |  |  | A
textbox | Measure Voltage at Main Distribution Board |  |  | V
textbox | Measure Voltage at Light Furthest From MDB |  |  | V
textbox | Any Other Comments
holdpoint | Supervisors Signature
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | LEVEL/AREA: | [5 empty] | PROJ3077 - ITC - (65) Temporary Wiring-Temporary DB's
section | Details
checkpoint | EQUIPMENT LOCATED CORRECTLY
checkpoint | EQUIPMENT SECURE/BOLTED DOWN
checkpoint | WIRING INSTALLED CORRECTLY
checkpoint | WIRING MECHANICALLY PROTECTED
checkpoint | POLE FILLERS INSTALLED
checkpoint | ESCUTCHEON / COVERS CHECKED
checkpoint | LOCKABLE COVERS AND PADLOCKS INSTALLED
checkpoint | EQUIPMENT TESTED AND TAGGED
checkpoint | TEMPORARY BOARD NUMBERED
checkpoint | BOARD LABELLED FOR SOURCE OF SUPPLY
checkpoint-no-status | REMARKS
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff