## ITC Fencing
FENCING ITC
Location
| Fencing Location | Location of Installed fencing | Textbox
| Date | Date of Installation | Date Text Box
Preconstruction
| Design Drawings | Issued for Construction Drawings available | P,F,Attachment
| Site Preparation | Visual inspection of cleared and levelled area | P,F,Attachment
Site free from debris, vegetation, and unevenness
| Survey and Marking | Verification of layout, alignment & grades | P,F,Attachment
Alignment with approved IFC drawings
Existing underground services in vacinity marked and located
Construction
| Post Installation | Relevant Specification: IFC Drawings
Test Method: Visual Inspection and Measurements
Timing/Frequency: Installed Posts
|  | Acceptance Criteria: Posts are installed per IFC drawings and are straight, level and aligned | Holdpoint United Civil P,F,Attachment
| Rail Installation | Relevant Specification: IFC Drawings
Test Method: Visual Inspection and Measurements
Timing/Frequency: Installed Rails
|  | Acceptance Criteria: Rails are installed per IFC drawings and are straight, level and aligned with required number of fixings | Holdpoint United Civil P,F,Attachment
| Running Wire | Relevant Specification: IFC Drawings
Test Method: Visual Inspection and Measurements
Timing/Frequency: Installed Wire
|  | Acceptance Criteria: Wire is installed per IFC drawings, is the correct number of runs and grade | Holdpoint United Civil P,F,Attachment
| Netting & Clip Installation | Relevant Specification: IFC Drawings
Test Method: Visual Inspection and Measurements
Timing/Frequency: Installed Netting/Clips
|  | Acceptance Criteria: Netting/Clips are installed per IFC drawings, is the correct number clips used and grade | Holdpoint United Civil P,F,Attachment
| Gates | Relevant Specification: IFC Drawings
Test Method: Visual Inspection and Measurements
Timing/Frequency: Installed Gates
|  | Acceptance Criteria: Gates and hanging/securing hardware is installed per IFC drawings | Holdpoint United Civil P,F,Attachment
| Concrete Work | Relevant Specification: IFC Drawings
Test Method: Visual Inspection, Measurements and Prepor Inspection of Concrete
Timing/Frequency: Each Concrete Pour
Acceptance Criteria: Concrete and steel are constructed as per IFC drawings
Post Construction and Handover
| Final Walkthrough & Inspection | Inspection of all elements relating to the fencing
Compliance with IFC drawings and specifications
Verify all fencing meets design and functional requirements
|  | Any required documentation added to ITC file | Holdpoint United Civil P,F,Attachment
| Date |  | Date Text Box