## ITP Fencing
FENCING ITP
Location
| Fencing Location | Site Location of Installed fencing | Textbox
Preconstruction
| Design Drawings | Issued for Construction Drawings available | P,F,Attachment
Holdpoint United Civil
| Site Preparation | Visual inspection of cleared and levelled area | P,F,Attachment
Site free from debris, vegetation, and unevenness
| Survey and Marking | Verification of layout, alignment & grades | P,F,Attachment
Alignment with approved IFC drawings
| Material Approval | Relevant Specification: IFC Drawings
Test Method: Visual inspection of Posts, Rails, Wire, Clips, Screws, Concrete
Timing/Frequency: As materials arrive and are incorporated
|  | Acceptance Criteria: Materials match what has been agreed for use or approved alternatives | Holdpoint United Civil & CHINT, P,F,Attachment
Construction
| Post Installation | Relevant Specification: IFC Drawings
Test Method: Visual Inspection and Measurements
Timing/Frequency: Installed Posts
|  | Acceptance Criteria: Posts are installed per IFC drawings and are straight, level and aligned | Holdpoint United Civil P,F,Attachment
| Rail Installation | Relevant Specification: IFC Drawings
Test Method: Visual Inspection and Measurements
Timing/Frequency: Installed Rails
|  | Acceptance Criteria: Rails are installed per IFC drawings and are straight, level and aligned with required number of fixings | Holdpoint United Civil P,F,Attachment
| Running Wire | Relevant Specification: IFC Drawings
Test Method: Visual Inspection and Measurements
Timing/Frequency: Installed Wire
|  | Acceptance Criteria: Wire is installed per IFC drawings, is the correct number of runs and grade | Holdpoint United Civil P,F,Attachment
| Netting & Clip Installation | Relevant Specification: IFC Drawings
Test Method: Visual Inspection and Measurements
Timing/Frequency: Installed Netting/Clips
|  | Acceptance Criteria: Netting/Clips are installed per IFC drawings, is the correct number clips used and grade | Holdpoint United Civil P,F,Attachment
| Gates | Relevant Specification: IFC Drawings
Test Method: Visual Inspection and Measurements
Timing/Frequency: Installed Gates
|  | Acceptance Criteria: Gates and hanging/securing hardware is installed per IFC drawings | Holdpoint United Civil P,F,Attachment
| Concrete Work | Relevant Specification: IFC Drawings
Test Method: Visual Inspection, Measurements and Prepor Inspection of Concrete
Timing/Frequency: Each Concrete Pour
Acceptance Criteria: Concrete and steel are constructed as per IFC drawings
Post Construction and Handover
| Final Walkthrough & Inspection | Inspection of all elements relating to the fencing
Compliance with IFC drawings and specifications
|  | Verify all fencing meets design and functional requirements | Holdpoint United Civil & CHINT, P,F,Attachment
| Non-Conformance-Reports | Each Non-Conformance Reported, Rectified & Closed Out | P,F,Attachment
| Punch List | Development of Punchlist with Client and Contractor Representative Punch List closed out in a timely mannor | P,F,Attachment
| Documentation | On completion of the fencing | P,F,Attachment
|  | Submission of all test results, ITC's and any as-built drawings | Holdpoint United Civil & CHINT, P,F,Attachment
Complete and approved by client