## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITC Fencing
section | Location
checkpoint-no-status | Fencing Location
textbox | Location of Installed fencing
date | Date of Installation
section | Preconstruction
checkpoint | Design Drawings
label | Issued for Construction Drawings available
checkpoint | Site Preparation
label | Visual inspection of cleared and levelled area
label | Site free from debris, vegetation, and unevenness
checkpoint | Survey and Marking
label | Verification of layout, alignment & grades
label | Alignment with approved IFC drawings
label | Existing underground services in vacinity marked and located
section | Construction
checkpoint | Post Installation
label | Relevant Specification: IFC Drawings
label | Test Method: Visual Inspection and Measurements
label | Timing/Frequency: Installed Posts
label | Acceptance Criteria: Posts are installed per IFC drawings and are straight, level and aligned
holdpoint | United Civil Hold Point
checkpoint | Rail Installation
label | Relevant Specification: IFC Drawings
label | Test Method: Visual Inspection and Measurements
label | Timing/Frequency: Installed Rails
label | Acceptance Criteria: Rails are installed per IFC drawings and are straight, level and aligned with required number of fixings
holdpoint | United Civil Hold Point
checkpoint | Running Wire
label | Relevant Specification: IFC Drawings
label | Test Method: Visual Inspection and Measurements
label | Timing/Frequency: Installed Wire
label | Acceptance Criteria: Wire is installed per IFC drawings, is the correct number of runs and grade
holdpoint | United Civil Hold Point
checkpoint | Netting & Clip Installation
label | Relevant Specification: IFC Drawings
label | Test Method: Visual Inspection and Measurements
label | Timing/Frequency: Installed Netting/Clips
label | Acceptance Criteria: Netting/Clips are installed per IFC drawings, is the correct number clips used and grade
holdpoint | United Civil Hold Point
checkpoint | Gates
label | Relevant Specification: IFC Drawings
label | Test Method: Visual Inspection and Measurements
label | Timing/Frequency: Installed Gates
label | Acceptance Criteria: Gates and hanging/securing hardware is installed per IFC drawings
holdpoint | United Civil Hold Point
checkpoint | Concrete Work
label | Relevant Specification: IFC Drawings
label | Test Method: Visual Inspection, Measurements and Prepor Inspection of Concrete
label | Timing/Frequency: Each Concrete Pour
label | Acceptance Criteria: Concrete and steel are constructed as per IFC drawings
holdpoint | United Civil Hold Point
section | Post Construction and Handover
checkpoint | Inspection of all elements relating to the fencing
label | Compliance with IFC drawings and specifications
label | Verify all fencing meets design and functional requirements
label | Any required documentation added to ITC file
date | Date:
holdpoint | United Civil Hold Point
checklist | ITP - Fencing | itp
section | Location
checkpoint-no-status | Fencing Location
textbox | Site Location of Installed fencing
section | Preconstruction
checkpoint | Design Drawings
label | Issued for Construction Drawings available
holdpoint | United Civil Hold Point
checkpoint | Site Preparation
label | Visual inspection of cleared and levelled area
label | Site free from debris, vegetation, and unevenness
checkpoint | Survey and Marking
label | Verification of layout, alignment & grades
label | Alignment with approved IFC drawings
checkpoint | Material Approval
label | Relevant Specification: IFC Drawings
label | Test Method: Visual inspection of Posts, Rails, Wire, Clips, Screws, Concrete
label | Timing/Frequency: As materials arrive and are incorporated
label | Acceptance Criteria: Materials match what has been agreed for use or approved alternatives
holdpoint | United Civil & CHINT Hold Point
section | Construction
checkpoint | Post Installation
label | Relevant Specification: IFC Drawings
label | Test Method: Visual Inspection and Measurements
label | Timing/Frequency: Installed Posts
label | Acceptance Criteria: Posts are installed per IFC drawings and are straight, level and aligned
holdpoint | United Civil Hold Point
checkpoint | Rail Installation
label | Relevant Specification: IFC Drawings
label | Test Method: Visual Inspection and Measurements
label | Timing/Frequency: Installed Rails
label | Acceptance Criteria: Rails are installed per IFC drawings and are straight, level and aligned with required number of fixings
holdpoint | United Civil Hold Point
checkpoint | Running Wire
label | Relevant Specification: IFC Drawings
label | Test Method: Visual Inspection and Measurements
label | Timing/Frequency: Installed Wire
label | Acceptance Criteria: Wire is installed per IFC drawings, is the correct number of runs and grade
holdpoint | United Civil Hold Point
checkpoint | Netting & Clip Installation
label | Relevant Specification: IFC Drawings
label | Test Method: Visual Inspection and Measurements
label | Timing/Frequency: Installed Netting/Clips
label | Acceptance Criteria: Netting/Clips are installed per IFC drawings, is the correct number clips used and grade
holdpoint | United Civil Hold Point
checkpoint | Gates
label | Relevant Specification: IFC Drawings
label | Test Method: Visual Inspection and Measurements
label | Timing/Frequency: Installed Gates
label | Acceptance Criteria: Gates and hanging/securing hardware is installed per IFC drawings
holdpoint | United Civil Hold Point
checkpoint | Concrete Work
label | Relevant Specification: IFC Drawings
label | Test Method: Visual Inspection, Measurements and Prepor Inspection of Concrete
label | Timing/Frequency: Each Concrete Pour
label | Acceptance Criteria: Concrete and steel are constructed as per IFC drawings
holdpoint | United Civil Hold Point
section | Post Construction and Handover
checkpoint | Final Walkthrough & Inspection
label | Inspection of all elements relating to the fencing
label | Compliance with IFC drawings and specifications
label | Verify all fencing meets design and functional requirements
holdpoint | United Civil & CHINT Hold Point
checkpoint | Non-Conformance-Reports
label | Each Non-Conformance Reported, Rectified & Closed Out
checkpoint | Punch List
label | Development of Punchlist with Client and Contractor Representative
label | Punch List closed out in a timely mannor
checkpoint | Documentation - On completion of the fencing
checkpoint | Documentation - Submission of all test results, ITC's and any as-built drawings
label | Complete and approved by client
holdpoint | United Civil & CHINT Hold Point