## Table 1
4. Process
No. | Description Inspection / test | Frequency | Spec/standard | Acceptance Criteria | Measuring Devices | Reporting Format | Inspected by* |  |  | Remarks
[7 empty] | HCL | SC | Consult
Pre
1 | Prerequisite quality check | Prior to commencing each work face | All notes | Check: Starter bar location Grid set out Scabbling surface Reinforcement detailed and supplied to site | NA | N/A | I | W | — | —
2 | Setout hand over | Prior to commencing each work face | As per set out drwgs | HL to confirm datums and setout marks for each work face | Physical marks provided onsite | N/A | I | W | — | —
3 | LBP details | Prior to starting | 8.3.1 | Accept/ reject | N/A | Certificate | R | SUB | R | —
4 | Material certs for masonry units | Prior to starting | 8.3.3; 8.6.1 | 12.5MPa | N/A | Certificate | R | SUB | R | Hawkins-TSUB- 000164
5 | Design Mix | Prior to starting | NZS3404 8.3.4., 8.6.6 | 25MPA | Off site | Design Mix | R | SUB | R | —
6 | Propsed method of grouting | Prior to starting | 8.3.1 | Accept/ reject | N/A | Methodology | R | SUB | R | —
Onsite
7 | Reinforcement steel placements | Daily, Continually throughout laying process | 8.6.7, 8.8.1 table 8.1 NZ4210 As per drwg DP001- MMD-DRW-ST-Z- 5050/51 & relevant details | +/-6mm and =/50 / ¼ grouted wall, centred in cell | Measuring tape/ level | QC checklist | M | — | S | Starter bars, tied reinforcement, ref to engineer if remedial works required
8 | Laps | Daily, Continually throughout reinforcement process | As per drwg DP001- MMD-DRW-ST-Z- 5050/51 & relevant details NZ3109 | 400mm – 1400m depending in the bar | Measuring tape | QC checklist | M | — | S | —
9 | Cast in items | Each elevation prior to pouring | section 6 8.6.6 MMD-DRW-ST-Z- 5050/51 & relevant details | — | Visual inspection | QC checklist | M | — | S | —
10 | Blockwork | Continually throughout laying process | Table 8.2 , 8.8,8.8.2 NZS4210 cl 2.6 MMD-DRW-ST-Z- 5050/51 & relevant details | As per table bottom course20mm ma and typical course 10 +/3mm | Measuring tape/ level | QC checklist | M | — | S | —
11 | Block clearances | Non strucuturual blocks and structural elements | MMD-DRW-ST-Z- 5050/51 & relevant details section 5 | 25 -200mm | Measuring tape/ rotating level | QC checklist | M | — | S | —
12 | Joints | Continually throughout laying process | MMD-DRW-ST-Z- 5050/51 & relevant details section 1 or as specifies | Every 6m or as per drwg or change in wall height, thickness or amove/below movement joints | Measuring tape/ level | QC checklist | M | — | S | 4 hour fire walls to have intumescent jointing sealent
13 | Cleaning Out | Each vertical bar | 8.8.3 NZS4210 sec 2.8 | 100 x 75 mm opening | — | QC checklist | R | Sub | R | —
14 | Grout testing | Each pour | NZS 4210 App 2A, NZS3112,2 8.3.4 | 25MPA at 28 days | Off site | Report & Drwg | R | Sub | R | —
15 | Protection of blocks | If temperature is extreme | 8.8.2 NZS 4210 2.18/19 | Less than 5 more than 25 | — | QC checklist | M | — | R | —