## Sheet1
1 | Prerequisite quality check | Prior to commencing each work face | All notes | Check: Starter bar location Grid set out Scabbling surface Reinforcement detailed and supplied to site | NA | N/A | I | W | — | — | 1 - Prerequisite quality check | Frequency - Prior to commencing each work face | Spec/standard - All notes | Acceptance Criteria - Check: Starter bar location Grid set out Scabbling surface Reinforcement detailed and supplied to site | Measuring Devices - NA | Reporting Format - N/A | Inspected by: HCL - I | Inspected by: SC - W | Inspected by: Consult - — | Remarks - — | 1 - Prerequisite quality check
2 | Setout hand over | Prior to commencing each work face | As per set out drwgs | HL to confirm datums and setout marks for each work face | Physical marks provided onsite | N/A | I | W | — | — | 2 - Setout hand over | Frequency - Prior to commencing each work face | Spec/standard - As per set out drwgs | Acceptance Criteria - HL to confirm datums and setout marks for each work face | Measuring Devices - Physical marks provided onsite | Reporting Format - N/A | Inspected by: HCL - I | Inspected by: SC - W | Inspected by: Consult - — | Remarks - — | Frequency - Prior to commencing each work face
3 | LBP details | Prior to starting | 8.3.1 | Accept/ reject | N/A | Certificate | R | SUB | R | — | 3 - LBP details | Frequency - Prior to starting | Spec/standard - 8.3.1 | Acceptance Criteria - Accept/ reject | Measuring Devices - N/A | Reporting Format - Certificate | Inspected by: HCL - R | Inspected by: SC - SUB | Inspected by: Consult - R | Remarks - — | Spec/standard - All notes
4 | Material certs for masonry units | Prior to starting | 8.3.3; 8.6.1 | 12.5MPa | N/A | Certificate | R | SUB | R | Hawkins-TSUB- 000164 | 4 - Material certs for masonry units | Frequency - Prior to starting | Spec/standard - 8.3.3; 8.6.1 | Acceptance Criteria - 12.5MPa | Measuring Devices - N/A | Reporting Format - Certificate | Inspected by: HCL - R | Inspected by: SC - SUB | Inspected by: Consult - R | Remarks - Hawkins-TSUB- 000164 | Acceptance Criteria - Check: Starter bar location Grid set out Scabbling surface Reinforcement detailed and supplied to site
5 | Design Mix | Prior to starting | NZS3404 8.3.4., 8.6.6 | 25MPA | Off site | Design Mix | R | SUB | R | — | 5 - Design Mix | Frequency - Prior to starting | Spec/standard - NZS3404 8.3.4., 8.6.6 | Acceptance Criteria - 25MPA | Measuring Devices - Off site | Reporting Format - Design Mix | Inspected by: HCL - R | Inspected by: SC - SUB | Inspected by: Consult - R | Remarks - — | Measuring Devices - NA
6 | Propsed method of grouting | Prior to starting | 8.3.1 | Accept/ reject | N/A | Methodology | R | SUB | R | — | 6 - Propsed method of grouting | Frequency - Prior to starting | Spec/standard - 8.3.1 | Acceptance Criteria - Accept/ reject | Measuring Devices - N/A | Reporting Format - Methodology | Inspected by: HCL - R | Inspected by: SC - SUB | Inspected by: Consult - R | Remarks - — | Reporting Format - N/A
7 | Reinforcement steel placements | Daily, Continually throughout laying process | 8.6.7, 8.8.1 table 8.1 NZ4210 As per drwg DP001- MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details | +/-6mm and =/50 / ¼ grouted wall, centred in cell | Measuring tape/ level | QC checklist | M | — | S | Starter bars, tied reinforcement, ref to engineer if remedial works required | 7 - Reinforcement steel placements | Frequency - Daily, Continually throughout laying process | Spec/standard - 8.6.7, 8.8.1 table 8.1 NZ4210 As per drwg DP001- MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details | Acceptance Criteria - +/-6mm and =/50 / ¼ grouted wall, centred in cell | Measuring Devices - Measuring tape/ level | Reporting Format - QC checklist | Inspected by: HCL - M | Inspected by: SC - — | Inspected by: Consult - S | Remarks - Starter bars, tied reinforcement, ref to engineer if remedial works required | Inspected by: HCL - I
8 | Laps | Daily, Continually throughout reinforcement process | As per drwg DP001- MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details NZ3109 | 400mm – 1400m depending in the bar | Measuring tape | QC checklist | M | — | S | — | 8 - Laps | Frequency - Daily, Continually throughout reinforcement process | Spec/standard - As per drwg DP001- MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details NZ3109 | Acceptance Criteria - 400mm – 1400m depending in the bar | Measuring Devices - Measuring tape | Reporting Format - QC checklist | Inspected by: HCL - M | Inspected by: SC - — | Inspected by: Consult - S | Remarks - — | Inspected by: SC - W
9 | Cast in items | Each elevation prior to pouring | section 6 8.6.6 MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details | — | Visual inspection | QC checklist | M | — | S | — | 9 - Cast in items | Frequency - Each elevation prior to pouring | Spec/standard - section 6 8.6.6 MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details | Acceptance Criteria - — | Measuring Devices - Visual inspection | Reporting Format - QC checklist | Inspected by: HCL - M | Inspected by: SC - — | Inspected by: Consult - S | Remarks - — | Inspected by: Consult - —
10 | Blockwork | Continually throughout laying process | Table 8.2 , 8.8,8.8.2 NZS4210 cl 2.6 MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details | As per table bottom course20mm ma and typical course 10 +/3mm | Measuring tape/ level | QC checklist | M | — | S | — | 10 - Blockwork | Frequency - Continually throughout laying process | Spec/standard - Table 8.2 , 8.8,8.8.2 NZS4210 cl 2.6 MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details | Acceptance Criteria - As per table bottom course20mm ma and typical course 10 +/3mm | Measuring Devices - Measuring tape/ level | Reporting Format - QC checklist | Inspected by: HCL - M | Inspected by: SC - — | Inspected by: Consult - S | Remarks - — | Remarks - —
11 | Block clearances | Non strucuturual blocks and structural elements | MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details section 5 | 25 -200mm | Measuring tape/ rotating level | QC checklist | M | — | S | — | 11 - Block clearances | Frequency - Non strucuturual blocks and structural elements | Spec/standard - MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details section 5 | Acceptance Criteria - 25 -200mm | Measuring Devices - Measuring tape/ rotating level | Reporting Format - QC checklist | Inspected by: HCL - M | Inspected by: SC - — | Inspected by: Consult - S | Remarks - — | 2 - Setout hand over
12 | Joints | Continually throughout laying process | MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details section 1 or as specifies | Every 6m or as per drwg or change in wall height, thickness or amove/below movement joints | Measuring tape/ level | QC checklist | M | — | S | 4 hour fire walls to have intumescent jointing sealent | 12 - Joints | Frequency - Continually throughout laying process | Spec/standard - MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details section 1 or as specifies | Acceptance Criteria - Every 6m or as per drwg or change in wall height, thickness or amove/below movement joints | Measuring Devices - Measuring tape/ level | Reporting Format - QC checklist | Inspected by: HCL - M | Inspected by: SC - — | Inspected by: Consult - S | Remarks - 4 hour fire walls to have intumescent jointing sealent | Frequency - Prior to commencing each work face
13 | Cleaning Out | Each vertical bar | 8.8.3 NZS4210 sec 2.8 | 100 x 75 mm opening | — | QC checklist | R | Sub | R | — | 13 - Cleaning Out | Frequency - Each vertical bar | Spec/standard - 8.8.3 NZS4210 sec 2.8 | Acceptance Criteria - 100 x 75 mm opening | Measuring Devices - — | Reporting Format - QC checklist | Inspected by: HCL - R | Inspected by: SC - Sub | Inspected by: Consult - R | Remarks - — | Spec/standard - As per set out drwgs
14 | Grout testing | Each pour | NZS 4210 App 2A, NZS3112,2 8.3.4 | 25MPA at 28 days | Off site | Report CHAR(AMP) Drwg | R | Sub | R | — | 14 - Grout testing | Frequency - Each pour | Spec/standard - NZS 4210 App 2A, NZS3112,2 8.3.4 | Acceptance Criteria - 25MPA at 28 days | Measuring Devices - Off site | Reporting Format - Report CHAR(AMP) Drwg | Inspected by: HCL - R | Inspected by: SC - Sub | Inspected by: Consult - R | Remarks - — | Acceptance Criteria - HL to confirm datums and setout marks for each work face
15 | Protection of blocks | If temperature is extreme | 8.8.2 NZS 4210 2.18/19 | Less than 5 more than 25 | — | QC checklist | M | — | R | — | 15 - Protection of blocks | Frequency - If temperature is extreme | Spec/standard - 8.8.2 NZS 4210 2.18/19 | Acceptance Criteria - Less than 5 more than 25 | Measuring Devices - — | Reporting Format - QC checklist | Inspected by: HCL - M | Inspected by: SC - — | Inspected by: Consult - R | Remarks - — | Measuring Devices - Physical marks provided onsite
Reporting Format - N/A
Inspected by: HCL - I
Inspected by: SC - W
Inspected by: Consult - —
Remarks - —
3 - LBP details
Frequency - Prior to starting
Spec/standard - 8.3.1
Acceptance Criteria - Accept/ reject
Measuring Devices - N/A
Reporting Format - Certificate
Inspected by: HCL - R
Inspected by: SC - SUB
Inspected by: Consult - R
Remarks - —
4 - Material certs for masonry units
Frequency - Prior to starting
Spec/standard - 8.3.3; 8.6.1
Acceptance Criteria - 12.5MPa
Measuring Devices - N/A
Reporting Format - Certificate
Inspected by: HCL - R
Inspected by: SC - SUB
Inspected by: Consult - R
Remarks - Hawkins-TSUB- 000164
5 - Design Mix
Frequency - Prior to starting
Spec/standard - NZS3404 8.3.4., 8.6.6
Acceptance Criteria - 25MPA
Measuring Devices - Off site
Reporting Format - Design Mix
Inspected by: HCL - R
Inspected by: SC - SUB
Inspected by: Consult - R
Remarks - —
6 - Propsed method of grouting
Frequency - Prior to starting
Spec/standard - 8.3.1
Acceptance Criteria - Accept/ reject
Measuring Devices - N/A
Reporting Format - Methodology
Inspected by: HCL - R
Inspected by: SC - SUB
Inspected by: Consult - R
Remarks - —
7 - Reinforcement steel placements
Frequency - Daily, Continually throughout laying process
Spec/standard - 8.6.7, 8.8.1 table 8.1 NZ4210 As per drwg DP001- MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details
Acceptance Criteria - +/-6mm and =/50 / ¼ grouted wall, centred in cell
Measuring Devices - Measuring tape/ level
Reporting Format - QC checklist
Inspected by: HCL - M
Inspected by: SC - —
Inspected by: Consult - S
Remarks - Starter bars, tied reinforcement, ref to engineer if remedial works required
8 - Laps
Frequency - Daily, Continually throughout reinforcement process
Spec/standard - As per drwg DP001- MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details NZ3109
Acceptance Criteria - 400mm – 1400m depending in the bar
Measuring Devices - Measuring tape
Reporting Format - QC checklist
Inspected by: HCL - M
Inspected by: SC - —
Inspected by: Consult - S
Remarks - —
9 - Cast in items
Frequency - Each elevation prior to pouring
Spec/standard - section 6 8.6.6 MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details
Acceptance Criteria - —
Measuring Devices - Visual inspection
Reporting Format - QC checklist
Inspected by: HCL - M
Inspected by: SC - —
Inspected by: Consult - S
Remarks - —
10 - Blockwork
Frequency - Continually throughout laying process
Spec/standard - Table 8.2 , 8.8,8.8.2 NZS4210 cl 2.6 MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details
Acceptance Criteria - As per table bottom course20mm ma and typical course 10 +/3mm
Measuring Devices - Measuring tape/ level
Reporting Format - QC checklist
Inspected by: HCL - M
Inspected by: SC - —
Inspected by: Consult - S
Remarks - —
11 - Block clearances
Frequency - Non strucuturual blocks and structural elements
Spec/standard - MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details section 5
Acceptance Criteria - 25 -200mm
Measuring Devices - Measuring tape/ rotating level
Reporting Format - QC checklist
Inspected by: HCL - M
Inspected by: SC - —
Inspected by: Consult - S
Remarks - —
12 - Joints
Frequency - Continually throughout laying process
Spec/standard - MMD-DRW-ST-Z- 5050/51 CHAR(AMP) relevant details section 1 or as specifies
Acceptance Criteria - Every 6m or as per drwg or change in wall height, thickness or amove/below movement joints
Measuring Devices - Measuring tape/ level
Reporting Format - QC checklist
Inspected by: HCL - M
Inspected by: SC - —
Inspected by: Consult - S
Remarks - 4 hour fire walls to have intumescent jointing sealent
13 - Cleaning Out
Frequency - Each vertical bar
Spec/standard - 8.8.3 NZS4210 sec 2.8
Acceptance Criteria - 100 x 75 mm opening
Measuring Devices - —
Reporting Format - QC checklist
Inspected by: HCL - R
Inspected by: SC - Sub
Inspected by: Consult - R
Remarks - —
14 - Grout testing
Frequency - Each pour
Spec/standard - NZS 4210 App 2A, NZS3112,2 8.3.4
Acceptance Criteria - 25MPA at 28 days
Measuring Devices - Off site
Reporting Format - Report CHAR(AMP) Drwg
Inspected by: HCL - R
Inspected by: SC - Sub
Inspected by: Consult - R
Remarks - —
15 - Protection of blocks
Frequency - If temperature is extreme
Spec/standard - 8.8.2 NZS 4210 2.18/19
Acceptance Criteria - Less than 5 more than 25
Measuring Devices - —
Reporting Format - QC checklist
Inspected by: HCL - M
Inspected by: SC - —
Inspected by: Consult - R
Remarks - —