## Table 1
Seq |  |  | Task/ QA Activity |  |  | Specification Standard | [7 empty] | ' Acceptance C'(iteria | [10 empty] | I Certify Doc I Ref | [8 empty] | PFS Engln11ring
Inspection and Test Plan Re\liewed 1 anfl AJ)provt!d by Cuslorncr | [5 empty] | P,ojecl Stmcllll& Specification C0702 Rt:v. 01 IFC structu,e OWG |  |  |  | Inspection and Tesl plan shall be submilled to the Engineer Im review and t1pprnval hefore fahriclltion is cornmenced | [16 empty] | IFC DWGs | [6 empty] | PM/PE
2 Submit the required documenls lo Clie11I Im review | [5 empty] | Project Struclurn Specification C0702 Rev. 01 |  |  |  | Site installatio11methodolog•, shall be submilled to the Engineer for review | [13 empty] | Erection Sequenci, Methodology | [9 empty] | PMIPE
3 loslollolinn Proi:urermml. Casi in ilems | [5 empty] | Project Strnctu10 Specification C0702 Rev. 01 IFC structwe DWG |  |  |  | Confirm Procuremen1and delivery of all Casi in llems: i.shear keys ii. uplift rnslrnints 011d ossociall':<I mils m. plate washers iv. M.icnlloy Bars (ETA 0&'01/25) and coLJplers 'MU1 denso v. Reidbar and couplers+ touch up protective coating. vi. t-Jyton wastiers arid rubber sleeves. vii. Trnn1m1nry he,1rin!J co1n1m11enls | [14 empty] | IFCDWC PFS: 39028-3202-000-FABRC PFG: 39028-3201-000-FAORC Mill Cells Compliance Documental1on | [8 empty] | PMJPE
4 lnspectio11111>011 receipt al site | [5 empty] | Prnjer:I St111t:tlllc Specification C0702 Rev. 01 IFC ::>hudure DWG |  |  |  | The mateual ,eceipt at site need lo be visually inspcc!ud fr>1 quantity and make swe no damage occurred during transport | [16 empty] | IFC DWG | [6 empty] | PM/PE
-
5 Inspection upot) receipt al sile - Cast in Items. 6 Preparation work- priOI to Spa11 Lifting forAll Spans | [5 empty] | Prnjed Stim:twe Specification C0702 Rev. 01 1FC shudure DWG Site installation methodology P1ojecl Structuriei Specification C0702 R1w.01 IFC stmchire DWG |  |  |  | ThH 111:-:JIH1i;il IHl'.1:!ipt ..itSltf:!need lo I)(! ViSLl.-llly inspected [Of quanlity, make sure no damage occurred during transport. All related documents have been received. Make sure survey has been done and cenler marks on the frame'M>fk ns a rererence have been pro'lided by Downer lr11:,tall<1lio11ol 100x100 EA a!>a lilh11u aid mI ltm1fiC>1al'y struclme Sptin unlotided from lruck ond placed on Dunnoge on 9m1mt'l primIt) rig9ing adjustment All.iching lhe t.ig lines to Spans to prevent rotalion clur11\g inslc1llc11ion | [16 empty] | 1Fc owe Lift plan | [6 empty] | PM/PE Sile project Manager
7 Confirm all Ma11ufacIure documentation has been completed to, Span #2 8 Installation of Span#2 9 Macalloy Ela,s inslallatioa fu1 Span U2 | [5 empty] | Project Stmcture Sp,:cilicntiun CD702 Rev. 01 Sile installatim1 methodology Project Stmcture Specif1cat1on C0702 Rev. 01 !FC struclLlle DWG S1I1:inslallatum methodology Prnjt:d Struct111t! |  |  |  | Co11fi1ming that the fabricalion, coating, a1ul fndo1y c11i1:1inn (indwling ha]uslrrnlt! n111J 1h 1:k11w1el bolting) wo1ks have been signed off. Verify that the structural component is secwely rigged occo1<ling to U1e ri 1ging plan Tn hll Span n2 amt Pnsilivn 11\H ,;nrnpt,llU:!111J)IBCISE!ly flV(:!I lhe pile and lower it slo y into its final placement on lempmary gircler st1ppoII slruclure Chain block will be connected to llut Wesl end lo adjust level. ,,.,,hen location is confirmed by surveyor <1fld PFS staff, span to be securect in place to the shm soldie1s. To keep Macalloy bar aligned, a coupler lo lie lightened 10 nxlm1d the M.ic,dloy bi!r a11d TerniK>ry 1111! v.;U he mfcled lo | [15 empty] | QA Dor:111111i11!.ilin11 Lift pla11 tFC Orn\..,;llH | [7 empty] | PMJPE I Site projecl I Manager I Site project
Specific,1tion C0702 Iha rod on the Span 2 high end. The nuts w!II be tighlened lo Manager
Rev. 01 IFC r,tmcll,rn OWG | [11 empty] | hold the f\l\acalloy bars in correct position.
Cnnlir111 fll1Mfl11ulc1clu1e do1:11111enlatior1 10 has he1e1n cornplet d for Span #3 | [5 empty] | Prnjec::tStmclme Spec1f1cal1on C0702 Rev. 01 |  |  |  | Cm1fi11ninu that Urn fabricalion, coating, and factory erection (including halustrmlc and decklland bol1mg) wmks ha'le been signed off. | [15 empty] | QA Docurmmtaho11 | [7 empty] | PM/PE
11 lnsl.illalion of Span#J | [5 empty] | Sile inslallalio11 methodology Project Structure Specification C0702 Rev. 01 IFC shucture DWG |  |  |  | Ve,ify that the structural compor1ent is securely rigged accordin!Jlo Ille lill plan To lilt Span #J and Position !he component precisely over the pile and lower fl slO\ 'f into ils final placement on t"'rnpcuary ui1cler support st1I11:luIe wt1en localio11is confirmed by surveyor and PFS staff, span lo be secured in lllace to lhe slim soldiers. | [16 empty] | Lift plan | [6 empty] | Sile projecl Manager
12 Shear Keys,Hold Ooi,..n Doll and Rcidbn1s lnslnllnlion for Span #J | [5 empty] | Sile i11slall.itio11 methodology Project Stmcture Specification C0702 Re•.1. 01 lFC strncture DWG |  |  |  | TI1e longitudinal arld laHludinal Shear keys fire lo be 111stallt!d lo secIIre Urn position ol sr.);.m trnm mr:>ve,rnrnl during Head slock Pouring Hold Down Bolt to be Installed Nuls (111Rt.>idba, to be soug t1 Jhtcncd to help mininml loleml movement | [14 empty] | Shear keys, H d Down bolls and Reidbars Ora'Mng | [8 empty] | Site project Manager
Conhnn all Manufactmti documenlatio11 Pro1ee1 Stmcture | [11 empty] | Confim1ing that the fab1icalion, coating,
13 has been completed for Span #4 | [5 empty] | Specificalion C0702 Re'I, 01 |  |  |  | and lacloiy erection {including balustrade and deck panel bollino) works have been signed off. | [15 empty] | QA Doc11menlation | [7 empty] | PMIPE
14 lnslallallon of Span#4 | [5 empty] | Site inslallaliorl methodolog•, PrnJ Ct Slruclu1e Specification C0702 Rev. 01 IFC slructurc DWG |  |  |  | V1:mt-y that the t;h111:t111al COllll)Ollfml 15 sec111el,yim:,ed according lo the lilt plan To Ht Span #4 and Position the component precisely over lhe pile ,u,d !O'M'!r ii slov.ty 11)10 its fi11al plrti:E!lllt!fll on lemporary gilder suppon str1Ichue •-d1en loca1ion is confirmed by suweyor and PFS staff, span to be 5ecmerl 111 pl.ice lo lhl! 5lim 5ul1l11!15 | [16 empty] | Lilt plan | [6 empty] | Site project Manager
Shear Keys, Hold Down Boll and 15 Rei<lba1s Installation ro, S1x111#4 | [5 empty] | Sile installation melhodolo0y Project Slruclwe Spet:iricalion C0702 Rev. Ot IFC slructure DWG |  |  |  | The longitudinal and latitudinal Shear keys are lo be installed lo secure lhe posilion of span from moveInenl during Head stock Powin 1 HoldDown Boll to be lnslallt!d Nuls on Reidhar lo ba 6nug lighlenacl lo halp mnmnal lateral movement. | [14 empty] | Shear keys, Hold Down bolls nf\d Rt!idba1s Oiawing | [8 empty] | Sile project Manager
Confirm all Manufoclti1e docume11Ialion 16 has been completed for Span #5 | [5 empty] | Project Stmclme Specification C0702 Rev. 01 |  |  |  | Confirming lhal the fabfication, coaling, and facto1y e1eclion (including baluslfade and deck panel hollin□)wmks have hecn signed off. | [15 empty] | QA Documentalion | [7 empty] | P.._\/PE
17 Installation of Span#S | [5 empty] | Sile installation n1ell1odol01JV P1ojeC1Structure Spec1ficatio11C0702 Rev. 01 IFC s1nicture DWG |  |  |  | Verily thal Ille stmclmal componenl is sacurely ri!J(Jed ;u:co1din9 lo the lift p!im To lill Span tlS and Position lhe component precisely ove, the pile and lower it slovAy into its final placement on temporary girder support structure \",hen locahon is confirmed hy surveyor and PFS staff, srt.-in lo be secured in place lo the slim soldiers. | [16 empty] | Lift plan | [6 empty] | Sile project Manager
Shear Keys, Hold Dowu Boll and 18 Reidba1s lr stallation for Span #5 | [5 empty] | Site installation methodol0<Jy Pro1ecl SIrw;h11e Specification C0702 Rev. 01 IFC structure DWG |  |  |  | T11e longitudinal and lalitudinal Shea, keys are lo be installed lo secwe 11\e position of span from movement chuing Head slock Poum'!) Mold DownBoll to be lnslalled Nuts on Reidbar to be snug tighlened to help minlmal lateral movement. | [14 empty] | Shear keys, Hold Down bolts ar11t Reidbars Drawing | [8 empty] | Site project Manager
Confi1m ell Maru1f11clure docun.enlelion 19 has been completed ror Span #6 | [5 empty] | Project Structure Spec1lical1on C0702 Rev, 01 |  |  |  | Confirming lhat the t brica1ion, coaling. and factoIy erection (inchKli11g baluslraclC!rmd deck panel bolling) works have been signed oft. | [15 empty] | QA Documentation | [7 empty] | PM/PE
20 lnslallalion of Sp;:111#6 | [5 empty] | Sile installation methodology Project Slrncltue Specification C0702 Rev. 01 IFC struct111e DWG |  |  |  | Ve,ily lhal the structural cornpo11cnl is securely rigged according to lht1lift plau To lift Span #G and Position the compo11ent precisely over the pile and lowe, 11slov.ty into its linal placement011 tempmaIy girde, s1Ippmt shuclu1e vmen location is confiJmed by surveyor and PFS slalf, span | [17 empty] | Lift plan | [5 empty] | Site project Manager
e se
lo b cllled in place lo the slim soldiers.
Shear Keys, Hold Dooo Bolt and 21 Reidbms lnstnllt1lio11fm Span #6 | [5 empty] | Site installation mell1odolngy P,ojecl Stmcture Specificalion C0702 Rev. 01 IFC strtrclure OWG |  |  |  | The lorlgitudinal and lalitudinal Shea, keys are to be inslnl1ed lo secure lhe position of span rrom movement during Head stock Pouting Hold Down Boll to be Installed Tempora,y Bearing installation under IO'oYer encl Nuts on Reidbar lo be snug tighte11ecJlo help minunal lalernl movement. Conduct a thorough dimensinal s11rvay inspection to confirm lt1at lh0 co111pn11enl Is coneclly positiouecl and sectued b;ised on IFC Drawing. Meas111ed dimerl:Sions shall be within slflled tolerances | [14 empty] | Shear keys. Hold Down bolts and Reidba1s Ora ng | [8 empty] | Site project Manager
S
ss
se
ile mstallalion | [12 empty] | unle noted otherwi .
22 Dimensional s1111,ey By Downer | [5 empty] | methodol0<Jy IFC 01avA11 s |  | P,oject specification clause C0702.1.3 Fu1iclional Tolerances shall be class 2 as per ASfNZS S1:l1 | [16 empty] | Marked up and Si!Jned IFC DWOs | [7 empty] | Sile project Manager
e F2.
Tahl I to F2,10
Record lhe lifting operation in t e project log, including any devi.ilinns 011equired adjuslme11ts to b made.
e
23 Remove Reid bar tension. | [5 empty] | Site i11slallc1lio11 melhodology IFC o,av.ings |  |  |  | lus |  |  | n Reidb |  | s In mak:h IFC drav.ill!J tltktil ;;1t ;-ill peir efo,e ,.ny headstock pours. | [7 empty] | IFC DWGs | [10 empty] | Site project Manager
se
;1r
b
24 R irl h..i, 1nuch up p.;rn1hr1u (If rn11uirwl) | [5 empty] | Sile inslallalion |  |  |  |  | Any coatirigs dtirnage lo ReK1bais touched up as pc, pain! spl'.!1:1licali<111, Co;:itings to r.omplv v.,n, note 1.2 on d wirig ST-3202. Remove additional nuts. tape (mas i11g <md double sided) | [14 empty] | Prnject Parnt Specificalion | [7 empty] | Site project Manager
ra
k
r1ielhmlology | [9 empty] | u d for atigmne,1I. Appl•{ 1ubbcr sleeves lo tl,e exposed
se
C
25 Hold Down Bolls li 1hteni11 | [5 empty] | IF Dra ngs Slandard operation pror:edurt;! Im shml structure boll lightening |  |  |  |  | lh1eads. Reinstall oversized washers, apply instulating ,v-<1she1s and lighle11nuts down lo acl1ive a 1mm gap between washer and nut, lock nut lo he installed ns per | [14 empty] | Bolt Tightening report | [7 empty] | Sile project M,rnag
er
S
1-lEO-01-02-00 | [7 empty] | delail C & Section 5 on T-3202, Detail O on ST-3200.
5
38
26 Macallo11Bolls lightening 27 m1101Rr,vestrainls 1e1110'IAI | [5 empty] | Sile instRllalion n1et1,ndnlouv IFC ora ...i.111JS Standard oparabon procedure lor steel struclure bolt ti{Jh!ening SH Q.01•02-00 Sile installation methodology IF Drav.rngs |  |  |  | to Unclothe couple,, 1emove temIJ01<11y c11ig111ne11\ mil, i11stal1 Ille mbhm sleeves lo lhcxposed rod,111sk1Uthe washers, ruIts nnd snug lighlt!n the nut ( s thP.rere cm,,preMlble components in contanc area) All temporal)' restraints lo the 1empora!)I shoring 10 be removed AllImsilioni11g Ji!]s <mtl scre....-sappliecl ICJPTFE011Shea, Kays to be rerno-ved | [15 empty] | Bolt T1ghl1011ing rlilporl | [7 empty] | ite projecl Manager Team leader
S
E
38
Te
C
S
ite installation methodology | [9 empty] | The Ternporary Bearing to be,emoved and ranor Bearing 1o he 111stalle1! 111 lhe position
G
C
IF Drmvinns | [7 empty] | lhfl Bohs 11eed lo be sm,g lightened 10 lhe girders (lop) and | [20 empty] | ile project
S
28 lnst.1llalm11of G1anor 8ear1119 lnsl<1llahon of re!nairnrnJ Decki11u 29 panels and wall pan,:,ls | [5 empty] | Slandoml01:>eration procedure for steel structure I.Joll ligl1le11ir19 HE0-01-02-0038 ill! inslallntior1 methodology | [5 empty] | scre\YSneed lo be snug tighte11ed into the base plate The keeper pl<1les' bolls (M20) fm upli1t reslrni11! lo lie tiHhlened (hill Tensioned). Carefully pos1tio11lhA D r:king ..irul wall pan1>.ls in ll1e co11ju11clion area according to the approved drawillgs. | [10 empty] | Bolt Tightenin!J report IFC DW s | [10 empty] | Manager Team leader
S
S
G
C
lF DravAngs
S11ug lightening ol Decking pa11cls and 30 wall pan ls 31 Installation of remaining handrails bet1...een the spans | [5 empty] | $landard operatio11 procedmc for steel StlLJClure halt ligllter\ill(I HEO-01-02-00 Sile installalion 11-iethodology |  |  |  |  | Fasteners of Der;kinu omt woll panel:; to Im inspected for snug light corldilion and marked v.ilh coloured paint pen lo confirm fixi condlion has been checked and verlf1ed. Carefully position the handrails in lhe conjunclion area ncco,ding lo the opprovccl drm tl!JS. | [14 empty] | Ool1Tightening reporl IFC OW s | [7 empty] | Site project Manager eam Leader
S
36
G
T
C
IF Orrn111nus I
andard operation | [11 empty] | Fnshmms of h<rndrnils tt1Im i11spech:fl Im snun linhl cor,d1lion v.,th addilion of Loctite 01lockJJut lo prevent
St
pr I | oc
S
se
32 nug lightening o( Cond11ti Bra ets | [5 empty] | e<1u1e for steel | [5 empty] | loo | ning and ma1ked \..,;t11colomed paint pen to confirm | [12 empty] | 8'11lTighllming rc1mII | [7 empty] | Site project
S
ck
ee
sln cture boll lighlcrnrl!] | [11 empty] | lhdng COll(ltiOll has h n cher.ked and ve,ille(I. | [17 empty] | Manager
s s
HEQ-01-02-0038 | [10 empty] | Note: The connections for the EA' | [9 empty] | panning lhe pie,
s s
C
63
mo\lemen1joinl | [15 empty] | hall be hand tighlen&d, Ref AN D .
33 Installation of Exp.:inslon plales | [5 empty] | Sile 1m;t; llc1lio11 melhodology |  |  |  | The |  |  | nsion pla1es to Ile inslallecl between Span 1 and 2 and between spar1 6 and 7 | [14 empty] | IFC DWGs |  |  | Team Leader
ex | pa
C
IF DrnvAngs
lnsp 34 |  |  |  | lion lo identify any damaga to |  | lr1spect painl for any required repair and touch up of pain! works (bolted connections ond any damage paint to steeh-'YOrk). epair metliod proposed shall be app10ved by | [17 empty] | Note 1.2. o,a.,..,;ng | [6 empty] | T 202 | ite p j!.!cl
ec
R
de
S
ro
S
.J
se
pec
pain1ed surfar.e |  |  |  |  | s requirill!J touchup | lhe i11depen r1I coaling ins | [12 empty] | tor, Arecs repaired shall be |  |  |  |  | Manager
e1;
1einsp ted hy the cm1lin 1aprlicalo1m1rl inrleper1rlent
ec
insp 1or.
Visual and Dimensional inspections completed by PFS Proj€d Manage, lo confi1rn rmirmlaclured items ha•,c been
tall | ed
acco
dfir | :.-1
Insp | [13 empty] | tion of erect |  |  | completely ins s1 lv rk in |  |  |  | . rdan | .,._;th ASIN S
ec
51
ed
ee
;i
10
ce
Z
c | :li
s s
31 Se | [14 empty] | on 13. 11 |  |  | f11lt 5r,e |  |  | tion C0702.l .10.
lns,peclion | [14 empty] | hall cover all relevant i1e111s.listed in clause 13.11.1.
E1ection sequence | [9 empty] | l11sp1?din11s shall he 1fr.1c11m1mted in iuspeclion reporls HS per clause 13.11.3 of A /N d cu l
S
o
ZS5 |  | 131, and included in the QA
mentation. IFC DWGs Site proj ucted by compele11t pe,sonnel. M.anage- | [13 empty] | ec
r
E
u
S
ocJ
35 Site lnstall tion and Sign-off. | [5 empty] | melhodol y ( M ) |  |  |  |  | lnspeclion tudl b cond
s s
id
e
nc
IFC Drnv.m s | [9 empty] | Ev cnct: r>I cxpe1ic: c r>11111.1!ificalinns to, nominated ind1vidual(s) shall be provided for review. An example or quallf1calion ot competent pe1sonnel is a relevant !Jade qLJahficalion and ver tO
o
s e |  | xpe
pec
year rience in struclUral steel erection.
Fo
pa
wi
b
e,
llo ng ins | [15 empty] | tion on sIl |  |  |  | stioulc1a.11y modillcat1on or
re
ee
re irs e quired a written procedure shall be submitted to
C
the Engin r prio, to nnv work proceedir\g as per 0702.3.
ec
:ilu
R
tu | re
1C | 0
36 Crunpile, IS'lit'!w a,ul suhlllll documentation | [5 empty] | Proj pei | t Strnc ;ali,11 7 av. 01 |  | Orn:w11e11\ahnn mu! iepmls to s11ppml i11slallalion ol sleel slrucluie items compiled i11to PFS Manulactures Data Repon | [14 empty] | Manulad111cs D.:ila Reprnl | [9 empty] | ite projecl Manager
S
S
PFS
C
G
IF structure DW -