## Sheet1
1 | Inspection and Test Plan Reviewed and Approved by Customer | Project Structure Specification C0702 Rev. 01 IFC structure DWG | Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced. | IFC DWGs | PM/PE | 1 - Inspection and Test Plan Reviewed and Approved by Customer | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced. | Certify Doc / Ref - IFC DWGs | PFS Engineering - PM/PE | 1 - Inspection and Test Plan Reviewed and Approved by Customer
2 | Inspection upon receipt at site | Project Structure Specification C0702 Rev. 01 IFC structure DWG | The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport | IFC DWG | PM/PE | 2 - Inspection upon receipt at site | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport | Certify Doc / Ref - IFC DWG | PFS Engineering - PM/PE | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
3 | Installation of Templates to identify the Hole locations | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Anchors Hole locations should be in complied with IFC Drawing | IFC Drawing | Team Leader | 3 - Installation of Templates to identify the Hole locations | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Anchors Hole locations should be in complied with IFC Drawing | Certify Doc / Ref - IFC Drawing | PFS Engineering - Team Leader | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
4 | Drilling the holes based in concrete | Project Structure Specification C0702 Rev. 01 | Studs' Holes location should be in compliance with IFC Drawing 22 mm Hole Diameter for M20 Studs Hole depth >210 mm | IFC Drawing Hilti HIT•RE 500 V4 Technical Data sheet | Team Leader | 4 - Drilling the holes based in concrete | Specification Standard - Project Structure Specification C0702 Rev. 01 | Acceptance Criteria - Studs' Holes location should be in compliance with IFC Drawing 22 mm Hole Diameter for M20 Studs Hole depth >210 mm | Certify Doc / Ref - IFC Drawing Hilti HIT•RE 500 V4 Technical Data sheet | PFS Engineering - Team Leader | Certify Doc / Ref - IFC DWGs
5 | Blow out all holes | Site installation methodology Project Structure Specification CD702 Rev. 01 IFC structure DWG | Blow out all hole to make sure all holes are free from dust | IFC Drawing Hilti HIT·RE 500 V4 Technical Data sheet | Team Leader | 5 - Blow out all holes | Specification Standard - Site installation methodology Project Structure Specification CD702 Rev. 01 IFC structure DWG | Acceptance Criteria - Blow out all hole to make sure all holes are free from dust | Certify Doc / Ref - IFC Drawing Hilti HIT·RE 500 V4 Technical Data sheet | PFS Engineering - Team Leader | PFS Engineering - PM/PE
6 | Chemical Anchoring | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Epoxy Studs using Hilti HIT•RE 500 V4 Make sure minimum 210 mm the embedment to achive Wait for epoxy to cure | IFC Drawing Hilti HIT-RE 500 V4 Technical Data sheet | Team Leader | 6 - Chemical Anchoring | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Epoxy Studs using Hilti HIT•RE 500 V4 Make sure minimum 210 mm the embedment to achive Wait for epoxy to cure | Certify Doc / Ref - IFC Drawing Hilti HIT-RE 500 V4 Technical Data sheet | PFS Engineering - Team Leader | 2 - Inspection upon receipt at site
7 | Land Base plates on studs level base plates with Jacking nuts | Project Structure Specification C0702 Rev. 01 | Make sure the base plates are leveled and confirm their elevation | IFC Drawing | Team Leader | 7 - Land Base plates on studs level base plates with Jacking nuts | Specification Standard - Project Structure Specification C0702 Rev. 01 | Acceptance Criteria - Make sure the base plates are leveled and confirm their elevation | Certify Doc / Ref - IFC Drawing | PFS Engineering - Team Leader | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
8 | Final alignment Bolt wide flange beams to base plate | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Verify that the structural component are aligned based on IFC Drawing Bolts to be Installed and snug tightened | IFC Drawing | Team Leader | 8 - Final alignment Bolt wide flange beams to base plate | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Acceptance Criteria - Verify that the structural component are aligned based on IFC Drawing Bolts to be Installed and snug tightened | Certify Doc / Ref - IFC Drawing | PFS Engineering - Team Leader | Acceptance Criteria - The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport
9 | Installation of Dura wall panels and cam covers | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure OWG | Carefully position wall panels and cam covers according to the approved drawings. | IFC DWGs | Team Leader | 9 - Installation of Dura wall panels and cam covers | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure OWG | Acceptance Criteria - Carefully position wall panels and cam covers according to the approved drawings. | Certify Doc / Ref - IFC DWGs | PFS Engineering - Team Leader | Certify Doc / Ref - IFC DWG
10 | Holing | Project Structure Specification CO? Rev. 01 IFC structure DWG SHE0-01-02-0040 | Manual holing shall be performed on GRP material. | IFC OWGs | Team Leader | 10 - Holing | Specification Standard - Project Structure Specification CO? Rev. 01 IFC structure DWG SHE0-01-02-0040 | Acceptance Criteria - Manual holing shall be performed on GRP material. | Certify Doc / Ref - IFC OWGs | PFS Engineering - Team Leader | PFS Engineering - PM/PE
11 | Dimension check | IFC DWG | Compliance vvith IFC DWGs |  | Team Leader | 11 - Dimension check | Specification Standard - IFC DWG | Acceptance Criteria - Compliance vvith IFC DWGs | Certify Doc / Ref - | PFS Engineering - Team Leader | 3 - Installation of Templates to identify the Hole locations
12 | Visual inspection of Fasteners | IFC Drawing | All fasteners {bolts, nuts, washers) are to be in compliance with the Project requirement (Grade, Size and Length) | IFC Drawing | Team Leader | 12 - Visual inspection of Fasteners | Specification Standard - IFC Drawing | Acceptance Criteria - All fasteners {bolts, nuts, washers) are to be in compliance with the Project requirement (Grade, Size and Length) | Certify Doc / Ref - IFC Drawing | PFS Engineering - Team Leader | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
13 | Snug tightening of fastener to fasten the brackets to the GRP material | Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | 100% of fixings securing brackets to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified. |  | Team Leader | 13 - Snug tightening of fastener to fasten the brackets to the GRP material | Specification Standard - Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Acceptance Criteria - 100% of fixings securing brackets to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified. | Certify Doc / Ref - | PFS Engineering - Team Leader | Acceptance Criteria - Anchors Hole locations should be in complied with IFC Drawing
14 | Assembly of the angles between bracke.ts | Project Structure Specification CO? Rev. 01 IFC structure DWG | The angles to be assembled between bracket with fasteners | IFC DWGs | Team Leader | 14 - Assembly of the angles between bracke.ts | Specification Standard - Project Structure Specification CO? Rev. 01 IFC structure DWG | Acceptance Criteria - The angles to be assembled between bracket with fasteners | Certify Doc / Ref - IFC DWGs | PFS Engineering - Team Leader | Certify Doc / Ref - IFC Drawing
15 | Snug tightening of fastener to fasten angles to the brackets | Standard operation procedure for steel structure boll tightening SHEQ-01-02-0038 | 100% of fixings securing brackets and angles to be inspected for snug tight condition and marked with coloured paint pen lo confirm fixing condtion has been checked and verified. |  | Team Leader | 15 - Snug tightening of fastener to fasten angles to the brackets | Specification Standard - Standard operation procedure for steel structure boll tightening SHEQ-01-02-0038 | Acceptance Criteria - 100% of fixings securing brackets and angles to be inspected for snug tight condition and marked with coloured paint pen lo confirm fixing condtion has been checked and verified. | Certify Doc / Ref - | PFS Engineering - Team Leader | PFS Engineering - Team Leader
16 | Final Inspection | IFC Drawings, AS/NZS 1554.1:2014 Category SP | Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured lo acceptable standard CHAR(AMP) tolerance and approved to progress to protective coatings. >Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure >Confirmation that required quantity and type's of NOE has been completed and any identified defects have been remediated. | IFC DWGs | Site project Manager | 16 - Final Inspection | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured lo acceptable standard CHAR(AMP) tolerance and approved to progress to protective coatings. >Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure >Confirmation that required quantity and type's of NOE has been completed and any identified defects have been remediated. | Certify Doc / Ref - IFC DWGs | PFS Engineering - Site project Manager | 4 - Drilling the holes based in concrete
17 | Compile, review and submit documentation | Project Structure Specification CO? Rev. 01 IFC structure DWG | Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report | PFS Manufactures Data Report | Site project Manager | 17 - Compile, review and submit documentation | Specification Standard - Project Structure Specification CO? Rev. 01 IFC structure DWG | Acceptance Criteria - Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report | Certify Doc / Ref - PFS Manufactures Data Report | PFS Engineering - Site project Manager | Specification Standard - Project Structure Specification C0702 Rev. 01
Acceptance Criteria - Studs' Holes location should be in compliance with IFC Drawing 22 mm Hole Diameter for M20 Studs Hole depth >210 mm
Certify Doc / Ref - IFC Drawing Hilti HIT•RE 500 V4 Technical Data sheet
PFS Engineering - Team Leader
5 - Blow out all holes
Specification Standard - Site installation methodology Project Structure Specification CD702 Rev. 01 IFC structure DWG
Acceptance Criteria - Blow out all hole to make sure all holes are free from dust
Certify Doc / Ref - IFC Drawing Hilti HIT·RE 500 V4 Technical Data sheet
PFS Engineering - Team Leader
6 - Chemical Anchoring
Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Epoxy Studs using Hilti HIT•RE 500 V4 Make sure minimum 210 mm the embedment to achive Wait for epoxy to cure
Certify Doc / Ref - IFC Drawing Hilti HIT-RE 500 V4 Technical Data sheet
PFS Engineering - Team Leader
7 - Land Base plates on studs level base plates with Jacking nuts
Specification Standard - Project Structure Specification C0702 Rev. 01
Acceptance Criteria - Make sure the base plates are leveled and confirm their elevation
Certify Doc / Ref - IFC Drawing
PFS Engineering - Team Leader
8 - Final alignment Bolt wide flange beams to base plate
Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
Acceptance Criteria - Verify that the structural component are aligned based on IFC Drawing Bolts to be Installed and snug tightened
Certify Doc / Ref - IFC Drawing
PFS Engineering - Team Leader
9 - Installation of Dura wall panels and cam covers
Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure OWG
Acceptance Criteria - Carefully position wall panels and cam covers according to the approved drawings.
Certify Doc / Ref - IFC DWGs
PFS Engineering - Team Leader
10 - Holing
Specification Standard - Project Structure Specification CO? Rev. 01 IFC structure DWG SHE0-01-02-0040
Acceptance Criteria - Manual holing shall be performed on GRP material.
Certify Doc / Ref - IFC OWGs
PFS Engineering - Team Leader
11 - Dimension check
Specification Standard - IFC DWG
Acceptance Criteria - Compliance vvith IFC DWGs
Certify Doc / Ref -
PFS Engineering - Team Leader
12 - Visual inspection of Fasteners
Specification Standard - IFC Drawing
Acceptance Criteria - All fasteners {bolts, nuts, washers) are to be in compliance with the Project requirement (Grade, Size and Length)
Certify Doc / Ref - IFC Drawing
PFS Engineering - Team Leader
13 - Snug tightening of fastener to fasten the brackets to the GRP material
Specification Standard - Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
Acceptance Criteria - 100% of fixings securing brackets to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
Certify Doc / Ref -
PFS Engineering - Team Leader
14 - Assembly of the angles between bracke.ts
Specification Standard - Project Structure Specification CO? Rev. 01 IFC structure DWG
Acceptance Criteria - The angles to be assembled between bracket with fasteners
Certify Doc / Ref - IFC DWGs
PFS Engineering - Team Leader
15 - Snug tightening of fastener to fasten angles to the brackets
Specification Standard - Standard operation procedure for steel structure boll tightening SHEQ-01-02-0038
Acceptance Criteria - 100% of fixings securing brackets and angles to be inspected for snug tight condition and marked with coloured paint pen lo confirm fixing condtion has been checked and verified.
Certify Doc / Ref -
PFS Engineering - Team Leader
16 - Final Inspection
Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured lo acceptable standard CHAR(AMP) tolerance and approved to progress to protective coatings. >Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure >Confirmation that required quantity and type's of NOE has been completed and any identified defects have been remediated.
Certify Doc / Ref - IFC DWGs
PFS Engineering - Site project Manager
17 - Compile, review and submit documentation
Specification Standard - Project Structure Specification CO? Rev. 01 IFC structure DWG
Acceptance Criteria - Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report
Certify Doc / Ref - PFS Manufactures Data Report
PFS Engineering - Site project Manager