## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1212-ITP-004 Balustrade Installation | itp |  |  |  |  | DN1212-ITP-004 Balustrade Installation RevA
section | ENGINEERING
checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
label | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
label | C - S
label | Downer - Downer
label | C - H
holdpoint | AUTHORITY HOLDPOINT
section | GOOD RECEIPT ON SITE
checkpoint | 2 - Inspection upon receipt at site
label | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport
label | Certify Doc / Ref - IFC DWG
label | PFS Engineering - PM/PE
label | C - V
label | Downer - Downer
label | C - R
section | INSTALLATION OF STUDS
checkpoint | 3 - Installation of Templates to identify the Hole locations
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Anchors Hole locations should be in complied with IFC Drawing
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 4 - Drilling the holes based in concrete
label | Specification Standard - Project Structure Specification C0702 Rev. 01
label | Acceptance Criteria - Studs' Holes location should be in compliance with IFC Drawing
label | ○ 22 mm Hole Diameter for M20 Studs
label | ○ Hole depth >210 mm
label | Certify Doc / Ref - IFC Drawing Hilti HIT-RE 500 V4 Technical Data sheet
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 5 - Blow out all holes
label | Specification Standard - Site installation methodology Project Structure Specification CD702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Blow out all hole to make sure all holes are free from dust
label | Certify Doc / Ref - IFC Drawing Hilti HIT·RE 500 V4 Technical Data sheet
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 6 - Chemical Anchoring
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Epoxy Studs using Hilti HIT-RE 500 V4
label | ○ Make sure minimum 210 mm the embedment to acheive
label | ○ Wait for epoxy to cure
label | Certify Doc / Ref - IFC Drawing Hilti HIT-RE 500 V4 Technical Data sheet
label | PFS Engineering - Team Leader
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Land Base plates on studs level base plates with Jacking nuts
label | Specification Standard - Project Structure Specification C0702 Rev. 01
label | Acceptance Criteria - Make sure the base plates are leveled and confirm their elevation
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Team Leader
label | C - V, D
checkpoint | 8 - Final alignment - Bolt wide flange beams to base plate
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | ○ Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
label | Acceptance Criteria - Verify that the structural component are aligned based on IFC Drawing
label | ○ Bolts to be Installed and snug tightened
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Team Leader
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Installation of Dura wall panels and cam covers
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure OWG
label | Acceptance Criteria - Carefully position wall panels and cam covers according to the approved drawings.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - D
section | ASSEMBLY - LIGHTNING AND CONDUIT BRACKET
checkpoint | 10 - Holing
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG SHEQ-01-02-0040
label | Acceptance Criteria - Manual holing shall be performed on GRP material
label | Certify Doc / Ref - IFC OWGs
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 11 - Dimension check
label | Specification Standard - IFC DWG
label | Acceptance Criteria - Compliance vvith IFC DWGs
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 12 - Visual inspection of Fasteners
label | Specification Standard - IFC Drawing
label | Acceptance Criteria - All fasteners {bolts, nuts, washers) are to be in compliance with the Project requirement (Grade, Size and Length)
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 13 - Snug tightening of fastener to fasten the brackets to the GRP material
label | Specification Standard - Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
label | Acceptance Criteria - 100% of fixings securing brackets to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 14 - Assembly of the angles between brackets
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - The angles to be assembled between bracket with fasteners
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - V/D
checkpoint | 15 - Snug tightening of fastener to fasten angles to the brackets
label | Specification Standard - Standard operation procedure for steel structure boll tightening SHEQ-01-02-0038
label | Acceptance Criteria - 100% of fixings securing brackets and angles to be inspected for snug tight condition and marked with coloured paint pen lo confirm fixing condtion has been checked and verified.
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 16 - Final Inspection
label | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured lo acceptable standard & tolerance and approved to progress to protective coatings
label | ○ > Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure
label | ○ > Confirmation that required quantity and types of NOE has been completed and any identified defects have been remediated
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Site project Manager
label | C - RA
section | QUALITY REVIEW
checkpoint | 17 - Compile, review and submit documentation
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report
label | Certify Doc / Ref - PFS Manufactures Data Report
label | PFS Engineering - Site project Manager
label | C - S
label | Downer - Downer
label | C - RA
section | FINAL ITP CLOSE-OUT
checkpoint-no-status | ITP APPROVAL PROCESS
textbox | Approved by [Engineer/Client] - Name:
textbox | Issued for Construction - Name:
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature