## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1212-ITP-015 Bearing Pad Grouting | itp |  |  |  |  | DN1212-ITP-015 Bearing Pad Grouting Rev1
section | 1 - PRELIMINARY AND GENERAL
checkpoint | 1.1 - Method Statement Development & Safety Analysis
label | Standard, Drawing or Specification Reference - The Downer Standards [TDS)
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review
label | Test Frequency - Once
label | QA Record - Method Statement & JSEA Completed & signed by relevant authority
label | DNZ Engineer - H
label | Engineer's Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Confirmation of superstructure position
label | Standard, Drawing or Specification Reference - Signed ITP
label | Construction Activity Description, Test Type and Acceptance Criteria - Signed ITP required for the position of the superstructure before grouting.
label | Test Frequency - Once
label | QA Record - Signed ITP
label | DNZ Engineer - I
label | Engineer's Rep - W
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
section | 2 - MATERIAL APPROVALS
checkpoint | 2.1 - Non Shrink Grout Approval
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 — PROPOSED ACCESS RAMP - EXISTING PIER 1 DETAILS
label | ○ 3235599-SP03-ST-3201 — PROPOSED ACCESS RAMP - EXISTING PIER 2 DETAILS
label | ○ 3235599-SP03-ST-3202 — PROPOSED ACCESS RAMP - EXISTING PIER 2 DETAILS
label | ○ 3235599·SP03-ST-3250 — PROPOSED ACCESS RAMP - ABUTMENT DETAILS - SHEET 1
label | ○ 3235599·SP03-ST-3252 — PROPOSED ACCESS RAMP - ABUTMENT BEARING
label | ○ App 1C - 746-24-847-AC — Tech Spec - Geo & Strut Spec - C0602.10.04
label | Construction Activity Description, Test Type and Acceptance Criteria - Non shrink grout - slka 212 HP to be submitted to designer for review and approval as it obtains 85 Mpa after 28 Days> 50 Mpa as per 3252 - Note 1.4
label | Test Frequency - Once
label | QA Record - MOS
textbox | In Eight Ref
label | DNZ Engineer - R
label | Engineer's Rep - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Glass Plate Trial
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3252 — PROPOSED ACCESS RAMP - ABUTMENT BEARING - Note
label | Construction Activity Description, Test Type and Acceptance Criteria - As per 3235599-SP03-ST-3252 — PROPOSED ACCESS RAMP - ABUTMENT BEARING - Note 1.4. Glass Plate trial to be undertaken to replicate bearing pad footprint of 230mm x 230mm x 20mm. Area is to be poured prior to installation of bearing grout to confirm voiding is less than 10% of area. Undertaken with MSQA observations.
label | ○ Methodology to submitted prior to commencement.
label | Test Frequency - Once
label | QA Record - Site Observation Report, Written acceptance of material following trlal.
label | DNZ Engineer - I
label | Engineer's Rep - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Curing Method
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - According to MDS sheet for Sika 212 HP, See below, grout to be sealed with timber shutter, left to cure within small shutter and then treated with Sika Anti Sol as per data sheet attached.
label | CURING TREATMENT
label | ○ Formwork should be left In place for at least 5 days if possible, to prevent moisture evaporation and provide restraint to early age hardened expansion.
label | ○ Once fomwork is removed a suitable curing membrane such a Sika Antisol should be applied to any exposed faces.
label | ○ Refer to separate data sheet for further information.
label | Test Frequency - Once
label | QA Record - MDS, Photos
label | DNZ Engineer - R
label | Engineer's Rep - R
label | Designer Rep - R
section | 3 - CONSTRUCTION ACTIVITIES
checkpoint | 3.1 - Construction Joint
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3252 — PROPOSED ACCESS RAMP - ABUTMENT BEARING
label | Construction Activity Description, Test Type and Acceptance Criteria - Formation of construction joint required on top of pier / abutment to the construction joint must be visible
label | Test Frequency - Once
label | QA Record - Photos
label | DNZ Engineer - H
label | Engineer's Rep - R
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Grouting Pre-Pour Inspection
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3202 — PROPOSED ACCESS RAMP - EXISTING PIER 2 DETAILS
label | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - No reinforcing requirements.
label | ○ Check to ensure that the surface is prepped, underside of bearing pad is in correct location prior to pouring. Nominal 20mm will be poured.
label | Test Frequency - Each Structure
label | QA Record - MSQA SVR, Pre-Pour Checklist, Photos
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Grouting Pour
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3252 — PROPOSED ACCESS RAMP­ - ABUTMENT BEARING
label | ○ NS3109
label | ○ AS1012
label | ○ Spec - C0602.10.04
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete to be poured as per manufacturer's recommendations where 3.7 lltres per bag.
label | ○ Samples to be taken from each batch using steel moulds where 1, 2, 3, 5, 14 and 28 day tests are to be taken to ensure that grout has reached necessary strength
label | MlXING
label | ○ Place about 70-80% of the premeasured clean water (depending on consistency required — refer to "Mix Ratio") into a clean container and gradually add the whole bag of SikaGrout - 212 HP into it while continuously mixing. Add the remaining water until the desired consistency is obtained. Mix for 3-5 minutes with a low speed drill (500 rpm max.). Allow to stand so any entrapped air can escape. Do not add more water to increase flow of the grout if a mix has stiffened due to time delays. If the grout is unworkable discard.
label | Test Frequency - Once
label | QA Record - Photos, Test Report for Compressive Strength
label | DNZ Engineer - H
label | Engineer's Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Post Pour Inspection
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC-Tech Spec - Geo & Struc
label | ○ 3235599-SP03-ST-3003
label | ○ NZS3114
label | Construction Activity Description, Test Type and Acceptance Criteria - Joint Inspection be undertaken with designer to inspect shutters of structure following removal of shutters and survey/check dimension of structure have achieved stipulated tolerance, stated In drawing suite and NZS 3109
label | Test Frequency - Once
label | QA Record - Visual Inspection, Photos
label | DNZ Engineer - H
label | Engineer's Rep - R
label | Designer Rep - W
holdpoint | AUTHORITY HOLDPOINT
section | 4 - FINAL RECORDS
checkpoint | 4.1 - As-Built
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Non-conformances
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
textbox | NCR Reference
label | Test Frequency - Each NCR
label | QA Record - NCR forms on InEight
label | DNZ Engineer - H
label | Engineer's Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
label | Prepared By: Project Engineer - Grant Wallace
label | Reviewed By: Project Manager - Dan Trotman
label | Reviewed By: Quality Mgr./Eng. - Nas Matar
label | Reviewed By: Design Engineer - Daniel Cvitanich
label | Reviewed By: AT Project Manager - Werner Nel
label | Reviewed By: AT Engineer to Contract - Mike Robertson
date | Date:
section | FINAL ITP CLOSE-OUT
checkpoint | FINAL ITP CLOSE-OUT
textbox | Downer Project/Site Engineer:
textbox | QA Mgr./Engineer:
textbox | Engineer Rep(Assistant):
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1212-ITP-004 Balustrade Installation | itp |  |  |  |  | DN1212-ITP-004 Balustrade Installation RevA
section | ENGINEERING
checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
label | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
label | C - S
label | Downer - Downer
label | C - H
holdpoint | AUTHORITY HOLDPOINT
section | GOOD RECEIPT ON SITE
checkpoint | 2 - Inspection upon receipt at site
label | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport
label | Certify Doc / Ref - IFC DWG
label | PFS Engineering - PM/PE
label | C - V
label | Downer - Downer
label | C - R
section | INSTALLATION OF STUDS
checkpoint | 3 - Installation of Templates to identify the Hole locations
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Anchors Hole locations should be in complied with IFC Drawing
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 4 - Drilling the holes based in concrete
label | Specification Standard - Project Structure Specification C0702 Rev. 01
label | Acceptance Criteria - Studs' Holes location should be in compliance with IFC Drawing
label | ○ 22 mm Hole Diameter for M20 Studs
label | ○ Hole depth >210 mm
label | Certify Doc / Ref - IFC Drawing Hilti HIT-RE 500 V4 Technical Data sheet
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 5 - Blow out all holes
label | Specification Standard - Site installation methodology Project Structure Specification CD702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Blow out all hole to make sure all holes are free from dust
label | Certify Doc / Ref - IFC Drawing Hilti HIT·RE 500 V4 Technical Data sheet
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 6 - Chemical Anchoring
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Epoxy Studs using Hilti HIT-RE 500 V4
label | ○ Make sure minimum 210 mm the embedment to acheive
label | ○ Wait for epoxy to cure
label | Certify Doc / Ref - IFC Drawing Hilti HIT-RE 500 V4 Technical Data sheet
label | PFS Engineering - Team Leader
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Land Base plates on studs level base plates with Jacking nuts
label | Specification Standard - Project Structure Specification C0702 Rev. 01
label | Acceptance Criteria - Make sure the base plates are leveled and confirm their elevation
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Team Leader
label | C - V, D
checkpoint | 8 - Final alignment - Bolt wide flange beams to base plate
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | ○ Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
label | Acceptance Criteria - Verify that the structural component are aligned based on IFC Drawing
label | ○ Bolts to be Installed and snug tightened
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Team Leader
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Installation of Dura wall panels and cam covers
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure OWG
label | Acceptance Criteria - Carefully position wall panels and cam covers according to the approved drawings.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - D
section | ASSEMBLY - LIGHTNING AND CONDUIT BRACKET
checkpoint | 10 - Holing
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG SHEQ-01-02-0040
label | Acceptance Criteria - Manual holing shall be performed on GRP material
label | Certify Doc / Ref - IFC OWGs
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 11 - Dimension check
label | Specification Standard - IFC DWG
label | Acceptance Criteria - Compliance vvith IFC DWGs
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 12 - Visual inspection of Fasteners
label | Specification Standard - IFC Drawing
label | Acceptance Criteria - All fasteners {bolts, nuts, washers) are to be in compliance with the Project requirement (Grade, Size and Length)
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 13 - Snug tightening of fastener to fasten the brackets to the GRP material
label | Specification Standard - Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
label | Acceptance Criteria - 100% of fixings securing brackets to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 14 - Assembly of the angles between brackets
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - The angles to be assembled between bracket with fasteners
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - V/D
checkpoint | 15 - Snug tightening of fastener to fasten angles to the brackets
label | Specification Standard - Standard operation procedure for steel structure boll tightening SHEQ-01-02-0038
label | Acceptance Criteria - 100% of fixings securing brackets and angles to be inspected for snug tight condition and marked with coloured paint pen lo confirm fixing condtion has been checked and verified.
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 16 - Final Inspection
label | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured lo acceptable standard & tolerance and approved to progress to protective coatings
label | ○ > Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure
label | ○ > Confirmation that required quantity and types of NOE has been completed and any identified defects have been remediated
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Site project Manager
label | C - RA
section | QUALITY REVIEW
checkpoint | 17 - Compile, review and submit documentation
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report
label | Certify Doc / Ref - PFS Manufactures Data Report
label | PFS Engineering - Site project Manager
label | C - S
label | Downer - Downer
label | C - RA
section | FINAL ITP CLOSE-OUT
checkpoint-no-status | ITP APPROVAL PROCESS
textbox | Approved by [Engineer/Client] - Name:
textbox | Issued for Construction - Name:
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature