## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1212-ITP-003 Site Installation | itp |  |  |  |  | DN1212-ITP-003 Site Installation RevC
section | ENGINEERING
checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
label | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
label | Certify Doc / Ref - IFC DWGS
label | PFS Engineering - PM/PE
label | C - S
label | Downer - Downer
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Submit the required documents to Client for review
label | Specification Standard - Project Structure Specification C0702 Rev. 01
label | Acceptance Criteria - Site installation methodology shall be submitted to the Engineer for review
label | Certify Doc / Ref - Erection Sequence Methodology
label | PFS Engineering - PM/PE
label | C - S
label | Downer - Downer
label | C - R
checkpoint | 3 - Installation Procurement - Cast in items
label | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Confirm Procurement and delivery of all Cast in Items:
label | i.shear keys.
label | ii. uplift restraints and associated nuts
label | iii. plate washers.
label | iv. Macalloy Bars (ETA 06/01/25) and couplers with denso tape.
label | v. Reidbar and couplers + touch up protective coating. vi. Nylon washers and rubber sleeves.
label | vii. Temporary bearing components.
label | Certify Doc / Ref - IFC DWG
label | ○ PFS: 39028-3202-000-FABRC
label | ○ PFS: 39028-3201-000-FABRC
label | ○ Mill Certs Compliance Documentation
label | PFS Engineering - PM/PE
label | C - V
section | GOOD RECEIPT ON SITE
checkpoint | 4 - Inspection upon receipt at site
label | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport
label | Certify Doc / Ref - IFC DWG
label | PFS Engineering - PM/PE
label | C - V
label | Downer - Downer
label | C - R
checkpoint | 5 - Inspection upon receipt at site - Cast in
label | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - The material receipt at site need to be visually inspected for quantity, make sure no damage occurred during transport. All related documents have been received.
label | Certify Doc / Ref - IFC DWG
label | PFS Engineering - PM/PE
label | C - V
label | Downer - Downer
label | C - R
section | STEEL STRUCTURE ERECTION
checkpoint | 6 - Preparation work - prior to Span Lifting for All Spans
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Make sure survey has been done and center marks on the framework as a reference have been provided by Downer Installation of 100x100 EA as a lifting aid on temporary structure
label | ○ Span unloaded from truck and placed on Dunnage on ground prior to rigging adjustment
label | ○ Attaching the tag lines to Spans to prevent rotation during installation
label | Certify Doc / Ref - Lift plan
label | PFS Engineering - PM/PE
label | C - H
label | Downer - Downer
label | C - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Confirm all Manufacture documentation has been completed for Span #2
label | Specification Standard - Project Structure Specification C0702 Rev. 01
label | Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off.
label | Certify Doc / Ref - QA Documentation
label | PFS Engineering - PM/PE
label | C - V
label | Downer - Downer
checkpoint | 8 - Installation of Span #2
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Verify that the structural component is securely rigged according to the rigging plan
label | ○ To lift Span #2 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure
label | ○ Chain block will be connected to the West end to adjust level.
label | ○ When location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers.
label | Certify Doc / Ref - Lift plan
label | PFS Engineering - Site project Manager
label | C - H
label | Downer - Downer
label | C - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Macalloy Bars installation for Span #2
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - To keep Macalloy bar aligned, a coupler to be tightened to extend the Macalloy bar and Tempory nut will be added to the rod on the Span 2 high end. The nuts will be tightened to hold the Macalloy bars in correct position.
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Site project Manager
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Confirm all Manufacture documentation has been completed for Span #3
label | Specification Standard - Project Structure Specification C0702 Rev. 01
label | Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off.
label | Certify Doc / Ref - QA Documentation
label | PFS Engineering - PM/PE
label | C - V
label | Downer - Downer
label | C - R
checkpoint | 11 - Installation of Span#3
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan
label | ○ To lift Span #3 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers.
label | Certify Doc / Ref - Lift plan
label | PFS Engineering - Site project Manager
label | C - H
label | Downer - Downer
label | C - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #3
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Nuts on Reidbar to be snug tightened to help minimal lateral movement.
label | Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing
label | PFS Engineering - Site project Manager
label | C - H
label | Downer - Downer
label | C - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Confirm all Manufacture documentation has been completed for Span #4
label | Specification Standard - Project Structure Specification C0702 Rev. 01
label | Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off.
label | Certify Doc / Ref - QA Documentation
label | PFS Engineering - PM/PE
label | C - V
label | Downer - Downer
checkpoint | 14 - Installation of Span#4
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan
label | ○ To lift Span # 4 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers.
label | Certify Doc / Ref - Lift plan
label | PFS Engineering - Site project Manager
label | C - H
label | Downer - Downer
label | C - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #4
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Nuts on Reidbar to be snug tightened to help minimal lateral movement.
label | Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing
label | PFS Engineering - Site project Manager
label | C - H
label | Downer - Downer
label | C - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - Confirm all Manufacture documentation has been completed for Span #5
label | Specification Standard - Project Structure Specification C0702 Rev. 01
label | Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off.
label | Certify Doc / Ref - QA Documentation
label | PFS Engineering - PM/PE
label | C - V
label | Downer - Downer
checkpoint | 17 - Installation of Span#5
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan
label | ○ To lift Span #5 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers.
label | Certify Doc / Ref - Lift plan
label | PFS Engineering - Site project Manager
label | C - H
label | Downer - Downer
label | C - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #5
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Nuts on Reidbar to be snug tightened to help minimal lateral movement.
label | Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing
label | PFS Engineering - Site project Manager
label | C - H
label | Downer - Downer
label | C - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 19 - Confirm all Manufacture documentation has been completed for Span #6
label | Specification Standard - Project Structure Specification C0702 Rev. 01
label | Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off.
label | Certify Doc / Ref - QA Documentation
label | PFS Engineering - PM/PE
label | C - V
label | Downer - Downer
checkpoint | 20 - Installation of Span #6
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan
label | ○ To lift Span #6 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers.
label | Certify Doc / Ref - Lift plan
label | PFS Engineering - Site project Manager
label | C - H
label | Downer - Downer
label | C - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 21 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #6
label | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Temporary Bearing installation under lower end Nuts on Reidbar to be snug tightened to help minimal lateral movement.
label | Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing
label | PFS Engineering - Site project Manager
label | C - H
label | Downer - Downer
label | C - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 22 - Dimensional survey By Downer
label | Specification Standard - Site installation methodology IFC Drawings
label | Acceptance Criteria - Conduct a thorough dimensional survey inspection to confirm that the component is correctly positioned and secured based on IFC Drawing. Measured dimensions shall be within stated tolerances unless noted otherwise.
label | ○ Project specification clause C0702.1.3 Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | ○ Record the lifting operation in the project log, including any deviations or required adjustments to be made.
label | Certify Doc / Ref - Marked up and Signed IFC DWGS
label | PFS Engineering - Site project Manager
label | C - H
label | Downer - Downer
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 23 - Remove Reid bar tension
label | Specification Standard - Site installation methodology IFC Drawings
label | Acceptance Criteria - Lossen Reidbars to match IFC drawing detail at all peirs before any headstock pours.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Site project Manager
label | C - H
label | Downer - Downer
label | C - H
holdpoint | AUTHORITY HOLDPOINT
section | POURING HEADSTOCK AND GROUTING BY DOWNER
checkpoint | 24 - Reid bar touch up painting (if required)
label | Acceptance Criteria - Any coatings damage to Reidbars touched up as per paint specification, Coatings to comply with note 1.2 on drawing ST-3202.
label | ○ Application/report methods shall be approved by independent coating inspector. Inspection of coating application shall be completed by coating applicator
label | Certify Doc / Ref - Project Paint Specification
label | PFS Engineering - Site project Manager
label | C - V
label | Downer - Downer
label | C - V
section | POST HEAD STOCK POURING ACTIVITIES
checkpoint | 25 - Hold Down Bolts tightening
label | Specification Standard - Site installation methodology IFC Drawings Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
label | Acceptance Criteria - Remove additional nuts, tape (masking and double sided) used for alignment. Apply rubber sleeves to the exposed threads. Reinstall oversized washers, apply instulating washers and tighten nuts down to achieve a 1mm gap between washer and nut, lock nut to be installed as per detail C & Section 5 on ST-3202, Detail D on ST-3200.
label | Certify Doc / Ref - Bolt Tightening report
label | PFS Engineering - Site project Manager
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 26 - Macalloy Bolts tightening
label | Specification Standard - Site installation methodology IFC Drawings Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
label | Acceptance Criteria - to Undo the coupler, remove temporary alignment nut, install the rubber sleeves to the exposed rod, install the washers, nuts and snug tighten the nuts (as there are compressible components in contanc area)
label | Certify Doc / Ref - Bolt Tightening report
label | PFS Engineering - Site project Manager
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 27 - Temporary restraints removal
label | Specification Standard - Site installation methodology IFC Drawings
label | Acceptance Criteria - All temporary restraints to the temporary shoring to be removed
label | ○ All positioning Jigs and screws applied to PTFE on Shear Keys to be removed
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 28 - Installation of Granor Bearing
label | Specification Standard - Site installation methodology IFC Drawings Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
label | Acceptance Criteria - The Temporary Bearing to be removed and Granor Bearing to be installed in the position the Bolts need to be snug tightened to the girders (top) and screws need to be snug tightened into the base plate. The keeper plates' bolts (M20) for uplift restraint to be tightened (full Tensioned).
label | Certify Doc / Ref - Bolt Tightening report
label | PFS Engineering - Site project Manager
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 29 - Installation of remaining Decking panels and wall panels
label | Specification Standard - Site installation methodology IFC Drawings
label | Acceptance Criteria - Carefully position the Decking and wall panels in the conjunction area according to the approved drawings.
label | Certify Doc / Ref - IFC DWGS
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 30 - Snug tightening of Decking panels and wall panels
label | Specification Standard - Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
label | Acceptance Criteria - Fasteners of Decking and wall panels to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condition has been checked and verified.
label | Certify Doc / Ref - Bolt Tightening report
label | PFS Engineering - Site project Manager
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 31 - Installation of remaining handrails between the spans
label | Specification Standard - Site installation methodology IFC Drawings
label | Acceptance Criteria - Carefully position the handrails in the conjunction area according to the approved drawings.
label | Certify Doc / Ref - IFC DWGS
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 32 - Snug tightening of Conduti Brackets
label | Specification Standard - Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
label | Acceptance Criteria - Fasteners of handrails to be inspected for snug tight condition with addition of Loctite or Locknut to prevent loosening and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
label | ○ Note: The connections for the EA's spanning the pier movement joints shall be hand tightened, Ref CAN 063
label | ○ Lock tight applied to all bolts
label | ○ Hand tight for expansion joins
label | Certify Doc / Ref - Bolt Tightening report
label | PFS Engineering - Site project Manager
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 33 - Installation of Expansion plates
label | Specification Standard - Site installation methodology IFC Drawings
label | Acceptance Criteria - The expansion plates to be installed between Span 1 and 2 and between span 6 and 7
label | Certify Doc / Ref - IFC DWGS
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 34 - Inspection to identify any damage to painted surfaces requiring touchup
label | Acceptance Criteria - Inspect paint for any required repair and touch up of paint works (bolted connections and any damage paint to steelwork). Repair method proposed shall be approved by the independent coating inspector. Areas repaired shall be reinspected by the coating applicator and independent inspector.
label | Certify Doc / Ref - Note 1.2, Drawing ST-3202
label | PFS Engineering - Site project Manager
label | C - H
label | Downer - Downer
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 35 - Site Installation and Sign-off
label | Specification Standard - Erection sequence methodology (EMS) IFC Drawings
label | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been completely installed.
label | ○ Inspection of erected steelwork in accordance with AS/NZS 5131 Section 13.11 as per specification C0702.1.10. Inspections shall cover all relevant items listed in clause 13.11.1.
label | ○ Inspections shall be documented in inspection reports as per clause 13.11.3 of AS/NZS5131, and included in the QA documentation.
label | ○ Inspections shall be conducted by competent personnel. Evidence of experience or qualifications for nominated individual(s) shall be provided for review. An example of qualification of competent personnel is a relevant trade qualification and over 10 years experience in structural steel erection. Following inspection on site, should any modification or repairs be required a written procedure shall be submitted to the Engineer prior to any work proceeding as per C0702.3.
label | Certify Doc / Ref - IFC DWGS
label | PFS Engineering - Site project Manager
label | C - H
label | Downer - Downer
label | C - H
holdpoint | AUTHORITY HOLDPOINT
section | QUALITY REVIEW
checkpoint | 36 - Compile, review and submit documentation
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report
label | Certify Doc / Ref - PFS Manufactures Data Report
label | PFS Engineering - Site project Manager
label | C - S
label | Downer - Downer
label | C - RA
section | FINAL ITP CLOSE-OUT
checkpoint-no-status | ITP APPROVAL PROCESS
textbox | Approved by [Engineer/Client] - Name:
textbox | Issued for Construction - Name:
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature