## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - 497 - Anti Graffiti Protective Coatings | itp |  |  |  |  | ITP - 497 - Anti Graffiti Protective Coatings Rev 3
section | Anti Graffiti & Protective Coatings
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Obtain Permits
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Permit to Work, PTW # 1 Fall Prevention, Notify Worksafe NZ if required. Permit to Work around services (Gas, Power etc) if required.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-construction sign offs (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Subcontract and Supplier Aggrements via email.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-construction sign offs (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure all Sub-Contractors and suppliers go through a Downer Induction
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Induction
label | Conformance Criteria - Issued induction stickers and number
label | Records - Hazard ID and Pre-starts to safety team
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-construction sign offs (3)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Subcontractor to produce specification for the extent and frequency of testing for Design Engineer for approval
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document submission
label | Records - Approved subcontractor testing schedule
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-construction sign offs (4)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Visual inspection to ensure it is dust free, clean and repaired prior to application.
label | ○ Any fairing coat/grout that is used to achieve the F5 finish will need the required curing time as per product specification.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Document review
label | Conformance Criteria - Ensure PCP and Snag List for the structure are both signed off
label | ○ BBO sign off for Pre paint inspection to ensure F5 finish has been achieved
label | Records - Completed PCP & Snag List
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-construction sign offs (5)
label | Detail - Collection of names, experience and qualifications of coating applicators
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - NZTA S/10 4.1 c
label | Records - Applicator's detail submission
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Design Engineer to be advised when painting is occuring so they can visit site and do a visual inspection
label | Frequency - During Painting
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint | 4 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the supplied paint system meets the requirements as per the specification. .
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - NZTA S10 Approved paint system to be signed off by the Design Engineer
label | Records - Painting system manufacturers records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirmation of Design life not less than 10 years
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Material Compliance (3)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirmation of cleaning product (to align with TDS) - Pressure washing of substrate no greater than 2700psi.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Environmental (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Weather checks to be undertaken prior to starting coating
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and review of forecast
label | Conformance Criteria - No painting during Inclement weather such as rain, snow, fog, mist, pollution or dust or excessively high winds
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Environmental (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Humidity and Temperature checks to be undertaken prior to starting coating. Also moisture check of substrate to be undertaken as per specification supplied.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | Conformance Criteria - No painting if the surface temperature is below 10 degrees or exceeds 32 degrees. Or the surface temperature drops to less than 3 degrees above the ambient dew point, Or humidity exceeds 85%. Or if moisture present.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Pre-paint cleaning and substrate verifications (1)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Demonstration of substrate cleaned all dust, dirt and other surface contaminants must be removed. Using manufacturer’s approved surface cleaner
label | Frequency - Before painting
label | Inspection / Test Method submission, visual inspection, testing, measure, review -
checkpoint | 6 - Pre-paint cleaning and substrate verifications (2)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Demonstration of surface moisture conditions. - 1 test every 46m² or for every time painting
label | Frequency - Before painting (minimum 28 days after concrete, grout and fairing coat has cured)
label | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | Conformance Criteria - NZTA S/10 8.8 refers to ASTM D4263
checkpoint | 6 - Pre-paint cleaning and substrate verifications (3)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Pre-paint checks
label | ○ Relative Humidity (Measured), Air Temperature (Measured), Surface Temperature (Measured), Dew Point (Calculated) Surface minus Dew Point (Calculated), Dry Surface (Visual Inspection)
label | Frequency - Before painting
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measuring Devices
label | Conformance Criteria - QA Checksheets
checkpoint | 7 - Painting (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure dust control throughout application and curing. Co-ordinate other site activites that may generate dust to stop until the paint is dry.
label | Frequency - Before and During painting
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - No dust
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Painting (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure subcontractor records the date, type, location and extent of all coatings
label | Frequency - During Painting
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Painting (3)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Recoating time as per manufacturers specifications, and weather conditions.
label | Frequency - After painting
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Completed paint system (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 1. Dry Film Thickness
label | 2. Bond Strength
label | Frequency - 14 days after painting
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NZTA S10 Section 13.2
label | Conformance Criteria - DFT minimum of 100 microns
label | ○ Bond strength minimum 2MPa
label | Records - IANZ Test Results or other approved
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Completed paint system (2)
label | Detail - Post works inspection with BBO Sign Off
label | Frequency - At completion of painting
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Dry Film Thickness
label | Conformance Criteria - The completed paint system or coating shall be of uniform thickness, free of runs, sags, pinholes and bubbles, mudcracking, dry overspray, grit inclusion etc. All such imperfections shall be removed or made good to the satisfaction of the Design Engineer.
checkpoint | 9 - Lot Number QA File (1)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all OFIs are closed and included within QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
checkpoint | 9 - Lot Number QA File (2)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Delivery Dockets to be included in QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Delivery Dockets
checkpoint | 9 - Lot Number QA File (3)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Attach Sub-Contractor's QA.
label | Frequency - At the completion of the lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
checkpoint | 10 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature