## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Floor Preparation
section | Details
checkpoint | Check area clear of all other trades and their materials
checkpoint | Grind Floor and feather as required
checkpoint | Are there any cracks that require remediation?
checkpoint | Remediate cracks
checkpoint | Apply feather coat, Sanded, Edges
holdpoint | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Vinyl Installation (Basic)
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Check wall for smoothness where coving
checkpoint | Measure area
checkpoint | Acclimatise vinyl
section | Installation
checkpoint | Confirm vinyl layout direction
checkpoint | Confirm coving location/type
checkpoint | Confirm Regupol acoustic underlay to First Floor vinyl areas
checkpoint | Glue out floors
checkpoint | Install vinyl required for area - sheet vinyl, safety vinyl
checkpoint | Install coving & capping/sealant as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
holdpoint | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Tile Installation (Basic)
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
checkpoint | Measure area
section | Installation
checkpoint | Confirm carpet tile pattern direction/layout
checkpoint | Glue out floors
checkpoint | Install carpet tiles
checkpoint | Install trims as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
holdpoint | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Entry Mat Installation
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Area clear of all other trades and their materials | YES, NO, N/A
button | Surface is clean, dry, and free from dust and debris. | YES, NO, N/A
button | Check Recess Level meets requirements | YES, NO, N/A
button | Assess, Discuss, Price, Confirm required works | PROCEED, NOT PROCEED, N/A
holdpoint | Hold works to confirm preparation required
checkpoint | 3. PREPARE ENTRY MAT FOR INSTALLATION
button | Install Matwell frame | YES, NO, N/A
button | Level Floor to suit Thickness | YES, NO, N/A
button | Dimention measured on site | YES, NO, N/A
checkpoint | 4. ENTRY MAT INSTALLATION
button | Drop Entry Mat in to matwell | YES, NO, N/A
checkpoint | 5. FINAL INSPECTION
button | Confirm no visible defects or issues. | PASS, FAIL, N/A
checkpoint | 6. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
holdpoint | Subcontractor representative (Full name)
checkpoint | 7. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
holdpoint | Verified by CLIENT representative (Full name)
checklist | External Stairs Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
checkpoint | Measure area
section | Installation
checkpoint | Confirm Nosings to external stairs
checkpoint | Confirm Tactile indicators with black carborudum to external stailrs
checkpoint | Install nosings and tactile as required
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
holdpoint | SEND TO CLIENT FOR QUALITY APPROVAL