## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: Zone C Grid Line E
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2.202.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2.202.02 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2.206.03 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2.206.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2.206.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2.208.03 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2.208.01 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2.210.01 W06
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-212.03 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-212.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-212.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-214.04 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-214.03 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-214.02 W04
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-102.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-104.02 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-106.03 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-106.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-106.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-108.03 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-108.01 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-110.01 W06
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-112.03 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-112.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-112.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-114.04 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-114.03 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-114.02 W04
| step |  |  | Tier 2: L0 GF
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-56.05 W09
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-02.01 W08
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-04.01 W08
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-06.01 W08
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-08.01 W08
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-10.01 W08
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-12.01 W08
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-14.01 W08
| step |  |  | Tier 1: Zone C Grid Line 17
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-214.01 W10
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-06.01 W10
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-215.04 W10
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-114.01 W10
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-9.01 W10
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-115.04 W10
| step |  |  | Tier 1: Zone C Grid Line B
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-215.03 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-215.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-215.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-213.03 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-213.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-213.01 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-211.01 W06
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-209.01 W06
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-207.03 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-207.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-207.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-205.03 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-205.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-205.01 W04
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-115.03 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-115.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-115.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-113.03 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-113.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-113.01 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-111.01 W06
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-109.01 W06
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-107.03 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-107.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-107.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-105.03 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-105.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-105.01 W04
| step |  |  | Tier 2: L0 GF
QA - Captive Glazing | checklist |  |  | Tier 3: W.G.13.01 W08
QA - Captive Glazing | checklist |  |  | Tier 3: W.G.11.01 W08
QA - Captive Glazing | checklist |  |  | Tier 3: W.G.09.01 W08
QA - Captive Glazing | checklist |  |  | Tier 3: W.G.07.01 W08
QA - Captive Glazing | checklist |  |  | Tier 3: W.G.05.01 W08
QA - Captive Glazing | checklist |  |  | Tier 3: W.G.03.01 W08
QA - Captive Glazing | checklist |  |  | Tier 3: W.G.01.01 W08
| step |  |  | Tier 1: Zone B Grid Line B
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-203.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-203.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-201.02 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-24.01 W03
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-21.01 W03
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-13.08 W11
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-13.07 W11
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-13.06 W11
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-13.05 W11
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-13.04 W11
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-103.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-103.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-101.02 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-101.01 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-33.01 W03
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-13.08 W11
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-13.07 W11
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-13.06 W11
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-13.05 W11
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-13.04 W11
| step |  |  | Tier 2: L0 GF
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-56.04 W14
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-56.03 W14
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-56.02 W14
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-56.01 W09
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-12.01 W03
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-46.01 W12
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-19.02 W14
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-19.01 W14
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-11.06 W14
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-11.07 W19
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-11.04 W14
| step |  |  | Tier 1: Zone B Grid Line 4
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-13.03 W11
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-13.02 W11
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-13.01 W11
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-13.03 W11
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-13.02 W11
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-13.01 W11
| step |  |  | Tier 2: L0 GF
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-11.03 W18
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-11.02 W18
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-11.01 W18
| step |  |  | Tier 1: Zone A Grid Line 7
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-217.01 W10
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-23.02 W10
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-216.02 W06
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-216.01 W04
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-117.04 W46
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-29.01 W10
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-116.01 W06
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-116.02 W04
| step |  |  | Tier 2: L0 GF
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-15.02 W16
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-15.03 W16
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-15.04 W17
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-15.05 W16
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-15.06 W16
| step |  |  | Tier 1: Zone A Grid Line 1
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-224.01 W13
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-01.01 W10
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-119.02 W13
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-10.01 W10
| step |  |  | Tier 1: Zone A Grid Line E
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-221.03 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-221.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-221.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-223.03 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-223.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-223.01 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-224.02 W06
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-121.03 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-121.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-121.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-123.03 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-123.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-123.01 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-119.01 W06
| step |  |  | Tier 2: L0 GF
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-25.01 W03
| step |  |  | Tier 1: Zone A Grid Line I
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-22.01 W10
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-222.03 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-222.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-222.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-220.03 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-220.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-220.01 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-219.01 W06
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-218.03 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-218.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-218.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-217.04 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-217.03 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L2-217.01 W04
step | bar: Tier 1 to Tier 3
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-31.01 W10
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-122.01 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-122.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-122.03 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-120.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-120.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-120.03 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-149.01 W06
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-118.01 W04
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-118.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-118.03 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-117.01 W05
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-117.02 W01
QA - Captive Glazing | checklist |  |  | Tier 3: W.L1-117.03 W04
| step |  |  | Tier 2: L0 GF
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-53.01 W25
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-53.02 W25
QA - Captive Glazing | checklist |  |  | Tier 3: W.G-15.01 W15