## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-271- CIV-Permanent Farm Fencing
ITP Description: |  | Permanent Farm Fencing
Discipline (e.g. CIV/STR/RAIL: |  | 271- CIV
Revision Number: |  | 0
Revision Date: |  | 2025-05-09
ITP created by: |  | Kamel Alshobaki
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Ferris Rd
Inspection & Test Plan - Permanent chain mesh Fencing
[9 empty] | Revision: | 0
[9 empty] | Date: | 2025-05-09
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Drawing No. SD3151 VicRoads Drawing No. SD3111 VicRoads Drawing No. SD3161 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Materials
2.1 | Timber | IFC Drawings SD3111 | Untreated Timber and Treated Timber according to Vicroads SD3111. | Document Review | All elements | IP | SE/Site Supervisor
2.2 | Concrete | IFC Drawings AS 1379 & SD3111 & SD3161 | Shall be 20 MPa concrete to be used as per IFC drawings & Vicroads SD3111 & SD3161 and AS1379. | Document Review | Each Mix | IP | SE/Site Supervisor
2.3 | Steel components including wires and posts. | IFC Drawings SD3111 | All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Star Pickets according to Vicroads SD3111. | Document review Visual and Measure | All elements | IP | SE/Site Supervisor | Supplier Certificate of Compliance
3 | Pre-construction / Pre-installation Activities
3.1 | Survey Set-out | IFC Drawings | Survey to set out the following but not limited to: existing services, footing points and fence start and end points. Offset checked against the running edge prior to installation of posts. | Visual and Measure | Each element | IP | Surveyor SE/PE | This ITP
4
4.1 | Excavation works | IFC Drawings | Excavation completed by auger outside of service working limits. Follow asset owners guidelines for work around their service. | Visual | Each fence footing | IP | SE/Site Supervisor | This ITP
4.2 | Ground Conditions | IFC Drawings | All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required. | Visual | Each post | IP | SE/Site Supervisor | This ITP
4.3 | Fence Installation | IFC Drawings AS 1379 SD3111 | Timber posts shall be set in dug or drilled holes. Posts shall be set solidly on star picket and any space left around the posts shall be backfilled and the backfilling compacted. Concrete Shall be 20MPA strength grade complying with the requirements of AS 1379/1991. | Measure | Each post | IP | SE/Site Supervisor | This ITP Concrete Dockets
| Timber Post Intallation | IFC Drawings AS 1379 SD3111 | Timber intermediate post to be used at not more than 40m intervals and at a minimum length of 1800mm long. Timbers 2 x 1175 Long to be spaced evenly in pannel and clipped or tied to wires as sepcificed. | Measure | Each post | IP | SE/Site Supervisor | This ITP
4.4 | Strainer Assemblies and wire installation | SD3111 | - High tensile wires to be either reeved through holes bored in posts or stapled to post. - Wires to be placed at 150mm from each other for the first 3 wires from the ground level and increase to 175mm, 200mm and 250mm for the top 3 wires. - First wire should be at minimum 25mm or maximum 150mm from the ground level. - Maximum height for the top wire should 1150mm from the ground level. - Optional, galvanised hight tensile barbed wire can be used for wire number 3. - Total of 7 wires must be installed for the fence. | Visual | Each element | IP | SE/Site Supervisor | This ITP
5 | Post-construction / Post-installation Activities
5.1 | As-Built Survey | IFC Drawings | Posts are to be checked for verticality and ensure spacings do not exceed standards. | Measure | Each lot | IP | SE/Site Supervisor | This ITP
5.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | IP | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /