## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-271-CIV-FER-Permanent Farm Fencing | itp |  |  |  |  | ITP-271-CIV-FER-Permanent Farm Fencing Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-271- CIV-Permanent Farm Fencing
label | ITP Description: Permanent Farm Fencing
label | Discipline (e.g. CIV/STR/RAIL): 271- CIV
label | Revision Number: 0
label | Revision Date: 9/05/2025
label | ITP created by: Kamel Alshobaki
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - IFC Drawings
label | 1.2 - Non Dependent
label | Reference - VicRoads Drawing No. SD3151
label | ○ VicRoads Drawing No. SD3111
label | ○ VicRoads Drawing No. SD3161
section | 2. Materials
checkpoint | 2.1 - Timber
label | Reference - IFC Drawings SD3111
label | Acceptance Criteria - Untreated Timber and Treated Timber according to Vicroads SD3111.
label | Method - Document Review
label | Frequency - All elements
label | Category - IP
label | Responsibility - SE/Site Supervisor
date | Date Completed:
checkpoint | 2.2 - Concrete
label | Reference - IFC Drawings AS 1379 & SD3111 & SD3161
label | Acceptance Criteria - Shall be 20 MPa concrete to be used as per IFC drawings & Vicroads SD3111 & SD3161 and AS1379.
label | Method - Document Review
label | Frequency - Each Mix
label | Category - IP
label | Responsibility - SE/Site Supervisor
date | Date Completed:
checkpoint | 2.3 - Steel components including wires and posts.
label | Reference - IFC Drawings SD3111
label | Acceptance Criteria - All Steel must comply with Australian Standards.
label | ○ Steel section sizes must be checked on site.
label | ○ Star Pickets according to Vicroads SD3111.
label | Method - Document review, Visual and Measure
label | Frequency - All elements
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Supplier Certificate of Compliance
date | Date Completed:
section | 3. Pre-construction / Pre-installation Activities
checkpoint | 3.1 - Survey Set-out
label | Reference - IFC Drawings
label | Acceptance Criteria - Survey to set out the following but not limited to: existing services, footing points and fence start and end points.
label | ○ Offset checked against the running edge prior to installation of posts.
label | Method - Visual and Measure
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP
date | Date Completed:
section | 4.
checkpoint | 4.1 - Excavation works
label | Reference - IFC Drawings
label | Acceptance Criteria - Excavation completed by auger outside of service working limits.
label | ○ Follow asset owners guidelines for work around their service.
label | Method - Visual
label | Frequency - Each fence footing
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Ground Conditions
label | Reference - IFC Drawings
label | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | Method - Visual
label | Frequency - Each post
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.3 - Fence Installation
label | Reference - IFC Drawings AS 1379, SD3111
label | Acceptance Criteria - Timber posts shall be set in dug or drilled holes.
label | ○ Posts shall be set solidly on star picket and any space left around the posts shall be backfilled and the backfilling compacted.
label | ○ Concrete Shall be 20MPA strength grade complying with the requirements of AS 1379/1991.
label | Method - Measure
label | Frequency - Each post
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP, Concrete Dockets
date | Date Completed:
checkpoint | 4.3 - Timber Post Intallation
label | Reference - IFC Drawings AS 1379, SD3111
label | Acceptance Criteria - Timber intermediate post to be used at not more than 40m intervals and at a minimum length of 1800mm long.
label | ○ Timbers 2 x 1175 Long to be spaced evenly in pannel and clipped or tied to wires as sepcificed.
label | Method - Measure
label | Frequency - Each post
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.4 - Strainer Assemblies and wire installation
label | Reference - SD3111
label | Acceptance Criteria - High tensile wires to be either reeved through holes bored in posts or stapled to post.
label | — Wires to be placed at 150mm from each other for the first 3 wires from the ground level and increase to 175mm, 200mm and 250mm for the top 3 wires.
label | — First wire should be at minimum 25mm or maximum 150mm from the ground level.
label | — Maximum height for the top wire should 1150mm from the ground level.
label | — Optional, galvanised hight tensile barbed wire can be used for wire number 3.
label | — Total of 7 wires must be installed for the fence.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Post-construction / Post-installation Activities
checkpoint | 5.1 - As-Built Survey
label | Reference - IFC Drawings
label | Acceptance Criteria - Posts are to be checked for verticality and ensure spacings do not exceed standards.
label | Method - Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP