## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Overall Progress
| Scope |  |  | Site QA
Rows
|  | Byford Type D&E Beams | dynamic | Byford Type D&E Beams | Site QA
Columns
|  | Stage 1 - Cast Number | Cast Number | Pre-Pour Checklist completed | Pre-Pour Checklist - Stage 1
|  | Stage 1 - Beam Number | Beam Number | Pre-Pour Checklist completed | Pre-Pour Checklist - Stage 1
|  | Stage 1 - Strand Arrangement Type | Strand Arrangement Type | Pre-Pour Checklist completed | Pre-Pour Checklist - Stage 1
|  | Stage 1 - Cast Date | Cast Date | Casting Information | Casting Checklist - Stage 1
|  | Stage 1 - Concrete Delivery Dockets | Concrete Delivery Dockets (list all) | Concrete Delivery Dockets | Casting Checklist - Stage 1
|  | Stage 1 - Slump (list all) | Slump (list all) | Slump within Allowable Tolerance (200+/-40) (Tested every truck) | Casting Checklist - Stage 1
|  | Stage 2 - Cast Number | Cast Number | Pre-Pour Checklist completed | Pre-Pour Checklist - Stage 2
|  | Stage 2 - Beam Number | Beam Number | Pre-Pour Checklist completed | Pre-Pour Checklist - Stage 2
|  | Stage 2 - Strand Arrangement Type | Strand Arrangement Type | Pre-Pour Checklist completed | Pre-Pour Checklist - Stage 2
|  | Stage 2 - Cast Date | Cast Date | Casting Information | Casting Checklist - Stage 2
|  | Stage 2 - Concrete Delivery Dockets | Concrete Delivery Dockets (list all) | Concrete Delivery Dockets | Casting Checklist - Stage 2
|  | Stage 2 - Slump (list all) | Slump (list all) | Slump within Allowable Tolerance (200+/-40) (Tested every truck) | Casting Checklist - Stage 2
|  | Concrete Test Report | Concrete Test Report | Concrete Strength Test Report Received | Concrete Strength Test Report
|  | Stripping Strength | Stripping Strength | Concrete Cylinders Crushed and Checked for stripping strength | Stripping Checklist
|  | Stage 1 - 7 Day Strength (List all) | 7 Day Strength (List all) | Concrete Strength Test Report Received | Pre-Pour Checklist - Stage 1
|  | Stage 1 - 28 Day Strength (List all) | 28 Day Strength (List all) | Concrete Strength Test Report Received | Pre-Pour Checklist - Stage 1
|  | Stage 2 - 7 Day Strength (List all) | 7 Day Strength (List all) | Concrete Strength Test Report Received | Pre-Pour Checklist - Stage 2
|  | Stage 2 - 28 Day Strength (List all) | 28 Day Strength (List all) | Concrete Strength Test Report Received | Pre-Pour Checklist - Stage 2