## QA Folder Structure
QA Folder Structure |  |  | Checklists
Site QA
East Elevation
| Shop Drawing - SKP-NCC- | O02 | ONSITE - Installation of Facade System
|  | O05 | ONSITE - Installation of Facade System
|  | S17 | ONSITE - Installation of Facade System
|  | S18 | ONSITE - Installation of Facade System
|  | S30 | ONSITE - Installation of Facade System
|  | G29 | ONSITE - Installation of Facade System
|  | G25 | ONSITE - Installation of Facade System
|  | G32 | ONSITE - Installation of Facade System
|  | G35 | ONSITE - Installation of Facade System
|  | G42 | ONSITE - Installation of Facade System
West Elevation
| Shop Drawing - SKP-NCC- | S02 | ONSITE - Installation of Facade System
|  | G02 | ONSITE - Installation of Facade System
|  | S07 | ONSITE - Installation of Facade System
|  | G01 | ONSITE - Installation of Facade System
|  | G10 | ONSITE - Installation of Facade System
|  | G16 | ONSITE - Installation of Facade System
|  | G20 | ONSITE - Installation of Facade System
South Elevation
| Shop Drawing - SKP-NCC- | S11 | ONSITE - Installation of Facade System
|  | S15 | ONSITE - Installation of Facade System
|  | S16 | ONSITE - Installation of Facade System

## ITPs Checklists
type | name | values
checklist | ONSITE - Installation of Facade System
section | Pre-constructions and Removal of existing EPS.
checkpoint | Existing condition of surrounding surfaces and finish is documented and photo evidence is obtained and emailed through to Skypanel Management
label | Insert photos of the existing condition of the surrounding surfaces.
Label | Insert Comment
checkpoint | Removal of sealant, flashings or fixings in a safe manner, place into bin for disposal and tidy work area.
checkpoint | Removal of EPS panels in a safe manner from facade, move to lay down area and secure ensuring work area kept tidy
checkpoint | Removed composite panels stacked neatly is recycling skips ready for removal from site.
Hold Point | Hold Point - Inspection and Approval by certifying engineer that structure is adequate for new cladding installation. Provide min 48H notice of inspection. | Sign off required by Manu Weerasinghe, Jabin Consulting Engineers. E: Manu.Weerasinghe@jabinpm.com.au
section | Assessment of Structure and structural support framing Installation
checkpoint | Visually check existing structure for condition. Identify any visible cracked welds, missing fixtures and connections and take photo graphic evidence
Label | Insert Comment
checkpoint | Identify existing structure. Capture images with tape measure showing type, size, spans, centers and connections at selected locations. Confim dimensions and gauge of all existing bracketry
Label | Comment
Checkpoint | Complete Pullout testing of existing chemical/ mechanical anchors into the concrete as per the shop drawing notes. Submit pullout test results to certifying engineer
Label | Insert Comment
Hold Point | Hold Point - Approval by certifying engineer that the existing chemical/mechanical anchors are suitable for re-use and/or new anchors are to be installed. | Sign off required by Manu Weerasinghe, Jabin Consulting Engineers. E: Manu.Weerasinghe@jabinpm.com.au
label | Insert Photos of exisitng structure showing member sizing, spans, centers & connections at selected locations and general structure at location.
checkpoint | Refer to design documents to ensure correct spans as per design for the project. Check existing bracketry is fit for reuse. Refer Askin Wall Connections Document
checkpoint | New bracketry to be installed if existing is insufficient or non-existent.
Label | Insert Comment
checkpoint | Check fixings types into structure: Fixings to be as per design drawings.
Checkpoint | Verify no existing cast in electrical, plumbing or other services are within the slab in new post fix anchor locations.
Label | Insert Comment
label | Insert Photos showing completed fixings at selected locations, if concrete scanning has been done add photos of the scanned area.
checkpoint | Prior to commencement of cladding installation: Ensure other services are complete: Ensure all framing requirements are met
label | Insert Photos showing completed structural support components, showing spans, sizes, fixings at selected locations
Label | Insert Comment
Hold Point | Hold Point - Approval by certifying engineer that existing bracketry is adequate for new cladding installation. | `
section | Installation of 150mm Volcore Cladding Panels
checkpoint | Ensure cladding material and colour is correct by referencing shop drawings - Check Internal & External skin colour.
checkpoint | Ensure existing channels are fixed as per the design and are fit to take the new cladding panels
label | Insert Photos of channels with the correct fixing at the correct centres.
Label | Insert Comment
checkpoint | Ensure all trims & flashing are installed as per the shop drawings.
label | Insert Photos
Label | Insert Comment
checkpoint | Ensure rivet fixing centres and rivet size is as per the shop drawings.
checkpoint | Ensure panels are defect free with no scratches and dents
label | Insert Photos
Label | Insert Comment
checkpoint | Ensure all panels are installed in the same direction, male to female or female to male depending on direction of install.
checkpoint | Ensure panel joint consistancy is maintianed
checkpoint | Ensure panels are installed plumb, square and true, and within Skypanel tolerances
checkpoint | Ensure panels are installed in correct position.
label | Insert Photos of installed panel, panel widths, junctions, fixing centers at selected locations
Label | Insert Comment
Hold Point | Hold Point - Inspection and Approval by certifying engineer that new Volcore cladding has been installed as per design documents. Provide min 48H notice of inspection. | Sign off required by Manu Weerasinghe, Jabin Consulting Engineers. E: Manu.Weerasinghe@jabinpm.com.au
section | Sealing of panels
checkpoint | Ensure the correct amount of sealant is applied to joins as per manufacturers specifications
checkpoint | Ensure the correct sealant type is used - PU As per Askin recommendations.
checkpoint | Ensure all penetrations are caulked
checkpoint | Ensure plastic film is removed and caulking residues are properly cleaned from cladding surface
label | Insert photos of sealed panels at selected locations
checklist-flat | Drawing Upload & Access
checkpoint | Ensure safest access method is selected and utilised, ensuring scaffold is signed off as complete and EWP/plant daily pre starts are undertaken and documented
checkpoint | Check dimensions nominated on shop drawings match the dimensions onsite with regard to existing cladding to be removed and replaced