## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
4bcfda3f-8248-4f66-b9cd-18db13e48f4c | checklist | Drawing Upload & Access |  | Drawing Upload & Access
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4d3476a2-d77f-47fe-816e-c786547c2c0b | checkpoint | Ensure safest access method is selected and utilised, ensuring scaffold is signed off as complete and EWP/plant daily pre starts are undertaken and documented
52e92e70-27e3-4093-8952-762959930881 | checkpoint | Check dimensions nominated on shop drawings match the dimensions onsite with regard to existing cladding to be removed and replaced
78db74f6-987c-44e5-b08e-fdcacbef6596 | checklist | ONSITE - Installation of Facade System |  | ONSITE - Installation of Facade System
8dd89738-a130-4e3c-b1c6-27041ea2af5b | section | Pre-constructions and Removal of existing EPS.
e25c3782-9a2d-4eed-93ec-dd2d95e7895b | checkpoint | Existing condition of surrounding surfaces and finish is documented and photo evidence is obtained and emailed through to Skypanel Management
ad5bfd5c-3ff6-5b57-a4a5-7a0ae6dc5405 | note | Insert photos of the existing condition of the surrounding surfaces.
add38756-f872-5daa-ab54-f79cc9b88b36 | textbox | Comment
d64879d8-889b-4a35-86ce-940feff780b3 | checkpoint | Removal of sealant, flashings or fixings in a safe manner, place into bin for disposal and tidy work area.
c826f09d-c22f-47ef-bbbd-7eae9de9178b | checkpoint | Removal of EPS panels in a safe manner from facade, move to lay down area and secure ensuring work area kept tidy
1d5620d1-0265-4966-9810-d30d82ad0ff1 | checkpoint | Removed composite panels stacked neatly is recycling skips ready for removal from site.
d4099070-2776-5948-a4ea-63a5f07979ec | note | Sign off required by Manu Weerasinghe, Jabin Consulting Engineers. E: Manu.Weerasinghe@jabinpm.com.au
a4d71d37-3aba-423b-8457-c7a0226d16bc | signoff | Hold Point - Inspection and Approval by certifying engineer that structure is adequate for new cladding installation. Provide min 48H notice of inspection.
546bcfec-f4e7-4f55-bd0c-565130d75dfb | section | Assessment of Structure and structural support framing Installation
e7a97d39-4340-4a39-9990-6f9fedb6234b | checkpoint | Visually check existing structure for condition. Identify any visible cracked welds, missing fixtures and connections and take photo graphic evidence
db6b6bfb-540c-547d-915a-5402ed25511b | textbox | Comment
a94a60e4-89b7-4af0-9170-213ebb8a8d78 | checkpoint | Identify existing structure. Capture images with tape measure showing type, size, spans, centers and connections at selected locations. Confim dimensions and gauge of all existing bracketry
40f4daf5-ceba-5b99-a12c-a3afa62ffcbe | textbox | Comment
80e57fcd-7698-4d1b-893d-dde91d64e8a5 | checkpoint | Complete Pullout testing of existing chemical/ mechanical anchors into the concrete as per the shop drawing notes. Submit pullout test results to certifying engineer
6900983f-4c2e-5839-9b8a-795622ff3b3c | textbox | Comment
89bbfee5-7062-538f-864f-afed4475a45f | note | Sign off required by Manu Weerasinghe, Jabin Consulting Engineers. E: Manu.Weerasinghe@jabinpm.com.au
13e2597a-c934-54db-9967-5475f627edff | note | Insert Photos of exisitng structure showing member sizing, spans, centers & connections at selected locations and general structure at location.
9f26089e-ba01-4f8e-bc7b-172702453963 | signoff | Hold Point - Approval by certifying engineer that the existing chemical/mechanical anchors are suitable for re-use and/or new anchors are to be installed.
0723ee4b-cb57-4fdb-9034-3d8d63da61e6 | checkpoint | Refer to design documents to ensure correct spans as per design for the project. Check existing bracketry is fit for reuse. Refer Askin Wall Connections Document
f0654298-d7a3-4d90-abc1-2eb97a70e9da | checkpoint | New bracketry to be installed if existing is insufficient or non-existent.
d7966cde-431b-5a2f-8c53-9094eb4cf5ca | textbox | Comment
81eceb6a-5dce-4957-88f5-5186f64fc878 | checkpoint | Check fixings types into structure: Fixings to be as per design drawings.
37c6d9a4-e4af-476e-9cfa-71bf9592da91 | checkpoint | Verify no existing cast in electrical, plumbing or other services are within the slab in new post fix anchor locations.
6b3c05f3-82d0-50bc-a0d9-3bd0c3f0c865 | textbox | Comment
29786681-bcf3-515e-b27a-c1e8e944123d | note | Insert Photos showing completed fixings at selected locations
8e857ff4-d0f2-42f8-a029-f7359cf183d5 | checkpoint | Prior to commencement of cladding installation: Ensure other services are complete: Ensure all framing requirements are met
dbdc8671-226d-5670-81c2-55b96119a8b6 | note | Insert Photos showing completed structural support components, showing spans, sizes, fixings at selected locations
ff99afe3-1c33-5b4e-92d5-231072e329bc | textbox | Comment
ab713c17-dbf9-4572-93de-d4c5962263e7 | signoff | Hold Point - Approval by certifying engineer that existing bracketry is adequate for new cladding installation.
d0351a01-6608-4394-aac7-9f198f0e5e97 | section | Installation of 150mm Volcore Cladding Panels
101cf4ce-c349-4b41-962e-4c28ff701a26 | checkpoint | Ensure cladding material and colour is correct by referencing shop drawings - Check Internal & External skin colour.
fbd789ce-536c-4cb0-be9f-0b2689f9f3ca | checkpoint | Ensure existing channels are fixed as per the design and are fit to take the new cladding panels
5ef3496b-2f60-510c-bc8d-160879c1de07 | note | Insert Photos of channels with the correct fixing at the correct centres.
9b1d3049-baf9-55ac-86a4-4e1a6d13937c | textbox | Comment
51055f68-02cb-49f4-8663-3f7cdd03b91f | checkpoint | Ensure all trims & flashing are installed as per the shop drawings.
bee74cb6-0d99-5ad0-9999-c4549319699f | note | Insert Photos
780a9df9-0458-5770-9e83-7b31102002e4 | textbox | Comment
73aaba6c-d80e-482b-83f9-bebff174bf95 | checkpoint | Ensure rivet fixing centres and rivet size is as per the shop drawings.
424567b4-b93a-4085-ad86-e4eccdafd7bb | checkpoint | Ensure panels are defect free with no scratches and dents
5a55299e-6c81-5986-a86b-73fad37caf84 | note | Insert Photos
19a9b3c7-e8a4-53fd-959d-40d598455b10 | textbox | Comment
c7adc259-10ac-46f6-8d6c-2a52eaf67237 | checkpoint | Ensure all panels are installed in the same direction, male to female or female to male depending on direction of install.
c2441a6c-4568-481d-8337-6ebf4b671d0c | checkpoint | Ensure panel joint consistancy is maintianed
f2692c9d-45b4-444c-9cc7-94a619bdcded | checkpoint | Ensure panels are installed plumb, square and true, and within Skypanel tolerances
a33ac6c6-f210-4609-9992-f78fd9691979 | checkpoint | Ensure panels are installed in correct position.
538f0723-8d48-5fff-a8b8-a3b5e469a768 | note | Insert Photos of installed panel, panel widths, junctions, fixing centers at selected locations
d7a0873b-6686-5d77-bdda-dda3f1e154a8 | textbox | Comment
aace4c33-378f-5582-9c84-c2ea7f9273a0 | note | Sign off required by Manu Weerasinghe, Jabin Consulting Engineers. E: Manu.Weerasinghe@jabinpm.com.au
487a769f-9a2d-4d03-8061-d5223b9042e0 | signoff | Hold Point - Inspection and Approval by certifying engineer that new Volcore cladding has been installed as per design documents. Provide min 48H notice of inspection.
71498683-6d8b-4ecc-8efb-0a76c1aea624 | section | Sealing of panels
6b336c69-c89a-4aa3-b409-21a6140b36c7 | checkpoint | Ensure the correct amount of sealant is applied to joins as per manufacturers specifications
d0b75a81-98db-4e0d-9aa6-cb19154565a1 | checkpoint | Ensure the correct sealant type is used - clear
233eafe9-ced3-4dae-a44e-be5436fa173c | checkpoint | Ensure all penetrations are caulked
f91b4ddc-8480-4d81-b9c6-4c381129c3cf | checkpoint | Ensure plastic film is removed and caulking residues are properly cleaned from cladding surface
e212cc5b-3454-535d-ac04-84a84ebea160 | note | Insert photos of sealed panels at selected locations