## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Overall Progress
Scope
Rows
|  | Site QA | grouping | Site QA
|  | L28 |  | L28
|  | L29 |  | L29
Columns
|  | Is the area clean, & cleared, ready for necessary prep |  | Is the area clean, and cleared, ready for necessary preparation
|  | Are flanges installed at correct depth in accordance with spec. wastes |  | Are flanges installed at correct depth in accordance with specified wastes
|  | Has screeding been completed to shower at correct height & falls with correct product |  | Has screeding been completed to shower at correct height and falls with correct product
|  | All falls to shower base, or outside shower are correct & signed off by TAL Tiling manager |  | All falls to shower base, or outside shower are correct and signed off by TAL Tiling manager
|  | Grinding, if req., completed before/after works |  | Grinding, if required, completed before works (photo required) after works (photo required)
|  | Floor levelling completed & applied as per reqs. (m2 rate) |  | Floor levelling completed and applied as per requirements. (m2 rate)
|  | Floor levelling completed - hours & bags used to be recorded (if per bag/labour rate) |  | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)
|  | Substrate to receive waterproofing has slimline installed to any corners & has been gib stopped |  | Substrate to receive waterproofing has slimline installed to any corners and has been gib stopped
|  | Gaskets have been installed to floor flange & wall plumbing fittings |  | Gaskets have been installed to floor flange and wall plumbing fittings
|  | Correct waterproofing is supplied as per project spec. |  | Correct waterproofing is supplied as per project specification.
|  | Waterproofing coat # 1 applied to floors, upstand & walls |  | Waterproofing coat # 1 applied to floors, upstand and walls (take photos)
|  | Waterproofing coat # 2 applied 90 degrees to 1st coat |  | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
|  | Flood tests, if req., undertaken & photos provided. |  | Flood tests, if required, undertaken and photos provided.
|  | Tiles set out according to latest drawing - always check revisions on site |  | Tiles set out according to latest drawing - always check revisions on site
|  | spec. product used with notched trowel or req. product |  | Specified product used with notched trowel or required product
|  | Correct spacer size used for spacing as per specs & tile lipping within BRANZ tolerances |  | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
|  | Floor/Wall substrate straight, signed off by MC & ready for install |  | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
|  | Install tiles to floors as per drawings to amenity floors |  | Install tiles to floors as per drawings to amenity floors
|  | Install tiles to floors as per drawings to floors near staff lounge |  | Install tiles to floors as per drawings to floors near staff lounge
|  | Install skirting tiles to amenity perimeter |  | Install skirting tiles to amenity perimeter
|  | Wall tiles set out to match floor grout lines or as per drawings |  | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
|  | Install tiles to walls as per elevations |  | Install tiles to walls as per elevations
|  | Install tiles to walls to wellness room |  | Install tiles to walls to wellness room
|  | Grout nominated is the correct colour & applied evenly & correctly |  | Grout nominated is the correct colour and applied evenly and correctly
|  | Grout is consistent throughout & no missing grout. |  | Grout is consistent throughout and no missing grout.
|  | Tiling completed, checked & Supervisor signoff |  | Tiling completed, checked and Supervisor sign off
|  | Silicone is completed to all tile junctions where req. |  | Silicone is completed to all tile junctions where required
|  | Sealer to all stone on L28 & L29 |  | Sealer to all stone on L28 and L29
|  | Area left clean & tidy |  | Area left clean & tidy
|  | Builders clean completed |  | Builders clean completed
|  | Install tiles to floors as per drawings to floors in kitchenette |  | Install tiles to floors as per drawings to floors in kitchenette
|  | Install skirting tiles to amenity perimeter |  | Install skirting tiles to amenity perimeter
|  | Install tiles to walls as per drawings |  | Install tiles to walls as per drawings
|  | Change of details & or instructions |  | Change of details and or instructions
|  | Site specific details to be added |  | Site specific details to be added
|  | Material Details - Notes to be added of materials used on site |  | Material Details - Notes to be added of materials used on site
|  | No items are left on fail. If so, provide reasons why before invoiced out |  | No items are left on fail. If so, provide reasons why before invoiced out.