## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-004 - Fill with Class 3 Material + EPS | itp | ITP-004 - Fill with Class 3 Material + EPS |  | 0917e50f-c88b-4f55-8a99-dc6a2289e5af
| section | 1.0 - Preliminary Works
| checkpoint | 1.1 - Induction
f24102b6-5553-5302-af2f-fc20c60a8d7e | note | FREQUENCY: Prior to Commencing
f5ab3b24-c2d9-5a95-ae02-51911c648ea2 | note | ACCEPTANCE CRITERIA: All personnel on site have completed the site specific induction
30c32350-a912-53da-a66f-568ea59cabd2 | note | REFERENCE DOCUMENTS: Inductions Register
e0353ed1-2069-5209-a67c-cb8558746d31 | note | INSPECTION/TEST METHOD: Document review
11599c9e-5d7a-5098-8513-ea3dcd7402fe | note | RECORD OF CONFORMITY: Site induction signed.
bac32292-5c0f-5987-b966-130ef0775c87 | note | AP
b8017442-d7f1-51a0-b1a1-1005376db78c | note | RESPONSIBILITY: Site Engineer / Site Foreman
2098a553-1fae-5c9b-a016-b3e7f548e02d | date | Date Completed:
| checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
e6f10fc7-8dd5-5c44-9dac-b2a98cf86dde | note | FREQUENCY: Prior to commencing
6ef7abcd-4c5b-57b6-bab4-700c0c6f1872 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
2197cbf1-b462-5142-b702-fed603bce064 | note | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
0f0bc5a1-6f47-5d21-be03-27d0cc268d8d | note | INSPECTION/TEST METHOD: Document Review
0a69fd7b-1852-54b6-aec3-4341afcad725 | note | RECORD OF CONFORMITY: SWMS(s) signed
35311ae8-f88c-5403-b889-8d0fa595f0bc | note | HP
89c023bf-1ec1-57cc-bd84-6f951580e9b7 | note | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
6d0d2af1-f758-52e4-bc91-4af632b0ad3f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Check that current revision drawings are being used
33543cf7-12f9-5a0c-b613-c812518ab00c | note | FREQUENCY: Prior to Commencing
e10ce98b-9009-55d5-909b-f95aca456083 | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
ebdb694e-5bdb-542e-9591-a0cb4347a18c | note | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
9a81c92e-f2a3-5fa3-9c97-2f639851060d | note | INSPECTION/TEST METHOD: Document review
cbc351e7-58d6-5664-9279-a94f4ae04ba6 | note | RECORD OF CONFORMITY: Latest Revision Drawings
e7e51ee6-e020-511f-82c7-2534929be831 | note | AP
19b143ef-42dc-5b9d-b16f-ca80a7251247 | note | RESPONSIBILITY: Site Engineer / Site Foreman
db7d56b2-640a-53de-abaa-418926e31428 | date | Date Completed:
| checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
9696ef3c-9dc0-5fe4-9e88-cbccec1d9940 | note | FREQUENCY: Prior to Commencing
092bba92-75ec-5db1-bd81-37993196b4f9 | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
aba1fb4c-b6e6-59db-a5d2-a9f9dde7fb75 | note | REFERENCE DOCUMENTS: IFC Drawings, CEMP, CHMP
fb1b2a43-8cad-5ec3-aeb4-d78aaf263309 | note | INSPECTION/TEST METHOD: Document review & Site inspection
608cf229-959e-5cb3-bbae-3ca98a2e4ebd | note | RECORD OF CONFORMITY: Signed ITP
c5760327-d240-5c38-afb6-55b0b80e891b | note | IP
2c8b6861-4763-5367-9806-2c69303c434c | note | RESPONSIBILITY: Site Engineer
677807f0-51a0-57e7-986e-37fed1aff10f | date | Date Completed:
| checkpoint | 1.5 - Excavation Permit issued
2a1cee37-fdfd-5fb4-9304-a28676bf0f1a | note | FREQUENCY: Prior to Commencing
d35a3e45-a906-5c5c-9397-cc55e6abab2f | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
77057dbc-a096-506c-9896-7e00820dcd97 | note | REFERENCE DOCUMENTS: Excavation Permit
06837f39-a0d4-506a-858d-24ca8312d449 | note | INSPECTION/TEST METHOD: Document review
75133f24-6166-5019-85e5-a65c920db740 | note | RECORD OF CONFORMITY: Excavation Permit #
44c7d5a6-d31f-593a-8820-841cf6924a13 | note | IP
1df20615-6c6e-5ee1-878c-05a45429db51 | note | RESPONSIBILITY: Site Engineer
71f026af-fcbf-5271-bea9-284eab0546a8 | date | Date Completed:
| section | 2.0 - Placing Class 3 Material
| checkpoint | 2.1 - Survey set-out
ac41bdd5-f2ca-513c-abdc-b77fa8054e0e | note | FREQUENCY: Prior to Commencing Excavation
62c859e7-7ae9-5693-8d4c-bcbfdadf6d5e | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
da789e19-a446-5cb2-af80-7e5fa2faa086 | note | REFERENCE DOCUMENTS: Latest IFC Drawings
9f16d6cb-7aad-53e9-b68b-3999c685922f | note | INSPECTION/TEST METHOD: Site Inspection
b8c0c3aa-60f3-54ac-ae52-6e1aea70e5f2 | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
2304ba8e-9f8f-56e2-9ce1-1d363c9a5e82 | note | SCP
5027881c-2ea4-5f77-8032-c2b261971b03 | note | RESPONSIBILITY: Site Engineer & Surveyor
e5975546-fe96-561f-866c-ca4dcf43a325 | date | Date Completed:
| checkpoint | 2.2 - Fill Construction
0480ab6f-7b60-5ebc-9475-30bc78effa3f | note | FREQUENCY: Prior to Commencing Excavation
d9aa51a5-f142-5e72-9d0c-96afb987e76a | note | ACCEPTANCE CRITERIA: No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent
63e4300e-415d-51ef-8236-e15714f3ad8e | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(b)
15b7e2e8-2987-55f1-95cb-61ce6d0ead7a | note | INSPECTION/TEST METHOD: Site Inspection
a1db1614-8c1c-5ab4-85a4-36230d048f50 | note | RECORD OF CONFORMITY: Area reviewed by Superintendent, Signed ITP
2fbc210d-812b-5782-a55a-23690c816a2c | note | HP
fcfe7614-0bcd-540b-989e-053e4e0c2075 | note | RESPONSIBILITY: Site Engineer & Superintendent
77790520-8f94-5981-8c54-31d8db6baa23 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Keyed fill layers
a41eca54-f38a-57b1-ba18-5c64e569898e | note | FREQUENCY: During Excavation
f58d576d-36bb-565a-a52a-a6f9457b4b08 | note | ACCEPTANCE CRITERIA: Placement surface textured to ensure layers keyed into each other.
f286ceeb-eb7c-5991-8456-85b0a337ad03 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(i)
92e92d9f-bb42-57d1-858f-a24f2ab409d2 | note | INSPECTION/TEST METHOD: Site Inspection
27f1f587-2598-50bd-8cc7-5c76d4894320 | note | RECORD OF CONFORMITY: Signed ITP
971978d2-7793-5359-b06a-feeae7ae70d0 | note | IP
13fdd5bb-2215-5751-8d8e-cc8fa2bb2e28 | note | RESPONSIBILITY: Site Engineer
dee2cbfc-2b24-5482-9fa6-677314907cd3 | date | Date Completed:
| checkpoint | 2.4 - Layer thickness
24b5cd3c-1030-572e-9ed8-5a92e80231f2 | note | FREQUENCY: During Excavation
326f9845-ef2f-5fbc-b925-c715ef6388f6 | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
3419363e-52cf-5efa-9088-151bfa77e351 | note | ○ A procedure shall be established to verify that compacted layers do not exceed the specified maximum thickness. Verification records must provide evidence of measurements taken at least every three layers in consistent locations across the filled areas, and must be retained with the lot records.
4025f617-7dd8-5ffa-bff9-896cf9d5ee1b | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(ii)
de8c0015-3ee6-5a79-8fba-ab47f0aa6479 | note | INSPECTION/TEST METHOD: Site Inspection
825fa8ef-96cd-5f62-ab19-122d15e6d9ba | note | RECORD OF CONFORMITY: Signed ITP
b73af66e-a569-50a5-abb6-f51d5f7d3013 | note | IP
5fe6bd64-cf69-5029-bbee-0c5be6fec01c | note | RESPONSIBILITY: Site Engineer
9a619cda-03b3-5eda-a174-32c29ce4419c | date | Date Completed:
| checkpoint | 2.5 - Proof Roll
21bfe41e-07dd-504c-8a42-381d8a0422ae | note | FREQUENCY: Each Fill Layer
870277a6-8653-505a-9456-f6fbcecf385c | note | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed, layers of fill shall be test rolled in accordance with Section 173. Where compaction methods have been deemed acceptable, proof rolling increments can be decreased as required.
e29157df-ae3d-5349-8b58-58712912251b | note | ○ Superintendent to be present during all test rolling.
003ea8f6-90ba-5718-8721-06be9685d6f5 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.12 Cl.173.03
95313e15-97a6-5ca7-9013-f16f065f1243 | note | INSPECTION/TEST METHOD: Site Inspection
5b9322b1-aa9d-5a05-a7aa-5136c5ce14d9 | note | RECORD OF CONFORMITY: Proof Roll Form completed & signed.
cf14fa1d-dc50-5f05-b0d3-896248ff307e | note | WP
d2f01e5f-a8f2-5e80-9623-adb3355387c3 | note | RESPONSIBILITY: Site Engineer & Superintendent
017f6748-ced1-5ad6-8082-9fcab24ea70c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Preparation of final surface
66ac16ee-5727-51c7-bf0d-424017120469 | note | FREQUENCY: Prior to construction of subgrade layer
8d7007c3-f966-5836-bcd7-b3290deda550 | note | ACCEPTANCE CRITERIA: The top of the Class 3 material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
29222bb9-b154-57ec-b583-c808629dc619 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.15, Cl. 204.03(g)
2e347d98-bcb2-55cf-8c5f-1453e4d64715 | note | INSPECTION/TEST METHOD: Site Inspection
6217f605-3e07-5a9e-8978-abef06a9a284 | note | RECORD OF CONFORMITY: Signed ITP
28d82f93-722b-52a0-bd33-9fc565bce401 | note | IP
8bad980e-7636-5d14-a15d-c8e2bef61478 | note | RESPONSIBILITY: Site Engineer
d9d530e5-a08d-5891-a0a2-d59c5b723082 | date | Date Completed:
| checkpoint | 2.7 - Conformity with Drawings
7be46b1d-51fa-5258-becf-924a75b5de63 | note | FREQUENCY: Prior to construction of subgrade layer
e5d87f77-33bb-5f77-96ce-67c9e27d7126 | note | ACCEPTANCE CRITERIA: Surface is smooth, hard, tightly bound and free from depressions which are capable of holding water. Surface is not to be more than 15mm or less than 30mm from what is specificed in IFC drawings
7b249351-847a-56b7-91b2-784798e3ba39 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.03(f)
0597628b-33cd-5b18-8661-dff575e0d457 | note | INSPECTION/TEST METHOD: Site Inspection
9a9203bf-7801-5cd4-97cd-6204e32f4b88 | note | RECORD OF CONFORMITY: Signed ITP
c67bd48c-1cdd-5fff-8170-bad1478d1c83 | note | IP
38a4ad46-1989-50a4-91db-3e3ac835fdc9 | note | RESPONSIBILITY: Site Engineer
7dce74bb-3905-5c94-ae52-50eae7f9a9a1 | date | Date Completed:
| section | 3.0 - Testing
| checkpoint | 3.1 - Compaction Testing
dfa1b55a-29b9-54b8-a817-3effea8d756e | note | FREQUENCY: 3 x tests every layer
04a867b0-65e1-514d-90f9-edd2486a3d1d | note | ACCEPTANCE CRITERIA: Compaction testing to ensure 100% Standard Compaction Density Ratio
17015359-1e7a-5981-a966-b171b0c26777 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.13(a), Cl.204.13(b), Table 204.131, Table 204.142
f397f759-0b59-517a-8ca1-082d4d7ce99a | note | INSPECTION/TEST METHOD: Site Inspection
dd1439f5-baec-5720-a9a7-5c9c9c56b5c4 | note | RECORD OF CONFORMITY: Compaction Test Records
edeb6981-b5af-5f93-8838-a3e09215420d | note | TP
08322d0f-7ef0-5cd8-a18c-8c34915dfbd9 | note | RESPONSIBILITY: Site Engineer
fb6b35a2-d0f8-5059-b667-0346e6790948 | date | Date Completed:
| section | 4.0 - Placing of EPS Blocks
| checkpoint | 4.1 - Procurement and Storage
| note | FREQUENCY: All blocks
| note | ACCEPTANCE CRITERIA: All blocks are H Grade and stored appropriately with pegs / webbing / tie downs to ensure they are stored securely
| note | REFERENCE DOCUMENTS: Manufactuers Specification
| note | INSPECTION/TEST METHOD: Site Inspection
| note | RECORD OF CONFORMITY: This ITP Signed Off
| note | IP
| note | RESPONSIBILITY: Site Engineer
| date | Date Completed:
| checkpoint | 4.2 - Foundation for EPS Placement
| note | FREQUENCY: Prior to placing EPS
| note | ACCEPTANCE CRITERIA: Prior to placement of EPS blocks, 20mm Class 3 layer must be levelled to ensure blocks are able to sit flush without noticeable iregularities
| note | REFERENCE DOCUMENTS: Drawings, Manufacturers Specification
| note | INSPECTION/TEST METHOD: Site Inspection
| note | RECORD OF CONFORMITY: This ITP Signed Off
| note | IP
| note | RESPONSIBILITY: Site Engineer
| date | Date Completed:
| checkpoint | 4.3 - Installation of Blocks
| note | FREQUENCY: All blocks
| note | ACCEPTANCE CRITERIA: EPS Blocks are installed as per manufacturers specification, ensuring an adequate overlap and orientation when layering blocks.
| note | ○ Ensure 7mm aggregate is placed in accordance with PSM recommendations underneath ground anchors
| note | ○ Coredrain is installed correctly on back face of wall in accordance with Drawings
| note | REFERENCE DOCUMENTS: Manufactuers Specification, PSM5331-030M EPS, Fill Drawings
| note | INSPECTION/TEST METHOD: Site Inspection
| note | RECORD OF CONFORMITY: This ITP Signed Off
| note | IP
| note | RESPONSIBILITY: Site Engineer
| date | Date Completed:
| checkpoint | Final Inspection
b5cc8ac9-7b77-53e3-9e92-8f3b41e7b221 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
99f8623f-9fd9-5d37-a259-019376e127e8 | textbox | Print Name:
0de97a92-e1de-5d9a-92cf-9ff3b52cce8d | textbox | Position:
f5a10656-a90a-506d-97b3-e6f5b8651b68 | date | Date: