## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
DTM-ITP-001- Clearing and Grubbing
| Scope |  |  | Clearing and Grubbing
Rows
|  | Clearing and Grubbing | dynamic | Clearing and Grubbing
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - check for correct documentation | 1 - preliminary works
|  | 1.2 - Limits of work |  | 1.2 - limits of work | 1 - preliminary works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - implementation of all measures and controls | 1 - preliminary works
|  | 1.3 - Implementation of environmental measures and controls |  | 1.3 - implementation of environmental measures and controls | 1 - preliminary works
|  | 1.4 - Flora and Fauna |  | 1.4 - flora and fauna | 1 - preliminary works
|  | 1.5 - Protection of Existing Vegetation |  | 1.5 - protection of existing vegetation | 1 - preliminary works
|  | 1.6 - Cultrual Heritage |  | 1.6 - cultrual heritage | 1 - preliminary works
|  | 1.7 - Authorisation for works |  | 1.7 - authorisation for works | 1 - preliminary works
|  | 1.8 - Utilities |  | 1.8 - utilities | 1 - preliminary works
|  | 1.9 - Traffic Management |  | 1 - preliminary works | 1.9 - traffic management
|  | 2.1 - Clear and grub trees and vegetation |  | 2.1 - clear and grub trees and vegetation | 2 - clear & grub
|  | 2.3 - Clear and grub trees and vegetation |  | 2.3 - clear and grub trees and vegetation | 2 - clear & grub
|  | 2.4 - Clear and grub trees and vegetation (embankment areas) |  | 2 - clear & grub | 2.4 - clear and grub trees and vegetation (embankment areas)
|  | 2.5 - Clear and grub trees and vegetation at culvert sites |  | 2.5 - clear and grub trees and vegetation at culvert sites | 2 - clear & grub
|  | 2.6 - Backfill holes |  | 2 - clear & grub | 2.6 - backfill holes
|  | 2.7 - Dispose of Trees and vegetation |  | 2 - clear & grub | 2.7 - dispose of trees and vegetation
|  | 2.8 - Damage to Fencing |  | 2.8 - damage to fencing | 2 - clear & grub
|  | 2.9 - Salvage of Vegetation |  | 2 - clear & grub | 2.9 - salvage of vegetation
|  | ITP completed in accordance with FH’s Quality system Procedures & verifies lot compliance with specs. |  | 2 - clear & grub | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications.
|  | QAV - Print Name: | QAV - Print Name: | 2 - clear & grub | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications.
|  | QAV - Position: | QAV - Position: | 2 - clear & grub | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications.
|  | Fulton Hogan - Print Name: | Fulton Hogan - Print Name: | 2 - clear & grub | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications.
|  | Fulton Hogan - Position: | Fulton Hogan - Position: | 2 - clear & grub | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications.
DTM-ITP-003- Earthworks Demolition
Scope
Rows
|  | Unbound Flexible Pavements - Type A | dynamic | Unbound Flexible Pavements | Type A
|  | Earthworks and Demolition - Subgrade | dynamic | Earthworks and Demolition | Subgrade
Columns
|  | 1.1 Check for correct documentation |  | 1 - preliminary works | 1.1 check for correct documentation
|  | 1.2 Implementation of all measures and controls |  | 1.2 implementation of all measures and controls | 1 - preliminary works
|  | 2.1 Survey Set-Out |  | 2.1 survey set-out | 2 - construction works
|  | 2.2 Excavation Permit |  | 2.2 excavation permit | 2 - construction works
|  | 2.3 Material Categorisation |  | 2.3 material categorisation | 2 - construction works
|  | 2.4 Stripping of Topsoil |  | 2.4 stripping of topsoil | 2 - construction works
|  | 2.5 Type A Material |  | 2.5 type a material | 2 - construction works
|  | 2.5 Type B Material |  | 2.5 type b material | 2 - construction works
|  | 2.6 Acceptance of Rock Subgrade (when applicable) |  | 2 - construction works | 2.6 acceptance of rock subgrade (when applicable)
|  | 2.7 Unsuitable Material |  | 2.7 unsuitable material | 2 - construction works
|  | 2.8 Groundwater |  | 2.8 groundwater | 2 - construction works
|  | 2.9 Trimming and Level conformity |  | 2.9 trimming and level conformity | 2 - construction works
|  | 3.1 Proof Rolling |  | 3 - testing | 3.1 proof rolling
|  | 3.2 Compaction Testing |  | 3 - testing | 3.2 compaction testing
|  | 3.3 Materials Property Testing |  | 3.3 materials property testing | 3 - testing
|  | Final Inspection |  | final inspection | 3 - testing
|  | Final Inspection - Name: | Print Name: | final inspection | 3 - testing
|  | Final Inspection - Position: | Position: | final inspection | 3 - testing
DTM-ITP-004- Service Relocations - Telstra and NBN
| Scope |  |  | Service Relocations - Telstra and NBN
Rows
|  | Service Relocations - Telstra and NBN | dynamic | Service Relocations - Telstra and NBN
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Preliminary Works
|  | 1.3 - Scheduling trenching works with Telstra/NBN contractor |  | 1.3 - Scheduling trenching works with Telstra/NBN contractor | 1 - Preliminary Works
|  | 1.4 - Proving Services |  | 1.4 - Proving Services | 1 - Preliminary Works
|  | 2.1 - Survey set-out |  | 2.1 - Survey set-out | 2 - Construction Works
|  | 2.2 - Excavation |  | 2.2 - Excavation | 2 - Construction Works
|  | 2.3 - Material Assessment |  | 2.3 - Material Assessment | 2 - Construction Works
|  | 2.4 - Bedding |  | 2.4 - Bedding | 2 - Construction Works
|  | 2.5 - Installation of Conduits and Cables |  | 2.5 - Installation of Conduits and Cables | 2 - Construction Works
|  | 2.6 - Back Fill of Trenches |  | 2.6 - Back Fill of Trenches | 2 - Construction Works
|  | 2.7 - Compaction |  | 2.7 - Compaction | 2 - Construction Works
|  | 2.8 - Installation of marker tape |  | 2.8 - Installation of marker tape | 2 - Construction Works
|  | 2.9 - Cable Pits & Pit Lids |  | 2.9 - Cable Pits & Pit Lids | 2 - Construction Works
|  | 3.1 - Cleaning of Site |  | 3.1 - Cleaning of Site | 3 - Completion
|  | 3.2 - Recording/As Built |  | 3.2 - Recording/As Built | 3 - Completion
|  | Final Inspection |  | Final Inspection
|  | Final Inspection - Name: | Print Name: | Final Inspection
|  | Final Inspection - Position: | Position: | Final Inspection
|  | Final Inspection - Work Completed On: | Work Completed On: | Final Inspection
DTM-ITP-005- Service Relocations - Power (TasNetworks)
| Scope |  |  | Service Relocations - TasNetworks
Rows
|  | Service Relocations - TasNetworks | dynamic | Service Relocations - TasNetworks
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Preliminary Works
|  | 1.3 - Scheduling trenching works with TasNetworks |  | 1.3 - Scheduling trenching works with TasNetworks | 1 - Preliminary Works
|  | 1.4 - Proving Services |  | 1.4 - Proving Services | 1 - Preliminary Works
|  | 1.5 - Excavations within 3m of poles or stays, Exacavtions within 1m of Underground Assets |  | 1.5 - Excavations within 3m of poles or stays, Exacavtions within 1m of Underground Assets | 1 - Preliminary Works
|  | 2.1 - Survey set-out |  | 2.1 - Survey set-out | 2 - Construction Works
|  | 2.2 - Excavation |  | 2.2 - Excavation | 2 - Construction Works
|  | 2.3 - Material Assessment |  | 2.3 - Material Assessment | 2 - Construction Works
|  | 2.4 - Bedding |  | 2.4 - Bedding | 2 - Construction Works
|  | 2.5 - Installation of Conduits and Cables |  | 2.5 - Installation of Conduits and Cables | 2 - Construction Works
|  | 2.6 - Back Fill of Trenches |  | 2.6 - Back Fill of Trenches | 2 - Construction Works
|  | 2.7 - Compaction |  | 2.7 - Compaction | 2 - Construction Works
|  | 2.8 - Installation of marker tape |  | 2.8 - Installation of marker tape | 2 - Construction Works
|  | 2.9 - Cable Pits & Pit Lids |  | 2.9 - Cable Pits & Pit Lids | 2 - Construction Works
|  | 3.1 - Cleaning of Site |  | 3.1 - Cleaning of Site | 3 - Completion
|  | 3.2 - Recording/As Built |  | 3.2 - Recording/As Built | 3 - Completion
|  | Final Inspection |  | Final Inspection | 3 - Completion
|  | Final Inspection - Name: | Print Name: | Final Inspection | 3 - Completion
|  | Final Inspection - Position: | Position: | Final Inspection | 3 - Completion
|  | Final Inspection - Work Completed On: | Work Completed On: | Final Inspection | 3 - Completion
DTM-ITP-006- Unbound Flexible Pavement Construction
| Scope |  |  | Unbound Flexible Pavement Construction
Rows
|  | Unbound Flexible Pavement Construction | dynamic | Unbound Flexible Pavement Construction
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1 - Preliminary Works
|  | 1.2 - Material Mix Design |  | 1.2 - Material Mix Design | 1 - Preliminary Works
|  | 1.3 - Material Quality |  | 1.3 - Material Quality | 1 - Preliminary Works
|  | 2.1 - Layer Thickness |  | 2.1 - Layer Thickness | 2 - Placement
|  | 2.2 - Jointing |  | 2.2 - Jointing | 2 - Placement
|  | 2.3 - Test Rolling |  | 2.3 - Test Rolling | 2 - Placement
|  | 3.1 - Determine Testing Scale & Initial testing frequency |  | 3.1 - Determine Testing Scale & Initial testing frequency | 3 - Testing and Conformance
|  | 3.2 - Compaction Testing |  | 3.2 - Compaction Testing | 3 - Testing and Conformance
|  | 3.5 - Completed Surface Level Compliance |  | 3.5 - Completed Surface Level Compliance | 3 - Testing and Conformance
|  | 3.6 - Pavement Dryback and Embedment |  | 3.6 - Pavement Dryback and Embedment | 3 - Testing and Conformance
|  | Final Inspection |  | Final Inspection | 3 - Testing and Conformance
|  | Final Inspection - Name: | Print Name: | Final Inspection | 3 - Testing and Conformance
|  | Final Inspection - Position: | Position: | Final Inspection | 3 - Testing and Conformance
|  | Final Inspection - Work Completed On: | Work Completed On: | Final Inspection | 3 - Testing and Conformance
DTM-ITP-008- Stormwater Drainage
| Scope |  |  | Stormwater Drainage
Rows
|  | Stormwater Drainage | dynamic | Stormwater Drainage
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Preliminary Works
|  | 2.1 - Precast Reinforced Concrete Pipe Supply |  | 2.1 - Precast Reinforced Concrete Pipe Supply | 2 - Procurement of Materials
|  | 2.2 - Precast Reinforced Concrete Pit Supply and Inlet and Outlet Structure |  | 2.2 - Precast Reinforced Concrete Pit Supply and Inlet and Outlet Structure | 2 - Procurement of Materials
|  | 2.3 - Covers, Lintels and Grates |  | 2.3 - Covers, Lintels and Grates | 2 - Procurement of Materials
|  | 2.4 - Provision for Stormwater Connections in Pits |  | 2.4 - Provision for Stormwater Connections in Pits | 2 - Procurement of Materials
|  | 2.5 - Bedding and Backfill Material Specification |  | 2.5 - Bedding and Backfill Material Specification | 2 - Procurement of Materials
|  | 2.6 - Setout of Works |  | 2.6 - Setout of Works | 2 - Procurement of Materials
|  | 3.1 - Excavation for pipe |  | 3.1 - Excavation for pipe | 3 - Installation of Underground Stormwater Drainage
|  | 3.2 - Trench Base Preparation / Bedding |  | 3.2 - Trench Base Preparation / Bedding | 3 - Installation of Underground Stormwater Drainage
|  | 3.3 - Laying of pipes |  | 3.3 - Laying of pipes | 3 - Installation of Underground Stormwater Drainage
|  | 3.4 - Jointing |  | 3.4 - Jointing | 3 - Installation of Underground Stormwater Drainage
|  | 3.5 - Haunching |  | 3.5 - Haunching | 3 - Installation of Underground Stormwater Drainage
|  | 3.6 - Pit Connections |  | 3.6 - Pit Connections | 3 - Installation of Underground Stormwater Drainage
|  | 3.7 - Culverts |  | 3.7 - Culverts | 3 - Installation of Underground Stormwater Drainage
|  | 3.8 - Tolerance |  | 3.8 - Tolerance | 3 - Installation of Underground Stormwater Drainage
|  | 4.1 - Filling |  | 4.1 - Filling | 4 - Backfilling of Stormwater
|  | 4.2 - Testing and Acceptance of Fill Materials |  | 4.2 - Testing and Acceptance of Fill Materials | 4 - Backfilling of Stormwater
|  | 4.3 - Installation of Inlet or Outlet Structure |  | 4.3 - Installation of Inlet or Outlet Structure | 4 - Backfilling of Stormwater
|  | 4.4 - Culvert Coverage |  | 4.4 - Culvert Coverage | 4 - Backfilling of Stormwater
|  | 5.1 - Finishing and Rendering Pipes |  | 5.1 - Finishing and Rendering Pipes | 5 - Finishing and Commissioning
|  | 5.2 - Repair of Damaged Pipes |  | 5.2 - Repair of Damaged Pipes | 5 - Finishing and Commissioning
|  | 5.3 - CCTV |  | 5.3 - CCTV | 5 - Finishing and Commissioning
|  | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. |  | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 5 - Finishing and Commissioning
|  | QAV - Print Name: | QAV - Print Name: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 5 - Finishing and Commissioning
|  | QAV - Position: | QAV - Position: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 5 - Finishing and Commissioning
|  | Fulton Hogan - Print Name: | Fulton Hogan - Print Name: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 5 - Finishing and Commissioning
|  | Fulton Hogan - Position: | Fulton Hogan - Position: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 5 - Finishing and Commissioning
|  | Work Completed On: | Work Completed On: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 5 - Finishing and Commissioning
DTM-ITP-010- Subsurface Drainage
| Scope |  |  | Subsurface Drainage
Rows
|  | Subsurface Drainage | dynamic | Subsurface Drainage
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Preliminary Works
|  | 1.3 - Material Classification |  | 1.3 - Material Classification | 1 - Preliminary Works
|  | 2.1 - Excavation Permit |  | 2.1 - Excavation Permit | 2 - Construction Works
|  | 2.2 - Excavation of Trench |  | 2.2 - Excavation of Trench | 2 - Construction Works
|  | 2.3 - Placement of bedding |  | 2.3 - Placement of bedding | 2 - Construction Works
|  | 2.4 - Placing pipes and geofabric (if required) |  | 2.4 - Placing pipes and geofabric (if required) | 2 - Construction Works
|  | 2.5 - Placement of granular backfill methodology |  | 2.5 - Placement of granular backfill methodology | 2 - Construction Works
|  | 2.6 - Placement of backfill |  | 2.6 - Placement of backfill | 2 - Construction Works
|  | 2.7 - Install Pits and Flushouts |  | 2.7 - Install Pits and Flushouts | 2 - Construction Works
|  | 2.8 - Flushing Test |  | 2.8 - Flushing Test | 2 - Construction Works
|  | 2.9 - CCTV |  | 2.9 - CCTV | 2 - Construction Works
|  | 2.10 - Marker Posts |  | 2.10 - Marker Posts | 2 - Construction Works
|  | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. |  | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 2 - Construction Works
|  | QAV - Print Name: | QAV - Print Name: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
|  | QAV - Position: | QAV - Position: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
|  | Fulton Hogan - Print Name: | Fulton Hogan - Print Name: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
|  | Fulton Hogan - Position: | Fulton Hogan - Position: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
|  | Work Completed On: | Work Completed On: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
DTM-ITP-011- Structural Concrete
| Scope |  |  | Structural Concrete
Rows
|  | Structural Concrete | dynamic | Structural Concrete
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1 - Pre-Construction
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Pre-Construction
|  | 2.1 - Submission of Mix Design |  | 2.1 - Submission of Mix Design | 2 - Prequalification
|  | 2.2 - Reinforcement |  | 2.2 - Reinforcement | 2 - Prequalification
|  | 2.3 - Reinforcement supply and certification |  | 2.3 - Reinforcement supply and certification | 2 - Prequalification
|  | 3.1 - Pre-mixed concrete |  | 3.1 - Pre-mixed concrete | 3 - Testing and Acceptance
|  | 3.2 - Concrete Testing - Sampling Frequency |  | 3.2 - Concrete Testing - Sampling Frequency | 3 - Testing and Acceptance
|  | 3.3 - Concrete Testing - Core Sample Frequency (Post construction) |  | 3.3 - Concrete Testing - Core Sample Frequency (Post construction) | 3 - Testing and Acceptance
|  | 3.4 - Concrete Testing - Slump |  | 3.4 - Concrete Testing - Slump | 3 - Testing and Acceptance
|  | 3.5 - Reinforcement |  | 3.5 - Reinforcement | 3 - Testing and Acceptance
|  | 3.6 - Building Permit |  | 3.6 - Building Permit | 3 - Testing and Acceptance
|  | 4.1 - Pre-pour |  | 4.1 - Pre-pour | 4 - Application
|  | 4.2 - Concrete Pumping |  | 4.2 - Concrete Pumping | 4 - Application
|  | 4.3 - Traceability |  | 4.3 - Traceability | 4 - Application
|  | 4.4 - Finishing |  | 4.4 - Finishing | 4 - Application
|  | 4.5 - Curing |  | 4.5 - Curing | 4 - Application
|  | 4.6 - Joints |  | 4.6 - Joints | 4 - Application
|  | 4.7 - Dimensional Tolerances |  | 4.7 - Dimensional Tolerances | 4 - Application
|  | 5.1 - Final inspection |  | 5.1 - Final inspection | 5 - Finishing Activities
|  | 5.2 - Repair of defective areas |  | 5.2 - Repair of defective areas | 5 - Finishing Activities
|  | 5.3 - As Built Documentation |  | 5.3 - As Built Documentation | 5 - Finishing Activities
|  | 6.1 - Compressive Strength (& VPV Test Results if requested by Superintendent) |  | 6.1 - Compressive Strength (& VPV Test Results if requested by Superintendent) | 6 - Post Construction
|  | 6.2 - Surface Inspection |  | 6.2 - Surface Inspection | 6 - Post Construction
|  | 6.3 - As-built Survey |  | 6.3 - As-built Survey | 6 - Post Construction
|  | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. |  | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 6 - Post Construction
|  | QAV - Print Name: | QAV - Print Name: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 6 - Post Construction
|  | QAV - Position: | QAV - Position: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 6 - Post Construction
|  | Fulton Hogan - Print Name: | Fulton Hogan - Print Name: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 6 - Post Construction
|  | Fulton Hogan - Position: | Fulton Hogan - Position: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 6 - Post Construction
|  | Work Completed On: | Work Completed On: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 6 - Post Construction
DTM-ITP-012- Masonry Block Wall
| Scope |  |  | Masonry Block Wall
Rows
|  | Masonry Block Wall | dynamic | Masonry Block Wall
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1 - Pre-Construction
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Pre-Construction
|  | 2.1 - Reinforcement |  | 2.1 - Reinforcement | 2 - Prequalification
|  | 2.2 - Reinforcement supply and certification |  | 2.2 - Reinforcement supply and certification | 2 - Prequalification
|  | 2.3 - Supply of masonry blocks |  | 2.3 - Supply of masonry blocks | 2 - Prequalification
|  | 3.1 - Pre-mixed concrete |  | 3.1 - Pre-mixed concrete | 3 - Testing and Acceptance
|  | 3.2 - Concrete Testing - Sampling Frequency |  | 3.2 - Concrete Testing - Sampling Frequency | 3 - Testing and Acceptance
|  | 3.3 - Concrete Testing - Core Sample Frequency (Post construction) |  | 3.3 - Concrete Testing - Core Sample Frequency (Post construction) | 3 - Testing and Acceptance
|  | 3.4 - Concrete Testing - Slump |  | 3.4 - Concrete Testing - Slump | 3 - Testing and Acceptance
|  | 3.5 - Reinforcement |  | 3.5 - Reinforcement | 3 - Testing and Acceptance
|  | 3.6 - Mortar |  | 3.6 - Mortar | 3 - Testing and Acceptance
|  | 3.7 - Building Permit |  | 3.7 - Building Permit | 3 - Testing and Acceptance
|  | 4.1 - Pre-pour |  | 4.1 - Pre-pour | 4 - Application
|  | 4.2 - Concrete Pumping |  | 4.2 - Concrete Pumping | 4 - Application
|  | 4.3 - construction of blockwork |  | 4.3 - construction of blockwork | 4 - Application
|  | 4.3 - Core-filling |  | 4.3 - Core-filling | 4 - Application
|  | 4.4 - Traceability |  | 4.4 - Traceability | 4 - Application
|  | 4.5 - Curing |  | 4.5 - Curing | 4 - Application
|  | 4.6 - Joints |  | 4.6 - Joints | 4 - Application
|  | 4.7 - Cleaning |  | 4.7 - Cleaning | 4 - Application
|  | 5.1 - Repair of defective areas |  | 5.1 - Repair of defective areas | 5 - Finishing Activities
|  | 5.2 - As Built Documentation |  | 5.2 - As Built Documentation | 5 - Finishing Activities
|  | 6.1 - Final inspection |  | 6.1 - Final inspection | 6 - Post Construction
|  | 6.2 - Compressive Strength (& VPV Test Results if requested by Superintendent) |  | 6.2 - Compressive Strength (& VPV Test Results if requested by Superintendent) | 6 - Post Construction
|  | 6.3 - As-built Survey |  | 6.3 - As-built Survey | 6 - Post Construction
|  | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. |  | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 6 - Post Construction
|  | QAV - Print Name: | QAV - Print Name: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 6 - Post Construction
|  | QAV - Position: | QAV - Position: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 6 - Post Construction
|  | Fulton Hogan - Print Name: | Fulton Hogan - Print Name: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 6 - Post Construction
|  | Fulton Hogan - Position: | Fulton Hogan - Position: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 6 - Post Construction
|  | Work Completed On: | Work Completed On: | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. | 6 - Post Construction