## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: Site QA
| step |  |  | Tier 2: Grd Unit 1
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Grd Unit 2
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Grd Unit 3
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Grd Unit 4
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Grd Unit 5
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Grd Unit 6
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Level 1 Unit 101
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Level 1 Unit 102
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Level 1 Unit 103
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Level 1 Unit 104
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Level 1 Unit 105
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Level 1 Unit 106
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Level 2 Unit 201
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Level 2 Unit 202
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Level 2 Unit 203
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Level 2 Unit 204
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Level 2 Unit 205
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Level 2 Unit 206
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Stairwell A
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Stairwell B
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 2: Stairwell C
QA - Metal Ceiling Grid Checklist | checklist |  |  | Tier 3: Metal Grid Ceilings
QA - Standard Wall Lining Checklist | checklist |  |  | Tier 3: GIB Fix
QA - Stopping Checklist | checklist |  |  | Tier 3: GIB Stop
QA - Painting Checklist | checklist |  |  | Tier 3: Paint
| step |  |  | Tier 1: Toolbox
| step |  |  | Tier 2: 2024
| step |  |  | Tier 3: Oct 24
| step |  |  | Tier 3: Nov 24
| step |  |  | Tier 3: Dec 24
| step |  |  | Tier 1: Site Visit
| step |  |  | Tier 2: 2024
| step |  |  | Tier 3: Oct 24
| step |  |  | Tier 3: Nov 24
| step |  |  | Tier 3: Dec 24