## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Concrete Pour Checklist |  |  |  |  | Yes | Concrete Pour Checklist | 117e0c9c-b635-45c0-a080-3f25315c5173
checkpoint-status |  |  | checkpoint | General Details
text | ed6cb7eb-86a8-57ee-af6f-b50eca1006c1 |  | textbox | Location
text | caf2ed35-29b1-5ea1-ad58-3f04eef64333 |  | textbox | Pre Pour Date
text | 43c81ae8-0670-5449-b46a-416fdd4abe52 |  | textbox | Concrete Strength (mPa)
text | 49d92feb-dd3a-5a79-8a66-3dda0f10471e |  | textbox | Volume (m3)
text | 52a0ebb3-f114-5e29-acf2-cf1e2d810732 |  | textbox | Mix Design
text | fc80e085-05c3-5b80-97a4-1ea053248326 |  | textbox | Additives
checkpoint-status |  |  | checkpoint | Formwork has been Checked and conforms to the drawings including:
label | 62e5b632-9007-5dd9-9c1d-0545a78c749f |  | note | Overall location, Bracing & Supports, Cleanliness, Construction Joint Positions, Construction Joints Prepared, Plan Dimensions, Pour Thickness, Diagonals, Straightness, Grout Tightness, Surface Finish, Rebate, Penetrations, Formwork Oiled, Angle Fillet , Divi nuts tight
checkpoint-status |  |  | checkpoint | Reinforcing has been checked and conforms to the drawings included:
label | 9cdb9cb9-0641-55be-a98f-4b74537ef7c8 |  | note | Bar Size & Grade, Lap Lengths, Lap Locations, Bar Supports, Bar Spacing, Cover, Steel Cleanness, Starter Positions
checkpoint-status |  |  | checkpoint | Pre Pour Sign Off
holdpoint |  |  | signoff | Pre Pour Acceptance
checkpoint-status |  |  | checkpoint | Pour Commenced
text | a3edf8dc-d005-51c2-b3fb-68622a9801bf |  | textbox | Pour Date
text | d9c6a144-6ad8-55b5-a73c-df307ea137fc |  | textbox | Pour Time
checkpoint-status |  |  | checkpoint | Slump Measured
text | be3ffe44-5cfe-5087-ae24-a257c1d28248 |  | textbox | Measurements
checkpoint-status |  |  | checkpoint | Dockets Attached
checkpoint-status |  |  | checkpoint | Concrete Cylinders Taken
checklist-sectioned |  |  | checklist | DS2672-ITP-S103 - Rev 1 - Jet Grout Installation |  |  |  |  | Yes | DS2672-ITP-S103 - Jet Grout Installation - Rev 1 | 235f83fc-0a31-406a-9db3-609d1fc91af3
checkpoint-group |  |  | section | 3.01 Site Requirements
checkpoint-status |  |  | checkpoint | 3.01.01 - Construction Pack
label | 8a8f0ff7-8cef-5d97-8a6d-b67c943409dc |  | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
label | f54a4c43-3c99-50ea-831c-f16c26b4b896 |  | note | Standard / Specification - Downer
label | b716779f-2b80-54b9-aea4-d07499d170b6 |  | note | Verifying Document - Construction Pack
label | 419b6164-ed03-5893-a91a-a72f007e26dc |  | note | Frequency - Submit Prior to commencement of works
label | 55f58789-9fa0-5f51-b068-7a81fd75c51a |  | note | Activity - H
label | 67c711fe-120a-583a-a9c5-35fa49b01aba |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.02 - Survey Setout
label | 24cce936-5e41-595c-9865-fa6f5920cc56 |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | bfaea4ce-f7dd-5387-a89f-9bab84877368 |  | note | Standard / Specification - Downer
label | cb457985-3697-5e24-8796-f36a773dcec6 |  | note | Verifying Document - Survey Records
label | 865eae83-6239-5bcd-8ef9-740dee09d59c |  | note | Frequency - Prior to Works
label | a9b9bd3e-3a0f-5af1-95d7-538cde74d9c9 |  | note | Activity - H
label | 948a1298-7696-5557-ae5c-25bdbd595e69 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.01.03 - Service Location
label | 5d9fb48a-cef3-53da-8500-9ddcf0c6839f |  | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | 3c77e130-4b72-5855-8208-c98ee9c2b324 |  | note | Standard / Specification - Downer
label | 2b6a1968-00a0-5384-b58b-a891598af506 |  | note | Verifying Document - Excavation Permit
label | 50e6d473-1519-5141-9716-af1f37dbbd0f |  | note | Frequency - Prior to Excavation
label | b0d3d605-38f5-5c75-b4b6-41c02e9ee809 |  | note | Activity - H
label | bb681ad0-815d-5db0-98d5-c12bc537588b |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.04 - Internal Permits
label | 16735e39-60b4-59bc-917d-5c4837422376 |  | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | 6b283994-6d2f-563d-9bf9-d460d97a8856 |  | note | Standard / Specification - Downer
label | c5451da6-8813-5a8c-99cf-54b038a96d3c |  | note | Verifying Document - Internal Permits
label | 0bc520eb-e4c8-55b6-a99d-d04b09f04698 |  | note | Frequency - Prior to Excavation
label | ff6a4e4f-4888-5d78-82b1-4c665f11f050 |  | note | Activity - H
label | 4a6494ee-68ad-5438-8763-23aebae87400 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.05 - External Permits
label | 54398eff-fc52-5919-81f1-b9fc1ddb1f65 |  | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | 4ce9b9f7-a9a1-5a5b-bf38-fc03fa593565 |  | note | Standard / Specification - Downer
label | 740658b3-5b76-5a18-b809-60c7fd621b79 |  | note | Verifying Document - External Permits
label | cc2e58c0-5bcb-5ae5-8e02-2efd1c6bfe25 |  | note | Frequency - Prior to Excavation
label | afc37158-3ec8-5274-aaed-08736c0a5134 |  | note | Activity - H
label | b93725d8-e217-59aa-a3a1-0d0c1df3b950 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.06 - Approved Construction Drawings
label | 969607d2-8b1f-52d1-95b4-dbbbd15f7f31 |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | 9f1a8acb-62e5-5af0-9d23-04d851ef5e2d |  | note | Standard / Specification - Downer
label | 734fb7d6-2e90-5032-b1ee-b995225abec8 |  | note | Verifying Document - IFC Drawings
label | 2bddaf2d-18c7-574c-a4ec-d7bf8320bdec |  | note | Frequency - Prior to works start
label | d7f20f79-388c-5e1a-b7c2-09d4ffef35d1 |  | note | Activity - H
label | 353ff513-a70d-57a7-9348-35602d16f431 |  | note | By - PE
checkpoint-group |  |  | section | 6.02 Jet Grout Installation
checkpoint-status |  |  | checkpoint | 6.02.01 - Jet Grout Work Start Notification
label | 4c07f364-3199-51d4-8de7-0f1c0f22ecfa |  | note | Acceptance / Conformance Criteria - Give the Engineer at least two Working Days’ notice prior to commencement of work on-site
label | fa7d008e-34fd-5b8b-8399-abd7f4147e06 |  | note | Standard / Specification - 14AED/AD4-C - 140.1.6
label | 48da341e-090f-5bec-b5ba-d6d88a82dee6 |  | note | Verifying Document - Hold Point Release
label | 2af7eabf-4998-5c62-94b0-de0de000f50a |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | 05ae61b5-9055-5589-a8b4-28025d70e130 |  | note | Activity - HP
label | 4e548b91-ae80-50aa-822d-0f9cf8d18d41 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.02.02 - Setting out
label | ada62adb-e7f1-5a98-8ff8-b9d03c314361 |  | note | Acceptance / Conformance Criteria - Setting out shall be carried out from reference lines and points shown in the drawings and approved by the Engineer. Immediately before commencement of jet grouting works, the jet grout column positions shall be marked with suitable identification pins or markers.
label | d194ae37-c6af-5d17-b6ed-4d50e270231f |  | note | Standard / Specification - 14AED/AD4-C - 140.1.7 / 140.3.1
label | 4ea28953-0d77-57a6-8c24-fd6ce4e75116 |  | note | Verifying Document - Survey Records
label | 599cdd38-957e-57d8-ad1d-0e26d010ea9b |  | note | Frequency - Prior to Jet Grouting
label | 506201f0-3216-5ded-b0d4-2a7ad7a81eb8 |  | note | Activity - HP
label | 29ffd062-5661-5097-8ac1-8ec4f1e4a837 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.02.03 - Services
label | 19f64327-fab3-5c8e-900f-2686b5337cba |  | note | Acceptance / Conformance Criteria - All services and shall be located and be clearly marked out on-site by the appropriate utility authorities prior to construction commencing.
label | 7a8456db-608f-5532-9b5b-9b6328539db3 |  | note | Standard / Specification - 14AED/AD4-C - 140.1.8
label | 2ddaa016-55af-5365-b4d0-d39020cd1610 |  | note | Verifying Document - Markout Record
label | 58389081-8e89-522a-b13f-28e00553c1a3 |  | note | Frequency - Prior to Jet Grouting
label | 47554b86-ecd9-5931-8d47-a6ea36873a53 |  | note | Activity - I
label | bebbe6b3-4138-5602-bc6e-c1ccb614160a |  | note | By - SE
checkpoint-status |  |  | checkpoint | 6.02.04 - Jet Grout First Column Notification
label | ba826b3e-7faa-593c-a07a-111e66bd2b81 |  | note | Acceptance / Conformance Criteria - Give the Engineer at least two Working Days’ notice prior to Commencement of column installation within the dam;
label | 402cf302-cb4e-54a5-b886-19c9bc011ab2 |  | note | Standard / Specification - 14AED/AD4-C - 140.1.6
label | a0f556a7-d983-5b9c-8b4b-9be748338bc8 |  | note | Verifying Document - Hold Point Release
label | 97b58ae3-ec73-5f4d-b60c-e41a743fddb0 |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | be721ed6-d071-5229-b6e6-93df2678468a |  | note | Activity - HP
label | eab550a5-22c8-5dec-87a2-66f8eecce771 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.02.05 - Jet-Grout Cut-off Wall Inspection
label | accc90b8-07fa-53bd-8131-e1aa4473961c |  | note | Acceptance / Conformance Criteria - Jet-grout cut-off wall: full-time designer site presence during installation must be inspected by the Engineer prior to further work being carried out in the area.
label | 1a313b7a-fa0f-5a0c-b242-b3d2aceed486 |  | note | Standard / Specification - 14AED/AD4-C - 030.3
label | 30e07865-2dcd-53c6-bcc1-ee2e8d402033 |  | note | Verifying Document - Hold Point Release
label | a742523f-ebd9-5797-abe0-ed511bac2fc5 |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | e40cd607-a426-53c7-a4e7-0cd2dff76e3f |  | note | Activity - HP
label | bde08d20-5cc8-5c64-a437-2beb489f56e9 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.02.06 - Drilling Records
label | 52d2cc18-37d3-504e-b88d-8c0b541c67e0 |  | note | Acceptance / Conformance Criteria - Each grout hole shall be Evaluated for continuous drilling and grouting with drilling records being submitted daily to the Engineer.
label | dfb85a2c-3551-5c01-ba3d-6c13e1664436 |  | note | Standard / Specification - 14AED/AD4-C - 140.5.2.3 140.5.2.4
label | 7dde778a-764b-58b8-8463-4aa52a272d75 |  | note | Verifying Document - Daily Checksheets
label | 19bdd9ff-c112-57d0-8f48-ac6438c7ee7a |  | note | Frequency - Each grout hole
label | 32976cfa-3468-5c45-990e-314731d0f13e |  | note | Activity - C
label | 88d98dda-e5ba-5c07-a552-0f0f3cd4cfeb |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.07 - Spoil Return
label | f11965ff-54c7-55d0-b6a7-40fb33f1579a |  | note | Acceptance / Conformance Criteria - Visual observation of the flow and features of the spoil shall be maintained during jet grouting.
label | 7b5efea4-3f3f-5f4c-b6a8-88d24f753ae8 |  | note | Standard / Specification - 14AED/AD4- C - 140.3.8
label | 6e68e527-675a-51c6-b544-97c76d3f3e6d |  | note | Verifying Document - Daily Checksheets
label | b90e28bc-7a17-5ae7-accc-eedbbe056867 |  | note | Frequency - Each grout hole
label | 594ad826-9714-5c53-be1f-8161cf49005a |  | note | Activity - C
label | 5b1d3126-4543-5a80-a725-bda70b49c4d6 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.08 - Overlap
label | 096884db-7980-5a08-9a63-9e9e5ea75037 |  | note | Acceptance / Conformance Criteria - Jet-grouted cut-off wall with approx. 20% overlap between each column
label | 58a406aa-2460-5d15-8d32-8c34daff05ec |  | note | Standard / Specification - DWG 14AED-AD4-116
label | 21819bd4-b1c4-5925-a2d0-48ab54ea152f |  | note | Verifying Document - Daily Checksheets
label | 7f1eb3ee-156f-5dd8-8554-5f78e86bcb80 |  | note | Frequency - Each grout hole
label | bf69f598-e220-5bc0-8d00-9fa0ea6c713b |  | note | Activity - C
label | 3695d7f0-d2e8-5588-9e9c-0778cb36a079 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.09 - Adjacent Structure Damage
label | 0a48bd6a-38fe-5bc3-8908-9ef3943aa451 |  | note | Acceptance / Conformance Criteria - If damage to the existing dam is suspected during the jet grouting operations, the work shall cease immediately, and the Engineer shall be informed.
label | dacdb34b-63bf-5a7c-8249-8aa8b47a584f |  | note | Standard / Specification - 14AED/AD4-C - 140.5.2.5
label | d634332b-4ccc-52fe-ad0b-cb12acaecc12 |  | note | Verifying Document - Daily Checksheets
label | b2e7f56e-3500-5ead-bebb-563fb7320cff |  | note | Frequency - Each grout hole
label | 63e9dc30-2c6e-5b87-8c52-6d3d46e4a559 |  | note | Activity - C
label | 3f364ddb-9b3c-5186-b798-392d764b8dca |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.10 - Position
label | 394168ea-2e03-5060-a0e9-c30a8c42dcf1 |  | note | Acceptance / Conformance Criteria - The maximum permissible deviation of the centre of each grouting point from the correct centre point as shown in the setting out drawing shall be 100mm in any direction.
label | f2890206-8331-5abd-801a-d16245de9e67 |  | note | Standard / Specification - 14AED/AD4-C - 140.3.2
label | cf7198bb-dc32-5a36-83f2-835e0d2f9f20 |  | note | Verifying Document - Daily Checksheets
label | afc2eec6-92ce-5cf3-88f5-f395243d904f |  | note | Frequency - Each grout hole
label | 524c5df0-214e-520c-a187-36c5b27f5f98 |  | note | Activity - C
label | 5c85ef1d-03ad-5593-9558-79e29ae67467 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.11 - Verticality
label | 518bb5f4-eb7b-5d71-ae7b-87ea3bab1800 |  | note | Acceptance / Conformance Criteria - Jet grouting for vertical bore hole shall be carried out as near vertical as possible. The drilling rod shall not deviate by more than 1 in 100 during drilling.
label | f568e2dd-e0b8-54a7-8bd3-627a44159cfc |  | note | Standard / Specification - 14AED/AD4-C - 140.3.3
label | a304ed48-3b44-5a86-be0a-1f454fafee52 |  | note | Verifying Document - Daily Checksheets
label | 4852007b-c296-537e-8665-730abf54f6a0 |  | note | Frequency - Each grout hole
label | 55c5cb61-1fe7-5173-b24b-6a7bacb21142 |  | note | Activity - C
label | 537cc0e1-7eec-5e9d-ac94-3e64ffb94992 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.12 - Length, Diameter and Spacing of Columns
label | bd012498-2cfc-5d3e-8da6-af5c6111ba7c |  | note | Acceptance / Conformance Criteria - The length, diameter and spacing of the jet grouting columns shown on the drawings are indicative only and shall be adjusted to suit site conditions when deemed necessary.
label | 92c6e6e3-59e5-5fb5-a518-a839a74b674b |  | note | Standard / Specification - 14AED/AD4- C - 140.3.5
label | f8d15458-6149-55e5-a51f-0239dbb38337 |  | note | Verifying Document - Daily Checksheets
label | 03e1c24f-5ab1-5521-96ae-49228d601d5b |  | note | Frequency - Each grout hole
label | 304b209d-ed4c-55cf-bcde-baa5da1bf26a |  | note | Activity - C
label | 09933f24-c5d4-5d7b-96aa-f487bfbf84c1 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.13 - Jet Grouting Interruption
label | 15130126-fe61-53da-a60b-429982596bf9 |  | note | Acceptance / Conformance Criteria - If the jet grouting operation is interrupted for any reason, re-grouting may be required upon confirmation from the Engineer on site to ensure continuity of the column.
label | 0b400254-b211-53d6-82ea-d9a95216752f |  | note | Standard / Specification - 14AED/AD4- C - 140.5.2.1
label | c363f2de-0dda-52a2-af61-86d7af34df90 |  | note | Verifying Document - Daily Checksheets
label | eb9a14b7-739e-5b85-896d-71c4ce53ab4c |  | note | Frequency - Each grout hole
label | a42d798e-426b-545c-8da8-467d69edebcd |  | note | Activity - HP
label | a09f31aa-d7e0-55e5-aa47-281572e75cba |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.02.14 - Jet Grouting Cleaning
label | ee2c8cda-fd5f-5e53-8ea6-e50e85d3514d |  | note | Acceptance / Conformance Criteria - At completion of daily jet grouting operations, the site shall be thoroughly cleaned, and all spoil debris, water, and spilled material shall be disposed appropriately. Spoil stockpiling overnight is permitted prior to transfer to a predetermined waste or fill location.
label | ce14cdce-7724-5e90-aab5-77d9042c11b5 |  | note | Standard / Specification - 14AED/AD4- C - 140.5.2.1
label | 8717a7ae-4cdd-5818-a970-29dcfb4d9bde |  | note | Verifying Document - Daily Checksheets
label | 30d4a979-c16b-5187-82e6-d79db67cd703 |  | note | Frequency - Each grout hole
label | 5989d42e-ba1f-5ecd-89a1-6d9f388361dd |  | note | Activity - C
label | 10cc0632-2534-5ce7-af03-43f408c36525 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.15 - Daily Grout Density Tests
label | 82cece44-fc2e-5039-9188-ce291844a6ba |  | note | Acceptance / Conformance Criteria - The quality as well as the suitability of the fresh grout shall be constantly assured by measuring its density with a hydrometer.
label | 794c45d6-70e6-512e-98a7-4d4a2a7a7444 |  | note | Standard / Specification - 14AED/AD4-C - 140.5.2.4 / 140.4.1
label | b32bc6d7-aea0-5a9b-9e25-8f892b1df9cb |  | note | Verifying Document - Site Results
label | b5311da5-c8ce-5e0a-954a-ec8d090f8cf0 |  | note | Frequency - Daily
label | 15f1dbfb-f941-58dc-8ed6-201f7d4c46ce |  | note | Activity - C
label | 8b100782-3701-5881-8764-ecd086668372 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.16 - Daily Spoil Density Tests
label | dc7d568a-521a-530d-bf16-db45044d93aa |  | note | Acceptance / Conformance Criteria - Three cube samples shall be collected from spoil return during jetting at different levels of each column for subsequent laboratory tests.
label | 447d78b5-2cd8-5f62-b644-374c8e5ddc6a |  | note | Standard / Specification - 14AED/AD4-C - 140.5.2.4 / 140.3.8
label | 32bdf648-cf2e-519f-b8fb-016719bdfa8f |  | note | Verifying Document - Lab Report
label | b21671d7-f7c7-5eec-8710-3a0d3a0dc79c |  | note | Frequency - Daily
label | 0a820f31-5e70-53dc-9630-e72bfc709db3 |  | note | Activity - R
label | e66c6fa9-0753-557b-ac85-22694492fa00 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.02.17 - Weekly Grout Compressive Strength
label | bc6820b2-8d92-5fe8-806d-7e027362aedc |  | note | Acceptance / Conformance Criteria - The minimum unconfined compressive strength (28 day) of the selected working columns shall be a minimum of 2 MPa. This shall be confirmed through laboratory tests on samples collected Weekly from backflow on site.
label | 95efffa8-4b2d-5b42-bb6d-a49cc0cba83a |  | note | Standard / Specification - 14AED/AD4-C - 140.3.6 / 140.5.2.4
label | 678a4616-7c4f-5359-a7f5-95322a9e1f65 |  | note | Verifying Document - Lab Report
label | a2522085-a6e1-5305-9758-c843eb9225e8 |  | note | Frequency - Weekly
label | 1907a343-676d-52e0-b428-5bcc482cf633 |  | note | Activity - R
label | 5f0e69ea-8b24-5052-be63-07c3e496073a |  | note | By - PE
checkpoint-group |  |  | section | 10.01 Site Post Construction Activities
checkpoint-status |  |  | checkpoint | 10.01.01 - Construction Record Compilation
label | e65b0100-b5d8-552a-a259-b303768162ed |  | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | 230c756a-720a-5969-a651-b2fb450f41b5 |  | note | Standard / Specification - Downer
label | fc043049-d918-572e-9cb8-c8c132ba7dd2 |  | note | Verifying Document - Records
label | 504a7bbb-1736-53e6-978a-1598f16621c7 |  | note | Frequency - Post construction
label | 167f3617-6646-5a8b-96b7-d59527ba76a9 |  | note | Activity - H
label | 08853699-6e0e-55d4-bb98-e13edd75e9cc |  | note | By - SE
checkpoint-status |  |  | checkpoint | 10.01.02 - Survey Records
label | ae616771-42b0-525b-96b0-54e50e971bc4 |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | 77084a6b-a55b-5d3b-9d1c-52b286fc3567 |  | note | Standard / Specification - Downer P&G 20.1
label | 02e21bd9-a78f-5f80-9fb2-cc4371f2c676 |  | note | Verifying Document - Records
label | 91fdbbd5-c2e6-5cb5-b7df-1e8fd71b78a7 |  | note | Frequency - Post construction
label | 16c32516-7664-56a7-8207-0f5be4a842dc |  | note | Activity - H
label | b26f7a53-fb71-5cb0-aa18-22a294d2bf14 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 10.01.03 - Redline Drawings
label | a61e2787-e2b6-56db-9d18-20dc84d0d081 |  | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red-pen mark-up copies of the Drawings and Specifications and other design documentation showing any deviations from the specified details and requirements produced in accordance with industry good practice.
label | 974188f6-7f1e-54cc-8984-fc81ce8e1df0 |  | note | Standard / Specification - Downer P&G 20.1
label | 53423a98-ba11-541b-99cf-0890f934defd |  | note | Verifying Document - Redlines
label | d2bbd8b5-d717-5025-ad53-f485e1b9cee7 |  | note | Frequency - Post construction
label | edf0fb85-7a51-5546-afd6-c7e0bc01bf7b |  | note | Activity - H
label | b1550515-f847-5c92-9649-b5ae90eace08 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 10.01.04 - Defect, Snag and Punch List
label | aeeef459-0f28-59eb-949e-893dac36a6a7 |  | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | d58fc400-bb2a-5a5c-bec8-cda72be46141 |  | note | Standard / Specification - Downer
label | fe288a98-5d10-5a7e-a60b-11f6ea363c01 |  | note | Verifying Document - Register
label | 1d141bef-af6a-5bb0-abb7-4e983b0b75dd |  | note | Frequency - Post construction
label | 6f30a09e-215d-51a2-a5b9-510233e2e987 |  | note | Activity - H
label | e3681fa5-c4e5-5111-abd4-24c935bdfd6b |  | note | By - PE
checklist-sectioned |  |  | checklist | DS2672-ITP-S108 - Piling Materials - Rev 1 | itp |  |  |  | Yes | DS2672-ITP-S108 - Piling Materials - Rev 1 | 28d45edf-afd2-42ee-92e5-685f5b62dbc1
checkpoint-group |  |  | section | 4.07 Piling Materials
checkpoint-status |  |  | checkpoint | 4.07.01 - Piling Supervisor
label | 220b0a74-0b19-5de4-870d-9fd4020a3c3e |  | note | Acceptance / Conformance Criteria - A suitably qualified and experienced person shall be nominated by the Constructor as the ‘Piling Supervisor’.
label | 798e03c1-89b6-5737-987d-59da8b1ba700 |  | note | Standard / Specification - 51/33669 - 3.9
label | 6cbee1b7-ad92-5273-82d0-0cf62b33415c |  | note | Verifying Document - Supervisor Approval
label | 7285d036-d25d-5ff0-aed5-895dc36de216 |  | note | Frequency - Prior to any piling works commencing.
label | 8c173789-b00a-5931-b5e1-5ce4d015a7fe |  | note | Activity - W
label | ce5e1508-87d6-5815-a0cb-151ab9030d60 |  | note | By - ENG
checkpoint-status |  |  | checkpoint | 4.07.02 - Pile Mix Design
label | 1ebba34d-d212-5806-bc6d-c627deb3db52 |  | note | Acceptance / Conformance Criteria - The Designer shall be provided with the proposed concrete mix design for review, prior to any piling works commencing.
label | 4ce1417b-7482-508c-ab6c-1db717bf85fa |  | note | Standard / Specification - 51/33669 - 5.1
label | 6db710fd-1470-52ca-8730-5ef89b11c657 |  | note | Verifying Document - Mix Design
label | 05ddba3c-d620-5b1b-a3fb-8128c9dfe0ba |  | note | Frequency - Prior to any piling works commencing.
label | 79c0d8c1-0565-50a1-ad53-70b2627809bf |  | note | Activity - HP
label | f590b14a-5774-59f2-bc3d-f923edbc6179 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.07.03 - Spiral Reinforcement Welding
label | 2915ae4e-e935-5a55-bc3d-798cea8b1c72 |  | note | Acceptance / Conformance Criteria - Spiral reinforcement shall not be lapped. Spiral reinforcement shall start and stop with 1.5 x pile cage circumference overlap and a single sided lap weld. Laps in longitudinal bars shall be made with D-clamps or similar means accepted by the Designer. Lapped joints shall achieve the full strength of the bar.
label | 9cb6a621-9844-5e00-8970-3e2f808af092 |  | note | Standard / Specification - 51/33669 - 5.2
label | 655a53f9-0e88-565f-aeed-bf6a8efc27d1 |  | note | Verifying Document - TPI Report
label | d1fbe9ac-fdb8-50a4-896a-45374520138f |  | note | Frequency - Prior to Installation
label | cd85a22d-6ba3-5940-a619-b0f26e06bed8 |  | note | Activity - HP
label | 708e1c44-b7a4-5ffd-8f8c-d202c5076f6f |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.07.04 - Reinforcement Cage Fabrication Inspection
label | 904a9381-c316-5c38-993f-973208da4649 |  | note | Acceptance / Conformance Criteria - Designer inspection of reinforcement cage fabrication process for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure)
label | e17050a0-cd40-5986-a745-f8859947f63a |  | note | Standard / Specification - 51/33669 - 9.4
label | 2abefdf4-e20b-5bf2-a891-a2691d36558c |  | note | Verifying Document - Hold Point Release
label | 5ed2e9aa-cdb5-51fa-9e26-e16b2ba63b8e |  | note | Frequency - First pile at every structure
label | ffec868d-aace-5c25-8be3-c1930d22227e |  | note | Activity - HP
label | cd21c12a-f4bc-56cc-be32-fe388f88dab4 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.07.05 - Permanent Casings
label | f421cc5e-f573-56aa-bead-75ed2860d2dd |  | note | Acceptance / Conformance Criteria - The casing dimensions shall comply with the outside diameter, wall thickness and internal diameter as shown on the Drawings
label | 4c1bd78a-3cb0-51cb-997f-7fc2b3f14090 |  | note | Standard / Specification - 51/33669 - 6.1.1
label | 0ccd0359-ff75-567d-8748-feb00db3a21b |  | note | Verifying Document - Mill Certs and Dimensions
label | 04821174-26ff-5926-b1c8-06070cef80ff |  | note | Frequency - Prior to Installation
label | 4688ea4c-41be-5465-b300-bcadceb87d5c |  | note | Activity - R
label | b14bd19d-30cd-5624-9bb0-b6fca3378f71 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.07.06 - Temporary Casings
label | 63e0d993-1354-5036-8d42-79edaf6b7630 |  | note | Acceptance / Conformance Criteria - the Constructor shall confirm that the properties of the casing are such that the bored piles are constructed to the dimensions, shape and depth.
label | 34748280-60cf-569b-bd4e-90e88023aa10 |  | note | Standard / Specification - 51/33669 - 6.1.2
label | 63d3239a-68c5-514a-8e89-a5dda67188bd |  | note | Verifying Document - Dimensions
label | a5c09c6b-0f71-5b86-9ca3-f42af464d592 |  | note | Frequency - Prior to Installation
label | 3d6aece0-0945-5db6-8fb7-8af8101359b4 |  | note | Activity - R
label | bc43d76b-ee72-5284-ab57-ec96b69f9114 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.07.07 - Bored Pile Construction Record Card Template
label | 8338f736-4d3e-56a7-97ac-e1fc497de46d |  | note | Acceptance / Conformance Criteria - Supply a Template for the bored pile construction record card a minimum of 3 weeks prior to the commencement of any piling works.
label | 104647dc-1fa1-5d37-a2be-47a9ff171a15 |  | note | Standard / Specification - 51/33669 - 9.1
label | e80a6585-7cc1-5459-b8e1-09cf86418943 |  | note | Verifying Document - Construction Record Card Template
label | 0e9f188c-6724-5dd6-beb1-9df373a9443b |  | note | Frequency - 3 weeks prior to the commencement of any piling
label | 6e27dace-7f96-58d4-966f-cfdaa3389e4c |  | note | Activity - R
label | a2922127-912a-5b13-807e-28cfdb986df9 |  | note | By - PE
checkpoint-group |  |  | section | 4.08 Concrete Materials
checkpoint-status |  |  | checkpoint | 4.08.06 - Reinforcement
label | d16ac47a-e5c8-5325-8c97-4e91533cb12c |  | note | Acceptance / Conformance Criteria - Reinforcing bars and mesh shall comply with AS/NZS4671:2001.
label | 05804ddb-3167-5d06-a1b9-4ead9dc924dd |  | note | Standard / Specification - RSV - CS - 1.19
label | 386538fe-7975-55d7-9a81-1d3fd456c2f5 |  | note | Verifying Document - Mill Certs
label | 8b72b54b-5f82-52ba-bc78-ab38603c4ba5 |  | note | Frequency - Prior to Installation
label | 5769bc0d-1593-5bab-b074-5e0f9d8ca4a0 |  | note | Activity - R
label | 4eeeed6e-d7af-50eb-9baa-dc9f59b0f9bf |  | note | By - PE
checklist-sectioned |  |  | checklist | DS2672-ITP-S105 - Pile Construction Card - Rev 1 | itp |  |  |  | Yes | DS2672-ITP-S105 - Pile Construction Card - Rev 1 | 372c61f5-cd14-44a2-a459-86cfc5705ff8
checkpoint-group |  |  | section | 7.02 Setout and Excavation - (Pile Construction Card)
checkpoint-status |  |  | checkpoint | 7.02.01 - Pile Set Out
label | b152b37c-7a2a-547a-8c66-531334ef09cf |  | note | Acceptance / Conformance Criteria - The position of all piles shall be accurately set out and checked by a suitably experienced surveyor prior to installation
label | 358beaa6-a084-5f5e-96fc-d3e7368fc5a2 |  | note | Standard / Specification - 51/33669 - 3.7
label | d847e3b0-06d8-5165-8859-8a53346a5367 |  | note | Verifying Document - Survey Records:
label | 278b31fb-e549-5ede-829e-64b8c91b34ce |  | note | Frequency - Each Pile
label | 2aa6f98e-ea27-5c7d-a20d-a1df0d1e296d |  | note | Activity - D
label | 778c54e2-6cba-52e9-88c8-1a659aa2c2df |  | note | By - SV
text | 0136890a-42ca-53ba-b1aa-be96f7c2704d |  | textbox | Location Co-Ordinate - X:
text | e385596c-3802-52e4-b9d8-53a8d83da472 |  | textbox | Location Co-Ordinate - Y:
text | 11c5a0a6-8c78-513e-aaa8-46d1edaa84db |  | textbox | Ground Surface Elevation - RL:
text | e2949f61-a505-570d-a411-10f5c245558e |  | textbox | Expected Stratum Elevation - RL:
checkpoint-status |  |  | checkpoint | 7.02.02 - Nature of Ground and Subsurface Conditions
label | 1bb4c1d6-90d6-5dcb-8cf2-f9f58fc10c81 |  | note | Acceptance / Conformance Criteria - The Constructor shall inform the Designer where circumstances indicate that ground and / or groundwater conditions differ from those presented in the reports, indicated on the Drawings or interpreted from proof bores.
label | 805b2fdb-335a-5eee-9030-3ff6f78a585a |  | note | Standard / Specification - 51/33669 - 3.5
label | a47a6883-4b29-517b-842b-e5342625a5f7 |  | note | Verifying Document - Notice
label | 1b6ad4d8-d544-570e-aea2-2fe9319bfc2d |  | note | Frequency - Ongoing
label | 10cd1bd5-3fa8-50e9-983e-0bbc1c51dcdf |  | note | Activity - S
label | 3b7311c5-8c14-5d75-b671-d5f6e0090294 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 7.02.03 - Pile Logging Inspection
label | 3e216c32-3252-5e3e-ba63-9d7e631abc6f |  | note | Acceptance / Conformance Criteria - The logging of selected piles shall also be undertaken by the Designer to agree with the Constructor in identifying the founding stratum.
label | 36a9eb3c-f95f-5a85-8eb3-6bdcb359ec44 |  | note | Standard / Specification - 51/33669 - 6.2.2
label | 0fb97265-24c3-54ee-8cbf-0a1877824baa |  | note | Verifying Document - Site Log
label | d207f521-13e3-53ba-8732-47f7a3e8d89f |  | note | Frequency - Each Pour
label | 2567a0c8-4dc9-5548-ba42-a8e5eb3cb9d1 |  | note | Activity - W
label | faa6fe6f-d3a0-58ce-ac1e-43f41775f473 |  | note | By - ENG
label | 826d2884-c832-5ac1-a546-d88aad6d8ffe |  | note | Comments / Closeout Details - Add First Pile Hold Points Checksheet and / or Selected Logging Hold Points Checksheet as required.
checkpoint-status |  |  | checkpoint | 7.02.04 - Pile Logging
label | db39d806-1153-5c13-98bb-40f3c9f63c7a |  | note | Acceptance / Conformance Criteria - The Constructor shall keep an excavation log for each pile that records the types of materials encountered and the depths at which those materials were encountered and any groundwater levels and inflows inside the pile
label | 4e20c731-536f-5d4f-b6fc-8e2cc98503d4 |  | note | Standard / Specification - 51/33669 - 6.2.2
label | a019ebbf-7cdf-55d7-a022-3fc7567c5875 |  | note | Verifying Document - Site Log
label | 40f9bf84-2d6f-5697-869e-db809f5f50ef |  | note | Frequency - Each Pour
label | c078a9e7-5db7-5495-b63c-46c0266ec9e0 |  | note | Activity - I
label | 7a9d7d21-ebb6-5793-a620-a782892d8a38 |  | note | By - SE
text | e3aa5cf9-41d0-56b6-b194-1c0a772d78bc |  | textbox | Casing Type - Permanent or Temporary:
text | 54b226a8-aa22-5801-b5e8-01be3d40f8f0 |  | textbox | Casing Finished elevation top (RL):
text | ef71acd5-6294-5088-b03b-b498e1570b5c |  | textbox | Casing Finished elevation bottom (RL):
text | fcda13aa-888c-5afc-b76b-c59f2abb0682 |  | textbox | Casing Depth (m):
text | 08818685-706e-5a3f-a9a1-471d695d15e4 |  | textbox | Casing Thickness (mm):
text | 0b856d02-715a-536a-8af2-71c1b4f86da7 |  | textbox | Excavation Commencement - Date and Time:
text | c8fda16e-1b66-5f52-8cab-ce23ecd759be |  | textbox | Detail Materal Type and when it Chages - Type and Depth:
text | c3f96648-2250-5af2-9efb-1ab6bf54b649 |  | textbox | The Depth to the Founding Stratum (m)
text | 946713a5-31d0-519b-8552-0dc71bee3dbd |  | textbox | Actual Stratum Elevation (RL):
text | 1d2f8348-a775-5278-b23c-a3046aea4e40 |  | textbox | Water Ingress - Depth (m) and Details:
text | 3196b220-dd39-578c-907e-f1f6c41a644b |  | textbox | Excavation Completion - Date and Time:
checkpoint-status |  |  | checkpoint | 7.02.05 - Pile Dimensions
label | 960c6b88-b6fb-56b0-9788-2121672046b4 |  | note | Acceptance / Conformance Criteria - Constructed piles shall not deviate outside the tolerances, unless otherwise shown on the Drawings or as accepted by the Designer.
label | 466ad8d2-4716-5247-b9f6-2aebaf8e2ff1 |  | note | Standard / Specification - 51/33669 - 3.8.1
label | 5e7ce026-0b59-55af-9b38-5bcaa0d2c90c |  | note | Verifying Document - Site Record
label | fa87c1a4-a834-5d4c-aa52-d33de31e2f45 |  | note | Frequency - Each Pile
label | ad0cad79-ac90-581e-ad01-53a6f9a28ff0 |  | note | Activity - D
label | bc80ed5c-bd66-535b-af4d-b8be8999ba0c |  | note | By - SV / SE
text | a4c1c5b9-103d-5ceb-9326-ac010381a577 |  | textbox | Actual Diameter:
text | 8f087ac3-342b-5d0c-81a0-e3efba9d11ad |  | textbox | Actual Length:
checkpoint-status |  |  | checkpoint | 7.02.06 - Pile Pumping
label | e4a8deee-9f01-56be-9aee-a795991a6318 |  | note | Acceptance / Conformance Criteria - Pumping from pile excavations are permitted provided the Constructor can demonstrate that the excavation has been sealed against further water entry (e.g. through sufficient keying into rock) or that the pile excavation is stable and will allow pumping to take place without ground disturbance below or around the pile.
label | 31fbef4b-8574-58f1-9bbf-e60d2092ea35 |  | note | Standard / Specification - 51/33669 - 6.2.1
label | 90694841-50e1-5a5c-b742-467cc8f8378a |  | note | Verifying Document - Site Record
label | 7868224b-99ff-5fc0-82bd-8cb47db8b073 |  | note | Frequency - Each Pour
label | 1b31a730-a618-574f-80f3-712683233cd1 |  | note | Activity - I
label | ec69cc17-4067-58eb-9ff1-8b6c80acb259 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 7.02.07 - Full Length of Pile
label | d618c39c-acd9-51bd-a0c7-d3a51d2200d5 |  | note | Acceptance / Conformance Criteria - Unless shown otherwise on the Drawings, each pile shall be in intimate contact with the ground over its full length.
label | 0b0181c9-3d28-524c-adb0-83cd1294a4bc |  | note | Standard / Specification - 51/33669 - 6.2.3
label | a7700b94-2924-5b66-bbea-7cea947ff203 |  | note | Verifying Document - Site Record
label | a5dee46d-a432-5919-9cd9-70f2dc736d1e |  | note | Frequency - Each Pour
label | 1f94bd7f-b2db-5adb-a733-04f85a38158d |  | note | Activity - I
label | 367aa36d-7431-5154-ad82-a14ba48d8002 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 7.02.08 - Pile Hole Side Cleaning
label | 5db6c8b0-f269-5e92-9398-a3a0655e942f |  | note | Acceptance / Conformance Criteria - On completion of the pile excavation and immediately prior to installation of the reinforcement cage Loose and / or smeared material shall be removed from the sides of the rock socket
label | 59081dc5-1662-5319-bbc9-0b774d4ed915 |  | note | Standard / Specification - 51/33669 - 6.3.1
label | fafe2f3f-d560-5a09-bd90-8ede931b03d7 |  | note | Verifying Document - Site Record
label | fa1d7fda-e867-5c24-b1fd-3f750cee30d0 |  | note | Frequency - Prior to installation of the reinforcement cage
label | 30644f82-8ad5-5183-8dee-01a0df673e54 |  | note | Activity - I
label | 42fe9225-ddc1-524a-816f-8b8d2f7c06b4 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 7.02.09 - Pile Hole Base Cleaning
label | 4b6ded08-9b67-5c43-8fb9-1b8e6a640081 |  | note | Acceptance / Conformance Criteria - On completion of the pile excavation and immediately prior to installation of the reinforcement cage Loose, disturbed and / or softened materials and any sedimentation shall be removed from the pile base
label | 9bfb1ad4-e32a-5e1e-b581-8ce319f54c1d |  | note | Standard / Specification - 51/33669 - 6.3.1
label | e0a01837-dffe-50e3-a2ad-ef6b747d6e58 |  | note | Verifying Document - Site Record
label | 24246067-7ee3-54b2-a871-a92b00e51c3f |  | note | Frequency - Prior to installation of the reinforcement cage
label | 5dfb77b5-b5ad-5282-9c3f-d62dc37a38d7 |  | note | Activity - I
label | 6f122791-5d52-53be-bb2e-fd982a52af90 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 7.02.10 - Pile Hole Inspection and Acceptance
label | 0152e5bd-2e22-57ac-b21a-99de237a7e73 |  | note | Acceptance / Conformance Criteria - The reinforcement cage shall not be installed, nor concreting begin for any pile, until the as-built founding level of the pile, the condition of the rock socket (where relevant) and the condition of the pile base has been accepted by the Designer
label | 777b521b-16fd-5d77-8f95-bd6849874e1b |  | note | Standard / Specification - 51/33669 - 6.3.2
label | 9a70ce65-5886-512f-8001-3a9ada513b4a |  | note | Verifying Document - Hold Point Release
label | 3c839f0d-5acc-59fd-b9d1-24f9f65d06e4 |  | note | Frequency - Each Pile
label | c1b592ac-ed58-5310-b58c-c795148e40fb |  | note | Activity - HP
label | 8e5160ff-d041-563c-b1fb-8d8fad154322 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7.03 Permanent Casings - (Pile Construction Card)
checkpoint-status |  |  | checkpoint | 7.03.01 - Pile Annulus
label | e21f3186-f889-5a7e-b412-78019c517a88 |  | note | Acceptance / Conformance Criteria - Permanent casings shall be installed in such a manner as to minimise any annulus between the outside of the casing and the in-situ ground.
label | b9df7da1-b150-59b7-b582-8f7851a4b8ac |  | note | Standard / Specification - 51/33669 - 6.1.1
label | eeafd1bd-abe4-5eb5-9483-b2ed54dd3d7d |  | note | Verifying Document - Site Records
label | 9930ea26-74c1-5df9-b37f-3cea1f805202 |  | note | Frequency - Each Pile Post Installation
label | 32339173-3e9f-5859-a667-c38a39b9e9b0 |  | note | Activity - D
label | 151781a7-47e9-523c-bb6f-6ec69e2ef8fc |  | note | By - SE
checkpoint-status |  |  | checkpoint | 7.03.02 - Installed Casing Profile
label | 17467328-9c7d-5198-a266-20643bda3b64 |  | note | Acceptance / Conformance Criteria - The installed casing profile shall be circular, with a deviation from the specified completed pile diameter of not greater than +5%, –0% of the pile diameter and with no distortions, dents, gouges or similar.
label | 0e3cf41b-5444-5ae9-9223-0a9094b4d29f |  | note | Standard / Specification - 51/33669 - 6.1.1
label | 94c6556c-4231-585a-bdea-1db01b7b9e62 |  | note | Verifying Document - Site Records
label | 02a2f7a4-e789-5be0-9ef3-e5de0a297d09 |  | note | Frequency - Each Pile Post Installation
label | 1625a8b5-8d0e-5916-95d7-6647961c740e |  | note | Activity - D
label | ea1e8187-cbff-5ed8-8c2b-63dbd4134dba |  | note | By - SE
checkpoint-group |  |  | section | 7.04 Temporary Casings - (Pile Construction Card)
checkpoint-status |  |  | checkpoint | 7.04.01 - Up-stand
label | d2e94323-eca6-5ddf-8b37-fdc9041439a2 |  | note | Acceptance / Conformance Criteria - As a minimum, an up-stand of temporary casing of at least 1 m above existing ground level shall be provided to prevent material falling into and contaminating the pile bore prior to and during excavation and concreting works.
label | 6b309d7a-788a-5521-a1db-a1888262fe65 |  | note | Standard / Specification - 51/33669 - 6.1.2
label | b8778b4a-c47f-5cbb-8f0b-d12ed0228302 |  | note | Verifying Document - Site Records
label | c3c8cfc6-f4c1-514c-a9b1-c030b9c6e129 |  | note | Frequency - Each Pile
label | ae2a447a-f99b-5317-a6dc-38dca08fea3c |  | note | Activity - S
label | 4524c137-df0b-5130-aa9e-c51d03734360 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 7.04.02 - Annulus Extra Concrete
label | 34936810-2b70-548f-b18e-40329797bbf9 |  | note | Acceptance / Conformance Criteria - Prior to the temporary casing being extracted, concrete shall be poured to the pile cut-off level plus the minimum over-cast allowance plus an allowance for the volume of annulus created by the extracted casing.
label | 7310b56f-0258-5044-930c-1b2f70153cdd |  | note | Standard / Specification - 51/33669 - 6.1.2
label | ffcbe5bf-fc65-537f-b949-971196c3ca44 |  | note | Verifying Document - Site Records
label | 063c3cb9-7bc0-5e95-8c6e-63ce1b10c0ed |  | note | Frequency - Prior to the temporary casing being extracted
label | be297510-5381-5e7e-8f83-7f4e7fc216b4 |  | note | Activity - I
label | 936a4897-8ee3-5bce-9065-679396e2a646 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 7.04.03 - Extraction Top-up Concrete
label | 855fe763-358a-560e-8d4b-d967fb2db87d |  | note | Acceptance / Conformance Criteria - When the temporary casing is being extracted, a sufficient quantity of concrete shall be maintained within such that the pressure from external water or soil is exceeded and that the pile concrete is not reduced in section or contaminated.
label | c46d4b59-9c83-5536-b317-9d5840e69a06 |  | note | Standard / Specification - 51/33669 - 6.1.2
label | 91e8cf00-a949-50f7-ae0d-2fcb5e95b5cd |  | note | Verifying Document - Site Records
label | b9d3fcb2-cda4-5604-a5fa-2dd7d236b969 |  | note | Frequency - Each Pour
label | 95d2bdd8-1812-54c9-acd6-505bb5bc53d2 |  | note | Activity - S
label | ed0040d8-9085-5959-903f-ecf5ff42d7b5 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 7.04.04 - Temporary casing Removal
label | 988914a1-cb12-5931-b484-cf22c04cb9f4 |  | note | Acceptance / Conformance Criteria - The temporary casing shall be extracted whilst the concrete within the pile remains sufficiently workable such that the concrete is not lifted. The temporary casing shall be removed vertically without applying lateral force. The rate of extraction shall not exceed 1 m per 5 seconds. The time at which the temporary casing is extracted shall be recorded by the Constructor.
label | c928a351-b3bc-550f-aaa6-15db11117d5c |  | note | Standard / Specification - 51/33669 - 6.1.2
label | eb364bbc-7f95-5d59-861f-76f4411d0ff8 |  | note | Verifying Document - Site Records
label | 48b91b34-b159-5593-97cf-a8de43b36423 |  | note | Frequency - Each Casing
label | cb5aa913-4962-548b-a2f1-fb6a5d0f3834 |  | note | Activity - S
label | 09b47a8d-d8b6-5e7a-9555-c19d2b889ed0 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 7.04.05 - Permanent Temporary Casings
label | c1a1d0bd-18d7-57ec-a748-6e33a4de436c |  | note | Acceptance / Conformance Criteria - Temporary casings that are in contact with concrete and which are not withdrawn prior to the initial set of the concrete has taken place, shall be left in place and the Designer notified.
label | 5dddc2df-73ba-5cbb-b2c1-4b9a33b7a7c1 |  | note | Standard / Specification - 51/33669 - 6.1.2
label | f3e664d3-8c49-5e33-8808-1f70b502cf1b |  | note | Verifying Document - Site Records
label | 22a50358-06ab-56d6-8671-858b2dc0be77 |  | note | Frequency - Each Occurrence
label | c1723416-0e74-53ad-9661-ec639f64c41c |  | note | Activity - M
label | 68cf90f9-fa0f-5d98-bc2c-3183f4391fa3 |  | note | By - SE
checkpoint-group |  |  | section | 7.05 Concreting in Dry Conditions (Preferred) - (Pile Construction Card)
checkpoint-status |  |  | checkpoint | 7.05.01 - Dry Hole Concrete Placement
label | 62b3cac0-a095-58e1-929e-8693e611d75a |  | note | Acceptance / Conformance Criteria - Where a dry excavation can be maintained and the depth of water at the base of the pile at the commencement of concrete placement is less than 25 mm, concrete may be chuted into piles and allowed to free-fall to the pile base by no more than 5 m and without striking the pile reinforcement cage.
label | 8b1e4cb8-ac50-56a8-a244-bb33a12fcec9 |  | note | Standard / Specification - 51/33669 - 6.5.2
label | 1b57e015-6581-5222-a485-e6001d9dbb4e |  | note | Verifying Document - Pile Construction Record Card
label | 88ca6f0a-d2f6-5d71-abd6-6ae9e9fc901b |  | note | Frequency - Each Dry Pile Pour
label | c27b2a28-78e1-5653-b9ec-3b0576bc6fe8 |  | note | Activity - I
label | 826173a1-dbb9-579a-9ef3-f53ee5021bc9 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 7.05.02 - Groundwater Inflow Measurement
label | 1324a0a9-4ecd-59b1-8999-36b23aca029d |  | note | Acceptance / Conformance Criteria - Unless clearly not significant, the rate of groundwater inflow shall be measured prior to placing concrete. Concrete shall be placed using under water concreting techniques, unless otherwise accepted by the Designer, when The rate of groundwater inflow compared to the rate of concrete placement is such that more than 5 litres of groundwater per cubic metre of concrete could be incorporated into the completed pile, or when The depth of water at the base of the pile at the commencement of concrete placement is more than 25 mm.
label | 32f5a6f1-cc39-511c-8af1-7ab67bb0f09f |  | note | Standard / Specification - 51/33669 - 6.5.2
label | 91374f15-aecf-593e-8666-477fa8e055a5 |  | note | Verifying Document - Pile Construction Record Card
label | 68c65055-3694-5619-9861-e042bd9ab43e |  | note | Frequency - Each Dry Pile Pour
label | a478045e-1194-577c-9cd9-3ffc63c27a2a |  | note | Activity - I
label | a7e96f4a-16bc-5219-aa7f-a30cbd6b2aa5 |  | note | By - PE
checkpoint-group |  |  | section | 7.06 Concreting under water (Alternative) - (Pile Construction Card)
checkpoint-status |  |  | checkpoint | 7.06.01 - Concreting Under Water - Timing
label | c6c539bc-ae4a-562f-839e-e4d8dd0e1b27 |  | note | Acceptance / Conformance Criteria - The time taken between placement of the reinforcement cage and commencement of concreting shall not exceed 4 hours. Reasonable efforts must be made to achieve this requirement. Where this requirement cannot be reasonably met, then the Designer shall re-check pile cleanliness and, if deemed necessary, the Constructor shall re-clean the pile immediately prior to concreting.
label | b95138ef-aa05-5a6a-bf82-e6bff2dd10ca |  | note | Standard / Specification - 51/33669 - 6.5.3
label | 5fcdc5f8-1704-5c4c-8952-8dc50f7db4d7 |  | note | Verifying Document - Pile Construction Record Card
label | 86cb0c06-2a15-559b-b860-715bb0e9cb79 |  | note | Frequency - Each Wet Pile Pour
label | 2492fd97-d063-52cd-94f2-ac268f2e6f5b |  | note | Activity - R
label | 61516f6c-8db9-5d4e-a0ba-322951daf155 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 7.06.02 - Concreting Under Water - Loss of Immersion of Discharge Pipe
label | 49a30648-1d91-5a0f-8d41-bf32d8b38a1d |  | note | Acceptance / Conformance Criteria - When the immersion of the discharge pipe is lost during concreting (for example, to repair breakages or to remove a blockage), further placement of concrete shall not proceed unless The concrete into which fresh concrete is to be placed has maintained its workability, The discharge pipe is re-immersed sufficiently deep into the previously placed concrete, and No water or other contaminant is introduced into concrete that will remain below the final pile cut-off level. If these conditions cannot be met, concrete placement shall be suspended, the discharge pipe shall be removed and alternative measures shall be agreed with the Designer to form a sound pile.
label | e22a870d-a026-5cee-8431-505113072664 |  | note | Standard / Specification - 51/33669 - 6.5.3
label | 04425a2f-b6eb-5a80-8fa3-4b5511a19196 |  | note | Verifying Document - Pile Construction Record Card
label | c5bf0c83-d11a-5f98-8d62-ad5a0d53cf08 |  | note | Frequency - When Required
label | cbac88c8-7fab-526c-b48a-524d777ad298 |  | note | Activity - R
label | cf01d0c6-c28c-544a-9eeb-b4fe0240f271 |  | note | By - PE
checkpoint-group |  |  | section | 7.07 Pile Concreting - (Pile Construction Card)
checkpoint-status |  |  | checkpoint | 7.07.01 - Cleaning of the Excavated Pile Bore
label | 38c11a02-3c9e-54a8-81ce-471eea7fab24 |  | note | Acceptance / Conformance Criteria - Cleaning of the excavated pile bore, as specified in subsection 6.3.1 of this Specification, shall be completed immediately prior to the installation of the reinforcement cage.
label | e2e41ac8-a344-5477-a057-5751edab4a6a |  | note | Standard / Specification - 51/33669 - 6.4
label | 0d61d01d-8fd9-57b6-90fb-d23be82de6e2 |  | note | Verifying Document - Site Record
label | 7842995b-97fb-5763-9e1e-bf5e0f325e96 |  | note | Frequency - Each Pile Prior to the Cage Installation
label | 7b200f6a-da68-5cfb-b668-a9d82fcab025 |  | note | Activity - I
label | 95b3e10d-c25f-5b6d-80a6-ff6d26c1c8a6 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 7.07.02 - Cleanliness State of the Pile Excavation
label | d4826cb3-ac42-5f1a-a524-e4fc88e8f8f0 |  | note | Acceptance / Conformance Criteria - The Constructor shall confirm, prior to the commencement of concreting, that the cleanliness state of the pile excavation has been maintained at the level required by this Specification and no circumstances have arisen that could change the condition at the base of the pile.
label | 8892036b-e34f-5c5c-86d5-54b0d7318edd |  | note | Standard / Specification - 51/33669 - 6.5.1
label | 978a443b-2348-52eb-bceb-916d8e409f67 |  | note | Verifying Document - Site Record
label | cd96e3a9-9b74-5064-8138-3696d68cf2d7 |  | note | Frequency - Each Pile Prior to the Commencement of Concreting
label | 143cb1e9-a1b4-52ed-a721-2138267916c0 |  | note | Activity - I
label | 79174c10-d192-5556-a042-676d55887419 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 7.07.03 - Loose and / or disturbed material during pour
label | 2fe20ea2-9087-558d-a2a5-9ba480105de6 |  | note | Acceptance / Conformance Criteria - No loose and / or disturbed material shall remain along the sides of the pile excavation nor lie at the pile base when concreting is started, nor be permitted to fall into the concrete as concreting proceeds.
label | 70331e86-f8c0-572a-b88d-33df639e8435 |  | note | Standard / Specification - 51/33669 - 6.3.1
label | 42117c6c-c3ae-5013-a37c-e5f79c57d2f5 |  | note | Verifying Document - Site Record
label | 5e291ddd-8458-54c7-8c33-83775db83baa |  | note | Frequency - Each Pile
label | 0220beb3-e755-5d24-9236-85ba691f69ad |  | note | Activity - I
label | 3761ac21-7d7f-592d-abbf-e02232d1293e |  | note | By - SE
checkpoint-status |  |  | checkpoint | 7.07.04 - Reinforcement Cage Cover
label | 4fba85d0-6730-5372-b2a4-c99e41567c51 |  | note | Acceptance / Conformance Criteria - Pile reinforcement cages shall be located centrally within the pile excavation, such that final concrete cover to the extremities of the reinforcement cages is not less than 75 mm at any location.
label | 2184bc44-7569-5198-b3c6-6ac7208c4017 |  | note | Standard / Specification - 51/33669 - 3.8.2
label | caaea375-c24b-535a-9482-24f83dba7f39 |  | note | Verifying Document - Site Record
label | 7bf35785-2028-5539-a472-fe25320c5314 |  | note | Frequency - Each Pile
label | ddd5895c-ac5d-504f-83c0-73a7c4d6960e |  | note | Activity - D
label | ea116a98-d77f-5969-845e-7eba7c9320b7 |  | note | By - SV / SE
checkpoint-status |  |  | checkpoint | 7.07.05 - Pile Head casting Level
label | 3fc2b05f-e039-55b2-b441-5e8c1f27e069 |  | note | Acceptance / Conformance Criteria - The heads of bored piles shall be over-cast by a minimum of 300 mm (concreting in dry conditions) / 1000 mm (concreting under water) above the cut-off levels.
label | b926b74d-0dab-5fe5-b1a9-84d2663b1f86 |  | note | Standard / Specification - 51/33669 - 3.8.3
label | 0d4bf762-8aa4-50e3-8030-be8df7dcf476 |  | note | Verifying Document - Site Record
label | 5995be01-b05e-57dc-9421-63892fbff967 |  | note | Frequency - Each Pile
label | abd92d7d-4b35-501e-a52b-7ee23ab7f07b |  | note | Activity - D
label | c6323108-1de6-5b96-ad75-b772dbc9399d |  | note | By - SV / SE
checkpoint-status |  |  | checkpoint | 7.07.06 - Concreting Timing
label | 6a54d2e5-1c01-58f9-9396-70044e0ed3f9 |  | note | Acceptance / Conformance Criteria - Concreting shall commence in a timely manner following installation of the reinforcement cage to minimise the potential for water ingress and/or collapse of the hole and/or sedimentation on the pile base, all of which could adversely affect the performance of the completed pile. Where it is suspected that these adverse conditions exist, the Designer shall re-check pile cleanliness and, if deemed necessary, the Constructor shall re-clean the pile immediately prior to concreting
label | d88a2aaf-7130-5dd1-84f3-1db0cf6ed9fd |  | note | Standard / Specification - 51/33669 - 6.5.1
label | 7377af0e-f8d2-515b-bdb7-40a3d9dd620b |  | note | Verifying Document - Site Record
label | 7d11ec83-2e40-550c-ac8e-80934eee8f41 |  | note | Frequency - Each Pile
label | 28b0f8e3-39bb-5485-8c63-d34ea9f15fca |  | note | Activity - W
label | 84bdd79a-9eca-5ab6-a730-8305feb1682d |  | note | By - ENG
checkpoint-status |  |  | checkpoint | 7.07.07 - Pile Concrete Compaction
label | efe4eef6-e40e-597d-bf95-05880411c2c0 |  | note | Acceptance / Conformance Criteria - The concrete in the upper 2 m of the pile is to be thoroughly compacted using vibrators.
label | 715f587b-a399-5338-b7ea-32390e00ee60 |  | note | Standard / Specification - 51/33669 - 6.5.1
label | a1603a3a-b4fe-59ba-97e0-5bb8f32c08cc |  | note | Verifying Document - Site Record
label | 1475da9c-fc5b-5951-811d-39500cdd2240 |  | note | Frequency - Each Pour
label | 12ca9708-ee81-52b7-aae5-186d19bd0199 |  | note | Activity - R
label | b1505555-65ab-58a2-8a2b-ed00625d6293 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 7.07.08 - Piling Timing
label | 13539765-fc5b-5f33-8867-5e7a93d537b4 |  | note | Acceptance / Conformance Criteria - The time period between commencement of pile excavation and completion of concreting shall not exceed 24 hours
label | b64b6e06-40ed-5bab-ad46-4305f0559ae3 |  | note | Standard / Specification - 51/33669 - 6.2.1
label | 138e2a23-9ff2-5fac-b6b9-ec97318afe7d |  | note | Verifying Document - Site Record
label | e13cd63d-aeb5-5d50-adde-a652289ea623 |  | note | Frequency - Concreting shall not exceed 24 hours
label | 487c78bd-4859-5603-8a3e-b5a8a72439eb |  | note | Activity - S
label | 00e58708-be81-5141-bcba-4cbdf0512719 |  | note | By - SE
checkpoint-group |  |  | section | 8.02 Concrete Pour - (Pile Construction Card)
checkpoint-status |  |  | checkpoint | General Details
text | ef45372f-57b6-549c-9990-4e326bc1493e |  | textbox | Pre Pour Date
text | 3220756e-8778-5fb8-9138-7a2ef42fb330 |  | textbox | Concrete Strength (mPa)
text | a9fe93d7-9abb-5087-9330-0d8533b04e03 |  | textbox | Volume (m3)
text | 9fc685e5-7cc8-52b5-9cc0-f18ea5eb6df3 |  | textbox | Mix Design
text | a05d4086-9648-54a0-a2d5-2ee7554fbf0b |  | textbox | Additives
checkpoint-status |  |  | checkpoint | Reinforcing has been checked and conforms to the drawings included:
text | be131298-3641-5995-88b5-c582a8ae4b4e |  | textbox | Bar Size & Grade, Lap Lengths, Lap Locations, Bar Supports, Bar Spacing, Cover
checkpoint-status |  |  | checkpoint | 8.02.03 - Reinforcement Washdown
label | 40561549-8ae5-55cf-b36d-333b1ab0af58 |  | note | Acceptance / Conformance Criteria - Washdown all steel reinforcement prior to pouring concrete to remove salts.
label | 6a7d66fb-291f-5316-a93b-4640569656c4 |  | note | Standard / Specification - RSV - CS - 1.19
label | 7ed615a1-736b-515e-943e-c71efa4697eb |  | note | Verifying Document - Pre-Pour Checksheet
label | a13a08ef-670c-524b-b3a0-18077ed09109 |  | note | Frequency - Prior to Pour
label | ef86133f-665d-59e5-9014-dc4e720dbbe2 |  | note | Activity - R
label | 516502a1-74ea-5e59-aeba-8d18d7624734 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 8.02.04 - Pre-Pour Inspections
label | da80ef02-3a46-5b96-a260-0df6ce9ccfd1 |  | note | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
label | 762459af-8126-5299-b08d-fa625de0ec15 |  | note | Standard / Specification - P&G 14
label | 112be8b4-a9cb-5709-b9f8-998e9cea4166 |  | note | Verifying Document - Signed Pre-Pour
label | 0091785c-60a3-57f5-9274-9246da5322f4 |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | 1f2035ac-d78e-5455-a2eb-219fc2a10cd2 |  | note | Activity - HP
label | b8357abc-37ff-5658-a527-caffb5f254bf |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Pour Details
text | 5ee47893-807c-51c1-98bc-da18c5fe8e85 |  | textbox | Pour Commencement Date and Time:
text | d5190f47-aa9c-516f-b3f7-22b4d54c2c84 |  | textbox | Weather
text | 323a899e-c04d-54cc-aef7-0fd1d6dd8b9f |  | textbox | Water level in pile from top - Distance from top of casing (m)
text | e0d5679c-77cc-5454-98c6-1c70a7930050 |  | textbox | Break in Continuity
text | a23ba284-0d8d-59ed-b8e7-923caf83d71d |  | textbox | Tremie pipe to elevation - Distance from top of casing (m)
text | 9156edcb-afd3-5760-8587-5fa79ae16d0e |  | textbox | Concrete top elevation - Distance from top of casing (m)
text | 8561b486-77da-5715-94af-8183e38f3c74 |  | textbox | Actual concrete volume
text | dff7827e-7595-5592-b7dc-b4aded076fee |  | textbox | Pour Completion Date and Time:
text | 155c6f02-01ec-51ec-9c0e-e754bf5c4acf |  | textbox | Casing removal - Date and Time:
checkpoint-status |  |  | checkpoint | 8.02.05 - Delivery Dockets
label | 48732291-cc22-591c-bf91-6bfabb797e41 |  | note | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
label | 10280ae6-b3bb-57fd-8e28-2e0def3ef3dc |  | note | Standard / Specification - RSV - CS - 1.9
label | 5ce0b691-e1ae-558e-b7b5-b5bbddf501fc |  | note | Verifying Document - Dockets
label | 01fe7744-bdb2-548a-87bb-0eebe8b45a35 |  | note | Frequency - Each Pour
label | 7c1c0aab-3fec-526b-a4d1-a63d6f11e031 |  | note | Activity - R
label | cfe53118-c66a-5bdf-bcd2-0116ed13d8a8 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 8.02.06 - Slump Testing
label | 0c036823-60ce-55c1-a5b9-3d2d02343381 |  | note | Acceptance / Conformance Criteria - Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor.
label | 53f5c816-1af1-5043-86eb-4511b6876c8d |  | note | Standard / Specification - RSV - CS - 1.12
label | 7b3d1b06-1fa0-5d63-98b9-fa513e5ba6de |  | note | Verifying Document - Pre Pour
label | 549e655e-8dab-5bca-b63b-2a47bfe15d81 |  | note | Frequency - Each Pour
label | 8f4f4d3d-df33-5cac-a7d5-6444b90f7224 |  | note | Activity - R
label | 7edb9924-27bf-5ef4-b2c1-0cc852faaa11 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 8.02.07 - Compression Testing
label | 92e01c86-8e76-520e-8a88-91e6264d01dd |  | note | Acceptance / Conformance Criteria - A set of specimens for concrete tests shall consist of four specimens from each major pour of concrete, one of which shall be tested at 7 days and the remaining three at 28 days after casting.
label | 3a4957e4-2970-59b1-b9fd-0b847e7f8990 |  | note | Standard / Specification - RSV - CS - 1.12
label | f935990d-ba9b-53a9-b505-c5d158134f2f |  | note | Verifying Document - Test Results
label | 834e2cab-e258-5692-a46d-7e7b4fe80db6 |  | note | Frequency - Each Pour
label | 743df849-7725-50ae-9eac-ff25622e606e |  | note | Activity - R
label | c4991e85-4d48-5ed6-8cd4-3278b209af06 |  | note | By - PE
checkpoint-group |  |  | section | 7.08 Pile Post Pour - (Pile Construction Card)
checkpoint-status |  |  | checkpoint | 7.08.01 - Pile Head Break Back
label | 7dd97f80-c6ad-5d63-941c-664af9ca4e91 |  | note | Acceptance / Conformance Criteria - Pile heads shall be broken back to achieve A slightly convex profile so that the middle of the pile is nominally 25 mm above the average level at the perimeter of the pile and A Type B construction joint in accordance with standard NZS3109:1997.
label | 76a7d506-f925-5f38-973f-fb37effbde2b |  | note | Standard / Specification - 51/33669 - 3.8.3
label | 6af19815-b059-5483-b3cc-4c76115563c0 |  | note | Verifying Document - Pile Construction Record Card
label | 5ae5f125-5f2e-5cf7-b6df-681a35216fa2 |  | note | Frequency - Each Pile
label | bcdac36e-4a13-587f-9471-a5a64fdf2a29 |  | note | Activity - I
label | 2eea5a48-9c44-5912-9ee2-7c93467539fb |  | note | By - SE
checkpoint-status |  |  | checkpoint | 7.08.02 - Pipe Asbuilting
label | 28c555df-d950-5e5c-8772-e98765496b89 |  | note | Acceptance / Conformance Criteria - On completion of pile installation and prior to incorporating any piles into the permanent works, the actual pile locations and verticality shall be confirmed by a suitably experienced surveyor.
label | d08230d4-edf3-5624-b8e2-b946b01113c1 |  | note | Standard / Specification - 51/33669 - 3.7
label | 092f287f-aaaa-52b9-9edd-348ebaa175a1 |  | note | Verifying Document - Survey Records
label | fb80cf73-2715-5535-b44d-4e35ac3e87c4 |  | note | Frequency - 5 working days prior to incorporating any piles into the permanent works.
label | 8a956547-c990-550a-9ce7-7296e77a16e9 |  | note | Activity - D
label | 0da7d8e0-e141-58f4-a90b-4610bd60f2e8 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 7.08.03 - Bored Pile Construction Record Card
label | aac73acd-da62-53e2-b750-e1a72a54ba36 |  | note | Acceptance / Conformance Criteria - Pile construction records shall be submitted to the Designer within 24 hours of completion of any particular pile. Copies of the records shall be retained on site and made available for inspection by the Designer as required.
label | 47ddec57-1f06-5171-8e8b-17acc3138370 |  | note | Standard / Specification - 51/33669 - 7
label | ed04033d-31a1-578d-a5d2-90916fe35011 |  | note | Verifying Document - Pile Construction Record Card
label | f79d4bd8-9ec0-5bb8-a649-954a4d9534bb |  | note | Frequency - Within 24 hours of completion of any particular pile
label | 9613c279-2aa6-591a-9184-ac9a4ee8ba87 |  | note | Activity - W
label | 77badb57-ba27-5c1c-bdd7-823174c6ddde |  | note | By - ENG
checklist-sectioned |  |  | checklist | DS2672-ITP-S102 - Rev 1 - Jet Grout Trial Columns |  |  |  |  | Yes | DS2672-ITP-S102 - Jet Grout Trial Columns - Rev 1 | 6c6b8741-c2d5-40f1-a5d3-911f7aaf10dc
checkpoint-group |  |  | section | 3.01 Site Requirements
checkpoint-status |  |  | checkpoint | 3.01.01 - Construction Pack
label | b8869eb6-2974-5114-9ad3-7761177899f5 |  | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
label | c01b26c4-df7e-5fca-8678-4d7ec13a0d61 |  | note | Standard / Specification - Downer
label | ad715a6f-e510-5d0a-af0c-8c6ffa7c4eeb |  | note | Verifying Document - Construction Pack
label | eea2b2dd-3adf-56f6-84d8-587822ae4890 |  | note | Frequency - Submit Prior to commencement of works
label | d773901a-f047-59b7-98f2-f3d01f48dd6b |  | note | Activity - H
label | da4a65db-cfbc-5268-a896-9e1d8369ab2d |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.02 - Survey Setout
label | b63370e5-5cf1-580f-a4ec-88ea8b6a73db |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | 9c58a725-aa09-5694-9831-77df88feece3 |  | note | Standard / Specification - Downer
label | b35459d2-9c2b-5687-aa50-1ee4bff5d503 |  | note | Verifying Document - Survey Records
label | 2489d652-d3ff-5a53-a203-b522b2adf08a |  | note | Frequency - Prior to Works
label | 367efa8e-37f5-521f-b456-994f5562db4b |  | note | Activity - H
label | 6b30348e-74c7-5b55-8661-855dc00dabbe |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.01.03 - Service Location
label | 09bbe2c2-7885-5f31-9510-fb9dafe4eb82 |  | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | 17788d64-342d-58f1-8cf2-ab2065940058 |  | note | Standard / Specification - Downer
label | 81c4fe83-1907-56ce-9553-4eb131663003 |  | note | Verifying Document - Excavation Permit
label | b0f8069e-10cf-5a5c-b786-7e83c1c88346 |  | note | Frequency - Prior to Excavation
label | e7af6958-4927-56b0-ab63-cbf341558ca0 |  | note | Activity - H
label | 3714d652-cfef-55e6-a019-544c5c792833 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.04 - Internal Permits
label | 68909a69-d858-5c97-a46c-587e54902278 |  | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | 735822d4-c4d3-5e95-881d-97a4f526116d |  | note | Standard / Specification - Downer
label | ca0a8629-c89e-598f-aa86-dcd907eaacae |  | note | Verifying Document - Internal Permits
label | 9ffc016d-144e-5e0d-b916-7a4c4be9231a |  | note | Frequency - Prior to Excavation
label | d6718158-e31d-51d4-8223-d3a4d6d083fd |  | note | Activity - H
label | e313d5b6-59cb-5736-9873-6acbf71c128b |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.05 - External Permits
label | 24134141-83fb-59c6-969f-c1367971370f |  | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | 17208da2-7439-5c64-896a-33c2495ef3da |  | note | Standard / Specification - Downer
label | d55c7e25-c2fc-5974-990b-9932212459e5 |  | note | Verifying Document - External Permits
label | 09731e45-9c41-5b92-b974-cccf039293f8 |  | note | Frequency - Prior to Excavation
label | 890cd651-5762-58af-a364-eeb7bdcd8fbd |  | note | Activity - H
label | 644cb1d7-20cf-5b4c-afd0-89a0bdbd313b |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.06 - Approved Construction Drawings
label | 9e71687c-c9d8-5f23-b7b0-a44f9806ed44 |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | cf0c9679-91fd-5aa0-837e-2b0d974d9a26 |  | note | Standard / Specification - Downer
label | 28e69320-6380-5a7d-949b-c43ffeefa695 |  | note | Verifying Document - IFC Drawings
label | 6eae0ab1-b5ad-5484-8b35-f3f111585022 |  | note | Frequency - Prior to works start
label | 06a78d1d-0001-5ba6-85cf-e303995ec768 |  | note | Activity - H
label | 0f7dbae9-23b1-5f40-899a-efd5efbe1c8a |  | note | By - PE
checkpoint-group |  |  | section | 6.01 Jet Grout Trial Columns
checkpoint-status |  |  | checkpoint | 6.01.01 - Jet Grout Methodology
label | 7d00df6b-8447-512b-a942-4818f107d08c |  | note | Acceptance / Conformance Criteria - Before starting the jet grouting works, a method statement shall be submitted.
label | 4954c7df-8bd9-5dd4-8ed3-11851ecead93 |  | note | Standard / Specification - 14AED/AD4-C - 115.1.11 / 140.5.1.1
label | a7fd506f-6d8f-5694-b050-8fa51e453c58 |  | note | Verifying Document - Method Statement
label | 1e3a7ba0-6163-5158-a7eb-49714daea6d3 |  | note | Frequency - Prior to Trial
label | 319fff97-d17e-50d4-b150-b0924188d9c3 |  | note | Activity - R
label | dc585efc-2be4-5cfd-a879-758b59c8219c |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.01.02 - Supervision
label | 996edaf4-0428-5f5a-8dbc-8e212f1cd6fb |  | note | Acceptance / Conformance Criteria - Execution shall be supervised by trained and experienced personnel.
label | b44b1d9e-2fd1-567f-9759-fbcab9a0785f |  | note | Standard / Specification - 14AED/AD4-C - 140.5.2.2
label | ebec093c-aba4-5b8f-96b7-a43e976c4074 |  | note | Verifying Document - Site Records
label | 04a9f4da-1661-5b6a-a67d-99e9761aceb0 |  | note | Frequency - Each Column
label | f3f2d723-b219-507b-ace6-0bbb47e36e14 |  | note | Activity - R
label | f76ac9fc-5b94-5116-9981-eff73c71a116 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.01.03 - Jet Grout Work Start Notification
label | 5dc748e1-93e5-5ce3-a801-2c74f02fb33c |  | note | Acceptance / Conformance Criteria - Give the Engineer at least two Working Days’ notice prior to commencement of work on-site
label | 17da409c-a0e1-5124-a732-aaf417d5dece |  | note | Standard / Specification - 14AED/AD4-C - 140.1.6
label | c47e0e08-ec41-5d58-bfc8-51bb6282c2f2 |  | note | Verifying Document - Hold Point Release
label | f6ee8fb7-3900-50e9-8223-85e818962bf5 |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | 282f9eb9-28f6-5879-8c2d-a896188a371d |  | note | Activity - HP
label | 200b4e82-a0df-50c5-8ff9-564c194d8cc9 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.01.04 - Jet-grout Onsite Trial Inspection
label | 2a148728-78bd-57f9-b6c9-317bc6c6f29b |  | note | Acceptance / Conformance Criteria - Jet-grout onsite trial away from the dam must be inspected by the Engineer prior to further work being carried out in the area.
label | 271f1c8e-c634-5ec6-96ab-5a8bcff1cf84 |  | note | Standard / Specification - 14AED/AD4-C - 030.3
label | 6114bf65-fe45-580a-bac0-b587d31a0e31 |  | note | Verifying Document - Hold Point Release
label | f36ba862-8632-58d6-b35d-91f583c3e54f |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | 08f82004-5e88-59cf-bcad-2c0a964accaa |  | note | Activity - HP
label | 962d5561-0258-5c88-8c6d-e994544be93c |  | note | By - ENG
checkpoint-status |  |  | checkpoint | 6.01.05 - Trail Location
label | 55cf8c98-ae38-5666-98c8-dd74bb65c7b0 |  | note | Acceptance / Conformance Criteria - The trial location will be agreed upon by the nominated Contractor and the Engineer and shall consist of a single module of at least two jet grout columns to 4m depth.
label | 04a02c67-470a-5d6a-b30f-33873d2c5389 |  | note | Standard / Specification - 14AED/AD4-C - 140.2.3
label | fbb12b1d-624e-5342-a616-49f47494c483 |  | note | Verifying Document - Survey Records
label | f60bb0ae-fa9a-5731-b4d4-e2ff282a4c68 |  | note | Frequency - Each Column
label | ccc93222-eef4-5602-a654-5879e1126e67 |  | note | Activity - D
label | cb598002-26ab-5627-8dbd-0f4f45218ecc |  | note | By - SV
checkpoint-status |  |  | checkpoint | 6.01.06 - Trial Details
label | 1d2f6615-ef54-5f20-8046-ed4faa6201a1 |  | note | Acceptance / Conformance Criteria - Tests will be performed at the centre of the module prior to and after grouting. Where excavation is possible, assessment of the geometric and mechanical characteristics of the jet grout column should be made by visual inspection. Laboratory tests on samples recovered by coring or excavation can be made.
label | 64d6fb56-6dcd-55f4-8c14-189ab1c41dcc |  | note | Standard / Specification - 14AED/AD4-C - 140.2.3 / 140.5.2.3 / 140.5.2.4
label | 79685e3f-2add-595b-8f32-498e605a29dd |  | note | Verifying Document - Trail Records
label | e005a387-a5fd-58f3-b2a3-a5fdf70ce7e3 |  | note | Frequency - Each Column
label | fd2cf483-73c2-5383-86d6-ae659eea736c |  | note | Activity - I
label | cf6a5a6f-d9df-5bb2-a299-1921f9b5922d |  | note | By - SE
checkpoint-status |  |  | checkpoint | 6.01.07 - Trail Results
label | 6dc106e3-eab4-5f45-aad4-787e48cfd24e |  | note | Acceptance / Conformance Criteria - If the trial indicates that the required design parameters has not been achieved, the nominated Contractor shall revise the Work Procedure Plan and re-test.
label | 0248acb4-f69e-56bd-93a3-c14cd02b8ba1 |  | note | Standard / Specification - 14AED/AD4-C - 140.2.3
label | 553b4a85-af3d-5552-9cac-83a3929e8c1b |  | note | Verifying Document - Trial Report
label | b17b6699-db06-54c9-9c5c-5dbd6511cd87 |  | note | Frequency - Prior to Production
label | e216ce5a-3daf-5f4e-958d-2d5394891eef |  | note | Activity - R
label | df799e7c-b12c-5544-8a12-85632a3d2405 |  | note | By - PE
checkpoint-group |  |  | section | 10.01 Site Post Construction Activities
checkpoint-status |  |  | checkpoint | 10.01.01 - Construction Record Compilation
label | 64803cfa-298e-5558-b077-27521ce137c5 |  | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | 019384f9-34d1-5bbc-8856-59d3c0910516 |  | note | Standard / Specification - Downer
label | 0099d855-0310-5f7f-aa89-0376769e3fe2 |  | note | Verifying Document - Records
label | df5e33d3-dc32-5aeb-80eb-7711e16ca2ed |  | note | Frequency - Post construction
label | 94d057dc-9a95-58e3-8ac0-4560e24ac2e2 |  | note | Activity - H
label | eec43fb2-4358-57fe-88e7-627959757af8 |  | note | By - SE
checklist-sectioned |  |  | checklist | DS2672-ITP-S107 - Piling Logging Hold Points - Rev 1 | itp |  |  |  | Yes | DS2672-ITP-S107 - Piling Logging Hold Points - Rev 1 | 9655f28e-1c1d-45cc-a03f-f40c6b47bdad
checkpoint-group |  |  | section | 7.06 Class 2 Pile Inspection Requirements
checkpoint-status |  |  | checkpoint | 7.06.01 - Logging of Spoil Excavation
label | e49a3125-647c-5f83-919e-4f2fbe093712 |  | note | Acceptance / Conformance Criteria - Class 2 – 25% of piles, First 2 No. piles constructed and then at random as advised by the Designer, Geological conditions match ground model and design assumptions. Designer to complete material logging for the first pile for all structures with the Opportunity to complete (at random) for subsequent piles.
label | f4631048-b89e-5455-8d8c-49b31a2ad84c |  | note | Standard / Specification - 51/33669 - 6.3.2
label | 087a7118-c670-5fa4-8518-9f7d9205d8fc |  | note | Verifying Document - Pile Construction Record Card
label | d00ccf1c-6960-544c-98d4-3304e1e72cfe |  | note | Frequency - First 2 No. piles constructed and then 25% at random as advised by the Designer
label | 1778e173-5ac7-5231-9111-969e4acb7667 |  | note | Activity - HP
label | 3ddf61f3-a3c2-596e-8683-abf7a216328f |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.06.02 - Shaft Cleanliness – Video
label | 0fee7210-584b-5525-96dc-4afe0b17c38f |  | note | Acceptance / Conformance Criteria - Class 2 – 10% of piles, First 3 No. piles constructed and then at random as advised by the Designer.[3], Clearly visible along the sides of the rock socket: The asperities or indentations created by the drilling process. Sand grains in the sandstone. No smear or loose debris. Designer to visually inspect the sides of the excavation in the rock socket zone
label | 6edfb1e1-6a98-55f3-9969-cb1207f7c89c |  | note | Standard / Specification - 51/33669 - 6.3.2
label | 6b88d61b-508d-5409-abac-ce8725edcc6f |  | note | Verifying Document - Video
label | 8cdd738d-f19c-580d-b172-118730dee8c6 |  | note | Frequency - First 3 No. piles constructed and then 10% at random as advised by the Designer
label | a73f972d-9b9c-52e5-bfd8-e13967ba5666 |  | note | Activity - HP
label | c4293b7e-d6f3-5251-a836-8383833d67e4 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.06.03 - Shaft Cleanliness – Visual
label | 4b23465f-a6b9-5f83-b9dc-c50210cd3928 |  | note | Acceptance / Conformance Criteria - Class 2 – 25% of piles, First 2 No. piles constructed and then at random as advised by the Designer.[3], Clearly visible along the sides of the rock socket: The asperities or indentations created by the drilling process. Sand grains in the sandstone. No smear or loose debris. designer's acceptance of rock socket cleanliness (where visibility permits)
label | 76f094c6-bb35-5772-88e8-1b7367fe37e7 |  | note | Standard / Specification - 51/33669 - 6.3.2
label | 3660862e-f57d-59a3-bd75-ce524b46f5a4 |  | note | Verifying Document - Site Record
label | 1496a5a3-f4f2-57f2-985f-adf9ada7a395 |  | note | Frequency - First 2 No. piles constructed and then 25% at random as advised by the Designer
label | dd378b7c-5f99-5ca9-aff5-051da0bc36cb |  | note | Activity - HP
label | 5832b55f-8b51-580c-930d-39fcfa89f0a6 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.06.04 - Base Cleanliness
label | 6e6e8bd2-5f43-5d30-bd72-850963c7408c |  | note | Acceptance / Conformance Criteria - Class 2 – 25% of piles First 2 No. piles constructed and then at random as advised by the Designer Average base rating = 1 (for piles cast in dry conditions). Average base rating ≤ 3 (for piles cast under water, i.e. via tremie method). Designer’s acceptance of cleanliness at the base of the pile and confirmation of pile founding level
label | bdd7d81e-4dce-5f2d-9a91-ee354ccb1ed0 |  | note | Standard / Specification - 51/33669 - 6.3.2
label | cce4379d-4757-5431-a196-629c5d82dfdd |  | note | Verifying Document - Pile Construction Record Card
label | 9b42c703-d94b-5237-9713-4c5d1e0f75b0 |  | note | Frequency - First 2 No. piles constructed and then 25% at random as advised by the Designer
label | 7c6e8b10-5801-5ea3-a3f4-d75d2500ceb7 |  | note | Activity - HP
label | aea8928e-abee-5e20-8564-838754781537 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | DS2672-ITP-S104 - Piling Overarching - Rev 1 | itp |  |  |  | Yes | DS2672-ITP-S104 - Piling Overarching - Rev 1 | a0f74a48-2b1b-475c-b516-fdb3a5084ef9
checkpoint-group |  |  | section | 3.01 Site Requirements
checkpoint-status |  |  | checkpoint | 3.01.01 - Construction Pack
label | 346e2db5-c0bf-5e8d-bd57-3b95251cdda2 |  | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
label | 6c42927a-68d9-558d-a633-0024ad4ffc67 |  | note | Standard / Specification - Downer
label | df8d54c8-46fa-5b3b-97d7-f71690761ff5 |  | note | Verifying Document - Construction Pack
label | f3530337-83c4-556c-97f3-3c2bdfe07363 |  | note | Frequency - Submit Prior to commencement of works
label | 5689a612-0582-5f28-9e81-42cbfc0054a9 |  | note | Activity - H
label | 80b7d646-ece6-5cfb-9d0d-55a5cb947313 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.02 - Survey Setout
label | eaabd187-69df-570c-9bc1-51d96b045a04 |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | 195589d5-b3fb-51d9-aa85-3bbb25ac9d0a |  | note | Standard / Specification - Downer
label | d9fdf4d6-a581-5036-b778-83d8214213ef |  | note | Verifying Document - Survey Records
label | 697778b5-7fb8-5767-84f4-0c5547ea4ff8 |  | note | Frequency - Prior to Works
label | 701bbc18-69af-5f12-8a82-6ec3d12a91df |  | note | Activity - H
label | 95496e00-33fa-573b-bbe1-453d7848b9de |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.01.03 - Service Location
label | fdeff3dd-06b9-5011-961f-de6342d9db08 |  | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | f11d3ed7-b2ee-594e-9cb9-d1ee03dd7083 |  | note | Standard / Specification - Downer
label | 41261758-d9e4-5e50-9bce-f79837618e4e |  | note | Verifying Document - Excavation Permit
label | e2ec3fed-97e6-57ad-bfee-bfca875a610a |  | note | Frequency - Prior to Excavation
label | 6298564c-ad5f-5db8-8196-76a3be9a2b51 |  | note | Activity - H
label | 841db883-5b1b-5c79-b0b6-6a40e0aa0219 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.04 - Internal Permits
label | 0bb8f953-a015-50c9-9b35-d7cc39b8dcdd |  | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | e2a988c6-5b35-551b-b123-f06e6ddd705b |  | note | Standard / Specification - Downer
label | e3ad4a47-be95-5669-87bb-9c598e96abe1 |  | note | Verifying Document - Internal Permits
label | 21604141-dac9-593c-9b32-ee14abf9b48d |  | note | Frequency - Prior to Excavation
label | aaead6ab-32b7-5777-9d3a-75f41063f0b6 |  | note | Activity - H
label | f672913b-1bac-55ae-a455-db18678f36f6 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.05 - External Permits
label | bf96bd29-5b55-5458-9f13-c530a6f5b3be |  | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | 22daee59-3fa0-5337-828e-de7a1d3b88f7 |  | note | Standard / Specification - Downer
label | 63182788-32b0-5e7f-90ff-f931a7d9e081 |  | note | Verifying Document - External Permits
label | 96293192-4b31-539c-b635-63a54f171bbe |  | note | Frequency - Prior to Excavation
label | c05892e4-1543-5d97-914b-d0eb013ae87f |  | note | Activity - H
label | f7a49555-29a4-5018-907a-c84f713d2de9 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.06 - Approved Construction Drawings
label | b354b6b6-b8e6-535c-9eae-a27490956dc0 |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | 77ab245f-658a-5c14-91b1-a49a2e6de12e |  | note | Standard / Specification - Downer
label | fbc922fe-9467-5fa3-a1ec-b3f161dfd2e7 |  | note | Verifying Document - IFC Drawings
label | 2738cde6-1c7d-5c5b-8b57-34fa60cb9c49 |  | note | Frequency - Prior to works start
label | 8eec1dae-ecd5-5315-b01f-b88eabbfd27f |  | note | Activity - H
label | bd473cba-c7f9-58ca-9ea9-2220a3c06c2c |  | note | By - PE
checkpoint-group |  |  | section | 7.01 Piling General
checkpoint-status |  |  | checkpoint | 7.01.01 - Method Statements
label | fba7e0db-65e5-55ec-bc77-fdbcb20699de |  | note | Acceptance / Conformance Criteria - A detailed method statement shall be prepared by the Constructor for the Designer’s review for each piling operation undertaken on the site.
label | 4927635a-7739-50c1-ba29-bd6123197376 |  | note | Standard / Specification - 51/33669 - 3.2, 4
label | f866071e-0e41-589b-bb65-b2c57936b1b8 |  | note | Verifying Document - Method Statement
label | 5d4400e7-71b4-5925-80a5-d618c336f597 |  | note | Frequency - 3 weeks prior to the commencement of each piling operation
label | 8c039f62-9ba3-5029-8e81-63bdbda86967 |  | note | Activity - HP
label | 43ebe8a0-63b1-5804-8da8-8be4a1fbcdfd |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.01.02 - Piling Change
label | dc1756ac-63e9-5adc-88fb-1ec3cef60cf6 |  | note | Acceptance / Conformance Criteria - When a change is made to the piling crew, excavation method or other change (e.g. variations in ground conditions) that could influence the quality of the works, the Designer may adjust the inspection requirement and frequency to suit the revised risk profile of the works.
label | 2db6b867-d528-5a6c-8d08-f318cded7f08 |  | note | Standard / Specification - 51/33669 - 6.3.2
label | bdf9bc67-b634-5657-9f54-11d74440f365 |  | note | Verifying Document - Notice
label | c12674f2-d3c3-53ec-b996-750b7cacb4cf |  | note | Frequency - When a change is made
label | 2b6c55b9-2433-53d7-8abe-66b25a541e3f |  | note | Activity - W
label | 2a4213f2-bcdc-59d2-bef5-ca13f4ba9acc |  | note | By - ENG
checkpoint-status |  |  | checkpoint | 7.01.03 - Jointing of permanent casing Inspection
label | c77047ed-d99e-523d-a82a-c90182244eae |  | note | Acceptance / Conformance Criteria - Designer inspection of jointing of permanent casings for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure)
label | 96284439-53a3-51e7-ac89-72ebc4ddc65a |  | note | Standard / Specification - 51/33669 - 9.4
label | e642b34d-02f5-519c-901f-4aa1ff5ac734 |  | note | Verifying Document - Hold Point Release
label | 288188cc-7bc8-51ab-a341-de20bf9ece6c |  | note | Frequency - First pile at every structure
label | 97f7247d-fa45-53d1-af69-b0b616e1c514 |  | note | Activity - HP
label | f8c23caa-e503-5bfc-b8d0-4128f8e76c4d |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 10.01 Site Post Construction Activities
checkpoint-status |  |  | checkpoint | 10.01.01 - Construction Record Compilation
label | fe614163-e272-5e4c-982d-d88e498eed33 |  | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | ba5799da-ca5c-580c-8ac9-d427c7487859 |  | note | Standard / Specification - Downer
label | 295421b1-7052-5fa4-93bf-f71078674123 |  | note | Verifying Document - Records
label | aec0a878-7467-5538-b7a9-5ca4c50f3ff8 |  | note | Frequency - Post construction
label | 8527f43e-556c-5fbb-9cd0-26529bb3a219 |  | note | Activity - H
label | c6844bf0-cdea-59ea-941b-019d536ee844 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 10.01.02 - Survey Records
label | b113f0f9-a0f9-50f1-87e4-65eaada2a53a |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | 5c1b57e2-eef5-54ec-87b7-0829b0d9de76 |  | note | Standard / Specification - Downer P&G 20.1
label | 5c8feecd-278c-5d91-b135-a3bc9071e70e |  | note | Verifying Document - Records
label | 40b34ea5-1cb3-52e5-a904-fdf0569ab5ca |  | note | Frequency - Post construction
label | b1eb2908-7786-5d9d-a1f1-73d4a6bc3cec |  | note | Activity - H
label | 71e6574c-7151-5a8f-afb6-47dd47478951 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 10.01.03 - Redline Drawings
label | db47ba82-8c4d-532e-99da-2c35f879803e |  | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red-pen mark-up copies of the Drawings and Specifications and other design documentation showing any deviations from the specified details and requirements produced in accordance with industry good practice.
label | 7b3b8b66-4758-5083-9a9c-37aa992629fc |  | note | Standard / Specification - Downer P&G 20.1
label | 3d291e19-7fe0-564f-857f-1f1ac19c278a |  | note | Verifying Document - Redlines
label | ec8b47f8-ded7-5bc0-9d88-4c14cff8d53e |  | note | Frequency - Post construction
label | e8e3476d-6b53-539a-992d-f530b40bc01d |  | note | Activity - H
label | f1497ffd-33c8-59e1-8e09-b557fa699706 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 10.01.04 - Defect, Snag and Punch List
label | 244f373f-75dd-53b2-af37-8f2bca64012e |  | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | b0007b84-85b8-597e-84c5-112d1e11c39b |  | note | Standard / Specification - Downer
label | fc3aaee1-2959-5f4b-af93-a4d2577c49ee |  | note | Verifying Document - Register
label | 17be0511-3eca-5141-a977-cbf56ccd1322 |  | note | Frequency - Post construction
label | f6443d82-698f-50ed-acc3-369ec2457d5a |  | note | Activity - H
label | eb76af2b-348d-52f4-9956-4ab9bce5e77d |  | note | By - PE
checklist-sectioned |  |  | checklist | DS2672-ITP-S106 - Piling First Pile Hold Points - Rev 1 | itp |  |  |  | Yes | DS2672-ITP-S106 - Piling First Pile Hold Points - Rev 1 | cd449533-8979-4be7-b381-ed843a91673c
checkpoint-group |  |  | section | 7.07 First Pile at Every Structure
checkpoint-status |  |  | checkpoint | 7.07.01 - Inspection of any Reinforcement Cage Extension
label | 5f8e2c20-0a9a-5cf9-af01-4c80fba840b7 |  | note | Acceptance / Conformance Criteria - Designer inspection of reinforcement cage extensions for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure).
label | 7fb1c168-2b22-5c25-b48f-e0b2d3ed6637 |  | note | Standard / Specification - 51/33669 - 9.4
label | 43b2e865-8206-5e70-bacb-7abaf4b33301 |  | note | Verifying Document - Reinforcement Cage Inspection Record
label | a262f45a-4d85-569e-ba1a-2129872178c6 |  | note | Frequency - First pile at every structure with the Opportunity to inspect remainder
label | 032ebc47-3a3b-5daa-a35a-5c1d3ef6690e |  | note | Activity - HP
label | 7151cd04-e73c-5a5b-8733-52b00d08b4a0 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.07.02 - Inspection of Reinforcement Cages Prior to Installation
label | 8db9f973-4f94-59f7-880e-90477a243b90 |  | note | Acceptance / Conformance Criteria - Designer inspection of the reinforcement cage for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure).
label | c3fe732e-4fb6-5c2a-8c77-a516649efdf8 |  | note | Standard / Specification - 51/33669 - 9.4
label | f7823d23-e00a-5a9b-81b3-b0b7aa2834e9 |  | note | Verifying Document - Reinforcement Cage Inspection Record
label | 593aa2a9-ce42-59ca-9b5b-f094bef210a4 |  | note | Frequency - First pile at every structure with the Opportunity to inspect remainder
label | 364594aa-6158-5b49-adf8-9ada10987c4d |  | note | Activity - HP
label | 9ac61ca7-797a-5aa0-a2fe-5dbc68b6f8eb |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.07.03 - Concreting of Piles
label | 81fc7695-f88a-518e-8179-acaed8f6ee2f |  | note | Acceptance / Conformance Criteria - Designer inspection of concreting for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure).
label | d5f76cce-a2fb-58ac-9f88-4163f59c5556 |  | note | Standard / Specification - 51/33669 - 9.4
label | 91ffc9ea-b7e3-5182-9ef8-bfe6b7b287c3 |  | note | Verifying Document - Pile Construction Record Card
label | 55f84937-0238-555a-8120-fb6784378c01 |  | note | Frequency - First pile at every structure with the Opportunity to inspect remainder
label | 5b93dddd-5dd6-5826-897f-5966b2c8b216 |  | note | Activity - HP
label | df18ad09-4e40-5b03-9d4e-f94db5ccc3db |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.07.08 - Pile Head Initial Inspection
label | c3dcc5a3-5967-5cc6-b805-953846889b8d |  | note | Acceptance / Conformance Criteria - Designer inspection of the pile head prior to incorporation into the connecting structure for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure)
label | 7c25abeb-ccf5-5d57-ada5-08ae53a304a6 |  | note | Standard / Specification - 51/33669 - 9.4
label | 8d30204e-8019-58ee-842d-701fe4115054 |  | note | Verifying Document - Hold Point Release
label | a47a13cb-69a7-59e3-a9a2-ca11af8c4344 |  | note | Frequency - First pile at every structure
label | 5af3fd90-38b2-5ba4-8585-5895d78ea0dc |  | note | Activity - HP
label | 3f94f87e-ca87-569b-8a7d-1411978a6f53 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | DS2672-ITP-S101 - Rev 1 - Jet Grouting Materials |  |  |  |  | Yes | DS2672-ITP-S101 - Jet Grouting Materials - Rev 1 | d23dfd72-9434-4cff-954b-1735b40f6290
checkpoint-group |  |  | section | 4.06 Jet Grouting Materials
checkpoint-status |  |  | checkpoint | 4.06.01 - Grouting Equipment
label | 6b205fe1-f6ab-5575-a144-0d81255fe9f9 |  | note | Acceptance / Conformance Criteria - Jet grouting equipment meet the requirements set out in the specification
label | ee980eab-4d33-5f70-ad3f-32e9108efaf5 |  | note | Standard / Specification - 14AED/AD4-C - 140.3.7
label | ee0ae534-121f-5bc3-abec-55269920da0a |  | note | Verifying Document - Datasheet
label | 1ef8e8a8-d063-5d2f-a78d-56e8678ce515 |  | note | Frequency - Prior to commencement of work.
label | 3089994a-d64c-5c96-8f51-cb91d9d559ac |  | note | Activity - R
label | 644c8413-f9e0-5892-9952-eb4ec6a72f8a |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.06.02 - Personnel
label | 73d9478c-3cdd-5e1c-84eb-adff980c8e4e |  | note | Acceptance / Conformance Criteria - The nominated Contractor shall employ only personnel experienced in jet grouting for this part of the Works.
label | f40756bc-f5d4-5054-b539-78292575166d |  | note | Standard / Specification - 14AED/AD4-C - 140.3.4
label | 61f550fc-c09a-5bf1-a0ef-18b8cdfdbab9 |  | note | Verifying Document - Training Records
label | 720af314-3a4e-5160-b5dc-31959c592355 |  | note | Frequency - Prior to commencement of work.
label | ea2a8cb3-05a6-52fd-bd2b-0f4de82fa70e |  | note | Activity - R
label | 6dc2a66c-6f9b-5d7b-af17-edbed4e743d2 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.06.03 - Grout Mix Design
label | 7ff5b532-81ec-54ca-baf4-7c7d8c06c936 |  | note | Acceptance / Conformance Criteria - The cement grouts shall comprise Portland cement, water and occasionally bentonite or additives as approved by the Engineer. The minimum unconfined compressive strength (28 day) of the selected working columns shall be a minimum of 2 MPa.
label | a5496a32-74f7-5e29-b7d3-561a2a85102e |  | note | Standard / Specification - 14AED/AD4-C - 140.4.1
label | a5ea86e1-ed28-5d42-bc28-cfcd1cffee8b |  | note | Verifying Document - Approved Mix Design
label | 5bee8560-daa9-509c-b2d8-4caf3aae30db |  | note | Frequency - Prior to commencement of Trials
label | 446b9b27-49aa-5462-bd2e-8fe1975abe91 |  | note | Activity - HP
label | 87ae4b3e-e981-5fbc-80d7-750612ff3e3b |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT