## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 42c8acff-71af-4fb9-aea4-30fa0b4e2efe |  | checklist | ITP-025 - Platform Concrete Footing |  |  |  |  | Yes | ITP-025 - Platform Concrete Footing | 008bba88-d761-468c-a1a2-898ddb32f0f9
checkpoint-group | 41ca733f-34da-4447-bd2b-a38816e32f29 |  | section | Preliminary Works
checkpoint-status | 0cf5f343-70e5-4d90-ab04-3b0a1b146991 |  | checkpoint | 1.1 Check for Correct Documentation
label | 6a36c141-8362-57de-baf0-a15b4a1f93ce |  | note | FREQUENCY: Prior to Commencing any Activity
label | 80313078-903e-5930-8aec-327d1c284dcc |  | note | ACCEPTANCE CRITERIA: All employees and subcontractors shall have the most current and complete set of drawings
label | ddc2d1fa-cb8b-5513-bfed-2453a32bbb92 |  | note | REFERENCE DOCUMENTS: Design Drawings and Register
label | cd78cdc5-e5b5-5bd7-bf97-8ad132a7d8ca |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | a47b013f-027c-5e57-9494-d0fe92cb2368 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | fa9514f3-778b-5d93-9e8e-dca761d41800 |  | note | HP*
label | 6ada61db-0340-5e44-b377-86f5f78b542f |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 70fc659f-12c2-5ee4-be4c-a5d6495713f0 |  | textbox | Date Completed:
checkpoint-status | 9f97b57a-11ef-4dfa-84e5-a84b321a6eec |  | checkpoint | 1.2 Implementation of all measures and controls
label | ad20030e-946a-5a72-b52d-4d3ced538247 |  | note | FREQUENCY: Prior to Commencing any Activity
label | 65eb5c25-3647-5f8f-a6a6-c692ce081e0a |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including; EMP, TMP, PSP, JSEA, SWMS & WP
label | e564021e-1ee5-5c85-9518-4a921f532fac |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | e0cd75ef-ed59-5e26-a8dc-89fb62136bc3 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 884cd2bf-9f1e-5def-bca3-4adf8c634bcb |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 82a1edca-041a-5855-8b2f-9ad0dddedef3 |  | note | HP*
label | 80d37b3d-695e-5728-b2da-189091ac09f1 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 9b4237d2-c1c3-5b33-9ba5-723773d6bd0a |  | textbox | Date Completed:
checkpoint-status | f0a30300-e7e0-470e-841f-82b57e9c38b3 |  | checkpoint | 1.3 Setting Out
label | cb46810c-7805-5f65-be53-d5a2cfab48ca |  | note | FREQUENCY: Prior to Commencing any Activity
label | 26d21657-ec54-526a-a40b-ecdfe75de39e |  | note | ACCEPTANCE CRITERIA: Ensure that position of footings has been correctly identified according to design drawings
label | 67ab7e21-dbbe-5636-9f61-163e05571f15 |  | note | REFERENCE DOCUMENTS: Design Drawings and Register
label | cb790f6c-5704-53a5-b5f1-3f4abe1b0fe0 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | b804c4e1-55cb-51b5-882a-5fa89808c433 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | d9f29269-e0df-507d-850a-ec1af5f53b63 |  | note | IP
label | 4741c425-5531-5d83-8dec-d75e231ea5c9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 42612588-b5a6-5bfa-87d6-2a3ecab7d243 |  | textbox | Date Completed:
checkpoint-status | 5e0b5595-ce2a-4b88-a878-ae48ccf0f3d0 |  | checkpoint | 1.4 Material Check
label | f8c4c644-f58e-56ab-8c16-8b7766ab9a48 |  | note | FREQUENCY: Prior to Commencing any Activity
label | 21c25a39-6622-5cf8-bbdc-f406f7078129 |  | note | ACCEPTANCE CRITERIA: Ensure that materials have been correctly ordered based on the intended use. All bolts shall be hexagon head class 4.6, unless otherwise stated. Ensure bolts are of specified length and grade
label | 8df893d0-2363-59d5-935f-2b76a8da71cb |  | note | REFERENCE DOCUMENTS: STD T6100
label | 98f5744d-9217-5ac5-88c7-965326325ce4 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | a9d0ce9b-4e3c-5ee6-b07c-c5a02ca7722c |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 9fbeaa8e-a2a2-5b1e-b3b2-c213d077ceb1 |  | note | IP
label | ca7ada39-27d7-54cd-b736-0171d1a2ebfa |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | fbcd0aa7-2b13-545e-a5f5-658d0446137e |  | textbox | Date Completed:
checkpoint-status | 9e2d8971-fc81-4aa5-b96c-4c6f6b87012c |  | checkpoint | 1.5 Concrete Slab Check
label | 71d5d95b-f1cb-5c10-8152-56522d8ac720 |  | note | FREQUENCY: Prior to Commencing any Activity
label | c53b3eb5-d0e4-562a-a204-69e44d092de7 |  | note | ACCEPTANCE CRITERIA: Ensure recess has been provided in concrete at location of footings, ensure recess is to correct depth. Refer to Adshel specifications
label | 36554759-e1d1-518e-9b72-79c2a107f4d3 |  | note | REFERENCE DOCUMENTS: STD T6102
label | c4908493-ec9f-5216-8b0d-68c73a19e4de |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 66540f13-57bd-515d-aa76-397f98a84bd1 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 352b4413-7a34-5f6a-8330-fddee7cd60d6 |  | note | IP
label | b0c23e8c-d3c3-5c88-8976-2b22250514d9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 60688346-c119-5a5e-8482-2996e1675adc |  | textbox | Date Completed:
checkpoint-group | ca8baaf7-6371-4eef-aaa7-3bb3bf0c063b |  | section | Construction Works
checkpoint-status | 422be50b-fec9-4e50-90d4-32506f06ba14 |  | checkpoint | 2.1 Bolt Installation
label | f69eb442-c6f0-5b65-a166-e30bcf58ab44 |  | note | FREQUENCY: Each lot
label | 98f85a62-2937-57de-95a7-43fd31e9b20c |  | note | ACCEPTANCE CRITERIA: Install bolts as per specified minimum anchorage depth. Ensure anchorage procedure conforms to standard"
label | 8afe35c3-22fc-5302-b743-72f91ff2bf33 |  | note | REFERENCE DOCUMENTS: STD T6102
label | 93232f4c-0842-5a56-998c-762fae90c427 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 46eade24-def5-53ef-b7e8-62c81383e06d |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 58857e25-c735-582b-aaf8-92035f3df3bb |  | note | IP
label | 86349776-bd7c-5e26-97bc-d7b7c5af79ed |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ed8afd91-2676-5a20-9676-adcf55007aa3 |  | textbox | Date Completed:
checkpoint-status | 29c34348-5f14-48f6-8b3f-6f68463d4392 |  | checkpoint | 2.2 Placement of non shrink grout
label | 1d4dee20-e96f-5d9b-9552-a9d195b8a2c9 |  | note | FREQUENCY: Each lot
label | de240681-251e-529a-a69b-e4fb94f3a18b |  | note | ACCEPTANCE CRITERIA: Non shrink grout shall be placed between concrete pavement and base plate, at thickness >35-75<mm
label | 83d01077-2aef-52fc-b77e-4eda79a6e9db |  | note | REFERENCE DOCUMENTS: STD T6100
label | b8da7315-8f16-54f7-bb52-6dac8b6e2aaa |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | dc09ed1e-9319-54e1-8ed8-d64ead867202 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 33aaed3a-9e87-56d0-b48a-d057a1e9af65 |  | note | IP
label | 0680d148-37c4-5b87-9968-7cc2dc3794e1 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 4627ba81-1703-586b-ab8d-33ddc4998cd0 |  | textbox | Date Completed:
checkpoint-status | 687084c7-c21f-4bdf-ab21-6baf6640c9f9 |  | checkpoint | 2.3 Placement of Grout
label | 20f14e68-7de9-5764-9a03-5caa40251058 |  | note | FREQUENCY: Each lot
label | 14e09f59-1586-57c0-91eb-8613c916f250 |  | note | ACCEPTANCE CRITERIA: Grout shall be placed as to fill the gap between baseplate and level height of concrete
label | 5aca15db-53a1-540b-b729-95028f89a9f1 |  | note | REFERENCE DOCUMENTS: STD T6100
label | e43cf61f-0cc5-5989-9dca-aa1ca12af140 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 91009604-3842-5c1c-8b93-6a47b72a5c07 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 4cc2a084-bef2-5486-af6d-906cbee14e27 |  | note | IP
label | 7645155d-9b39-56de-839e-ce1f1292033a |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 7417d717-42b4-5697-a78e-9edd4a52daf2 |  | textbox | Date Completed:
checkpoint-status | dc8e77d7-4cda-497b-b574-61c1ad9dad47 |  | checkpoint | 2.4 Pavement (if required)
label | d3254f0b-225a-5bfa-9b08-3b343fb9ebf6 |  | note | FREQUENCY: Each lot
label | 63f41f09-7f56-5036-8afb-b53bdc17daf5 |  | note | ACCEPTANCE CRITERIA: Minimum depth of specified pavement shall be 50mm, ensure the bolt assembly is not covered by pavement
label | c1fd2181-cbfa-5069-a546-1b5d11a3eada |  | note | REFERENCE DOCUMENTS: STD T6100
label | 053188d2-1cfe-5848-909b-ea3986ae52cd |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 77169c7f-cbe5-5d44-9eca-fac25dc32b24 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 9d34ae26-5120-5c0b-bd17-600f98d80b56 |  | note | IP
label | 47cbe41a-7762-5efe-b26e-2b2b7a69b6bf |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | f30b7946-61df-51d9-8b19-e0b875b59575 |  | textbox | Date Completed:
checkpoint-status | 0077eb53-bb02-4057-b92e-2be723e92f10 |  | checkpoint | Final Inspection
label | cb786e83-fd78-501b-9d58-5708e7634fe0 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | d5deb707-ab10-52c4-95ef-ca97eec9d8cd |  | textbox | Print Name:
text | e8daf0df-a571-575e-90ca-acd52e0df1c3 |  | textbox | Position:
text | 76b7f067-1ecd-559f-bd03-a554293f44a1 |  | textbox | Date:
checklist-sectioned | ef9adb73-4025-4c46-b76c-9fd74476ae5e |  | checklist | ITP-009 - Site Survey |  |  |  |  | Yes | ITP-009 - Site Survey | 080f9f8b-ab9f-42dc-b5c2-114f343f207b
checkpoint-group | 27d38ee6-7096-4ac2-a0d6-39853269658e |  | section | Preliminary Works
checkpoint-status | 958b804e-2684-4468-bef7-5939180f8782 |  | checkpoint | 1.1 Check for Correct Documentation
label | ff6ace04-9922-546d-8976-3e06dc5ee2bc |  | note | FREQUENCY: Prior to Commencing Any Activities
label | 60129060-88e2-5013-8ff1-448c1ec17ca0 |  | note | ACCEPTANCE CRITERIA: •Ensure that all employees and subcontractors are using the most current and updated complete set of drawings
label | 7e1bbb17-09b5-58ee-9024-bdacb5168d9f |  | note | REFERENCE DOCUMENTS: Design Drawings and Registers
label | 27c69a3f-4567-5811-9a9a-1ba7e2999558 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 2ac2d28a-8b83-52ef-b5be-fa191013505c |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | db8480bc-a597-58b1-ae1a-7d8acc0c0eaf |  | note | WP
label | 86a70e5d-98c3-5dbd-899d-ce9e77937000 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | a70d21b5-cceb-550f-99e4-646b8b8f1d95 |  | textbox | Date Completed:
checkpoint-status | 56b8f698-22bf-46ac-b13d-32951dafca24 |  | checkpoint | 1.2 Implementation of All Measures and Controls
label | c1cd39ed-c47a-52fe-a314-dd4a369c79ec |  | note | FREQUENCY: Prior to Commencing Any Activities
label | 6d5ea1cf-06f6-5c57-b5b8-f3207b68b1a3 |  | note | ACCEPTANCE CRITERIA: •All necessary measures and controls are implemented, including: SWMS, WP, TMP, EMP, PSP, PMP and QMP
label | 4ea6ee31-211b-5fae-8c7e-810064e214c8 |  | note | REFERENCE DOCUMENTS: SWMS, WP, TMP, EMP, PSP, PMP, QMP
label | eeeb9014-3641-5e03-8e56-9c325ea6864b |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 93a08f4a-41db-5d26-9b1c-074ef7b7133b |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 457921e1-5219-50d8-b6ac-2c6a5ba3527b |  | note | WP
label | 2715a98e-dabf-5342-869e-0f7b86f95ea3 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 3796228a-6e73-5600-a5f7-4c947e7d597b |  | textbox | Date Completed:
checkpoint-status | 71c9df2a-1cf5-4f55-8898-1ace8a255d20 |  | checkpoint | 1.3 Confirmation of Design Drawings
label | c7766e33-6cdd-5013-8390-2fc8e141e342 |  | note | FREQUENCY: Prior to construction activities
label | a013b26a-5341-5d88-ba78-08a90af967bd |  | note | ACCEPTANCE CRITERIA: •Surveyor shall validate RL points, kerb, pavement, platform and track dimensions, measurements and levels specified in design drawings based on bench marks and control points specified by superintendent •Superintendent shall be made aware of any discrepancy between design and actual values
label | eaac8b96-084a-5bfc-8db4-a9e45c241dbc |  | note | REFERENCE DOCUMENTS: Design Drawings and Registers TS 1313 cl4.2.5
label | 45ceb344-1bf8-51c6-bbd2-cc90944c93dc |  | note | INSPECTION/TEST METHOD: Verify
label | 02128d6e-618d-5b72-8cd3-1312eb548425 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 8258a5dc-8b3f-59a2-babe-f33d1c7b54e3 |  | note | HP*
label | 1a5ed7b3-c3c0-57e0-909b-b79c474ee4ac |  | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
text | 77e89f07-c37c-526e-bf0c-1b3d9533fe77 |  | textbox | Date Completed:
checkpoint-group | 2febd351-12b5-4af4-94d9-e341bfecfdee |  | section | Construction Works
checkpoint-status | 89ec485e-d888-469f-917f-68e738907db4 |  | checkpoint | 2.1 Set Out
label | 778ed5bc-3017-55e6-8370-02eab34ce32a |  | note | FREQUENCY: Prior to start
label | 33a63fee-2847-533c-8538-c54a0e862ef7 |  | note | ACCEPTANCE CRITERIA: •Tramway track shall be set out to an accuracy of +/- 3mm, based on bench marks and control points specified by superintendent design drawings
label | 8cb9ba7e-ae21-5a6e-ab91-a8a6a83a3a84 |  | note | REFERENCE DOCUMENTS: VRIOGS 005.2 Pt1 cl4.0
label | d521a8f7-4b42-5d8f-ae67-8b95f357bdac |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | a87a3f09-3a2b-517c-a64f-ec2e70d8e8cb |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 4fa5fdf7-337d-5206-9e00-016933d7a618 |  | note | IP
label | bbe692c8-b801-5f56-b645-89e7afdcb770 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ce0de9f7-cfba-505f-8584-8eda970eb2b5 |  | textbox | Date Completed:
checkpoint-status | 2d9a987b-76a2-4856-a98a-cb2bc7586075 |  | checkpoint | Final Inspection
label | 05f25f34-af5e-594a-a75b-bf1401819c15 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | f66262ef-f319-5007-b503-3ead941c7393 |  | textbox | Print Name:
text | 6591a265-f154-5da5-81e1-8318aa7efc4a |  | textbox | Position:
text | 6cc3d668-f717-5684-9642-64a5624e2de5 |  | textbox | Date:
checklist-sectioned | feaccad0-1cc6-4852-b305-10633d349c6e |  | checklist | ITP-019 - Fencing Installation |  |  |  |  | Yes | ITP-019 - Fencing Installation | 0cf8f201-382e-45c2-9d26-833586929976
checkpoint-group | 4a42966f-d30b-4e74-80d8-628c0857a678 |  | section | Preliminary Works
checkpoint-status | aba07417-a9fa-4b0d-9419-7a41a5e10222 |  | checkpoint | 1.1 Check for correct documentation
label | 86fde12f-5661-568a-a3df-36093d4a7645 |  | note | FREQUENCY: Prior to commencing any activity
label | 790bbcc5-870b-500e-95f0-51685ba38c79 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
label | e30f1a54-fc0f-52c1-9bcc-3b9d0bc7af30 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 39f9a67f-3453-5f8e-a8a3-0e25ac221937 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | fb67d309-1a47-5ed6-a6b4-936dc3c1951a |  | note | RECORD OF CONFORMITY: This ITP signed off
label | a92c3aac-bf91-5a0b-a83e-43fc7c3efaf4 |  | note | HP*
label | 58ef852f-1386-5cb2-a0c7-ebd63118066e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | bc6760f0-d553-591b-909e-35db646f8f1c |  | textbox | Date Completed:
checkpoint-status | 39d5b15b-3a73-4bc2-b531-2c232f638ad8 |  | checkpoint | 1.2 Implementation of all measures and controls
label | e61787cd-986a-5b1e-83ad-acb6027d00be |  | note | FREQUENCY: Prior to commencing any activity
label | cdb43d3c-e5e5-5f75-8ec6-a6f5c8598c02 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | 3037b6ce-4972-5164-9635-d013b4e09f6f |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 0323f1e8-eae6-5808-9cd4-68a11c805e68 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 2a7aae24-1d7a-5cf1-ba4b-190ba749da4c |  | note | RECORD OF CONFORMITY: This ITP signed off
label | ac0e4a7b-cecf-5973-9df8-4be7888d0df8 |  | note | HP*
label | 4abdf5c3-9d8e-5f7a-95f1-a575878377ff |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 8a1ffe2e-5909-5aab-9ebc-4ed864513bbf |  | textbox | Date Completed:
checkpoint-status | 3c0aec95-6a38-49c5-9b6a-5cfaa6bd3518 |  | checkpoint | 1.3 Check Materials
label | d4f7c5de-adf6-52e2-b396-1df50a565327 |  | note | FREQUENCY: Prior to commencing any activity
label | 9d1b317a-8f11-5209-8556-3dfdc605ebf4 |  | note | ACCEPTANCE CRITERIA: Confirm manufacturing process with supplier, fencing material shall be laser cut with clean finish, linished, pickled and electropolished. Welding shall be in accordance with AS1554. Ensure all components and fastenings are procured to the materials, sizes and grades specified in STD_T6000
label | e62792f1-0920-5a3c-b412-137e40f5e936 |  | note | REFERENCE DOCUMENTS: STD_T6000, CE-021-ST-0012, cl 4.3.1.4
label | 8349d94e-5b0b-58b1-8201-a973a4eff7f1 |  | note | INSPECTION/TEST METHOD: Verify
label | a8069f06-f02b-5205-a94a-620353aaeba5 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 024921b1-926b-5578-adb3-ab6c8988afd4 |  | note | HP*
label | 4021779d-0ec2-5564-bbc1-4779540072fc |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 21941661-f36f-5959-83ae-9dcb0889f2a4 |  | textbox | Date Completed:
checkpoint-status | 6ecc4b94-46aa-4405-9539-5ea73adfdafd |  | checkpoint | 1.4 Confirm Footings position
label | 119b20df-c82b-5572-a8a6-8f74fa74330b |  | note | FREQUENCY: Prior to commencing any activity
label | 4b0c3afe-1076-5efb-bf26-4834be217a75 |  | note | ACCEPTANCE CRITERIA: Confirm footings are set out to locations specified on design drawings
label | 1f2a5d57-7c0d-54ad-9c8a-777f1427277b |  | note | REFERENCE DOCUMENTS: Construction Drawings
label | db3b173d-e600-5af0-8b8f-57ce054d1b64 |  | note | INSPECTION/TEST METHOD: Verify
label | 7d00e8e7-cfd1-5916-bebf-43e9df0ec90c |  | note | RECORD OF CONFORMITY: This ITP signed off
label | efc3b4c3-42a4-5bac-8ffd-91e6f8f79b24 |  | note | HP*
label | a287fe8b-ca5a-5123-8eb7-099b5b298218 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | c567e8bf-6014-5b36-986c-2a6c8bdae3b3 |  | textbox | Date Completed:
checkpoint-status | 0d662e65-602e-4cb4-8fcd-f966f812bd1a |  | checkpoint | 1.5 Bonds
label | 0824e45e-faf1-54bf-a5e9-05332fc4812a |  | note | FREQUENCY: Prior to commencing any activity
label | abaeef60-6b3b-541e-86a8-1c999bfa6af5 |  | note | ACCEPTANCE CRITERIA: Ensure fencing is isolated and earthed to achieve electrical isolation. Lug shall be fitted to baseplate at specified fencing location
label | 67cab031-5460-511b-b332-1b781443aaf9 |  | note | REFERENCE DOCUMENTS: STD_T6000
label | a0d1634e-2e93-5b83-ad16-f526a88a8f2d |  | note | INSPECTION/TEST METHOD: Verify
label | 6a0992a3-606e-534e-a697-9fa908b19acd |  | note | RECORD OF CONFORMITY: This ITP signed off
label | d5861211-1759-5f22-963c-e5a239fa3b73 |  | note | HP*
label | 11c6fdfd-9856-503d-97d0-d581a1d34157 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 924a1afb-4bb2-58d5-971c-190b794bb827 |  | textbox | Date Completed:
checkpoint-group | 7d1e8369-e34e-4757-955a-bdd3f66716c9 |  | section | Construction Works
checkpoint-status | 5cf3a7e8-5d12-4fd9-893a-7b79a38ed373 |  | checkpoint | 2.1 Footing Installation
label | 530bfb72-3729-511b-8052-f3d982c87b0f |  | note | FREQUENCY: Prior to Asphalt
label | 704d4e59-b220-5ee6-b75a-6ad49118df71 |  | note | ACCEPTANCE CRITERIA: Concrete shall be of minimum strength N20. 4 M16 hot dipped galvanised bolts shall be chemset 175mm into embedment, per footing
label | ad8c0df6-4c16-5ae5-8d6e-f3afdaaeff09 |  | note | REFERENCE DOCUMENTS: STD_T6002
label | a7f280b7-7fc3-5f5c-a7b4-2e7a1224292a |  | note | INSPECTION/TEST METHOD: Verify
label | b49f42e4-f631-50e8-afc7-a131a343d2a3 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 0a682e0b-3ec2-558d-9c14-c9b0a9ba5de9 |  | note | IP
label | eb1ceb8c-bd89-5f7c-b8cf-d6a1080ff909 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2d42928e-883a-56c7-9a51-f4bbc566137e |  | textbox | Date Completed:
checkpoint-status | 7fcc8f7d-1b57-4ab2-ac1f-fcca80c31ead |  | checkpoint | 2.2 Post Installation
label | e91b5e1e-4cf0-5776-877f-86dc8eaa582d |  | note | FREQUENCY: Each Lot
label | 12e277d0-2c90-5545-ba21-bd35fed3cd3b |  | note | ACCEPTANCE CRITERIA: Post shall be installed to designated height and level. Installed to footings with bolt assembly. All bolts shall be insulated from base plates, using non metallic sleeves and washers. The top of fence base plate shall be level with surrounding pavement.
label | 3a4effde-9177-5ca0-94fc-a3040553d95a |  | note | REFERENCE DOCUMENTS: STD_T6002
label | 153cc8b7-f8d1-5ecb-9ed0-2b69d63a01d5 |  | note | INSPECTION/TEST METHOD: Verify
label | cfb389bd-85db-536d-867e-b80081af4143 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | a363507f-a075-5110-a4a4-e63c5deb26bf |  | note | IP
label | e4ea7d3a-812b-5317-8b03-5991acae9399 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | fe4c4abf-f176-54af-885f-81902b63b048 |  | textbox | Date Completed:
checkpoint-status | 2884354c-6021-46dc-bfea-6226b6d2392a |  | checkpoint | 2.3 Grout Installation
label | 815ec29e-c34c-5b13-8cf6-076ab75cf170 |  | note | FREQUENCY: Each Lot
label | f0ef7231-df0c-5776-9e7e-fc5cc838ff9d |  | note | ACCEPTANCE CRITERIA: Footing surface shall be cleaned and roughened before application. 50mm of Non shrink dry pack grout shall be placed under base plate
label | 576e5f0a-7aff-5280-aba7-e9fd972b3080 |  | note | REFERENCE DOCUMENTS: STD_T6002
label | b621e1ce-8a3d-5ca9-bdad-9a8694d3f8c4 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | f66e8eae-6b03-568e-b3c1-e7926eb5b475 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 63be8778-224d-5bda-92af-996de4b2989b |  | note | WP
label | 63d168ea-ee15-576e-98bd-67b4f6a5ad19 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | c2d01ad0-1d7f-5a32-868d-e994d13a5c22 |  | textbox | Date Completed:
checkpoint-status | c7610ba6-d217-4480-ab75-46866c30c725 |  | checkpoint | 2.4 Continuous Handrails
label | f83684e5-5b78-5aff-b474-e47fd2d260eb |  | note | FREQUENCY: Each Lot
label | 1bd5f1df-9e65-5459-a34b-9a8b91e35988 |  | note | ACCEPTANCE CRITERIA: 5mm cap plate on handrail returns. All sections to be welded as per AS 1554. All sharp edges and welds to be ground back to smooth finish. Domed buttons to be welded on top of handrail 150mm from the post centreline.
label | ac8a3f30-b8a5-5b4e-8723-3451c4e5efe2 |  | note | REFERENCE DOCUMENTS: STD_T6001 & T6002
label | e0f42eb1-9502-589c-9e0e-7ceb0ad4b6d8 |  | note | INSPECTION/TEST METHOD: Verify
label | 7d4259b4-64e9-5d61-9708-2130d18b6322 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 24719845-0f5d-5dbc-a6c1-456eb527d3a6 |  | note | IP
label | c0aa6569-652c-59b1-8226-6a8a4e311f32 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | e0c9178f-5e96-5a11-a91c-20dee2942434 |  | textbox | Date Completed:
checkpoint-status | a0ddcf8d-d95c-490f-a76b-cef4546e7154 |  | checkpoint | 2.5 Wire Rope Tensioners
label | 4f0a7ef7-c213-5298-94f8-f2a9abeb90e9 |  | note | FREQUENCY: Each Lot
label | 562a3c3f-1700-5c61-aa94-b4df2f78dba3 |  | note | ACCEPTANCE CRITERIA: Architectural wire rope cables to be inserted into ferrel on fence post and to be tensioned with tamper proof fastenings (Loctite 243 Threadlock)
label | 9c8eea9b-d819-5d49-9fb3-3224faf7ade2 |  | note | REFERENCE DOCUMENTS: STD_T6000, T6001 & T6002
label | 168a2387-8ca4-559e-bc90-151c5ceb1219 |  | note | INSPECTION/TEST METHOD: Verify
label | d2d139c7-d47c-5289-a6ab-fcb1c34e7515 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | afb2e819-fee4-5464-b62f-1cb3f1d537c5 |  | note | IP
label | 42bd34b4-c022-548e-b0be-64aad8546e64 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 885fdd8e-5f5e-55e8-a44f-e962c1d9ec7f |  | textbox | Date Completed:
checkpoint-status | 2fdf12ee-2167-4bdd-9472-05524417183a |  | checkpoint | Final Inspection
label | ad178de0-99db-537a-a948-ddedb327fef3 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | bf42e633-c6ad-5391-899e-322476b1386c |  | textbox | Print Name:
text | 703c9e86-6dc3-5af9-9577-2ec2f819ea6c |  | textbox | Position:
text | 9846a06d-672a-5758-93aa-65a24ca508a1 |  | textbox | Date:
checklist-sectioned | aaa6dbf5-cf25-4126-9ef5-dd082805c45c |  | checklist | ITP-014 - Bluestone Kerb Installation (MCC) |  |  |  |  | Yes | ITP-014 - Bluestone Kerb Installation (MCC) | 10a57480-4151-4077-a8ae-2511ca4b6d6e
checkpoint-group | 2823aaee-1362-4792-93f9-179a7c3f7d3b |  | section | Preliminary Works
checkpoint-status | 7c0e8567-8c47-48d5-99d9-faceb15a0103 |  | checkpoint | 1.1 Check for Correct Documentation
label | 88036de9-7ada-5464-85b7-b679c7e3891e |  | note | FREQUENCY: Prior to Commencing Activity
label | b2e6c174-701c-571c-b0a8-4c8e5c56b2d5 |  | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | 38302d59-ddc4-595f-ba4a-9b2aa8397ce4 |  | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | 751797ce-b577-5ce9-b69a-db4d45c15c41 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | cce78733-5588-50de-be57-50ac3789ce18 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 49c3a646-1df9-5add-8228-e5d47f6900e5 |  | note | HP*
label | de51f12c-4f08-5e02-9e77-a6f4f6da252b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 34bbfe26-e321-57c4-90a9-ee8b55c5af20 |  | textbox | Date Completed:
checkpoint-status | 7320f1d3-a27f-43e8-b34f-de1de9ba4123 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 361113f3-84fb-5b87-82eb-4c9b21544828 |  | note | FREQUENCY: Prior to Commencing Activity
label | 708cbc8d-fb46-5a50-8943-1ba09fae27d4 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | cb7fb956-6921-5cba-8bb0-d65aa8d29927 |  | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | 413db448-f729-5032-9a80-1b844c1929e6 |  | note | INSPECTION/TEST METHOD: Inspection
label | f8d6e1f3-caa6-5ddb-9083-dddb67d69860 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | a8bde62d-497b-5cb1-8435-e3534d0c440c |  | note | HP*
label | 640d0896-6e76-57fb-8c09-feb4c2d5739b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 3be7282b-72d7-5eea-a59c-f62a599a390c |  | textbox | Date Completed:
checkpoint-status | 1a1d61a1-7b17-420d-a14d-96fbb268e9b9 |  | checkpoint | 1.3 Existing Bluestone Kerb Demolition
label | 30f6f458-e137-5c4d-ade4-8e5225257661 |  | note | FREQUENCY: Each Lot
label | da606d4e-055f-5ae7-b652-9ffe5331fb9c |  | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone Bluestone shall be salvaged and re-used in new kerb alignment
label | 1fefcf1c-4ea7-5dd8-9efe-86247802a13a |  | note | REFERENCE DOCUMENTS: Work Procedure
label | 9bc7bbd8-778b-5f1a-9ab6-6c20bea90c83 |  | note | INSPECTION/TEST METHOD: Inspection
label | 0e67b9b0-15e3-588d-ae43-daf61b8c28b1 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 3d0bc8eb-1a34-5568-b4f3-d7d925a16179 |  | note | IP
label | c848906e-758c-5263-9434-5e814428b2fd |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | a95c0d53-c25d-5a5f-9e7f-5f054228c9aa |  | textbox | Date Completed:
checkpoint-status | 312baa09-c14c-46dd-b295-5e2f3e9df60c |  | checkpoint | 1.4 Setting out
label | e94980ea-8d29-5e02-a6a0-30f13f375372 |  | note | FREQUENCY: Each Lot
label | 61ee84b1-729f-59e5-b4da-db59ee653aa8 |  | note | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans Alignment of new kerb shall be marked out using string line
label | bd4ed746-87f7-5573-8073-bacccf93399c |  | note | REFERENCE DOCUMENTS: Work Procedure
label | e092313f-9c6b-5af0-ae07-0f46fdfecaea |  | note | INSPECTION/TEST METHOD: Inspection
label | fb78a4dd-1947-5d6e-a3cd-4bea09650435 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 13a0e05e-4387-5bad-a8d9-05172c62f96c |  | note | HP*
label | b05f8309-8deb-513a-bdee-00a2142f20cf |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 5fad23b2-527d-5612-8adf-b6bc51511eb9 |  | textbox | Date Completed:
checkpoint-group | 25305b7f-a4e6-4531-90d0-9e9052aef347 |  | section | Construction Works
checkpoint-status | d0ad7f30-7d55-4deb-884f-6b6bd19c96f3 |  | checkpoint | 2.1 Saw cut (if required)
label | 39fe1332-6f05-5e21-9b2e-90531da2a94f |  | note | FREQUENCY: Each Lot
label | 4ec90fa0-ffcf-5cd2-b47b-6f4803974f8d |  | note | ACCEPTANCE CRITERIA: Saw cuts shall be made to the following depth for existing asphalt pavements: - Footpath: Minimum 75mm - Roadway: Minimum 125mm Excavate to allow for design heights
label | e80053f8-492f-5662-9dac-00c4639e56c2 |  | note | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 2.0
label | 72df02b5-bb95-5570-b8c3-139f6d3fe936 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 76eb9fca-68a7-5293-8af1-1a93d2a83d5b |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | a0fe31b6-91e3-5672-a873-89c2c6cd34be |  | note | IP
label | 45e26502-b55a-5cdc-9a97-831f2d38e4f4 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 64f30b8f-88f7-5211-b601-10d285f7b784 |  | textbox | Date Completed:
checkpoint-status | 212cca58-f25d-47b4-9b81-14f7530aa2e2 |  | checkpoint | 2.2 Concrete Placement and Setting
label | 6e95ae52-be72-5a0b-8eef-b049d61dd8e3 |  | note | FREQUENCY: Each Lot
label | a87ba097-ef71-583f-abdc-d0a38e48478d |  | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness Gaps of >10-30mm< shall be provided and filled with mortar
label | c3e08ea0-0658-5c7c-b288-4102345d0539 |  | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
label | 2b762a49-fcca-50c4-b0cf-331c84caa425 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c667295e-304e-5fd2-9e6c-288ca9711e32 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | f03124bc-f0d7-523a-9869-5c5379157a30 |  | note | IP
label | 3b4bc136-1efc-5027-8758-29ac8be0e860 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | f068f975-84e8-579d-9fd2-e5f0875c84f2 |  | textbox | Date Completed:
checkpoint-status | fbfe8fae-f22f-494c-9467-f696f9ae5a78 |  | checkpoint | 2.3 Mortar Mix
label | c2488668-22fd-54ca-bd7d-193b1fe5e30b |  | note | FREQUENCY: Each Lot
label | ce510f21-dff7-5b9f-99f2-66203e047cbe |  | note | ACCEPTANCE CRITERIA: Joints shall be filled with mixed grout composed of the following: - 16% cement - 16% stonedust - 67% blended wash sand - 1% lime ready mix grout
label | d8ac4772-aa1a-5987-81e8-a436bc6ccc95 |  | note | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 4 AS 3972 CoM SD 1P 50406
label | c38262b9-795b-5af8-a5ab-d60fd99d0737 |  | note | INSPECTION/TEST METHOD: Verify
label | c3bcea6d-e6bd-55ba-b97d-bec4ed7f55d9 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 599fbdb7-2358-5e0f-a086-cc445fe77c3c |  | note | IP
label | 0ebbcf15-296b-5d56-bd33-73951a8bb5e6 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2db6f630-19e1-558d-a142-dd1bc8fabfad |  | textbox | Date Completed:
checkpoint-status | 7f422229-6fbe-415d-9265-be7d128b6f38 |  | checkpoint | Final Inspection
label | b5c507e6-a4d8-502c-9ba2-49e49291973d |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 21b0693a-3131-59aa-9377-735d5461a9ea |  | textbox | Print Name:
text | 438dd459-8e7d-5a2e-80cc-7e6f23da0581 |  | textbox | Position:
text | 956ef8a0-e733-59a2-bd30-02ac69ebb754 |  | textbox | Date:
checklist-sectioned | 1222cb7a-e022-4002-a00a-6b6987c55519 |  | checklist | ITP-012 - Signage Installation |  |  |  |  | Yes | ITP-012 - Signage Installation | 10ef6e9d-c2dd-41f7-8fb5-b022dc74eb11
checkpoint-group | a3504402-fb6e-4be1-9968-c9e4dc246c89 |  | section | Preliminary Works
checkpoint-status | 59218fd9-56ec-447b-b971-319d8263f4f4 |  | checkpoint | 1.1 Check for correct documentation
label | 5b55b167-d026-501c-8827-496e53cc2c99 |  | note | FREQUENCY: Prior to commencing any activity
label | a2bbe5c2-e40a-516b-8d6a-5bd338064f3d |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
label | 1dc872bc-603e-5c1f-8c2c-51ab396f3a31 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | d047aa87-a871-54e9-bba3-fbcef3254131 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 997f144a-5452-5f6a-8496-46a3f5935a99 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | c3ff9d1e-afe6-57f5-9f09-5fb7c9914da2 |  | note | WP
label | 073c5a2e-9218-5b2e-a926-e7f0815dc495 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | c246c574-34b4-5aa5-a1a4-0af831e4032f |  | textbox | Date Completed:
checkpoint-status | 5a9a42c2-574c-49dc-8407-3a1c7c2b823b |  | checkpoint | 1.2 Implementation of all measures and controls
label | 54d00be6-a510-5435-b05f-ef3b2bf18253 |  | note | FREQUENCY: Prior to commencing any activity
label | 4451c61c-67b3-5309-bf9d-998b0a8153ee |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | 0b24013b-7218-5674-a8b9-d5ddb4ec8cf1 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 35e74f4f-00d5-55c2-9ea8-9fae5c02b358 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 514978bb-6d92-5132-952c-f741fcb0a156 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 7a686923-c73a-549b-9038-134e6f733e96 |  | note | WP
label | b580089b-ab1a-5576-97b1-86c2a82b4eb3 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | f1adc6a5-3426-5078-a2f6-954f75314887 |  | textbox | Date Completed:
checkpoint-status | ff943067-b05f-430d-86e6-77d43279198e |  | checkpoint | 1.3 Signage Conformance
label | d6dfd112-7563-53ee-8ee0-b15d67538f0e |  | note | FREQUENCY: Before commencement of activity
label | 757d46d8-9e93-5d69-9982-0547b32395a6 |  | note | ACCEPTANCE CRITERIA: Ensure sign size and image correspond with contract drawings and meets specification
label | 838ef221-7600-57a7-b5e1-afc9721a8221 |  | note | REFERENCE DOCUMENTS: Drawings AS 1742
label | da6f0f2a-80a0-563f-8197-093ca535beff |  | note | INSPECTION/TEST METHOD: Verify
label | c710acb3-4ef5-50a4-bc63-aa4dd73fad7b |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 67ffedcb-e52d-5de5-a61d-17ed98f0fc0b |  | note | WP
label | 2ea98616-5bd9-5484-ade0-860f258b5af3 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 1aa05846-88a1-5db5-90f4-a3d91d1d4b5f |  | textbox | Date Completed:
checkpoint-status | f315cbe4-cfac-4c52-88c4-b0f5a40eb144 |  | checkpoint | 1.4 Service Identification
label | d3a40923-9164-54e3-a8be-1127e62894e4 |  | note | FREQUENCY: Prior to start
label | 2859eaec-d183-5b60-abbb-1971ffaa4507 |  | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
label | 4921dd9e-fc81-5235-ae02-d9a75879af53 |  | note | REFERENCE DOCUMENTS: DBYD
label | a2ca2c7c-6e74-529d-bb4c-98bc0c8513e1 |  | note | INSPECTION/TEST METHOD: Verify
label | 96810005-6e0c-525b-a740-d4dd959435c5 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 0165270b-667e-509e-95e9-15923e4bcebd |  | note | WP
label | 9c78692b-6fd9-5653-b8ff-89ef15177f05 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 8548e621-9ed6-5bc4-b52b-76359d87bf4c |  | textbox | Date Completed:
checkpoint-group | 0442a90f-cd5e-4d48-8c8f-757f335c94a5 |  | section | Construction Works
checkpoint-status | f12adca8-db8f-4b1d-a87c-2799d8dc3816 |  | checkpoint | 2.1 Setting Out
label | 490ef352-e2bb-5f23-82af-bc35fd975863 |  | note | FREQUENCY: Prior to start
label | d5c39923-eaa4-5bf7-8cf3-2cf39be4afb2 |  | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
label | 2d32d08c-77e3-5317-84f7-3323793b1ca4 |  | note | REFERENCE DOCUMENTS: Drawings
label | 23e504d8-7158-531e-b6ed-55efe689fe60 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 2c7080b6-372e-554e-9702-97060ba4aa2e |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 91388a12-4cce-5e5f-9587-6e06242aaa5a |  | note | IP
label | 8be419db-8384-5fc3-8b32-6e7c7b0259d6 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | edd7d644-0a85-5a17-b369-a046513845d9 |  | textbox | Date Completed:
checkpoint-status | 1c3cbc98-4927-40b4-ae31-81834e3636be |  | checkpoint | 2.2 Signage Install
label | 001a8804-fc11-5e93-8de4-fad871ab7dba |  | note | FREQUENCY: Each Sign
label | 8ce4d4de-dfc4-54f5-844b-cbae46592b04 |  | note | ACCEPTANCE CRITERIA: Sign to be installed as per most current drawings, local council documentation, and to the correct height and position. Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
label | 89cc30a2-29cb-55e3-a273-89117f2ed837 |  | note | REFERENCE DOCUMENTS: AS 1472 TS 1313 Drawings
label | 399a2021-dcae-51db-8557-991ba0b867d8 |  | note | INSPECTION/TEST METHOD: Verify
label | c0eb98ee-56f6-53ea-a83a-8398da7e20fd |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 8ad17730-f3f4-5e2e-9204-44480e88a5f3 |  | note | WP
label | 54413ac4-6ccd-5ddb-8472-611ddfaed9dd |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 7e44db39-f4a0-54c0-a2d2-e71983c52afd |  | textbox | Date Completed:
checkpoint-status | 44b3c2fa-3d72-4db4-b802-56e8a2427706 |  | checkpoint | Final Inspection
label | a044ca53-f4b0-5c8d-acdc-77469c77b6a4 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 9fe4154e-b069-5888-9cfe-afd49da76428 |  | textbox | Print Name:
text | c90e1941-725a-5840-a525-5d9b21ac2cde |  | textbox | Position:
text | 89a9edd3-9241-5394-bab0-064c79dd5fee |  | textbox | Date:
checklist-sectioned | de86af6c-b39a-49c1-a9dd-950af0bdeb03 |  | checklist | ITP-034 - Safety Zone Construction |  |  |  |  | Yes | ITP-034 - Safety Zone Construction | 1125ec7f-0e15-4c4c-a6d7-c1679f8cf8fe
checkpoint-group | 592c053d-4de9-4506-8dda-832c102b4c8f |  | section | Preliminary Works
checkpoint-status | c32c0172-a1c0-46a4-b021-57207240eab9 |  | checkpoint | 1.1 Check for correct documentation
label | 0fc069c3-8a9d-52b5-a723-d58e8e039d47 |  | note | FREQUENCY: Prior to Commencing Activity
label | ec4adba3-fe97-5e02-847f-1b169713e6c7 |  | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | a8fce97a-0e78-58fe-8dbf-d52940da31fc |  | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | bfa90eb7-bf54-5484-b943-0dfa2e20d87d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 59457f23-7141-5d47-bd79-933af3af11c6 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | ef4bcf8a-9cee-5098-bb97-154007e55d23 |  | note | HP*
label | c8f62898-1f30-579e-81d7-d340f9a8de7c |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ccf61aaa-8350-52da-8a46-f8682e51996e |  | textbox | Date Completed:
checkpoint-status | 5214b235-c8ad-4fef-9db4-e8dd7f1a021b |  | checkpoint | 1.2 Implementation of all measures and controls
label | fca4106f-7482-5365-b02d-fe624cb043e6 |  | note | FREQUENCY: Prior to Commencing Activity
label | 23733788-acf7-50e7-8d05-d43c78afbc29 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | 61050be2-503c-5e9c-89e2-c8f20eaa2c08 |  | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | f3759995-54c0-5dc9-a98d-a274902fbc98 |  | note | INSPECTION/TEST METHOD: Inspection
label | d9808507-6595-50d2-a1cb-a707ca4be3f2 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | fa980c01-1c2e-5296-ba07-4f869d577686 |  | note | IP
label | 8b71d6e4-e095-5595-8f23-a25198fe0a66 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 5d3b30d9-c8f3-5124-803a-4c452768c15c |  | textbox | Date Completed:
checkpoint-status | cb65326e-08f3-4d13-9700-34748f090501 |  | checkpoint | 1.3 Material classification
label | bcc1c52b-0370-572c-ae6d-0fe4d4b99fa4 |  | note | FREQUENCY: Each Delivery
label | 9abfabb2-c969-51c3-8e43-717fc78dca2b |  | note | ACCEPTANCE CRITERIA: All kerb shall be inspected at delivery for visible damage. Ensure correct single panel Type A fencing & sleeves are being used and are free of damage.
label | 4b8235b1-f359-5717-af71-d899cab72604 |  | note | REFERENCE DOCUMENTS: STF T6107
label | 9904d9cd-7d4b-5027-8454-9e0741a6cd91 |  | note | INSPECTION/TEST METHOD: Inspection
label | de7c5b00-50c3-5061-bf01-64e986344444 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | baeb4500-b721-5948-9b0a-0b03db131bf2 |  | note | IP
label | a05e7f13-b47d-556d-96b9-ce8784cd6337 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 5ab49eb0-efc2-55da-aca0-50bf3f8bf455 |  | textbox | Date Completed:
checkpoint-status | 5361fbc1-13d3-47a4-ac64-4394e55e3185 |  | checkpoint | 1.3 Setting Out
label | 1a2ab982-973d-5d83-a6e8-606e1887f37d |  | note | FREQUENCY: Each Lot
label | 708050d5-a8c4-5004-8900-0cb624671cf5 |  | note | ACCEPTANCE CRITERIA: Line and level of kerb, fencing & linemarking shall be set and marked out according to the design and standard drawings.
label | 37af523d-bf54-5d53-ac0c-94b13060f6de |  | note | REFERENCE DOCUMENTS: Design Drawings Dwg P15671
label | 94aaa178-18fc-5ea2-a934-93a373ef2640 |  | note | INSPECTION/TEST METHOD: Inspection
label | 900df7a1-6ee8-5d5c-8d00-6b8b00310a38 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | e1352696-9da5-515c-b9fe-8dda823e7e17 |  | note | WP
label | 8f87863d-7e44-519d-a55d-c1110be9016f |  | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
text | 50fe781f-0784-52af-bbd4-5576bbbaa7f6 |  | textbox | Date Completed:
checkpoint-group | 76dc6b2a-c524-4f0f-9e4c-3f64cd7a521d |  | section | Installation of Concrete Kerb
checkpoint-status | c2c597d3-805c-44e7-ba42-3c76f61a44ac |  | checkpoint | 2.1 Base Preparation
label | 81dac243-3175-5ddb-8bb1-8ca1b0eda300 |  | note | FREQUENCY: Each Lot
label | 573f5f6a-b550-501b-99bf-699b87db47da |  | note | ACCEPTANCE CRITERIA: Pavement base shall be inspected to be solid free of loose materials.
label | 74648c53-7a77-58be-adfd-692c85fba7b6 |  | note | REFERENCE DOCUMENTS: Dwg P15671
label | d9f7cbac-2559-5694-b4fb-489fe862907a |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | dd179456-965a-5262-a092-8c46f58300c8 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | d0ebf45c-11a7-57c8-b0d1-06a25268c0de |  | note | IP
label | 55ea7807-de49-5831-b4a8-0eacdcd881b9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | cbae07f7-e235-559e-a0d5-6a3d3a00eefe |  | textbox | Date Completed:
checkpoint-status | b2c8db37-84b1-4d1c-8a64-461608f0bf6d |  | checkpoint | 2.2 Drilling of Holes
label | 95ebc4af-41c4-5a55-8504-9ac24fffda38 |  | note | FREQUENCY: Each Lot
label | dfb44868-9816-58dc-af5d-d3084c61a2e8 |  | note | ACCEPTANCE CRITERIA: Location of holes drilled must align with the provided design drawings. Two holes per stone shall be drilled to an approximate depth of 130mm. The width of the hole drilled shall be minimum 4mm larger than the width of the pin to allow for Chemset material.
label | b211d74f-4380-55cd-a54b-dcfe42fbedae |  | note | REFERENCE DOCUMENTS: Dwg P15671
label | b4d8ee3c-3c18-5b99-8111-c47a4472f84f |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c0f1d7eb-479e-5f85-9b32-e3ef5d2c31f6 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 8487bee7-c608-5f7a-8252-151a62252e97 |  | note | IP
label | e9646013-db5d-5a5c-bbdf-c6e59ba6c86d |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2daba6f7-b059-588b-bce9-dc6a0aa0a236 |  | textbox | Date Completed:
checkpoint-status | 25b49dbe-e8a4-4003-b64f-6769eda84bb2 |  | checkpoint | 2.3 Placement of Kerb
label | cbbc7fe1-9c83-50d5-afb7-b2190b597323 |  | note | FREQUENCY: Each Lot
label | c001d2d9-fd9a-594a-ba8b-d4d38cf75c20 |  | note | ACCEPTANCE CRITERIA: Apply Chemset material and position kerb stones such that the pins sit in the holes allowing the stone to lie flat on the pavement.
label | e7399f23-f6bd-5a7d-a03e-ef8b33935d0b |  | note | REFERENCE DOCUMENTS: Dwg P15671
label | d67ff664-d461-5293-a2ab-9c3bfb7d13a5 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 6021cebf-35bb-5157-8071-b0e3a82ded04 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | abdc4403-8049-5977-a8a9-26bcc64e4b53 |  | note | IP
label | 83b6cf50-c75c-50ac-893f-28ce235d7a5b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | a4826c22-1842-50dc-92f1-d436fb9c75f7 |  | textbox | Date Completed:
checkpoint-group | 5e9af24b-6a18-4eb4-832d-bfabcc2d3324 |  | section | Installation of Single Panel Guard Rail
checkpoint-status | bac37641-fd11-4bfa-a767-9560f5229b03 |  | checkpoint | 3.1 Installation of Rail Post Sleeves
label | 913f1405-6715-5511-ab95-af09b6d9aef6 |  | note | FREQUENCY: Each Lot
label | d115328d-68f8-5337-b164-0e9210f8a0c9 |  | note | ACCEPTANCE CRITERIA: Location of post sleeve's must align with the provided design drawings & 2.4m spacing. Core two 100mm diameter, 300mm deep holes per panel at 2400mm centres. Insert post sleeve and secure using non-shrink structural grout.
label | cae17f7e-6158-5750-bcfe-e3b10fada6a9 |  | note | REFERENCE DOCUMENTS: Dwg P15671
label | 135e1168-14e7-5a91-82df-a93ec5fdff14 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | aa24cbc8-d4db-5d56-8ad9-95f62d66d608 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 5fd1bab7-7b8b-5e14-9a41-207e3bc371bb |  | note | IP
label | 869bfc51-ebc0-53a4-9774-1cc48477e078 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 087a78dd-4cf1-5043-ae46-ffe9cf53baaa |  | textbox | Date Completed:
checkpoint-status | 9750ec5f-1fb0-4e4d-acb5-41329d3cce55 |  | checkpoint | 3.2 Placement of Fencing Panel
label | ab80a9ff-c698-5d78-b3c6-0b0151d92d42 |  | note | FREQUENCY: Each Lot
label | 244697dd-6d76-54d7-863e-b581a07c2d5d |  | note | ACCEPTANCE CRITERIA: Align fencing panel such that the posts sit securely in the installed post sleeves. Ensure fence panel is free of damage and is positioned in accordance with the design line and level.
label | 9768a069-6d83-54cf-8384-4c416452c71e |  | note | REFERENCE DOCUMENTS: Design Drawing Dwg P15671
label | c1b00404-fc1a-5a27-a9d8-739f8f47f149 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | dd535384-0703-51ff-8836-9a226a10d492 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | bd13d590-95c5-5a26-be0f-e27a358c47ca |  | note | IP
label | 41bb2732-1785-52d5-82b8-8942d76e0cad |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ccc1de5d-4ffe-52f5-8a20-4347cd72f15c |  | textbox | Date Completed:
checkpoint-group | d4fa836e-4ee1-4f5b-b985-1fed84806a0a |  | section | Linemarking
checkpoint-status | 268686da-d1ba-4589-99b6-a97b373a68c3 |  | checkpoint | 4.1 Linemarking
label | 376d91c2-4301-575c-8fe7-53faf9174d33 |  | note | FREQUENCY: Each Lot
label | 1af6d83f-1030-5fe2-b79b-e244bba53283 |  | note | ACCEPTANCE CRITERIA: Linemarking to be completed in accordance with design and standard drawings.
label | 40f6c336-475f-50d0-8c1b-12e0a0cc8393 |  | note | REFERENCE DOCUMENTS: Design Drawings Dwg P15671
label | 71482c99-e856-5500-ba96-68694b9df0e5 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 3ba0a6b3-9148-535a-8264-6220eb9daa9d |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 717c228d-0020-53c1-afcb-2720934319c8 |  | note | IP
label | 5734164f-925f-5655-b62b-3b23904445ec |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 03aada48-0183-5207-917f-8d4cd8c44572 |  | textbox | Date Completed:
checkpoint-status | f90328e9-877d-4a8e-9f8a-e86bfbb6f883 |  | checkpoint | Final Inspection
label | e1de1ee9-e9e2-5a8e-9b23-3bd8b7df9da5 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 1cc3aef9-c3bc-557c-befd-353b428987ed |  | textbox | Print Name:
text | 754b0f78-c289-505c-99f5-10f7ba9a5274 |  | textbox | Position:
text | a2921bcd-2e25-5174-b756-098eae9ed6a3 |  | textbox | Date:
checklist-sectioned | b44c53f5-2775-437c-a27e-382ef6cef6b0 |  | checklist | FHC-ITP-027 - Pile Footing Construction |  |  |  |  | Yes | FHC-ITP-027 - Pile Footing Construction | 14631d90-23fb-47b9-ab76-c1c5268941cb
checkpoint-group | a9606d97-83a6-42bd-91f8-5f82cf6691c5 |  | section | Design and Submissions
checkpoint-status | 6aed04b1-273d-4082-aa0c-2d2c06c25eff |  | checkpoint | 1.1 - Check for correct documentation
label | 41b5fbfa-0c65-55f8-b8ec-2faa4920aa1f |  | note | Frequency - Prior to commencing any activity
label | d5cc93cd-55b2-547a-aada-21008d730254 |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
label | 5089950e-c80f-5435-b5f9-e658365c603a |  | note | Reference Documents - Drawings and drawing registers
label | 9111c2bf-499b-5d3f-965b-1b1d616658cf |  | note | Inspection / Test Method - Visual inspection
label | dea63f20-213b-5aaf-8ced-3bd1091dcea6 |  | note | Record of Conformity - This ITP signed
label | 84cb033c-daca-5e01-997f-3e89d32aefbc |  | note | HP*
label | 29fa5ad2-b165-52af-9639-39630c863223 |  | note | Responsibility - Fulton Hogan Engineer
checkpoint-status | 63278886-be38-4500-8788-af26c2095326 |  | checkpoint | 1.2 - Implementation of all measures and controls
label | ea76ea31-532f-55c2-9b86-d7d890adf4fe |  | note | Frequency - Prior to commencing any activity
label | 68241834-6fda-587d-a3f2-753aae4a832c |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | a9ba51de-8f61-5a9b-8eb9-a856a13f19f3 |  | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | d93df1f8-33e4-53fa-83ed-e78584fc8df4 |  | note | Inspection / Test Method - Visual Inspection
label | 27264cdb-f599-567a-a42e-1562aa52c91f |  | note | Record of Conformity - This ITP signed
label | a6b067f1-d2ed-5e57-bb6a-4db6f0ff7b4d |  | note | HP*
label | ff2d8007-1e3e-53fa-b409-5858451a86cd |  | note | Responsibility - Fulton Hogan Engineer
checkpoint-status | ca5438c8-ec72-43c7-af9e-bb86a9bd2747 |  | checkpoint | 1.3 - Approval of mix design
label | 9e346216-a2f8-5c3a-a245-fb88a8604a97 |  | note | Frequency - Prior to the first concrete pour
label | c5c90217-dd4f-5eb0-aba8-33c1bcdfe4db |  | note | Acceptance Criteria - Structural Concrete Design & Submission ITP completed and signed.
label | cae5060d-a254-57c1-ad04-249a2157a854 |  | note | Reference Documents - 610.07
label | 50feb7a6-d997-5b8a-8592-ed8c5fcd7970 |  | note | Inspection / Test Method - Verify
label | fb8b9322-83b6-588e-af87-6727f6ec55cb |  | note | Record of Conformity - This ITP signed
label | 4d200d9a-c088-5d71-84a5-b35d440a0124 |  | note | IP
label | c3990c24-021a-5a85-a4a2-afc90ace4b68 |  | note | Responsibility - Fulton Hogan Engineer
checkpoint-status | 77999047-2ff3-43c4-a3cc-d40bcc0e672e |  | checkpoint | 1.4 - Reinforcement schedule
label | 55110260-2523-5174-af97-effa788da9d3 |  | note | Frequency - Prior to concrete pour
label | 55b119ae-5ff3-58e3-a8e4-393b81ac0991 |  | note | Acceptance Criteria - Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
label | 6f6f2bf9-d07e-5383-a41a-506ce80874ae |  | note | Reference Documents - 611.04
label | c285b9a7-ee78-5aac-b8e9-857101a1cd5e |  | note | Inspection / Test Method - Verify
label | 8eb8ad1c-55ee-5ed5-8546-1faba1fb1bc7 |  | note | Record of Conformity - This ITP signed
label | 8e79e002-9f44-5765-9ef9-4aa7a1cd60d2 |  | note | IP
label | 35ae1da2-880f-5d46-915c-4fa82c4ec01d |  | note | Responsibility - Fulton Hogan Engineer
checkpoint-group | 6a2de901-1239-4a24-bf1b-30ae5c9c5f15 |  | section | Construction/Erection of Formwork
checkpoint-status | 55c3e925-f079-45ae-bed5-f25d88341991 |  | checkpoint | 2.1 - Excavation (Pile)
label | 104e6d5d-d9db-542b-9c38-0df46a00178e |  | note | Frequency - Prior to concrete pour
label | 8f6f5052-15db-53b0-b708-0281df1914ab |  | note | Acceptance Criteria - The Contractor shall notify the Superintendent for inspection of the pile excavation by the Superintendent. Prior to inspection, the pile excavation shall be de‑watered and the walls and base of the pile cleaned out, including the internal surface of the casing, to remove all mud, loose or foreign material.
label | 732e1646-fbc2-5c4f-9bda-64971da9b889 |  | note | Reference Documents - 606.05
label | d2341ece-bd8a-5fbc-b916-beb8d7721e76 |  | note | Inspection / Test Method - Inspect
label | 801b9b68-5fea-5454-9378-d7c6c7e9606b |  | note | Record of Conformity - This ITP signed
label | 74ff7e1a-5463-56e6-8dba-6625c96e44cd |  | note | HP
label | a013ca08-b549-56f1-b157-f9e71392ddb8 |  | note | Responsibility - Fulton Hogan Engineer / Superintendent
holdpoint | ec1f205a-e28b-4f0e-a188-ee48b4ad0295 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 17205d50-a2e9-4b0a-8456-4b27f996a539 |  | checkpoint | 2.2 - Construction Methodology
label | 6948f667-bda9-5cac-b198-8327c2edcc85 |  | note | Frequency - Prior to erection
label | 65fd2c44-e188-50eb-a88f-0c3fcf42479d |  | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
label | f35a01a1-e2e9-5f47-91a3-30e7bea414cf |  | note | Reference Documents - 614.04 614.06
label | 21182d8c-272f-510e-81c8-6f68e02e0442 |  | note | Inspection / Test Method - Verify
label | d447e2ce-9cbe-5602-b203-250168abbbc7 |  | note | Record of Conformity - This ITP signed
label | e61fcd87-86bf-5412-b727-23ee52beb229 |  | note | IP
label | bf91616c-3cc2-5ea9-a3ad-220864fe4af9 |  | note | Responsibility - Fulton Hogan Engineer
checkpoint-status | 9d26adc6-abcd-4f3c-96aa-ab8cbe38391a |  | checkpoint | 2.3 - Construction Methodology (Pile)
label | eccf29bc-83a4-5944-9713-1999ea6ccfdb |  | note | Frequency - Prior to construction
label | 11fe077a-b0a8-51e1-a0c7-87d5668b385e |  | note | Acceptance Criteria - Further to the requirements of clause 611.10 spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained. Concrete shall be placed through a tremie tube and shall not be dropped from a height greater than 2 m through air.
label | 1ff6f786-7e10-5fff-a123-45881c3e24d5 |  | note | Reference Documents - 611.10 606.06
label | 7ac7d958-a9fe-57ac-91e4-c7d89ff30e2f |  | note | Inspection / Test Method - Verify
label | 6be7516d-97d9-5875-9ceb-2ff616ae00ff |  | note | Record of Conformity - This ITP signed
label | 4ba494f4-a406-51a1-8d40-9d482adc26e6 |  | note | IP
label | 21875110-e14f-5b02-89e1-78347f66eb9e |  | note | Responsibility - Fulton Hogan Engineer
checkpoint-group | dd1745e9-9a7a-4110-ab19-7bb6a9270019 |  | section | Pre-Pour Planning and Inspection
checkpoint-status | 19f0ab39-100d-4f55-bfb4-ed91ab89ad99 |  | checkpoint | 3.1 - Cleaning formwork
label | e266b62e-0aab-5cc0-9f3c-8c6a18532bbc |  | note | Frequency - Each concrete pour
label | fc2b384d-582f-573c-99ac-4e08baf63918 |  | note | Acceptance Criteria - Concrete shall not be placed until all foreign material has been completely removed from the forms
label | 38dc67d8-e1b3-594d-970c-1f033bbb495c |  | note | Reference Documents - 610.18 (a) (iii)
label | 0d851ab0-053e-5194-a2c9-54ab91cb0abd |  | note | Inspection / Test Method - Verify
label | 29e51262-4b6c-5fce-a36b-c5fa1dae30ec |  | note | Record of Conformity - This ITP signed
label | aa2a2062-c5f1-5eb7-b5e2-f755ccb59765 |  | note | IP
label | a99b692e-e797-55ea-8da9-4436256e0df6 |  | note | Responsibility - Fulton Hogan
checkpoint-status | ba276b2f-ca59-4f68-9e57-30d791ac92f7 |  | checkpoint | 3.2 - Correct forms, reinforcements, rag bolt assembly and embedments
label | 54e6d429-3681-5931-8731-015fc8d7c1f4 |  | note | Frequency - Prior to concrete pour
label | 0d8cc00f-536e-55ea-885e-6d77f679628f |  | note | Acceptance Criteria - Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications. Pre-pour checklist completed and signed.
label | 9ffb4e76-cecb-5eda-b50f-810ad09fe976 |  | note | Reference Documents - 610.18 (a)
label | 9d1195ca-283e-50dc-94b7-16b69b16e8dc |  | note | Inspection / Test Method - Verify
label | f9635a85-c86b-5b08-8bb0-f7bec1da408c |  | note | Record of Conformity - This ITP signed & Pre-Pour checklist completed
label | 39ae11c6-5e5e-53fc-ab8d-35a1ebc1c93e |  | note | HP
label | 55762235-099b-5d8b-9833-bfbe662e6241 |  | note | Responsibility - Fulton Hogan / Superintendent
holdpoint | 1bcdc184-7551-4e98-9022-449d472b8025 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 59e1fa3f-5c96-4dc0-bbe8-6a9cf6b0fc07 |  | checkpoint | 3.3 - Reinforcement assembly of piles
label | 80d032e7-90e4-5566-8d31-31aa7096a40b |  | note | Frequency - Prior to concrete pour
label | 7fe3e4bd-af03-5ff7-b139-f3bf2a4b6293 |  | note | Acceptance Criteria - Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
label | 2b7e5ef5-a494-514b-ba6e-e709e5a6d939 |  | note | Reference Documents - 610.17 (b),( c), (d)
label | 11be937b-083e-516e-bb3d-3c569ba932d8 |  | note | Inspection / Test Method - Verify
label | 763cc17b-d87e-5830-b119-0de7e58f5675 |  | note | Record of Conformity - This ITP signed
label | 24ffe73d-2479-5b7d-9683-21972940042b |  | note | HP
label | 42629505-5ab9-5e9c-a867-45b62ceaa243 |  | note | Responsibility - Fulton Hogan
holdpoint | f9cfa77c-c435-4c1d-9ecb-41df250c24f4 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 79676b3d-6c02-4ca8-948d-008ec9baed98 |  | checkpoint | 3.4 - Monitoring weather
label | 6c4637e7-4ac8-5d64-a011-3a6754014dde |  | note | Frequency - Prior to concrete pour
label | 152e0784-f8b1-56b6-8684-6a57e79013bf |  | note | Acceptance Criteria - Concrete shall not be place when temperature is <5°C or > 35°C All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
label | c5995841-d4f7-58b8-a78b-784a4b2567fe |  | note | Reference Documents - 610.17 (b),( c), (d)
label | e86fd3a5-03e6-5b94-ae1a-71b0c2bc075f |  | note | Inspection / Test Method - Verify
label | 8baa2e9d-cefc-5d08-a3ed-38bb1ce35663 |  | note | Record of Conformity - This ITP signed
label | 04c43df5-0f35-59e3-8605-c2f780f0a29a |  | note | IP
label | b6023ca2-16cb-5781-84ec-19046c0bbe60 |  | note | Responsibility - Fulton Hogan
checkpoint-group | d160cb7d-efb0-407d-b9b4-bb5bb32d9110 |  | section | Placing and Finishing Concrete
checkpoint-status | 06f7f196-c73a-43fb-ab64-cefb6226feca |  | checkpoint | 4.1 - Carry out sampling of concrete
label | faee9827-b11d-598d-8cde-da7ee69d4187 |  | note | Frequency - Each concrete pour
label | dd88ce79-7eb7-526a-bcfe-8e84335fbda8 |  | note | Acceptance Criteria - Sampling in accordance with 610.16
label | ba56bd2d-8e7e-531b-8811-e9f150ab5bf0 |  | note | Reference Documents - 610.16
label | 44342323-a7cd-516c-860d-fb497500dcda |  | note | Inspection / Test Method - Checklist
label | 2b8f272a-e701-5daa-9692-fef959cf4fb0 |  | note | Record of Conformity - This ITP signed
label | dd1679b4-7e6c-52c1-a214-98acd2b4c7a9 |  | note | IP
label | b6c21dd2-17c1-5f28-bced-acb0435f8dc6 |  | note | Responsibility - Fulton Hogan
checkpoint-status | 38fd1056-9930-4a44-aa43-20482f6dd8dd |  | checkpoint | 4.2 - Discharge time
label | dad6b884-d4d4-5be8-9bde-e3d30b319f25 |  | note | Frequency - Each concrete pour
label | de46c082-818a-52d4-9667-c1b729bb9b13 |  | note | Acceptance Criteria - Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise. Batch to be used has a discharge time of 180 minutes.
label | 33282b20-955b-5962-99e3-a39de2d849c1 |  | note | Reference Documents - 610.13
label | 25f0b82f-ffdc-5861-9a49-45459af90b34 |  | note | Inspection / Test Method - Verify
label | acd2881d-cb67-5284-a970-7ee840a796bc |  | note | Record of Conformity - This ITP signed. Accurate Site Notes & Load Mapping
label | d6c7f8e0-03fd-5a70-bdb1-5f88fa26db3f |  | note | IP
label | 71a193bc-0cf1-5cb7-ba40-5ef170ebee8b |  | note | Responsibility - Fulton Hogan
checkpoint-status | 2c760b5c-1d46-4bbf-871f-c77200b573ef |  | checkpoint | 4.3 - Methodology of placement (structural)
label | 5191d644-6362-5021-a4dc-9ee9255c9342 |  | note | Frequency - Each concrete pour
label | e72d49ff-6adf-568b-99f9-1a8a0d6bfb6f |  | note | Acceptance Criteria - Concrete shall be transported, handled and placed in a manner that will prevent segregation or loss of materials In continuous pours the max. time lag between truckloads on site is 25 minutes
label | 60620b75-3adf-5718-9a40-9b26ecfb9a37 |  | note | Reference Documents - 610.18
label | 3384093f-d743-53db-96b5-52ca61313fba |  | note | Inspection / Test Method - Verify
label | 35ccd945-f007-5aa4-a080-a90a73ed21b7 |  | note | Record of Conformity - This ITP signed
label | 435ccc89-1b94-5123-a666-c838d7e91ec4 |  | note | IP
label | a235b76b-499a-509f-8354-063ee8a3b024 |  | note | Responsibility - Fulton Hogan
checkpoint-status | d41a7348-257d-4c22-9354-9be74bc96e0b |  | checkpoint | 4.4 - Methodology of placement (piles)
label | d62e3a04-2ad7-553f-a867-23db2c60ba86 |  | note | Frequency - Each concrete pour
label | d40e2577-0309-5433-b92f-6055db88b3c5 |  | note | Acceptance Criteria - Unless otherwise approved by the Superintendent, temporary casing shall be used to prevent collapse of holes during the excavation operation. Care shall be taken to prevent soil and rock dislodging from the side of the hole and contaminating the concrete forming the minimum cover to the reinforcement.
label | 9f98a56c-3d0e-5e6a-a936-cb7252789ef0 |  | note | Reference Documents - 606.03(b) 606.05
label | 472dbe60-9d17-5669-8f60-a5c91dc116e2 |  | note | Inspection / Test Method - Verify
label | d872d330-c818-597d-aff1-96695a23698a |  | note | Record of Conformity - This ITP signed
label | e59cfb15-2488-571c-9005-517251794ba4 |  | note | IP
label | 7bbdcd88-b0b1-5b93-88e2-cef4c90b0db8 |  | note | Responsibility - Fulton Hogan
checkpoint-group | 340c9a40-014e-4119-b2d7-4cb5bf6139eb |  | section | Post-Pour Details and Inspection
checkpoint-status | 97201dd0-7470-4848-911e-97b8348ca8dc |  | checkpoint | 5.1 - Curing
label | 6b2ec9f9-26e7-5c4f-a7f6-f0c54df1498a |  | note | Frequency - Each concrete pour
label | b77ffcd8-01df-59e0-aefc-a9bcc69ebb73 |  | note | Acceptance Criteria - Sufficient time shall be given for the concrete to cure prior to loading.
label | 924bc59d-e5bf-569f-830c-8955c19313b9 |  | note | Reference Documents - 610.23
label | f48c59d3-0c42-5c5b-90c5-5ffbebad1853 |  | note | Inspection / Test Method - Verify
label | eec77213-632c-5d99-98e4-37f8d5faf11e |  | note | Record of Conformity - This ITP signed
label | f76c478a-f448-5857-a287-b40547b4a573 |  | note | IP
label | 814fdc63-3d0f-5338-8aa9-c4c772db32e8 |  | note | Responsibility - Fulton Hogan
checkpoint-status | d416af72-8ef1-4f05-837b-ab35a4c3e107 |  | checkpoint | 5.2 - Formwork removal
label | 62c75727-4e20-5d69-b8bd-6ae76fb0093d |  | note | Frequency - Each concrete pour
label | 30956ed4-2d67-54a2-85da-514daac270ea |  | note | Acceptance Criteria - Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
label | 11460b4f-fffd-5851-98a4-1ef2ddbb3856 |  | note | Reference Documents - 610.25
label | cf54a589-066b-55e8-8bf9-802c0cab5bf5 |  | note | Inspection / Test Method - Verify
label | cef41683-1980-5506-be0c-685c3bb96fb0 |  | note | Record of Conformity - This ITP signed
label | c5fc8f30-71f4-53df-ba79-bac53dc2f563 |  | note | IP
label | ca7d804c-dd0f-5cba-9d41-cce29e50774d |  | note | Responsibility - Fulton Hogan
checkpoint-status | fe0a317d-c234-4f51-99b6-9c771b3654f1 |  | checkpoint | 5.3 - Positional tolerance and dimensions of concrete members and piles
label | be793b8f-8805-5c94-9006-a5911b7761ea |  | note | Frequency - Each concrete pour
label | ead02442-53fd-5ff2-9656-27cf9da3086f |  | note | Acceptance Criteria - The centre of the pile head shall be in the specified plan position ±75 mm;
label | c80f312e-1a92-5043-9c85-e1ff51916959 |  | note | Reference Documents - 607.06
label | b3cebe4d-1cc7-5fc3-ac47-f0377a83e72b |  | note | Inspection / Test Method - Verify
label | 8d0ec1e8-28a7-58f7-a540-3c98c1caeb99 |  | note | Record of Conformity - This ITP signed Post Pour Checklist completed
label | 1f8f02b9-cea6-5ec5-915b-8356b80b89fe |  | note | IP
label | 59b4166c-f7bc-5a3e-a681-cee2829555fd |  | note | Responsibility - Fulton Hogan
checkpoint-status | 4d00edab-6aac-49d6-a3a7-81ee24c361ad |  | checkpoint | 5.4 - Concrete Sampling and Testing
label | a09c58dd-dd0b-576e-b7e6-dafe3f6ced57 |  | note | Frequency - Prior to lot closure
label | 1691a350-b210-59b7-845e-2f9324914400 |  | note | Acceptance Criteria - Concrete sampled and tested for Compressive Strength: - 2 cylinders @ 28 days Compressive Strength=32MPa - 1 cylinders @ 7 days for Compressive Strength=20MPa
label | bb036c42-6f29-5742-8a7e-da9915f28b1d |  | note | Reference Documents - 610.05 610.06 610.13 610.16
label | 1d7416e5-d528-546d-bf77-21274c7ccf38 |  | note | Inspection / Test Method - Verify
label | 95fb1b75-5ee6-5c2a-83f4-f2fbf92e91ac |  | note | Record of Conformity - This ITP signed
label | 5726aa87-1c3a-51da-988f-05da1bbb3298 |  | note | TP
label | 9cf89bae-1b5e-551c-9486-1ed071d0a994 |  | note | Responsibility - Fulton Hogan
checkpoint-status | 98102819-03e1-481a-ab26-68af6f449bd4 |  | checkpoint | 5.5 - Protection of Adjacent Piles
label | 2d2fc5a0-0c39-508c-9be6-a6688672a2e2 |  | note | Frequency - Prior to commencing any piling
label | b2e8ac37-bff0-518a-842c-e7fc1b76d8a3 |  | note | Acceptance Criteria - No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa. Installation of piles by methods which involve driven temporary casing or result in significant vibration shall not be carried out within the distance 2.5 m to 9.0 m until the concrete in the pile has attained a strength of 15 MPa and set for a minimum of 24 hours.
label | 86eb7f8c-3ab7-5e46-a3bf-81e630b8527e |  | note | Reference Documents - 606.04(a) 606.04(c)
label | e6e14890-595c-507c-94e8-eaf3b7fbd743 |  | note | Inspection / Test Method - Verify
label | 2351f335-8221-5b4c-a897-5b118a1b2427 |  | note | Record of Conformity - This ITP signed
label | 3c4cc24b-eaea-54c0-9b0e-20878168a82c |  | note | HP*
label | 8a3240af-7eca-5d38-b292-cf63ca5d21c5 |  | note | Responsibility - Fulton Hogan
checkpoint-status | 4fd8e4ce-331c-4d7c-863e-142326f7e3c3 |  | checkpoint | 5.6 - Testing Post-Pour
label | e1797f58-9370-5757-b5f3-11569e77fab2 |  | note | Frequency - Prior to lot closure
label | 413b5e4f-993e-5d82-ace1-7ac592732849 |  | note | Acceptance Criteria - Where necessary, piles shall be tested in accordance with 606.07; integrity testing, static load testing & dynamic testing
label | 13801b1b-5146-5cc6-b435-99e55b00741a |  | note | Reference Documents - 606.07
label | 0e7f76c6-0588-51af-ad12-cb20a22bcdaa |  | note | Inspection / Test Method - Verify
label | 33bde039-ac34-53c4-9804-2acb9bfba7e9 |  | note | Record of Conformity - This ITP signed
label | 4e97a354-3c72-5172-96a4-a4126c64da03 |  | note | TP
label | fe3ed722-af6a-58a3-9679-98b9acaad95b |  | note | Responsibility - Fulton Hogan
checkpoint-status | 66c81391-2390-4652-9da1-2114912acd1e |  | checkpoint | 5.7 - As Built Drawings
label | fc5624dc-f5b1-5e19-8f57-612a07e96b01 |  | note | Frequency - Prior to lot closure
label | c826f6f4-31ea-5541-b538-241403f8ba89 |  | note | Acceptance Criteria - Recorded of as-built drawings
label | ca3d3e80-e4de-5149-be29-91406315d872 |  | note | Reference Documents - Fulton Hogan Procedure
label | 1fd47524-96d1-57dc-b4b1-1746c7931d24 |  | note | Inspection / Test Method - Verify
label | 19995901-d6d7-5e4d-8332-decd8eaa709a |  | note | Record of Conformity - This ITP signed
label | a1030f85-90d4-56da-af70-ffa7df4b4ecb |  | note | IP
label | 010bdfda-ddee-52b7-91e4-2d557d9c0f33 |  | note | Responsibility - Fulton Hogan
checkpoint-status | d3d581e3-d49d-4d8e-a579-369bb77cb50e |  | checkpoint | Final Inspection
label | 7addda81-6635-50fe-ad77-0aacdf678c00 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 5b88f1cc-2273-504c-a2c0-5e1442b31792 |  | textbox | Print Name:
text | 613a9401-f597-5261-a635-af34abe6abca |  | textbox | Position:
text | 33c004a5-b7fa-57ff-b9cc-5653b0f99fc4 |  | textbox | Date:
checklist-sectioned | 25d7565f-5736-496a-8704-c9660d16debf |  | checklist | ITP-036 - Kerb Access Ramp Bluestone Footpath |  |  |  |  | Yes | ITP-036 - Kerb Access Ramp Bluestone Footpath | 1551706f-f69b-4dfc-bef1-ed06b70ef7ca
checkpoint-group | 0b3593f3-1c12-471b-9301-c32445cfa140 |  | section | Preliminary Works
checkpoint-status | 688e3f50-14fc-44e3-aa1d-6ffbe222eb41 |  | checkpoint | 1.1 Check for Correct Documentation
label | 52a82d19-ec0c-56e3-90c4-f85541b6c528 |  | note | FREQUENCY: Prior to Commencing Activity
label | 0a74bd90-1b91-51c3-96db-97290d11357f |  | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | e6033190-16fe-5ebb-a278-a6b021d7c863 |  | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | 0fdcac02-c350-536b-8617-90423224d98e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9b0e1498-cc0b-5d33-a429-c74a579f3985 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | bc19dbf7-f4b7-5be9-9480-03f3067b327f |  | note | HP*
label | 584bd54e-daeb-55ae-9e8e-e8a581664b98 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 61c4586d-1882-5917-9dda-b7d77e7a15bc |  | textbox | Date Completed:
checkpoint-status | 039129e0-ad40-4bad-b51d-af42e7643145 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 49057b71-ecef-5b2f-a685-288fa05e769f |  | note | FREQUENCY: Prior to Commencing Activity
label | 3220773b-998e-53ff-b214-9d46f72bd022 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | d6530e4a-d954-59d8-9f69-ef10724ae7c1 |  | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | ec80cb64-7a70-5f74-b268-bbf5e4dfb0c2 |  | note | INSPECTION/TEST METHOD: Inspection
label | 342425c4-f3da-5164-82aa-add7acece86b |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 4d204ad3-588f-54f5-959f-727e514880d0 |  | note | IP
label | 7ffd214e-0473-554c-8c0b-0a97f7501b02 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | bac8af11-47ce-523d-badc-30aa39fba668 |  | textbox | Date Completed:
checkpoint-status | 80babcc9-4562-413b-9284-021ef481d3de |  | checkpoint | 1.3 Existing Bluestone Kerb Demolition / Removal
label | ab0c6ec7-df48-5664-a433-c644aee7097a |  | note | FREQUENCY: Each Lot
label | 7c6f569e-c681-5469-951c-b6f32b3ed29d |  | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone (if applicable) Bluestone shall be salvaged and re-used in new kerb alignment where possible
label | c6868cbc-1f85-568c-a273-ee239da2556b |  | note | REFERENCE DOCUMENTS: Work Procedure
label | 452a9189-7249-5d0e-8fe5-757023656522 |  | note | INSPECTION/TEST METHOD: Inspection
label | 39ff74cc-7862-538b-9637-2d74c8fa1de2 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | df2c841a-208d-5073-baf3-c1a411862826 |  | note | IP
label | 87291d57-9dfb-5b79-b7e3-87f66f93b812 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 4c661aaa-e156-5b1b-9818-5772d910b141 |  | textbox | Date Completed:
checkpoint-status | 5cde3d72-e3b3-4672-9045-2ae97432a0af |  | checkpoint | 1.4 Check Materials
label | e327a5ce-2a04-56bf-9e63-07a6f66ae583 |  | note | FREQUENCY: Prior to Commencing Activity
label | e5114e7f-793d-5aeb-b212-7899edbb405b |  | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage. Tactiles in paved areas shall be Versatac Granite Tactiles. Granite inlay shall be 50mm wide x 40mm thick Spring White Granite Inlay.
label | d60b0906-683a-57ef-b354-f6131a6f9d9c |  | note | REFERENCE DOCUMENTS: Receivable Inspection List
label | a3ccf43c-aa8d-5624-bc6f-e4af87cadb2b |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 653f887a-2864-5a63-a889-9469047d19da |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 72fce0d1-73d0-5bcb-9d91-d8ba1f59116b |  | note | HP*
label | 4ae4f0a5-5855-5929-9a14-9aa4b40da0bb |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 299d7987-1b32-549b-a190-5a2466d28b74 |  | textbox | Date Completed:
checkpoint-status | 3dbc03a7-a781-46f2-9167-b9f522085d07 |  | checkpoint | 1.5 Setting out
label | 31a701b0-bbab-5283-a013-65a75375a2f3 |  | note | FREQUENCY: Each Lot
label | be7441cb-d317-5ac9-a567-905c33e984d1 |  | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels. Line and level of bluestone pavers, tactiles and granite inlay shall be set out according to design levels to suit new kerb heights.
label | c80b481f-a8d3-523f-a117-681ae2f0a01d |  | note | REFERENCE DOCUMENTS: Work Procedure
label | 56fb8338-2bc9-535d-aa08-90fa35be8064 |  | note | INSPECTION/TEST METHOD: Inspection
label | c488b3eb-16b9-599c-993c-bdc4d342f24c |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 8ad4de1b-cec2-5e31-8c7f-9ed98ac861f2 |  | note | WP
label | d0c1e82b-8d20-531b-bfb5-1913a4e008cb |  | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
text | 51a70221-b718-522e-b320-41d9f70a363a |  | textbox | Date Completed:
checkpoint-group | f153a454-fa28-4b14-b62b-23f76955f258 |  | section | Construction of Access Ramp Bluestone Footpath
checkpoint-status | 7fba1661-5af5-4ece-a0ef-708857e702bf |  | checkpoint | 2.1 Re-levelling of bluestone kerbing and ramp
label | 0d1ff6d0-b93e-57a4-adb1-c002374bc45b |  | note | FREQUENCY: Each Lot
label | 55d3a471-c121-5bbd-9f6f-44e019f57b38 |  | note | ACCEPTANCE CRITERIA: Bluestone kerbing to be re-installed to new design levels. Bluestone kerb shall be placed on a bed of low slump 20MPa concrete, minimum 75mm thickness. Formed groove of 10x25mm in concrete face shall be filled with caulk
label | 22eaee7a-2294-5c7e-a5ba-5d072b5fe431 |  | note | REFERENCE DOCUMENTS: Dwg 1P50201
label | 7f236e87-5ad0-5753-a780-441899617ca4 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 706a4b98-7524-538c-8659-9dc8bab16046 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 9ecc27c0-3db7-59e1-ad16-77d88ad763ac |  | note | IP
label | cebfa0cd-ffd2-56e3-9955-233ca351c406 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | fc5c889d-fff5-535a-8fde-38ca6da7cfe6 |  | textbox | Date Completed:
checkpoint-status | 042aa90c-a509-472f-b5ac-6d72ecd09ceb |  | checkpoint | 2.2 Base preparation
label | 7df007d9-7ae9-5fd3-b023-82de931cfe8c |  | note | FREQUENCY: Each lot
label | aeca823e-e1d2-5390-8d6a-c1c0aed0f7e9 |  | note | ACCEPTANCE CRITERIA: Sound base should be achieved with 50-100mm for bedding materials
label | 76ef5fc8-1ddb-5638-aadc-d6fd4bee5f04 |  | note | REFERENCE DOCUMENTS: Dwg 1P50201
label | 4ab996dc-a468-5533-8cb3-a0c63065891d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d349eac5-20f1-5325-a65d-3967645a8e18 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 126ef5e5-d3ec-5281-bacb-5f85e4df5b45 |  | note | IP
label | 5542865a-c848-5c99-aaeb-edc79837339e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 8ecbfcfa-0c61-56df-9f99-890fb8491392 |  | textbox | Date Completed:
checkpoint-status | 3728a1ab-e6e2-4213-b04a-6465381b89f1 |  | checkpoint | 2.3 Installation of Kerb & Gutter Blustones
label | 3ee56d97-6244-52f8-b626-dedb4d282e9c |  | note | FREQUENCY: Each lot
label | 2f169779-f6ea-5dcb-b9ca-6c84a782f3fd |  | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness Gaps of >10-30mm< shall be provided and filled with mortar.
label | d96020f9-5fb3-58a3-8b02-aabd3172594f |  | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
label | e83e726c-2c9a-529a-bcf3-c055bba54cdb |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 4ba37a8c-1618-5e0d-9e47-21b35b8d59a4 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | e033e206-77c1-5eaa-bfbb-61e99887aa1d |  | note | IP
label | 8772d12f-73b6-53a5-8a33-3c84d68cf539 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 10f67431-785f-5894-873d-1322f8c80891 |  | textbox | Date Completed:
checkpoint-status | 1cc76863-1dcc-4b2c-b6af-d98c26bdbb59 |  | checkpoint | 2.4 Placement of bluestone pavers on mortar bed
label | 63988fc2-7712-55a0-87b8-56793eba1d3c |  | note | FREQUENCY: Each lot
label | d4eb2237-1cb9-5ab9-8f02-8232163227d7 |  | note | ACCEPTANCE CRITERIA: Pavers shall be placed in accordance with Dwg 1P50402 on average 30mm thick mortar bed of sand & cement mixture. All pavers shall be coated in mortar slurry on rear face before laying Kerb access ramp wings shall be at an angle of 45° or as per design and the ramp gradient shall not exceed 1:8. Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
label | 973179b1-9cb0-5536-ace3-d115afe3c676 |  | note | REFERENCE DOCUMENTS: Dwg 1P50402 Dwg 1P50201
label | ad173cdf-6b60-5b28-8eff-84d93d5de3cf |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 8376f787-b372-5107-902d-8167260aa378 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | effe72bb-0052-56b9-aa57-061e3965e23a |  | note | HP
label | 9f1fc268-f65e-5a4b-9877-2764f5a6482c |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 628b10d1-9f77-5e22-9ee2-997cf6e4452a |  | textbox | Date Completed:
checkpoint-status | 49f87046-fb34-4c98-b711-340be5f3b8bd |  | checkpoint | 2.5 Curing
label | d5ac25e0-f0ad-5752-a9e1-6a6266adcd8f |  | note | FREQUENCY: Each lot
label | 6a36d447-30e5-5b37-ae96-33b18aaa5c22 |  | note | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic Where required, ply shall be laid over area of works
label | d5bdb2c7-84ad-59c0-abfc-77aec2f77c41 |  | note | REFERENCE DOCUMENTS: Manufacturers Specifications
label | 736083fa-21c5-5cb5-b8bc-47d838a48aa7 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f0f41911-799e-5ddb-be56-80e9aeeea1ad |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | af9bc0ab-1618-5f93-a027-a3ab842d1275 |  | note | IP
label | 33c88afc-cda9-59c9-beeb-6c4c5c447b6b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 6bf64d62-09f9-58e8-a1cb-406e18404e0c |  | textbox | Date Completed:
checkpoint-status | bf4fa1c9-857f-4f9f-9db1-5c1dd779e5e1 |  | checkpoint | 2.6 Grouting
label | d19502a1-9960-5cec-bc53-009c2d977e62 |  | note | FREQUENCY: Each lot
label | 7c515a70-dc99-5d8f-8e48-2bb3ecdb9fb8 |  | note | ACCEPTANCE CRITERIA: Pavers shall be grouted using Lanko Durabed to specified mixture content. Grout shall be spread & clean appropriately as required.
label | 2dafafdd-ae9c-58b2-bda1-7a51aad5c511 |  | note | REFERENCE DOCUMENTS: Manufacturers Specifications
label | 88dbcd67-b5b2-516f-b38f-828ddf17fb00 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 334fe15c-402b-5249-b75c-3ae13a316f6d |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 8b25f0f1-80e5-5799-90d2-7db921648b47 |  | note | HP*
label | 6114bd38-f29d-5d37-a89c-3eff7cf43448 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 69045bf6-7f4c-52dd-8217-b7cef302796f |  | textbox | Date Completed:
checkpoint-status | 486c5cac-73d1-4652-9665-0178fc5ef76e |  | checkpoint | 2.7 Installation of Versatac Granite Tactiles and Granite Inlay
label | 4a83cfb9-5a64-5b66-9d18-7475ce6ff673 |  | note | FREQUENCY: Each Lot
label | 5b5463ad-6499-5cfb-912d-ad1edaad7579 |  | note | ACCEPTANCE CRITERIA: Granite tactiles and inlay shall be placed in accordance with Standard Drawing 1P50201 with surface deviation of under 5mm.
label | b64b0af9-12b7-5db3-be49-486c3d23a90f |  | note | REFERENCE DOCUMENTS: Dwg 1P50201
label | f14ebd65-f4cf-5f6e-a21e-7452d3f1a0fa |  | note | INSPECTION/TEST METHOD: Verify
label | a362edf4-2729-5f81-9603-3eeea2cd7c2c |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | f9a31461-2dda-508d-bc15-b0accd859462 |  | note | HP
label | 424d42bd-6df8-5c61-8f20-3df21f3653ac |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | a32b07ee-a476-58e3-97dc-bddfd37a0a19 |  | textbox | Date Completed:
checkpoint-group | f72932ed-29f9-4250-bfd4-50f5ea7cc1f4 |  | section | Completion
checkpoint-status | efefcfa7-dc38-4cac-b277-c7c189ae47dc |  | checkpoint | 4.1 Completion
label | 87451054-568e-5756-be2b-c9decdbddd27 |  | note | FREQUENCY: Each lot
label | 535a060e-b0e0-5a29-ae29-219c485f6502 |  | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste Bluestone pavement is free of mortar stains and cleaned to satisfaction
label | d864fa9a-bacf-53c9-9deb-5bf0ca8c3c44 |  | note | REFERENCE DOCUMENTS: Visual Inspection
label | 2d0a96b0-2057-5ca0-aa9e-08f9551d7a5e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 2a2402e2-84ee-5333-8167-d18ca640043c |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 5cc4fe1d-22d7-5540-a9ba-2f7a1f41b6b2 |  | note | IP
label | dc1f0f4a-e91a-547a-90d3-138d09beaed3 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 6e2b4d67-5d9e-5672-9845-2205c6eb2d9c |  | textbox | Date Completed:
checkpoint-status | ed32126a-613f-4a19-a7ea-e326df4104db |  | checkpoint | Final Inspection
label | 5c8f6d1c-fc16-5ec6-84e5-58c8b623e131 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | dec04793-661d-57b6-a2b9-7c1562f14aa9 |  | textbox | Print Name:
text | 210132a6-9b5d-5fd8-8f62-a36ef4d0da1d |  | textbox | Position:
text | be62c7f8-80d4-5ddf-ae58-6d043228323e |  | textbox | Date:
checklist-sectioned | 1ce6797f-d51e-4033-9607-d5923e46636c |  | checklist | ITP-007 - Concrete Track Slab Pour |  |  |  |  | Yes | ITP-007 - Concrete Track Slab Pour Rev2 | 1d7bbd54-65e5-448b-9941-e1dbe69a2f62
checkpoint-group | 7573ddb6-51e4-4823-a3b1-1525b3f16f5f |  | section | Preliminary Works
checkpoint-status | 95f4a151-8f9c-4ae3-baa9-5d62264affa6 |  | checkpoint | 1.1 - Check for correct documentation
label | ee857424-c0fb-538e-9f68-ac109d69fae2 |  | note | FREQUENCY: Prior to commencing any activity
label | df932296-2db0-550e-93ae-de804f34ba07 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 667f2216-43f3-54f3-b6a0-dc9bc4e425fe |  | note | - using the correct and complete set of drawings
label | 280cc5bb-df7f-5b6c-9571-6d2989b9d460 |  | note | -all drawings are the latest revision
label | 09b20c06-7140-5799-beb5-d3b19bfb8d0a |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 7c7c3d8b-a184-5db6-a0a7-c50cd53ee161 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 9cab7367-16df-52bc-8412-e8fc3db44066 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | e2a570ba-2c5e-5b2f-8874-6069489c9f4b |  | note | HP*
label | 1ba1ce18-77b8-503b-a515-a354ae2a7721 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | c64fe870-941d-5743-8757-87fa80de2f78 |  | textbox | Date Completed:
checkpoint-status | b74895e9-1c0a-4413-8fe2-39f1007662a1 |  | checkpoint | 1.2 - Submission & Approval of Concrete Mix Design Prior to Commencement of Project
label | ff5b598d-4a85-5fe2-9675-943fc266d23f |  | note | FREQUENCY: Prior to first concrete pour
label | 96b80d78-31d4-5f4c-a98f-e5c8695239b9 |  | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
label | 67137bfe-d298-5930-b25a-63052b392f41 |  | note | Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
label | 722fef58-1b6a-5b00-8ad8-d3973623aa4a |  | note | Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
label | 6752e1da-5584-56f9-8121-b04b8350c669 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033
label | b100e7d1-1c41-5759-b4de-69fc8b8302bd |  | note | INSPECTION/TEST METHOD: Verify
label | 2b063d62-76b9-596d-b6e7-139cdb3d6165 |  | note | RECORD OF CONFORMITY: Mix Design ITP
label | abfd35c4-34cc-5f79-bdd2-f3d5b0dc192a |  | note | HP*
label | 0bf96026-6b55-5bb8-b787-af69bf130beb |  | note | RESPONSIBILITY: FH Engineer / Superintendent
text | 515c8055-41fa-5e2d-a6de-d35cc164a2ce |  | textbox | Date Completed:
checkpoint-group | 285581b7-4bd3-4240-8dac-82e6f3592690 |  | section | Construction Works
checkpoint-status | 077e157d-05f0-4cbf-bb61-f5183db8a93c |  | checkpoint | 2.1 - Weather Monitoring
label | 9b81781f-b0ec-5c27-86f9-8dc8974c5913 |  | note | FREQUENCY: Prior to start
label | 59055cb9-0c5e-57b6-9141-8b765e0f1ef7 |  | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
label | be58d2ab-671f-525f-93b5-dfd05415f689 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.10
label | 27fd0530-f40f-57ae-90aa-f8ca57f2627c |  | note | INSPECTION/TEST METHOD: Verify
label | 37d938f4-3c87-543c-9215-3aa10d512b4c |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 682d2c61-dcc2-5c6c-bcfd-9e7f686e467e |  | note | HP
label | 173ddbfd-e7bb-5357-816c-fa1b14570cea |  | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
text | 709dd92a-1d37-53aa-b867-0a96d68804e4 |  | textbox | Date Completed:
holdpoint | cdb9a3fc-2b16-4d57-a1a8-db02cdef6a06 |  | signoff | Authority holdpoint
checkpoint-status | 81c139af-a909-421f-b89a-30809d6f4564 |  | checkpoint | 2.2 - Surface Preparation
label | 55d84d11-2861-5384-aee4-eecee09a62ab |  | note | FREQUENCY: Prior to start
label | 346afd86-0f65-519d-ab61-2ec80e8a2820 |  | note | ACCEPTANCE CRITERIA: Crush rock surfaces shall be moist and thoroughly cleaned of all foreign and loose matter prior to pour
label | 6a58cbc9-82c0-5090-9109-c3ee90082332 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033
label | c49010e5-41b0-514f-80af-368a00ec17f3 |  | note | INSPECTION/TEST METHOD: Verify
label | dd742909-cee2-5d20-81eb-9f3fa0a01faa |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 636dce9e-7f3b-539d-bf18-29dac39b82cd |  | note | IP
label | 59ae8e94-f00b-5a41-8909-c0c9ab87e715 |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
text | 23269c63-10e9-5332-a6ab-88b523c8b1f6 |  | textbox | Date Completed:
checkpoint-status | bacc303b-97ab-4a91-8a07-e5d28b68c8eb |  | checkpoint | 2.3 - Setting Out
label | 88bac1e6-6379-50e9-8e62-d5bcdd126fe1 |  | note | FREQUENCY: Prior to start
label | 5b847524-8eed-5288-a2d6-c062dc3596a4 |  | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications. No survey/level pegs to be removed by any persons until completion of works.
label | c97d97a1-87a5-5947-9070-5ea26aa91a70 |  | note | Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
label | fcf77c11-eb57-5edb-b3f5-ba355a618de9 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033
label | 3f132706-6d2f-513b-b2ad-5312fe152b08 |  | note | INSPECTION/TEST METHOD: Verify
label | 2923c12d-8d2f-558c-a122-a4875ee3a04a |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 149b7d97-87f6-52d9-ace8-f04d4ed80062 |  | note | IP
label | bac245a9-264f-545c-82c7-1faff91d7395 |  | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
text | 7b1e6a40-043a-53b3-a7ff-a04c9626d75f |  | textbox | Date Completed:
checkpoint-status | afcdcadb-cf75-45d6-8dd7-2e7ee849dbcb |  | checkpoint | 2.4 - Formwork
label | dc92854c-cce3-55fc-adc8-3893dc98d871 |  | note | FREQUENCY: Prior to start
label | f99bb01d-d5d7-5dbb-aa06-9b63aa4f93a8 |  | note | ACCEPTANCE CRITERIA: Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement.
label | e4575ac9-c560-5ec1-b628-c9dc42c2bacb |  | note | The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings.
label | 0e3d0a05-828d-5443-a2e4-3ba857914cc0 |  | note | Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent.
label | 785e66be-b1c4-54e5-b182-77b42835632e |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.9
label | de7db1d9-7358-56f0-b3d8-0bf85a6a7f16 |  | note | INSPECTION/TEST METHOD: Verify
label | 8c36e20d-cad7-57d5-8f86-83946eb61369 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 6a4ba589-dd7a-5eec-9ab6-79275642de07 |  | note | WP
label | 2cb850d7-5029-5829-ab94-11e2d44c9361 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 34619dad-c35f-5b42-a9ac-fde25f581172 |  | textbox | Date Completed:
checkpoint-status | 227f7cb0-a882-403b-b85b-c814e91bc347 |  | checkpoint | 2.5 - Reinforcement
label | fed8968b-ec9b-5fd3-97b5-64fdae48896c |  | note | FREQUENCY: Where Required
label | 57500128-42c5-5782-a50c-fa651eb83896 |  | note | ACCEPTANCE CRITERIA: Ensure that all reinforcement is placed as specified by construction drawings.
label | 8e57bb31-1c5a-5e0b-b2e7-608e43197f89 |  | note | All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
label | f8042961-c72d-5f0c-9610-fbf49417b412 |  | note | Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and ied with wire at a maximum spacing of 500 mm.
label | 5c9d6253-e208-5419-a9a4-5982ac1af5e7 |  | note | Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
label | 53b6c89c-9d28-5e9d-8bfe-44e9129b7857 |  | note | Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
label | 52de4106-4316-5729-b49b-71a3b0118468 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
label | bbc4abbe-5752-55fe-92dc-80b2641fa87b |  | note | INSPECTION/TEST METHOD: Verify
label | 00277aa0-f849-5f09-b213-313a785413dd |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 7a69909d-9a27-564a-a2e9-120cc9744aab |  | note | IP
label | ec132ec0-988b-552a-829b-06f896cfaa72 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2ba1e866-0ed2-5976-bcca-dc9073e7d57d |  | textbox | Date Completed:
checkpoint-status | b99e4786-f44a-4073-8cec-6b06962c6d91 |  | checkpoint | 2.6 - Dowels
label | 86f62947-55cf-5c24-bf41-2ad02ab7ab62 |  | note | FREQUENCY: Where Required
label | ad65bc98-efc3-5b94-b6f7-59af1ef28bff |  | note | ACCEPTANCE CRITERIA: Ensure that all dowels are placed as specified in the construction drawings
label | 1e3cc1b0-47dd-5403-8007-5bee65de76c5 |  | note | All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
label | a0566b04-6102-596e-b857-ffde4e0b3d86 |  | note | Dowels shall be clean and free from mill scale, loose rust or oil.
label | 2810edff-3e7a-559f-b14a-22ce80d7111e |  | note | Ensure that all dowels are securely held in their correct position until the concrete has set.
label | 52e4c036-868c-5c2f-a190-d5bce12e2610 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
label | ff0f2061-49f9-5ec1-8a90-02aacabbd8c5 |  | note | INSPECTION/TEST METHOD: Verify
label | 6a6ce224-a5d7-5256-9738-6e704cc89d85 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 407c16c9-735a-55a3-ae5b-f6309ba12de7 |  | note | IP
label | 9a3a64ad-18d8-537e-8a15-28ec6425b0f3 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 1b516b76-2e40-5ba6-b071-27f22884b08e |  | textbox | Date Completed:
checkpoint-status | c35ff610-a18d-4607-ba58-049848f0c7d5 |  | checkpoint | 2.7 - Pre Pour Inspection
label | de203b85-5c77-5ce8-89c6-6ea1d68e6453 |  | note | FREQUENCY: Prior to start
label | c0038681-3e78-5172-8b46-f4d1fd8f0631 |  | note | ACCEPTANCE CRITERIA: • Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180degree difference in gauge placement
label | c1124da6-e29a-5126-a8ed-20ccaaf43ab2 |  | note | Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure
label | b42dab07-a8ca-5956-b377-b1625f874104 |  | note | Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
label | 0d9f4777-c629-5b19-b3c4-66df6083016d |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033
label | 4ecc14e3-8935-5bfd-bfb1-1dc581703433 |  | note | INSPECTION/TEST METHOD: Inspection / Test Method
label | ae292319-e7e1-534b-9d0e-3588dd80850a |  | note | RECORD OF CONFORMITY: FH Track Inspection
label | 453f01ad-c13a-51f8-9632-be2e6dcd1d99 |  | note | HP
label | c9856493-ae69-504c-bdc6-c38a92b98885 |  | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
text | e8a3d328-941e-5c36-ad1c-27f42893ad70 |  | textbox | Date Completed:
holdpoint | dbbdf0fc-eb6e-4fd7-8968-94a2eedb6049 |  | signoff | Authority holdpoint
checkpoint-status | a2488d4f-f070-441f-b37f-0cca5d9c6fcc |  | checkpoint | 2.8 - Carry out sampling of concrete
label | 99c66ec4-33a9-5770-8143-744c9f37199f |  | note | FREQUENCY: Each concrete pour
label | 65686a19-5707-5b89-95a0-7bc137055684 |  | note | ACCEPTANCE CRITERIA: Slump:
label | 57ef3a76-e9a3-5914-9352-74fd4b35e6fd |  | note | Concrete Slump shall be 75mm +/-20
label | ee5ee354-280c-506b-b24c-b4020872d612 |  | note | Compressive Strength:
label | 1f54b83e-ae63-5ee6-92a1-3dabebf9b309 |  | note | Shall be measured in accordance with CE-019-ST- 0033
label | 6d5429ea-44d6-5687-99c1-5de7c591fafb |  | note | • Testing frequency =
label | 3b7fe8c1-80f0-5c86-ae7d-8b1801d24e15 |  | note | - 0-50m3, 1 sample
label | c401e829-1f36-50dc-bc4f-63075430e43b |  | note | - 50-100m3, 2 samples
label | dc32b76c-6750-502c-9438-d530dcae6383 |  | note | - 100m3 +, 3 samples
label | 9c184d68-620a-55e7-be13-fae9627e379c |  | note | Each sample shall consist of 4 cylinders
label | c7c36110-b17b-5851-b662-e28ef124a17f |  | note | Test Results will be provided to the Superintendent
label | 0a7326b7-dcb5-5035-a33a-0f99ab7b8361 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5 & 4.7.18.4
label | 2bc27874-6ef5-5482-9d5e-0890f15b8219 |  | note | INSPECTION/TEST METHOD: Verify
label | 7b577220-9dc0-5802-95e3-6b79df573a86 |  | note | RECORD OF CONFORMITY: Concrete supplier test sheet
label | c45af8e7-a824-5ce1-85e8-fd33df8a5ceb |  | note | TP
label | 20cc6289-d26f-507e-bffc-5f3b3e0d3000 |  | note | RESPONSIBILITY: Fulton Hogan Engineer/ Superintendent
text | 9c3b0335-8145-5073-ae07-5914f3e100a9 |  | textbox | Date Completed:
checkpoint-status | 1fb87705-8d95-4ce6-8c42-11de6e92264a |  | checkpoint | 2.9 - Concrete Placement
label | b27d8f08-e2ce-5579-abc1-22502136fef2 |  | note | FREQUENCY: Each Lot
label | a2583a0a-6d66-5f5f-840b-0d17acaf5240 |  | note | ACCEPTANCE CRITERIA: Ensure formwork is clean
label | 7a2b4018-d96d-5435-9234-23c1f82e3527 |  | note | Concrete shall be entirely discharged 60 minutes after batching,
label | 94ae6b2e-e4ba-5aef-b8d4-939f6e08d06a |  | note | Ensure that pouring does not occur from a height greater than 1200mm
label | bd18e3c1-ce6a-5c36-b262-6bb899434a3d |  | note | Concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation
label | ae5dc2a6-41b3-5781-a807-2a1ed1e3b6fb |  | note | The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage
label | 48854429-7daf-5eff-9b76-7297528a39a2 |  | note | There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
label | c2dc1fd6-5271-5df3-b76f-3d0b881192f2 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.6
label | 9e082f55-b5ff-5f44-8bba-4cdd551aa37e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 7c58e271-bd69-5f67-86ff-9bcf155d86b3 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 93773ae1-ca10-51bc-b18e-b7499ed68496 |  | note | WP
label | 10a48503-e40f-5e98-a738-05a64b161972 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 595bf7b8-8439-5cae-9952-0d133f289b1f |  | textbox | Date Completed:
checkpoint-status | 9559c3f6-a684-4549-ac56-818fece1d92e |  | checkpoint | 2.10 - Compaction
label | 89cf7682-5439-5166-aff1-854b54d2f8ef |  | note | FREQUENCY: Each Lot
label | e6fbcb0f-9c1b-5f59-bb68-6179a22c6bd6 |  | note | ACCEPTANCE CRITERIA: Immediately after concrete placement, compaction shall take place with an approved vibrator
label | cdfdcb50-af60-5255-8224-e19d30366214 |  | note | Vibration shall take place until exposed concrete surface is free from air voids
label | 9e17ef20-dc8a-5aeb-8487-bd043006e616 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
label | 9f2c99ba-7590-557c-8430-673ac7e7ce5f |  | note | INSPECTION/TEST METHOD: Visual inspection
label | e2f3469e-9f67-5033-95b1-7a4094433224 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | c6f2dc56-00f1-5a3a-aaab-56372a0aeeab |  | note | IP
label | aaf0f5e0-c8d9-593b-b7ba-43aaef90b1bd |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 145ff878-eef1-5dad-b0e9-b6fb390a3d25 |  | textbox | Date Completed:
checkpoint-status | 1a0b6e06-10b6-4f93-bc5f-7e57634e7891 |  | checkpoint | 2.11 - Record location of each batch
label | ac5a70bf-b8a8-5326-bc88-8fa75edbd284 |  | note | FREQUENCY: Each concrete pour
label | ed1f0d35-040e-56ee-8dbd-4d6c54469f45 |  | note | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
label | ed5cdaac-b529-5a01-9331-7e5413c0abce |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033
label | d11e68a8-6bf8-5ac5-a917-1644ff3a9d3e |  | note | INSPECTION/TEST METHOD: Checklist
label | be03f9c8-e730-5227-a432-6016d190a0e6 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 1a3467fe-58c3-51c4-9e87-9eb434cf15ee |  | note | IP
label | a0c3f4d3-f6a4-51e5-9ed5-c2dc1236bc7f |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2e99c1d6-c3c0-5530-a0c2-a6802d7110bd |  | textbox | Date Completed:
checkpoint-status | becc21b1-ceb9-4418-aa74-644241e19c24 |  | checkpoint | 2.12 - Curing
label | 3f8f2d4d-354e-5182-b897-b60e32865cc4 |  | note | FREQUENCY: Each concrete pour
label | 4729015b-e57e-5c50-ab06-a1e81f4c11c3 |  | note | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming
label | 1205bdef-7f37-5324-ba72-9e064244e4e2 |  | note | Concrete less than 4 hours old shall be protected by covering with waterproof covers where appropriate (Concrete to surface).
label | c7cc748e-de7d-59ce-b67f-3714eeb51151 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5
label | 4d10fc7d-ad76-57a0-ad4c-d97d55eb7534 |  | note | INSPECTION/TEST METHOD: Checklist
label | bbbbf519-c6ce-5522-beee-4e6b0c6bfb00 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | e0495389-9f3c-53f3-b39d-1b744b519214 |  | note | IP
label | 0f5c7335-8ed5-55c9-822a-941bd33c4640 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 3fccf8a6-8e27-5461-a658-d73212281cee |  | textbox | Date Completed:
checkpoint-status | e1306be6-50f6-4dde-a1e5-f90a65680b32 |  | checkpoint | 2.13 - Tolerances
label | 5d7ac8c6-2daa-5f26-a0c5-19813130b1bd |  | note | FREQUENCY: Each concrete pour
label | 0e73cf87-17ae-5e55-8f2e-40561a0af132 |  | note | ACCEPTANCE CRITERIA: All concrete shall finish true to the dimensions, the following tolerances apply:
label | b8d278a0-d66e-5bb7-8e50-68b4be681fba |  | note | Plan dimension of slab +10,-10mm
label | 24594932-2d14-5681-975a-4d33369afe96 |  | note | Thickness of slab +10,-10mm
label | d0966fdc-fd4e-5acc-aa40-8289626a7ba4 |  | note | Cover to reinforcement +5,-3mm
label | a49151c7-37d7-5558-a336-7ffd745f35bb |  | note | Finished level of slab +3,-3mm
label | 5ce53748-897a-5d74-a6c6-90d853c31636 |  | note | Foundation level of slab +0,-20mm
label | 77686c58-859f-5516-b0ef-4cff54bb2969 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
label | 2e73a78e-0cf3-591f-b00f-25919afef0a1 |  | note | INSPECTION/TEST METHOD: Checklist
label | 1a7e3e41-09dd-55e7-9153-deef1b4ed9d3 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 0903f12e-0075-5a34-8d15-bc1932e93d64 |  | note | IP
label | a1a9b94a-1518-5ea4-954b-ed5c1d79a4de |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 6f6e6220-b363-59e0-ba57-dd430d6e9a1a |  | textbox | Date Completed:
checkpoint-status | a0bca0b6-9fa8-4d36-9d6a-a3a9bc4ff942 |  | checkpoint | 2.14 - Slab finish
label | d3b36911-b163-52a8-9baa-c1f5f7f43a9f |  | note | FREQUENCY: Where applicable - if track is Type 1 structure
label | abc8befb-4ca7-57f5-9474-9a0c31f0212f |  | note | ACCEPTANCE CRITERIA: Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities. All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections.
label | 48a2f81c-556a-5be4-91a4-6e833833c8c0 |  | note | A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C.
label | c9b3c88b-5322-579f-8c4d-2c072a9458ab |  | note | The slab surfaces shall be broomed to provide a non- slip finish.
label | 01579e79-f3a1-5660-bb58-004f150e4644 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.17
label | 87ed8d9b-3b7d-5519-ac73-e39f7d3cb86d |  | note | INSPECTION/TEST METHOD: Checklist
label | a1526ff6-5af9-5067-b3ba-ca21fe997d40 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | d4bdb06c-342e-50c4-80e4-9c7b6d78975d |  | note | IP
label | a1e03b47-f3a6-5145-9c8a-bc28c1f076a9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | f0f41690-eafc-5958-93a1-de52182c0dc0 |  | textbox | Date Completed:
checkpoint-status | bb8c182e-c8e8-4e0b-9aef-cb20e89cd0ae |  | checkpoint | 2.15 - Post Pour Inspection
label | 7cc1f174-4ba2-5ab6-b6d3-31e6893fd9ca |  | note | FREQUENCY: Each Lot
label | ddae189f-952b-558f-a474-eb2d2b7d10ab |  | note | ACCEPTANCE CRITERIA: • Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
label | b43f74ea-e40a-51b9-8a9d-a5896ec00ee0 |  | note | Ensure no defects are present in slab
label | 0c14ab92-abc3-5d8b-b053-fe9581c071ca |  | note | Complete Fulton Hogan Post Pour Checklist
label | 43608c17-a3bc-5364-b8bb-3ecf34f13d07 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033
label | 57cf9234-707f-5ae1-ae49-4d7a10d85bb5 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 02fa2d51-8844-528c-9d45-e27dc9d7c8d4 |  | note | RECORD OF CONFORMITY: Post pour checklist
label | 5d3ef81b-e998-5d4b-bb79-4303d236a702 |  | note | IP
label | 00006a23-488a-5239-89bb-6cb62837bff0 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2b7741f5-0dfd-5c63-8618-31604700b047 |  | textbox | Date Completed:
checkpoint-status | cb652dcf-ad5a-4982-9db4-f0865dbf0643 |  | checkpoint | Final Inspection
label | a85b2083-49c9-593c-905c-2d1b35e0cb24 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 03facfaa-e37c-5e08-8a88-8c3c7ab055b5 |  | textbox | Print Name:
text | aa29a5da-bd80-5f5c-b6c2-688a457dcfcf |  | textbox | Position:
text | bccc0b8b-2322-5347-a8e9-065cce305ec4 |  | textbox | Date:
checklist-sectioned | a7f1f03d-db95-4641-bc12-a3d0b45b2292 |  | checklist | ITP-040 Profiling |  |  |  |  | Yes | ITP-040 Profiling | 231982a2-a7fe-4c13-a1fa-43f53c5589fe
checkpoint-group | a3145305-e412-4ecb-b98b-f9132961c192 |  | section | Preliminary Works
checkpoint-status | 7cf6bd6a-4c44-447c-912f-6857ddf6d9df |  | checkpoint | 1.1 Check for correct documentation
label | 97c54224-c447-5197-9069-e4495b0bedfa |  | note | Frequency: Prior to commencing any activity
label | 6daecadc-f256-54de-a1e4-02d4b402b0a2 |  | note | Acceptance Criteria: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
label | 59518539-7c59-5db8-aa89-76259c219fd6 |  | note | Reference Documents: Drawings and drawing registers
label | 3107d175-5d2d-5513-b8dc-6c8c181ed93b |  | note | Inspection / Test Method: Visual inspection
label | 84ee334e-7c0e-5015-a99b-26d982019d43 |  | note | Record of conformity: This ITP signed
label | e563d5d2-ce90-595d-b0eb-e7e70c5967a0 |  | note | HP*
label | 621fde66-b294-5590-9cbf-910e7301f7e4 |  | note | Responsibility: Fulton Hogan Engineer
text | 88d64e37-9477-511b-82e9-87c0f0e7503a |  | textbox | Date Completed:
checkpoint-status | d4e12744-a2f9-4876-9dc3-3b0a8a46d09f |  | checkpoint | 1.2 Implementation of all measures and controls
label | ac22608f-a399-51f6-9652-43729f65fd48 |  | note | Frequency: Prior to commencing any activity
label | 91471fae-f9a6-5454-a42f-19e4b46952a2 |  | note | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 82b39f5d-abc9-5699-9f6f-973f81121f10 |  | note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
label | 6244853a-5390-576a-a62b-b03ebda2f286 |  | note | Inspection / Test Method: Visual Inspection
label | b778c2c7-28b8-51b0-b2b0-dc8bf28e535b |  | note | Record of conformity: This ITP signed
label | 0c434e1f-be73-50b5-9640-a13dcabc33a3 |  | note | HP*
label | 16439db9-b58c-59be-a752-8f7175f9f3fb |  | note | Responsibility: Fulton Hogan Engineer
text | 0bede1d1-d38b-58e9-8e37-9594dc217b07 |  | textbox | Date Completed:
checkpoint-group | 6fe56937-938d-425a-997f-beea7392fab2 |  | section | Construction Works
checkpoint-status | 67cab5d9-09d0-44d2-946a-eefa468169e6 |  | checkpoint | 2.1 Profiling Works
label | 4449d6a1-c799-50c9-adaf-79e36131d89b |  | note | Frequency: Each lot
label | 48a4f441-7eaa-539b-a0b1-7f3440a35f02 |  | note | Acceptance Criteria: Cold planing shall be carried out in a manner such that a uniform surface is present on a plane parallel with the ultimate finished surface of the pavement
label | a26641c2-959a-53ef-b76a-748f2b5b087f |  | note | Reference Documents: 402.02
label | 647162cb-a223-544b-8a45-828eaa202bbb |  | note | Inspection / Test Method: Visual Inspection
label | f016e26b-c0f7-59a4-8c0e-ec6e9f51f1dc |  | note | Record of conformity: This ITP signed
label | 6f1fdb96-f7dc-50a4-90b7-c396d507f36e |  | note | WP
label | 9c3814cd-0956-5f11-a2a3-15769a02c460 |  | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
text | 7912f9aa-45a9-51be-bb84-48a979b3023c |  | textbox | Date Completed:
checkpoint-status | 5b31bde6-386c-4dd6-b5cb-5a42c77678b6 |  | checkpoint | 3.2 Depth check
label | 66fa1fdf-bde6-5679-9c88-1b3a528f8584 |  | note | Frequency: Each lot
label | 602d82c0-6c6d-54dc-9278-19e7cab3cf3a |  | note | Acceptance Criteria: Ensure average depth of pavement removed is in accordance with relevant methodologies. Ensure a maximum of 50mm to be removed per pass. After planing, no point on the planed surface shall be positioned more than 15 mm below a 3 m straight edge placed on the planed surface in any direction.
label | bf58295b-16a7-570b-b100-0b9c5aaa37a1 |  | note | Reference Documents: 402.02
label | 229ffd84-1ac3-56f8-bc36-1d40fde0cdf6 |  | note | Inspection / Test Method: Visual Inspection
label | b5863a80-7f03-5443-83d0-34f1cc80aaf9 |  | note | Record of conformity: This ITP signed
label | ada234b2-e3d4-532a-a403-07d24d1f0a4d |  | note | WP
label | 2a388f4a-960a-5c31-8cae-db469e23dbc9 |  | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
text | f14389a4-fa57-55c6-9ba4-6a21d5e72654 |  | textbox | Date Completed:
checkpoint-status | 233c163b-51d1-4847-9780-8389d65d5e8a |  | checkpoint | 3.3 Temporary ramping (longitudinal)
label | 0e4d81f8-239e-5698-9e73-7fd78eabfa4b |  | note | Frequency: Longitudinal edges
label | 95e44ac4-5ff1-50e0-8d83-4801e8a5612d |  | note | Acceptance Criteria: Any exposed longitudinal edges within the trafficked area shall be ramped down at a slope no steeper than 5 horizontal to 1 vertical.
label | ffb5a7d6-da2a-5cde-bbdb-29386b0a10f6 |  | note | Reference Documents: 402.05
label | 830aeb40-de89-5cba-afa3-0171d6903e9d |  | note | Inspection / Test Method: Verify
label | bec4641a-1028-558f-bcae-f65a6b7fbde9 |  | note | Record of conformity: This ITP signed
label | 95a47d7e-642e-5295-9e59-db63c3f57b2b |  | note | WP
label | 22086039-271f-519d-b349-e076343ae56c |  | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
text | 5d0360ba-baf5-5b7d-85b5-1e20dca8d77f |  | textbox | Date Completed:
checkpoint-status | 060193d4-3b8e-414f-ad58-8123a12e8c65 |  | checkpoint | 3.4 Temporary ramping (transverse)
label | 3902fe53-38e8-5c24-ac4c-bf5642cb297a |  | note | Frequency: Transverse Edges
label | 0d87018c-74bd-599d-8904-d18b69c2a7f0 |  | note | Acceptance Criteria: Temporary ramping shall not be steeper than 20 horizontal to 1 vertical for traffic speeds of more than 75 km/h or 10 horizontal to 1 vertical for traffic speeds of 75 km/h or less
label | 2e10ada8-219a-506a-a78b-3d940bfeb200 |  | note | Reference Documents: 402.05
label | 7780f9ca-021e-57fb-90f1-3298d0403068 |  | note | Inspection / Test Method: Verify
label | 8962aa8a-0d94-568b-8c97-a1d0462721fb |  | note | Record of conformity: This ITP signed
label | 40fcde4f-b4af-50ba-8102-1e9a8c12a237 |  | note | WP
label | 71e948e6-ec5f-58d1-afbe-ac8474c3df1e |  | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
text | 64f82dbd-01f0-5ca6-90f2-3b80447a5cce |  | textbox | Date Completed:
checkpoint-status | f774ef02-473d-4432-9df8-fb8ceeeebd3d |  | checkpoint | Final Inspection
label | 2ba2d2e8-1642-53b2-ab2a-ecd625c182a7 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | d1b51efe-c36a-505a-afe1-6e7869c67307 |  | textbox | Print Name:
text | fc2ce66f-00d1-5efe-b4dc-0b122b8b2913 |  | textbox | Position:
text | e2f61699-30d0-5667-b70a-7377a6cc6773 |  | textbox | Date:
checklist-sectioned | 61b0af87-1424-4859-b3d0-cf322d0d5c7a |  | checklist | ITP-004a - Class 2 Base Course Placement Rev2 |  |  |  |  | Yes | ITP-004a - Class 2 Base Course Placement Rev2 | 2eec0feb-730a-477b-9958-7e16cd5bb074
checkpoint-group | 0dcded0f-6911-427a-b297-aeb69d34c2d7 |  | section | Preliminary Works
checkpoint-status | aa9057b8-6923-4779-808b-6ce9e42f2c4f |  | checkpoint | 1.1 - Check for correct documentation
label | eef91d5a-f837-5839-930f-5473b2497aab |  | note | FREQUENCY: Prior to commencing any activity
label | 84db9e43-3dd8-5df6-be5f-62c69ddde189 |  | note | ACCEPTANCE CRITERIA: Ensure that employees and subcontractors are using the most current and complete set of construction drawings.
label | d02c4a52-4474-5194-910b-4c7161923dcc |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 30c0e7a3-73f5-5b72-a7eb-f13a26e15dbd |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 5a4ac37e-af0a-5ead-8598-72047698c2c1 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 62535004-9aa8-594f-8daa-aa3f02596fa3 |  | note | HP*
label | ece700da-f66e-586c-9256-f71cfc6ec07b |  | note | RESPONSIBILITY: FH Engineer
text | b0384619-674c-5c6c-985e-58ee3d37a1f6 |  | textbox | Date Completed:
checkpoint-status | b8dfa60f-643e-424c-bbc8-40d0ef911d3f |  | checkpoint | 1.2 - Implementation of all measures and controls
label | fc7dcc62-2082-5c5c-8cc1-52bc0a723c98 |  | note | FREQUENCY: Prior to commencing any activity
label | 1a680cde-7660-5501-bb79-5ddc5578053f |  | note | ACCEPTANCE CRITERIA: All necessary project measures and controls are being implemented, that is: EMP, TMP, SWMS & WP
label | e7851ce6-2936-5ed5-b5be-65dee865138e |  | note | REFERENCE DOCUMENTS: EMP, TMP, JSEA, SWMS, WP
label | 0b551fb5-d5b9-58c4-8844-af21ff81c2f1 |  | note | INSPECTION/TEST METHOD: Verify
label | 5ed90e30-9a9b-5a2f-9388-dc44e7a89477 |  | note | RECORD OF CONFORMITY: This ITP signed
label | a069b083-00bd-549c-9e05-30f28dfc61e2 |  | note | HP*
label | f0f6985b-2521-5b9d-98dc-a5d2c732ac7f |  | note | RESPONSIBILITY: FH Engineer
text | 327a8ca3-d198-5ff9-a867-d6ba43fc9043 |  | textbox | Date Completed:
checkpoint-status | 3ec7999d-fe67-4e4d-89df-5043215e03e6 |  | checkpoint | 1.3 - Material Compliance
label | e82ac387-ff02-5e15-ab93-3eefc5250091 |  | note | FREQUENCY: Prior to commencing any activity
label | 1bf9ab70-5939-5955-a56f-ae13922abd44 |  | note | ACCEPTANCE CRITERIA: Ensure that the base course material complies with the requirements of VicRoads Standard Specification Section 820.
label | e904aa9d-c9fa-5645-a247-8ee3a53e8d93 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033
label | a358e1e5-8eeb-5535-a9dc-f3f257f7f5c3 |  | note | INSPECTION/TEST METHOD: Document Review
label | eb0466f9-bd69-5d68-95f4-1046c3bfe706 |  | note | RECORD OF CONFORMITY: Test Reports from supplier
label | 1dac424b-f976-5139-bb61-b381a7b925bc |  | note | HP*
label | ced59007-5c8b-5fc4-9c04-c979b360e1f6 |  | note | RESPONSIBILITY: FH Engineer
text | 8adf8e0b-46ae-5575-bd2a-eaa29414b272 |  | textbox | Date Completed:
checkpoint-group | e2218d35-1110-4789-a69e-5876e619e25f |  | section | Construction Works
checkpoint-status | 65b2037f-7e03-43ce-b996-a938436deb28 |  | checkpoint | 2.1 - Sub Base
label | 8daeafc4-a682-5c4e-af73-522275246ecd |  | note | FREQUENCY: Each Lot
label | b888a4e1-9d3b-5cc3-902b-eaadd50ad384 |  | note | ACCEPTANCE CRITERIA: •Sub grade has been inspected, no visible ponding, springing presence, or visible deformation. •ITP-001 HP for subgrade inspection signed off
label | ba22bed7-ddc4-58b2-9505-94dfafbcf2cf |  | note | REFERENCE DOCUMENTS: VicRoads 173.03
label | 66e97eea-806e-54e5-b4d2-0e243fd0e8db |  | note | INSPECTION/TEST METHOD: Inspection / Test Method
label | e174b0f7-6cd8-5d29-874f-38508af138f6 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 3d3aa363-9310-5347-8030-7fb946a02060 |  | note | HP*
label | 7f97e0fb-e641-5fb2-84c6-dc5a3f07648a |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 1099080b-28cb-5b02-aff0-bdf51ef921dc |  | textbox | Date Completed:
checkpoint-status | ccd23935-1f11-4dfb-8437-9b4fc9e1c91c |  | checkpoint | 2.2 - Spreading material
label | 9e2b7c62-1dc5-58c3-b5c9-67b03ea11e9a |  | note | FREQUENCY: Each lot
label | 8f966443-2fd9-52c2-a085-1ce0f0d2b7d9 |  | note | ACCEPTANCE CRITERIA: Material shall be spread in such a manner as to minimise segregation of the material into fine and coarse components. The pavement material shall be spread in even and equal layers more than 60 mm but not exceeding 120 mm in compacted thickness
label | ed078c52-eda9-5ee9-849c-3c8eeaed2936 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.2.
label | 187ad34a-5dec-5c13-b603-cb88931b35ae |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 8d744c30-ed30-584f-a72c-401373f8cfc7 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 28099315-bed7-5049-8c33-d3bce69d5758 |  | note | IP
label | eddcbe64-d787-5c47-99ae-67faa5c4d88c |  | note | RESPONSIBILITY: FH Engineer
text | 65e3ad3b-761e-56a2-9fb1-1a5af70933ad |  | textbox | Date Completed:
checkpoint-status | e8aa4bbf-c360-4e34-bcea-1681091275fa |  | checkpoint | 2.3 - Compaction
label | 5d7ad225-482c-597d-9110-863daa2445f7 |  | note | FREQUENCY: Each lot
label | dabf21ad-be7b-5980-8c10-68e910937fb3 |  | note | ACCEPTANCE CRITERIA: Immediately after spreading the material, compaction is to take place and moisture is to be applied to maintain moisture content within 1% of optimum moisture content. Each layer of material shall be separately compacted to a density of not less than 95 percent Modified Relative Compaction. Compaction of earthworks shall be carried out at a moisture content appropriate to the compacting equipment being used and between 85% - 125% of the optimum moisture content found in the compaction test. Compaction testing shall be carried out once per days production and shall comprise of three samples
label | b94ad6da-b02f-5a95-854f-fb0045334c40 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.8.1 & CL4.2.8.2.
label | 96f757bd-8e2c-5c0d-bb6d-135467a3032d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 1a326134-5b92-5d5d-937d-561080adccf0 |  | note | RECORD OF CONFORMITY: Test Results
label | fc686ef0-37a9-562d-b112-dcfbaa564523 |  | note | TP
label | 58387605-66b9-52cd-82e4-bcfa483a3bd2 |  | note | RESPONSIBILITY: FH Engineer
text | f32ea8e2-a01f-5968-80a6-0c6e9b99fa3a |  | textbox | Date Completed:
checkpoint-status | f701963b-3aa8-415e-83ae-ee60218748ce |  | checkpoint | 2.4 - Level Checking and Conformance
label | 475275c0-ac92-5903-abe8-352c2068a9a4 |  | note | FREQUENCY: Any deficiencies in the level or surface of the base course are to be rectified within the same day of placement
label | bc73e642-60d7-59ef-b134-f4937154e1f3 |  | note | ACCEPTANCE CRITERIA: CE-019-ST-0033 CL4.2.8.3. & CL4.2.8.4.
label | ab119d18-cb8c-5197-a5e9-c43f6801d4f3 |  | note | REFERENCE DOCUMENTS: Verify
label | 5328e5bc-46fa-5a60-9297-617d1cf4ea83 |  | note | INSPECTION/TEST METHOD: This ITP signed off
label | de698c9b-1185-5d02-8800-6059665c9de0 |  | note | RECORD OF CONFORMITY: IP
label | b173bd24-e549-5951-a7b7-2eee0d9a4f28 |  | note | FH Engineer
label | d3fc8745-778b-5c1a-8b80-8fa72dc44efa |  | note | RESPONSIBILITY: N/A
text | 11fe45d4-30a7-5de7-8745-e29cb13176b8 |  | textbox | Date Completed:
checkpoint-status | c85ac2be-0fd2-4780-b5fc-567c81c47969 |  | checkpoint | 2.5 - Finished surface
label | f7166abb-ad84-5d87-affb-0f1e1122a1b0 |  | note | FREQUENCY: Each lot
label | 7433e2e8-359c-50fd-9d34-47f24856ec75 |  | note | ACCEPTANCE CRITERIA: Base course shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings Layer to be finished to a smooth and uniform surface and after compaction shall conform to acceptable limits.
label | c3c4ecdb-915b-5342-994d-27176ae51f97 |  | note | REFERENCE DOCUMENTS: •CE-019-ST- 0033 CL4.2.2.8 •Contract drawings
label | 254a6555-18b0-5c68-b418-7d974169d062 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | db50be59-4048-5051-a90d-119c974582c8 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | c0aad2f6-6bda-54d9-ad08-36b1a9085c9b |  | note | SCP
label | 066992cc-acb5-5974-96ee-5f62d6bf7713 |  | note | RESPONSIBILITY: Surveyor/ FH Engineer
text | a1daa22c-f86e-584b-a6bb-298e8ef9d48d |  | textbox | Date Completed:
checkpoint-status | d7bd8cb7-f657-4c48-93d6-b1745b4d9c0b |  | checkpoint | Final Inspection
label | 00bf2141-6f55-5909-bd01-9750e86e105e |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | cb1f4194-31b5-5522-82d2-405c7f380264 |  | textbox | Print Name:
text | fa211b4d-6b05-51c2-ac9b-f724283170f4 |  | textbox | Position:
text | f049c979-d774-5cfd-8d1a-26564e4caf7f |  | textbox | Date:
checklist-sectioned | 144a62ff-d937-42c8-aed8-e070e93130b3 |  | checklist | ITP-020 - Exothermic Welding |  |  |  |  | Yes | ITP-020 - Exothermic Welding | 36639b34-5aad-4ed9-95f0-03036719d1f9
checkpoint-group | 1de85215-d329-45f4-91af-4cbfdb59cd35 |  | section | Preliminary Works
checkpoint-status | 5b89e1c0-f82f-446b-abd8-3a322c5483a6 |  | checkpoint | 1.1 Check for correct documentation
label | 5737a2e5-ab17-5742-af36-4c0929d81c87 |  | note | FREQUENCY: Prior to commencing any activity
label | 555905d4-f59f-59f6-bb4b-bc9015110c63 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
label | d7e1a8d4-1fda-583b-aff3-450afc6ef321 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 15841062-e649-5bed-8773-1d08a8f7e184 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 1e6025d9-1a6d-5444-af4d-c3930647b11e |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 8b34f132-1111-5e48-8dca-5cbfb7812037 |  | note | HP*
label | 6cd44bb3-0168-5dcd-9081-09ddc2b8d537 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 93a4d347-85d1-5229-be6d-c1c60ab675d3 |  | textbox | Date Completed:
checkpoint-status | 8478ab02-ab79-4742-8802-10c6119e72f7 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 141cc903-1e99-5079-919b-8beaf2659c58 |  | note | FREQUENCY: Prior to commencing any activity
label | 3d270118-7b9f-53f5-87f6-21bde4e48224 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP. Ensure that all employees and contractors involved in the welding process have been inducted onto the relevant Hotworks permit
label | 24a13351-3266-54c0-bb1d-b58e7612f558 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | e067120b-951e-5014-b441-cce06ebcfbc8 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9aa47274-60f4-5a98-b690-66f7d48c9776 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 82dee1d2-4ae3-5f2e-87f6-bd59ff3fee40 |  | note | IP
label | abc8ba22-f6fd-5eda-ac40-2184e81cb02c |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 69e0bd2a-602b-5efb-9aee-84dd05d3d085 |  | textbox | Date Completed:
checkpoint-status | 9190b21a-5cc8-48ba-bcf9-058160918646 |  | checkpoint | 1.5 Materials Check
label | 2e8d2da0-10c0-5337-8f47-32fe9b261f5d |  | note | FREQUENCY: Prior to commencing any activity
label | 32eec5ba-ce2e-5b5c-a972-97a79726096f |  | note | ACCEPTANCE CRITERIA: Ensure the materials and equipment gathered are for the correct type of connection being made. Inspect the mould ID tag to ensure that it corresponds to the application, indicated by the following parameters:
label | 6cd3cb08-6977-5108-8f13-939415c26a55 |  | note | 1. Mould part number:
label | e3085b7a-c123-5864-bcbe-cea63d3bfc62 |  | note | 2. Conductor size:
label | ff5a1219-8caf-58ea-b2ff-9f07ee5e84bf |  | note | 3. Welding material required
label | 85203a54-acc5-5d52-bca5-7c3357c255bd |  | note | Check to ensure the graphite mould is not worn or broken, which could cause leakage of molten weld metal during the reaction.
label | d5c1916c-6153-52c4-80ca-f2ccbecaf5d3 |  | note | Ensure a working fire extinguisher is available within 10 metres of the working area.
label | 480fce13-7862-5158-9f13-b3d7e89d6951 |  | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
label | 44704c48-abea-517c-a779-1e8fa4d0ed74 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 1b5896b1-847b-55bc-a701-10fd71936bac |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 58a209ca-249a-5177-937e-376618bb6510 |  | note | HP*
label | ee240a90-4a30-5981-9d65-505e86dafa24 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 5d4aa062-9b8f-5069-8a18-7f13014a7f58 |  | textbox | Date Completed:
checkpoint-group | 37560977-beb2-4c13-9241-d0362dc8a225 |  | section | Construction Works
checkpoint-status | d585d52c-faeb-4325-9ce0-cdf114bcca4d |  | checkpoint | 2.1 Preparation
label | e05b7f0f-7739-5e5a-b823-799072a1c8f7 |  | note | FREQUENCY: Each Weld
label | 51c919b1-c094-5481-b275-e1f5bcd0842a |  | note | ACCEPTANCE CRITERIA: Ensure the position of the conductors being welded is correct. Heat mould to ensure it is dry. Strip & clean conductors, ensure they are dry & clean.
label | 41cdae8b-0e39-521f-902d-790581224b43 |  | note | REFERENCE DOCUMENTS: Design Drawings and Register
label | 885bda41-4138-5f44-88e2-8fa4ac8ccb2c |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 663fdf37-3ac6-5cff-a954-b8b1397bf3b0 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 0b0e2e67-87e7-589a-934c-2ca86e399977 |  | note | IP
label | 5d8ff630-fd50-5355-8d00-c068f7f4763b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | f6ccf044-bb96-54f0-b658-dcbb60541fce |  | textbox | Date Completed:
checkpoint-status | 3959a5ef-0740-42fd-bf8d-ba3b9f85fc6e |  | checkpoint | 2.2 Welding
label | 3f69303a-5f5a-5d8e-8340-6d2124b1dc4a |  | note | FREQUENCY: Each Weld
label | cdf94c59-85f5-5b28-a32f-358f1abb95d7 |  | note | ACCEPTANCE CRITERIA: Ensure conductors are correctly positioned in the mould, allowing the mould to close tightly. Ensure welding material has been inspected and is intact. Ensure reaction is completed and molten material has solidified (allow 30 seconds post ignition)
label | a8db93ee-8900-5f45-bd07-6394d484814c |  | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
label | bb2eb571-5e08-5997-a9d3-0bc8303aeb90 |  | note | INSPECTION/TEST METHOD: Verify
label | a7fcd6b7-4f18-5fe2-9865-2714d763e3da |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 6a81fced-e910-5354-b5c0-c03a6ef0cb9f |  | note | IP
label | 0b60f5e4-906b-54ae-b9e7-6910cc6e0c52 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 7f02524f-5c97-554b-ad4d-f9c6203bbc7b |  | textbox | Date Completed:
checkpoint-group | 7b1c6888-4c2c-482c-9591-a0b245f7c0d2 |  | section | Testing
checkpoint-status | 7cb79786-abe3-4e66-b6ba-49db04981b28 |  | checkpoint | 3.1 Weld Review
label | 40886372-ffb2-5bc0-818d-02b1ba7496aa |  | note | FREQUENCY: Each lot
label | d0d9c1cf-e7c1-5b27-b32a-9db32aa6374d |  | note | ACCEPTANCE CRITERIA: Ensure weld is inspected and that a quality connection has been made. All welds shall be inspected a Fulton Hogan engineer.
label | 2f0f6626-0e58-5812-b2d8-1bd286bbe3f9 |  | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
label | a670037f-24d6-54d1-860f-a15486475ab8 |  | note | INSPECTION/TEST METHOD: Verify
label | 883ffe5e-c3b9-5190-93b9-6fe79d9603cb |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 75ff4990-aac6-59e4-a5cd-a4a518682e0d |  | note | TP
label | e94d4a8e-7df4-5a0c-b636-646e348f6b2c |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 82c6b158-5f97-5091-acf3-45e22b985b6f |  | textbox | Date Completed:
checkpoint-status | 48cf313d-e667-4c0d-a644-a09ff72e7668 |  | checkpoint | Final Inspection
label | 5cb96962-5184-5919-afe6-94ac0528e8ea |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | e2a9991b-31f7-533b-bf6e-db9008abe381 |  | textbox | Print Name:
text | 499aa2b6-8c69-56dd-8834-4c08ca22afcb |  | textbox | Position:
text | 56e67e63-fc15-594a-829b-b897e3213996 |  | textbox | Date:
checklist-sectioned | e25de9b9-6ed1-4c2a-a425-b5f501e3686f |  | checklist | ITP-017 - Bluestone Paving Works |  |  |  |  | Yes | ITP-017 - Bluestone Paving Works | 45a05c9e-c037-48d7-8027-7c02b5a65f91
checkpoint-group | 9c653a61-6004-4a61-9bbb-4d8a22309fb8 |  | section | Preliminary Works
checkpoint-status | 9630952a-79fe-4e1f-9cc6-6e89fb6e0e94 |  | checkpoint | 1.1 Check for Correct Documentation
label | da852508-2839-5929-8d3a-115c3403a5b7 |  | note | FREQUENCY: Prior to Commencing any Activity
label | 175ddb91-e267-5ba2-be28-7cfbe7335219 |  | note | ACCEPTANCE CRITERIA: Ensure all employees and subcontractors use all current and complete set of design drawings
label | ca961dac-661d-5b53-8257-89a892ca0357 |  | note | REFERENCE DOCUMENTS: Design Drawing and Registers
label | 52a11ca3-ec01-5bcf-916d-cdcf44ae671d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 958f424a-381c-562a-a847-39027df1d2bb |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 05940d70-10cc-5a27-ad9c-117ecd33011b |  | note | HP*
label | e126a03c-8c52-57cc-85d7-82cf610194d5 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ed547ee2-192b-5935-a332-fd88dd9d28fb |  | textbox | Date Completed:
checkpoint-status | f9513f63-413d-400d-a3d2-d53624c9ecd4 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 2b9c722f-1c2f-56fc-9d15-e5b2b9b6d497 |  | note | FREQUENCY: Prior to Commencing any Activity
label | c8ac200a-0987-5b1d-b120-8feb1378c5d1 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls shall be implemented, including: EMP, PSP, SWMS, TMP and WP
label | c8e087c6-751b-5797-8b1a-f8e6b9f5d3e7 |  | note | REFERENCE DOCUMENTS: EMP, TMP, PSP, SWMS, WP
label | 76451bcc-5c01-5fa5-917a-1a5b3fe6e4b7 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | afec54ee-b630-5d42-b8e1-c603131b464c |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 4937d070-9cd6-533b-805c-efefed4f7350 |  | note | HP*
label | 70a5345f-9a59-5716-83c0-5030b411907d |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 5462603a-52ce-5cb9-ade1-2a604faac659 |  | textbox | Date Completed:
checkpoint-status | 4baad907-dad8-4ec2-bcc8-c04d1f43da28 |  | checkpoint | 1.3 Check Materials
label | dbfad4f1-2dfd-58ca-b50b-f0f252b899f2 |  | note | FREQUENCY: Prior to Commencing any Activity
label | 46d06369-6f5c-5770-82fa-3c8e1848b9fb |  | note | ACCEPTANCE CRITERIA: Inspect materials for any chips, cracks or other visible damage.
label | 3aa662f4-028e-5782-98ef-724c023ba7ba |  | note | REFERENCE DOCUMENTS: Receivable Inspection Checklist
label | 4b5b4347-d3cf-50fc-9be4-84f206ea61c1 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 37a4f2b5-14ab-58e5-b21f-4ca972b44f8f |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | f8f24a4f-640e-5aa6-9afe-e4601fbb744e |  | note | HP*
label | cac8a09a-fecc-5802-9d83-102eb5d5eb12 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 1eae1869-d569-5563-a1a0-2a57f4797868 |  | textbox | Date Completed:
checkpoint-group | f1472b87-ce40-425f-a00a-93773b90d8dd |  | section | Construction Works
checkpoint-status | 63383330-6a63-4ec5-bec9-5440a10c9b8c |  | checkpoint | 2.1 Base preparation
label | 8898c624-325f-5e92-b1c9-b9f66f71ca09 |  | note | FREQUENCY: Each lot
label | d7ab0d21-2052-5ef3-909c-c34df4663568 |  | note | ACCEPTANCE CRITERIA: Concrete base shall be inspected to be free of foreign materials and water pooling. Formed groove of 10x25mm in concrete face shall be filled with caulk
label | 4c5d05b9-31a1-5b3e-ae76-4930fe1689bd |  | note | REFERENCE DOCUMENTS: DWG MMR-AJM-NPDM-DR-DD-640054
label | 05b291b7-6421-5ef6-860e-99d78f4d0fbb |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d3d3e42f-237d-52c2-a33e-3bd96d253c94 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | e3696ee3-363b-5ff4-b6d3-a19f28957d30 |  | note | WP
label | 966f178a-8783-5942-9ae9-9363d49f46a6 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 05f855de-b302-507a-9bdd-2573812be780 |  | textbox | Date Completed:
checkpoint-status | 7c64a3ed-e2a9-49b3-a772-1bbd5c727820 |  | checkpoint | 2.3 Mortar Bed
label | 40763fe9-0be8-5291-ad39-a68c2c0e71a6 |  | note | FREQUENCY: Each lot
label | 1c267cc9-af08-5ea7-a52f-7c17403d3f1d |  | note | ACCEPTANCE CRITERIA: Mortar shall be applied at average thickness of 30mm to concrete base. All pavers shall be coated in mortar slurry on rear face before laying
label | d9b1b95e-da34-588b-ae56-0c1277258cc6 |  | note | REFERENCE DOCUMENTS: DWG MMR-AJM-NPDM-DR-DD-640054
label | 0bd139bb-837e-5278-a65b-99ae5a854372 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 4ad10e17-0ea0-5752-a148-79591572f173 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 53051dd4-cebe-5d85-86ea-2f05dd295d80 |  | note | IP
label | e13db657-5d85-5879-8b70-5683d3e33b95 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 8b14e489-3743-549c-ade7-443d15e58c7c |  | textbox | Date Completed:
checkpoint-status | a1380dcc-d3d6-4699-b47f-cca7e7ed7cba |  | checkpoint | 2.5 Cutting of Pavers
label | a3d3bb09-4527-52d2-84be-cbe84e67384e |  | note | FREQUENCY: Each lot
label | 28ebcb66-d6f9-55c7-953b-825f7dbaa5f4 |  | note | ACCEPTANCE CRITERIA: Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
label | 98955e67-a02c-5a59-b573-48e7aea516e5 |  | note | REFERENCE DOCUMENTS: DWG MMR-AJM-NPDM-DR-DD-640054
label | a5b4052f-77b5-50ae-bec9-df5698b39d2a |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 72ce4eb5-a640-535e-9b5a-2a37d506d48a |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | e4ad5e8e-9513-50f3-bf8e-7fab4c80ad55 |  | note | IP
label | 86106bf2-0fcc-5965-bf44-0ab5c4633f86 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ed5560bb-68d1-5c79-8b9f-dcb64ae77b12 |  | textbox | Date Completed:
checkpoint-status | cfe890a3-1b78-4f1d-8ebd-319dfa7c5039 |  | checkpoint | 2.6 Curing
label | 7eef6d4c-da3c-5469-9ce7-93776e6d82dc |  | note | FREQUENCY: Each lot
label | 8141e62d-7ea1-5b60-8a4e-fefda6a46dc8 |  | note | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic. Where required, ply shall be laid over area of works
label | c58f3e15-c489-5e13-804a-c2971fc08f0e |  | note | REFERENCE DOCUMENTS: Manufacturers Specifications
label | c0646f52-78df-5ae3-a893-e58d0d4967d0 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e4266fb5-61b1-5a2b-8223-9998d11faca1 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | f2c2b2c7-37bf-5282-a020-a5097cb0ccca |  | note | IP
label | 164e64a9-1e09-5a51-85b2-40f916e462bf |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | b0088dce-e5d6-5bb6-970a-7145ab28a5c5 |  | textbox | Date Completed:
checkpoint-status | d561adf7-334e-432f-b4f9-6da169e9b719 |  | checkpoint | 2.7 Grouting
label | 2bd0ff4b-4353-566a-ac83-a3ff51e03452 |  | note | FREQUENCY: Each lot
label | 6e8648d0-a067-5891-ab3d-3739adaf5fb8 |  | note | ACCEPTANCE CRITERIA: Pavers shall be grouted using agreed colour and mixture
label | a4633d92-7e59-57f4-b214-161f0e47d6c0 |  | note | REFERENCE DOCUMENTS: Manufacturers Specifications
label | 1cbfa87d-7038-573d-9dcd-60aa305acb5b |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 57053a4f-c69e-5334-ac1e-07a494a5b14d |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | e163b2d5-6406-5b19-ae05-66ec66490bc9 |  | note | HP*
label | 367cfa0a-e6ac-585e-9fa8-ac0e93215746 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | b6adbf9a-c500-5cdc-992c-b64feddbd1fc |  | textbox | Date Completed:
checkpoint-group | d482e4d5-980c-43f6-bcc3-c269da74813e |  | section | Completion
checkpoint-status | 5c258841-3f54-4b01-86c7-68e4d2be0262 |  | checkpoint | 3.1 Completion
label | 9a9e700d-e0f7-571d-ade2-febc6408be5a |  | note | FREQUENCY: Each lot
label | f5a04fd5-a9ed-5687-9035-ddcc9cd607f2 |  | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste. Bluestone pavement is free of mortar stains and cleaned to satisfaction
label | 6b898521-1124-5796-9219-9a1de667a0a8 |  | note | REFERENCE DOCUMENTS: Visual Inspection
label | e3d700a1-20dd-595b-8f7d-3227be8cc470 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 1f5c5f8f-8b91-5710-abfd-f8664b91f3f5 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 397520c1-e255-5c50-baa1-538a9096df03 |  | note | IP
label | a6a50501-4ca5-592b-82ff-815316a4d1b2 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ba027320-2903-530e-a4ab-b8f253da3146 |  | textbox | Date Completed:
checkpoint-status | c44a7ce0-99e3-483b-9f37-908d07e37bba |  | checkpoint | Final Inspection
label | e89590e4-4186-5bf4-b60b-ab4eb7184e65 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | a2c7b2e5-85c4-5e91-bcf6-968e75228cee |  | textbox | Print Name:
text | 90f91f29-ca67-5965-a9c9-3aef5df87012 |  | textbox | Position:
text | efa56ab8-ad83-53ba-878b-c45b1d8905f9 |  | textbox | Date:
checklist-sectioned | 4021f14a-48fd-40a8-acd1-152d16690d08 |  | checklist | ITP-016 - Platform Bluestone Kerb |  |  |  |  | Yes | ITP-016 - Platform Bluestone Kerb | 478b80a2-ba37-4f8a-8269-cf1571eca4d8
checkpoint-group | 80341959-40c4-4fad-b47a-fe6dbfbb360b |  | section | Preliminary Works
checkpoint-status | d0acd62d-23cb-49de-ac05-f87f51002f72 |  | checkpoint | 1.1 Check for Correct Documentation
label | a2548de4-5c7a-5e89-9e80-2d7280378a5b |  | note | FREQUENCY: Prior to Commencing Activity
label | 442d5e1e-9fd7-5e37-950e-55fcffb2e3e1 |  | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | 35505b02-60af-5afd-b61f-c19eeca0be5c |  | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | 9143e769-18d4-5f6c-9742-36481ea6b2e9 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d039153c-c0d3-5735-ae27-aa3fa69c3def |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | cb8db0b0-e55a-5f2e-82c4-49ae13dfb24f |  | note | HP*
label | d92a7554-2a30-5006-b8cd-62f895881157 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 5f3928e1-26ac-5600-a0d3-73b3cb60dc66 |  | textbox | Date Completed:
checkpoint-status | e62ff21e-031d-4733-8578-51404186517e |  | checkpoint | 1.2 Implementation of all measures and controls
label | c5e2b3f9-2965-53b4-afe9-e493d8ee83b8 |  | note | FREQUENCY: Prior to Commencing Activity
label | 339c9aec-e1bb-5253-9003-1fcc9f709fad |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | ae2f27a8-478f-5fdb-831e-026d28e7e734 |  | note | REFERENCE DOCUMENTS: Work Procedure
label | 95158c27-b862-561b-8441-97dd15674345 |  | note | INSPECTION/TEST METHOD: Inspection
label | 65f88381-ca6a-5755-be78-882effa1423e |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | b10bd37c-75bf-50f1-80fa-a43a749d7193 |  | note | HP*
label | 9524b755-9d3a-51fe-8db6-d0b9597ec82d |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2bdeaf86-1d47-5722-92cf-07d202e7072f |  | textbox | Date Completed:
checkpoint-status | b477b789-8f1b-4afe-b7ee-c5b104163247 |  | checkpoint | 1.3 Check Condition of Material
label | 7eda0ea8-ad97-5b89-a48a-ac656fd4232a |  | note | FREQUENCY: Prior to Commencing Activity
label | 01105d52-b3ea-5761-bac6-dd3bf03d8c14 |  | note | ACCEPTANCE CRITERIA: All bluestones shall be inspected at delivery for visible damage
label | e13af6eb-7611-505a-ba14-ebbdd888c1ad |  | note | REFERENCE DOCUMENTS: Work Procedure
label | 97b83582-6907-57c5-ba13-67611673cafb |  | note | INSPECTION/TEST METHOD: Inspection
label | ddd1b6b9-64a4-57a9-b441-768e51e3d9c9 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 16d40d2b-789b-501e-91e2-f8340e486580 |  | note | HP*
label | 57bafc94-b97c-5e41-ac88-14aa6fbb2d20 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | f9519560-6553-52d3-9b60-492c7daaa7ec |  | textbox | Date Completed:
checkpoint-status | 548eb07d-8904-4aba-aeea-81025079e62e |  | checkpoint | 1.4 Lifting method
label | 8f3009a4-2edd-52ac-9cfc-1e02160ce34a |  | note | FREQUENCY: Prior to Commencing Activity
label | 90ae9b66-46f1-561d-8c60-cc54bbc42a1c |  | note | ACCEPTANCE CRITERIA: Bluestones can be moved with excavator and grabs/slings or with a vacuum lifter.
label | 19893db3-0002-5118-97f8-849c6c5b0194 |  | note | REFERENCE DOCUMENTS: Work Procedure
label | 78079a0a-a702-5928-8ea7-d349d3bbf6e5 |  | note | INSPECTION/TEST METHOD: Inspection
label | 3671fafe-1116-51ca-aec6-5cd0297883a3 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 8e112798-fcb7-526b-aaf7-e3c541219a1a |  | note | HP*
label | 31a022a9-699b-539e-953f-5b9ff456198f |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 934d19c9-41c9-5e6b-89cf-0af21b1ec1b3 |  | textbox | Date Completed:
checkpoint-group | 81ce272e-1839-481c-a3c0-00f773f4d8b0 |  | section | Construction Works
checkpoint-status | 6945bfc5-6823-4c3d-ac94-3a548b525cb2 |  | checkpoint | 2.1 Base Course
label | df2cdd04-a4f2-5928-90aa-5f8ba780d258 |  | note | FREQUENCY: Each Lot
label | 43ad9c04-717c-5640-9e39-b678375ddeb9 |  | note | ACCEPTANCE CRITERIA: Class 2 compacted rock (98% modified density) shall be compacted to 100mm thickness. Soft or areas deemed unsatisfactory shall be removed and rectified
label | b93b58fa-66ad-5113-b713-91618255027b |  | note | REFERENCE DOCUMENTS: STD_T6111
label | d17ce53b-de0e-5ef6-8156-e2ad71292c7c |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c87e6fd0-dbd2-582a-b25e-52cef81b4c75 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 8fc9f920-8b21-5218-8918-f6ae4bc06758 |  | note | IP
label | 9b7cb503-e4f7-50ea-980b-68dd7e806ccd |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | c701b563-1866-5592-8080-e20fe11ae464 |  | textbox | Date Completed:
checkpoint-status | 002f722b-4cba-45c0-be4a-9592446b3b85 |  | checkpoint | 2.2 Concrete Placement
label | 5467dda5-9d09-58f3-994c-9e90fb20cf45 |  | note | FREQUENCY: Each Lot
label | 633c3079-ee33-503d-bda5-e211bd4afe2a |  | note | ACCEPTANCE CRITERIA: Bedding shall be >100mm 32MPa concrete with 6mm aggregate
label | 8cf704b0-5737-5005-82da-87683f7dba8e |  | note | REFERENCE DOCUMENTS: STD_T6111
label | 22ae1d88-2d57-5ffb-a0dc-12b0bef821cc |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 8ee73d6e-0397-5c55-a6b2-94596a8eed37 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 1c7213a3-4ccb-56e4-bdbf-2c8d1cb69e83 |  | note | WP
label | 93fe0ac8-55aa-57b7-93cc-c1bd48321385 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 8238da5a-c039-5712-a107-b0af0b934838 |  | textbox | Date Completed:
checkpoint-status | d483adcc-c504-4c88-b1fd-21132ac600d0 |  | checkpoint | 2.3 Setting
label | 9fda5c45-e6ec-5194-b171-903831e7b28c |  | note | FREQUENCY: Each Lot
label | b2335ecb-db47-5cf5-b465-58de02e444de |  | note | ACCEPTANCE CRITERIA: Tie rods shall be N12 (300mm long) and chemset 100mm into kerb, 2 per stone. Tie rods shall be installed with bond breaking compound specified by superintendent. Bluestone shall be laid 150mm below finished surface level
label | 09a3f1a2-7d46-55a3-b243-35ca92c6ec67 |  | note | REFERENCE DOCUMENTS: STD_T6111
label | 7ced3642-be25-5a53-a4ac-ead42286e5b7 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 4a0fafb2-a83e-5d70-b079-9c328f3e7dab |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | a440a053-ede6-51ca-bcb2-bb82e3536669 |  | note | WP
label | 8991cd87-206f-510b-b422-9ead3712fc67 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2c20f57c-be04-530d-a1d7-6e2055600b6b |  | textbox | Date Completed:
checkpoint-status | 0088aed7-4fbe-41c7-a1b6-607df81ce210 |  | checkpoint | 2.4 Sealant
label | 36b74be9-38aa-507a-8ca2-cf4c8ce5f647 |  | note | FREQUENCY: Each Lot
label | 1602cc34-fb4d-5d7c-a864-d901185c7167 |  | note | ACCEPTANCE CRITERIA: Sealant at construction and expansion joints at back of kerb shall be 'Gun Grade THC 900' by Tremco, of black colour. Loose materials shall be removed as not to impair adhesions
label | 7fed2930-1f76-511e-bcf7-a11431289edf |  | note | REFERENCE DOCUMENTS: Work Procedure
label | ad95e78f-3348-5e7b-94bd-d4095d4ce5c0 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 3f20adc4-5ada-5913-836b-4ef18b97912d |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 2d09d70a-4586-5fbb-b669-26d88b4a706f |  | note | WP
label | 54dff88f-bc42-5fe7-bec0-0ae5f83772a9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 9bc4e390-4e92-59d6-8c5c-0a463a75bdd0 |  | textbox | Date Completed:
checkpoint-status | 9965b26d-e31e-4414-99fc-c5881786f830 |  | checkpoint | 2.5 Platform line marking
label | 130986b2-14da-50cb-bff4-ade747cbf2ac |  | note | FREQUENCY: Each Lot
label | 3eec5748-9193-5020-b042-549c6ad13cbc |  | note | ACCEPTANCE CRITERIA: 50mm yellow lines shall be placed along the edge of platform, one on the top face and one on the front face of the kerb.
label | 84f0efd7-39e7-5a49-b82e-bf5aaa6524d9 |  | note | REFERENCE DOCUMENTS: VRIOGS 005.3 Cl 7.9
label | 4fc7bb84-e0b7-5e98-a0d5-d434727ff397 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | bab7fdfa-098f-5f80-aa59-2e6f0aba4996 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 3e2d50fb-91d0-559e-a125-5c4ae5572182 |  | note | WP
label | 708737ac-7cd0-53d1-9bc7-f40a6c688a79 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 887c1057-f440-5fe6-adde-27e80ae44a62 |  | textbox | Date Completed:
checkpoint-status | 05db137c-415f-46a6-a565-031f66e844bc |  | checkpoint | Final Inspection
label | 9edd7723-aab9-5b7b-9ab2-fb9dcd3b997d |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | a4416711-96fb-5d71-972f-2db1cdd0a460 |  | textbox | Print Name:
text | 61f72a9c-1db5-58d8-9a6c-3d0503e4ee78 |  | textbox | Position:
text | 4f054cac-e682-539d-b1c0-60ee385087bb |  | textbox | Date:
checklist-flat | f2fde9e7-9c31-4b6a-b1b5-5c987f27409a |  | checklist | Contract HoldPoint Checklist |  |  |  |  | Yes | Contract HoldPoint Checklist | 47e3f28e-96d9-4351-92d9-383af79cfeb3
checkpoint-status | 96a78813-95b0-48fa-9a93-357ec9a1b8cb |  | checkpoint | Holdpoint Release
text | e37a2a86-d6e9-5a29-aadc-aad1b77ad6c5 |  | textbox | Enter Name
text | 1a23eb1a-cd8f-5c38-b50b-5bc9b39bbe1b |  | textbox | Enter Description
holdpoint | 60a1eb35-e850-40c9-a4b9-af7b0196da59 |  | signoff | Contract Holdpoint Release
checklist-sectioned | d03f0845-e8cd-47ce-8852-ec86c20aece8 |  | checklist | ITP-010 - Kirby Welding |  |  |  |  | Yes | ITP-010 - Kirby Welding | 4c055f6d-a589-4c90-85a0-fe7b3afb1373
checkpoint-group | 6ce9e30f-12bc-45cd-9aa0-c09a091c93be |  | section | Preliminary Works
checkpoint-status | 051f4121-146b-4d86-a108-0be9f86526f4 |  | checkpoint | 1.1 Check for Correct Documentation
label | c4135c7d-f290-5049-9631-86d7201e6f4e |  | note | FREQUENCY: Prior to Commencing Works
label | ad3b879e-b855-5f56-99a8-13b7e096f41e |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
label | cdeef963-9471-5f44-8d02-c41b531e3b95 |  | note | REFERENCE DOCUMENTS: Design Drawings and Register
label | 6de449b4-fb10-5b05-ba4e-a4bc02977b0d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e50a247c-39a1-553f-848b-0bc66b04ddb4 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 7e8acf33-25ec-5d0d-8ab1-4c24fce13230 |  | note | HP*
label | 1d0ca30a-a16f-5f72-b401-a7e636a607eb |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 149c0676-5a9d-5ea8-8273-bf05c5cd6d91 |  | textbox | Date Completed:
checkpoint-status | 5771f382-d89a-4d14-8e9a-82b6b134021a |  | checkpoint | 1.2 Welders Qualifications
label | cfb90772-86e5-541b-8d67-8450eec546ad |  | note | FREQUENCY: Prior to Commencing Works
label | f0cce697-1374-5bd6-a950-64e893efa9f7 |  | note | ACCEPTANCE CRITERIA: Welders shall be trained and qualified for the brand and each type of weld used, e.g. standard gap, long preheat, short preheat, junction etc. Certification shall be provided to and approved by the Superintendent prior to commencement of welding.
label | 00207a98-7ecd-567e-a888-429e8b150190 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 Appendix C
label | e77cd084-179f-5674-80ad-e016b96493e2 |  | note | INSPECTION/TEST METHOD: Verify
label | fb3c56d2-4f35-5a76-92c1-abccbc18a108 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | b3f2a0ec-bccc-5d29-8524-816665c1a93d |  | note | HP*
label | bb4df4b9-0bd1-5566-ad93-64848a82cf41 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | afedd8f0-9aa0-59c2-bdc0-e76b2a2bce6d |  | textbox | Date Completed:
checkpoint-group | 41f3b9be-f7da-43c2-a73f-9d4d28c8b696 |  | section | Construction Works
checkpoint-status | b5c2963f-0605-4e1d-84e4-1495201687ff |  | checkpoint | 2.1 Cutting Rail Ends
label | f0722c4e-e6e1-5b5c-8e14-f8e50ecf0147 |  | note | FREQUENCY: Each Weld
label | 4be6dc8d-0666-59b9-a64c-b141b5d6d5b2 |  | note | ACCEPTANCE CRITERIA: Rail ends shall be saw or friction cut. The cut ends of each rail shall permit butting of the rail heads to within 1 mm across the full head of the rail. The prepared surfaces shall be visually inspected for cracks and reground if any are detected.
label | 11c1640d-f60c-521a-874f-0753f7e36699 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.4.6 & Appendix C
label | b90a7230-d04d-5b1a-af0c-cda3a6b0cbac |  | note | INSPECTION/TEST METHOD: Inspect
label | 7a36dbbc-db97-5c81-92f1-bb67330c58b5 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 0276a335-eec4-5fa7-b0fb-8aff26bedec4 |  | note | IP
label | 49f547d0-fe16-5599-9c9b-f8ddd084b264 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | b0b63861-3f55-5156-9a67-7b630c849482 |  | textbox | Date Completed:
checkpoint-status | 57b8639d-0bc6-431b-b2b3-14a40a05da14 |  | checkpoint | 2.2 Butting and Aligning Rail Ends
label | 2efc677b-d2d8-5702-8dd5-e3fba854c8af |  | note | FREQUENCY: Each Weld
label | 8baaaf2a-f69c-5243-9ecb-c8bc6eeed8a9 |  | note | ACCEPTANCE CRITERIA: Rail ends to be welded shall be butted together as closely as possible, preferably with no gap between rail heads. Care shall be taken to ensure that the rails are not pulled together excessively, forcing the feet of the two rails together and producing a peaked or high joint. Rail ends shall be butted and aligned, and assembled with base plate and spacer blocks, if applicable, prior to commencement of pre-heating.
label | 5f96e2fb-6888-5aec-835e-ca46b76ed0c2 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.6 & Appendix C
label | 8ee5942f-e4c7-5a25-8e84-b5b57ff757e8 |  | note | INSPECTION/TEST METHOD: Inspect
label | 0e1d7fcb-ce36-5f6d-b1b1-3bbdb179c93f |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | e2fa2f17-147b-52e6-b391-4064b5de6f17 |  | note | IP
label | 36bd4369-06f9-5086-b685-6d1d3d11623e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 002c4ff9-619b-5084-81ee-fbf05e1795ab |  | textbox | Date Completed:
checkpoint-status | cb88010c-b72e-4a28-85f6-9e8491681ac0 |  | checkpoint | 2.3 Preheating
label | 6c62c2fe-d42a-5a9e-97d9-5572beb6a080 |  | note | FREQUENCY: Each Weld
label | b3eb1232-aea8-57cd-acd3-35420a2a38cf |  | note | ACCEPTANCE CRITERIA: A correctly adjusted, suitable oxy-LPG pre-heating torch shall be used. The preheating torch shall not be applied closer than 30 mm to the rails being pre-heated. Both sides of each rail end shall be evenly pre-heated from the rail ends to150 mm beyond the rail ends. Pre-heating shall be confined to the top surface of the foot of each rail and to half the height of the web. Preheating shall be such that during welding, the foot and web of the rail shall be at a temperature of between 270°C and 350°C
label | 1a4a7a41-ba0f-5204-8017-19d83a96b559 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 Appendix C
label | 4da2f7ab-9e37-50d4-a862-0f5800769bb9 |  | note | INSPECTION/TEST METHOD: Inspect
label | 94b02f7c-a747-567d-bc47-3b7fae7de6ce |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 6d9288b0-3412-55c3-9cf7-0344e447054b |  | note | IP
label | 67418c94-9042-54f6-a518-feb429ea44be |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 81132e57-781b-5205-bf2a-cbcff8314f5d |  | textbox | Date Completed:
checkpoint-status | adf58520-86c4-47d1-a243-43a5f4a40ec7 |  | checkpoint | 2.4 Welding
label | 8f4cc3d2-a15a-518b-9b41-956740ad4ca5 |  | note | FREQUENCY: Each Weld
label | 1829aff1-1535-5897-8776-d50c66b5017a |  | note | ACCEPTANCE CRITERIA: Rails and components shall be clamped in position prior to welding. Welding of the joint shall be carried out as a continuous operation. A disruption to the procedure may require additional preheating. All weld ends shall be welded using an overlapping back welding technique over the weld for a minimum length of 20 mm to ensure that all craters are fully filled to the full cross section of the weld.
label | 90fcbbc0-3804-5730-879c-5e8247854d51 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.9 & Appendix C
label | d9d08cf6-bbca-52d4-b0ea-fab0a1821a3c |  | note | INSPECTION/TEST METHOD: Verify
label | 332d1979-a0c6-5e73-b709-32ed40318008 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | b8e0de61-3036-5ade-ac71-a095d76dcdb8 |  | note | IP
label | 962774ca-7607-56dd-b744-5c514ceaa794 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 95e02d87-edb1-5bae-8a44-6801b27caa5e |  | textbox | Date Completed:
checkpoint-status | caf878d5-2a10-48be-96e6-cc7c32c804a6 |  | checkpoint | 2.5 Cooling Weld
label | be7c2430-8121-519c-9176-0d2b514e2c14 |  | note | FREQUENCY: Each Weld
label | 744989a2-860a-5d48-96a8-2048873e0cf9 |  | note | ACCEPTANCE CRITERIA: The welded rails shall not be permitted to cool rapidly. Heat blankets shall be used to cover the welded portions of rails (i.e. web and foot on each side of the rail ends. The blankets shall extend a minimum distance of 300 mm beyond the extremities of the welds, i.e. minimum length 900 mm. The heat blanket shall remain in place for a minimum period of 15 minutes after completion of welding.
label | 6a7e27bb-4680-55ad-9d4e-18db254b5370 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.9 & Appendix C
label | d4390b9d-dc49-54e2-8556-48dc7ff14243 |  | note | INSPECTION/TEST METHOD: Verify
label | 7f204b56-e8eb-5c93-8177-83f965714724 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 877bc161-443b-5464-92f0-4387635bf43f |  | note | IP
label | 8b5d4aa0-58c0-53d1-8b4a-0356b18cb3e0 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | f72a56f2-77ec-5891-a3a6-f12777ca2c82 |  | textbox | Date Completed:
checkpoint-status | c027ee32-7767-46d8-8976-f32f7b3be326 |  | checkpoint | 2.6 Grinding Weld
label | b6cbf54e-f1f9-51d9-9946-db15e1d8b585 |  | note | FREQUENCY: Each Weld
label | 8464a60e-9d86-552f-bba3-7641318a691a |  | note | ACCEPTANCE CRITERIA: Grinding of the rail head, as applicable, shall be performed only after the rail head has cooled to below 50°C. A rail profile grinder shall be used to grind the rail head weld. A spindle (straight) or disc grinder shall be used to grind the rail check and groove. A 1 m straight edge shall be used while grinding the rail head (wheel running surfaces) to ensure a good straight surface and profile.
label | 7175a633-6788-56ea-ae7e-681b0b57f0f2 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.6 & Appendix C
label | 8a597317-5d3c-5c47-8278-e7d90f64d1c6 |  | note | INSPECTION/TEST METHOD: Verify
label | 3a4815cb-1c4b-51e4-8933-360072aacf19 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | d975281f-616d-58b9-8e9d-7fbd653604c3 |  | note | IP
label | 4e0d9898-d90d-578f-8a71-994e8fc98f2c |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 24c64d01-6b5b-5492-bd39-0e568e1209bc |  | textbox | Date Completed:
checkpoint-status | 34d1791a-5010-4168-aa9d-ce9e84763fab |  | checkpoint | 2.7 Flushness of joints
label | 3f8312d4-d8cf-5673-a90b-129972d94155 |  | note | FREQUENCY: Each Weld
label | 84cb6a30-8bc8-50e2-94a7-9da79d06186b |  | note | ACCEPTANCE CRITERIA: Misalignment of rail heads on the running and gauge surfaces, due to different amounts of rail wear, shall be rectified by grinding. The slope of transition shall not be greater than 1:25. Misalignments of the groove and check not exceeding 3mm shall be rectified by grinding. The slope in transition shall not be greater than 1:10. Any grinding required to make joints flush shall extend to 500 mm each side of the joint
label | 1ac262bc-c6fd-5c9f-aa4c-6c6cea28f828 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.6 & Appendix C
label | a38b15e8-6693-5608-b52d-ed696ee3a8f2 |  | note | INSPECTION/TEST METHOD: Verify
label | 59fedffe-b35e-5351-b462-3c69579240fa |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | b9bd3c31-63d9-57fb-82f0-a9190eccca59 |  | note | IP
label | c8e29fbd-a43a-536d-8cf1-15c4eb9f61d8 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | be68efcf-f874-5b48-9ae0-5c03472fd780 |  | textbox | Date Completed:
checkpoint-group | 6f153477-065b-4671-ac37-2cb8a80467f3 |  | section | Testing
checkpoint-status | d9408c89-b47c-4bf2-886c-b4e43a7be02b |  | checkpoint | 3.1 Weld Review
label | 99a7f5de-dbd8-56ed-9ff7-d183c46bf2d6 |  | note | FREQUENCY: Each Weld
label | 6676ea1b-79f1-5b7b-8d15-49bc1a1b226e |  | note | ACCEPTANCE CRITERIA: All welds shall be inspected by the Superintendent & Fulton Hogan Engineer; Unsatisfactory welds shall be cut out and replaced
label | 4fe24971-21f1-584c-b853-e2bbc77dc753 |  | note | REFERENCE DOCUMENTS: Works Procedure
label | 6540be9c-be9a-52ba-99c2-fd6a965fe788 |  | note | INSPECTION/TEST METHOD: Inspection
label | b2a6ae53-e3d5-5de0-94b8-a79ff9ff6ff5 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 59dd73a0-f399-5e16-9eee-167b3970abd4 |  | note | TP
label | 2004bc84-3009-5664-9660-1e39b03304ec |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 8ba95dd6-8f3b-5aa9-a18b-7502d08d0c08 |  | textbox | Date Completed:
checklist-sectioned | d7ec063e-611c-4e9e-adaf-5f2074f7ccfe |  | checklist | ITP-039 Hot Mix Asphalt (Bridge Deck) |  |  |  |  | Yes | ITP-039 Hot Mix Asphalt (Bridge Deck) | 4ecd0d84-3322-4493-a337-ba480fff178b
checkpoint-group | 58e1f488-9d19-4b78-9420-bacad103258e |  | section | Preliminary Works
checkpoint-status | 57395820-d650-4079-bf35-1fef5d95984e |  | checkpoint | 1.1 Check for correct documentation
label | 17ba1f8e-0582-5ffc-ae1d-8616c9d524c3 |  | note | Frequency: Prior to commencing any activity
label | 39cdd592-1d88-5026-a1f7-ddc815570eeb |  | note | Acceptance Criteria: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
label | 1ab25a50-1d40-5b2a-a022-aff9b234faea |  | note | Reference Documents: Drawings and drawing registers
label | dd0b25ba-5b46-53d7-8415-78996c2ad85b |  | note | Inspection / Test Method: Visual inspection
label | 7d39613d-cd9f-5c96-925f-b84e83162cad |  | note | Record of conformity: This ITP signed
label | 00c4a6fb-ebfe-5d3e-b8a3-22805c72e6a8 |  | note | HP*
label | 8cbe38e8-dca3-5420-8bc2-752303769014 |  | note | Responsibility: Site Engineer/ Site Foreman
text | 7a02144e-848d-5ace-a4ae-93c0e4b2abdd |  | textbox | Date Completed:
checkpoint-status | d93c7cad-5c00-473a-a8ff-8b0926e3b0fa |  | checkpoint | 1.2 Implementation of all measures and controls
label | 26b0a905-b024-577f-81e7-5a00ecf766f0 |  | note | Frequency: Prior to commencing any activity
label | b2d12075-5d1e-572d-8432-6626b36ea630 |  | note | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | bfab76f9-4d1f-5497-ad0b-fa2a45dfe879 |  | note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
label | 46bdca6b-3494-59f9-a6cc-71bbc83afcdd |  | note | Inspection / Test Method: Visual Inspection
label | 92ec21fd-8eb6-5723-9d39-899584e37c8a |  | note | Record of conformity: This ITP signed
label | eeaef569-f5ef-5fd7-a097-aebc34126250 |  | note | HP*
label | 89e52b71-9f61-5b45-b8ad-3887dc54bd1d |  | note | Responsibility: Site Engineer/ Site Foreman
text | f49ca45d-f861-5d48-b27d-eab33926f184 |  | textbox | Date Completed:
checkpoint-status | 317cbe30-2a21-4b06-b91d-2c5f2e6ba8b2 |  | checkpoint | 1.3 Service Identification
label | f18feb1f-4e35-5a45-a1f7-700859e29f39 |  | note | Frequency: Prior to start
label | 65f86fd0-a846-5254-baae-9ebb01aa2663 |  | note | Acceptance Criteria: Services within vicinity of area to be demolished should be identified and marked, and all services to be retained shall be protected
label | e3c639b2-051e-57cd-92ea-f0fdde74f9f2 |  | note | Reference Documents: ITP sign off
label | 5d3aa8cf-0b22-5e16-8d4a-62d918e84954 |  | note | Inspection / Test Method: Verify
label | 45ba84a8-76dc-51dd-9826-81bb911d77a1 |  | note | Record of conformity: This ITP signed
label | 89d5eeef-42a3-5a73-8a06-1de693d6618c |  | note | HP*
label | 114c1e2e-d56d-5ae1-b381-351aaa8391b9 |  | note | Responsibility: Site Engineer
text | d7dfacb5-4bf7-54b6-a507-b35bd40be8fd |  | textbox | Date Completed:
checkpoint-group | 09ded1a6-0997-45c4-a2e0-c8d14a31ddc8 |  | section | Construction Works
checkpoint-status | a9399a36-386d-4937-9107-5dccf3723ccb |  | checkpoint | 2.1 Saw cutting
label | 2d7721da-c1ee-51e7-9402-2b9df5464ead |  | note | Frequency: Where required
label | ae3f6b73-d61b-5183-a083-199bc2700619 |  | note | Acceptance Criteria: Extent and location of cuts to be clearly set out and checked prior to saw cutting
label | 84127890-790d-5a00-9f99-46877d5adce5 |  | note | Reference Documents: ITP sign off
label | f77a5277-7bcd-5215-8dda-e11bcf983975 |  | note | Inspection / Test Method: Visual Inspection
label | b51907de-ed09-548d-84c8-4e09fc83641f |  | note | Record of conformity: This ITP signed
label | 052f6fb5-f5ae-564e-b2b6-35da015494b0 |  | note | WP
label | d80f5403-6bc4-5dd8-b24a-929d13b30126 |  | note | Responsibility: Site Engineer
text | d4e709ea-59c8-589d-a463-b8fe757a1592 |  | textbox | Date Completed:
checkpoint-status | ada727d8-a332-4756-ad6b-1707afcbcf36 |  | checkpoint | 2.2 Excavation Permit
label | 53bb1da5-bc41-5f3f-91f5-7516cbe456cc |  | note | Frequency: During excavation
label | 3bb51f0b-6361-568d-ad21-35fb713cdc34 |  | note | Acceptance Criteria: An excavation permit must be issued prior to any excavation commencing.
label | 181ab458-86fc-5c81-829c-ae9375b9015c |  | note | Plant and equipment shall be appropriate for the task
label | 06458665-30a4-53af-b0e3-200d26533a9e |  | note | Excavation operations shall not disturb areas outside the limit of excavation
label | aa6ef954-9147-563f-b180-dbf23625dc5c |  | note | Reference Documents: VicRoads 204.06
label | 60fedb0a-f65f-5dae-a972-97736dae32a7 |  | note | Inspection / Test Method: Visual Inspection
label | 5e95ddb3-2be3-57b8-9a4b-4a10ef00507e |  | note | Record of conformity: This ITP signed
label | 081f2658-c797-5d96-bc5f-8b6b273bff99 |  | note | HP*
label | 8f9e4d2f-a152-505c-ba71-e325e47ba788 |  | note | Responsibility: Site Engineer
text | 5d40a03d-848f-52ce-9218-9469ba46d038 |  | textbox | Date Completed:
checkpoint-status | 457aabec-2288-4a7a-804f-09bbaaeb03ed |  | checkpoint | 2.5 Disposal of Material
label | dcd6300c-c8a1-57c1-89a8-93f75e9a2bba |  | note | Frequency: All times
label | 121d42a5-a072-5d74-a17a-b15ec45e009a |  | note | Acceptance Criteria: Surplus material, debris and demolished material are to be sorted and transported off site. Material to be kept in condition for re-use where possible.
label | 0fb33536-2701-5cd8-9bff-92d9ba2fbbf6 |  | note | Reference Documents: ITP sign off
label | 6dd6ef68-7a9f-53a1-8edc-4ea0e312beb4 |  | note | Inspection / Test Method: Visual Inspection
label | c19ee478-993d-53c4-b17d-af8ec41feacf |  | note | Record of conformity: This ITP signed
label | a1428dc8-2194-5cde-9764-0d6105a1218d |  | note | WP
label | d0da379e-9486-52d4-8c24-2d19ed9ccd74 |  | note | Responsibility: Site Engineer/ Site Foreman
text | 9167c07f-3586-5cf9-b7c1-f8aa58c4e80b |  | textbox | Date Completed:
checkpoint-status | 8cd30147-4604-4a58-9bb9-8f8243152aa9 |  | checkpoint | 2.6 Maintaining cleanliness of site
label | fb62a9c7-968b-54f9-9f2e-ed3dee3acb6d |  | note | Frequency: All times
label | 92a2075e-416f-5d70-8475-f0a16f94b9c3 |  | note | Acceptance Criteria: Site and surrounding environment are to be maintained at a good standard of cleanliness
label | 438865d6-1225-5041-b040-784574c07c05 |  | note | Reference Documents: ITP sign off
label | 274e549a-5a31-5e0a-9760-d9a5265a5a2d |  | note | Inspection / Test Method: Visual Inspection
label | 08872d04-8be9-5519-823d-d6252384ecdb |  | note | Record of conformity: This ITP signed
label | 2f433bac-9267-52af-bd88-4d0bb0108266 |  | note | WP
label | c549f36c-6b30-509d-b384-eaeb25dcb315 |  | note | Responsibility: Site Engineer/ Site Foreman
text | 056090ff-97ba-585d-919d-b522386d7fbd |  | textbox | Date Completed:
checkpoint-status | 12802673-3a8f-4e13-8ff2-e920dac40a7a |  | checkpoint | Final Inspection
label | 7bd34bdd-b334-51df-a05c-9dc3ce8c332d |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | b5c76705-5b68-5a61-8f7b-a409620f82ab |  | textbox | Print Name:
text | d7ac6532-547c-500b-b811-6f6d5ca15639 |  | textbox | Position:
text | 3b4373c6-64ea-58b4-aeb9-e1e64c9cb098 |  | textbox | Date:
checklist-sectioned | 7d7261fe-15da-4958-999c-0a311bebf277 |  | checklist | ITP-004b - Cement Treated Crush Rock Sub Base Rev2 |  |  |  |  | Yes | ITP-004b - Cement Treated Crush Rock Sub Base Rev2 | 53b3f872-236f-4436-a838-ed14aaa956b1
checkpoint-group | 2d7b8342-653a-41d7-8560-f48ed38a2bba |  | section | Preliminary Works
checkpoint-status | 024a39ca-a139-4995-87e5-19ae019e4c54 |  | checkpoint | 1.1 - Check for correct documentation
label | b979d9aa-6a01-57f7-b64b-44610b82fecc |  | note | FREQUENCY: Prior to commencing any activity
label | 9870f5cf-cfaf-5dba-b457-c668a7c550c4 |  | note | ACCEPTANCE CRITERIA: •Ensure that all employees and subcontractors are using the most current and complete design drawings
label | 76c84cb3-7c1f-5e9a-ba2e-ed583e27bbd2 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | fe97673e-860b-5a8e-86c6-2f15c213662c |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 2621deaf-610f-5cd1-a82b-85b922385cb9 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 00ba2b62-1e42-5fe1-8118-ca1b3cca3cfc |  | note | HP*
label | cafc0b61-3dd1-522d-a5a8-8492d32229cf |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 30421942-5ed1-5cba-a24a-c8fdb6223279 |  | textbox | Date Completed:
checkpoint-status | 38b9add4-d930-471c-875b-40b75f294906 |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 9969843f-fc55-5ffe-89b7-70184a77ce13 |  | note | FREQUENCY: Prior to commencing any activity
label | 01573ea4-5ec8-5d86-a74e-a721e2fe8eb7 |  | note | ACCEPTANCE CRITERIA: •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 3083eff3-0da3-5fba-903d-21e59becd9b8 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 2f320348-f001-5b91-9e67-736279484241 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c406ceb9-a796-580d-bccd-de6e3e773343 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 9a75c135-7e1f-57c3-bfc3-c44fe3bb2cbc |  | note | HP*
label | 767668ad-c44d-5906-8136-e6bb37a40970 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | dbbc1e78-a90f-590b-8829-c0c6d953c370 |  | textbox | Date Completed:
checkpoint-status | 9c1a91b2-1c8c-4843-90af-74ee7295c8ba |  | checkpoint | 1.3 - Confirm CTCR is Appropriate Mix
label | ec19e46f-6476-51a3-9ee1-22721cc8407e |  | note | FREQUENCY: Prior to commencing any activity
label | 2e9df7a5-2770-54a3-86e7-3247ff257886 |  | note | ACCEPTANCE CRITERIA: •Cement treated crushed rock proposed for use shall be current, registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product. •CTCR shall be tested in accordance with 815.141 by supplier
label | 2127715f-9d09-5c78-ab52-7c9b6732fa3f |  | note | REFERENCE DOCUMENTS: Design Mix
label | b82d4654-3b95-51b5-8d79-3e1bded313ed |  | note | INSPECTION/TEST METHOD: Inspection
label | 6de37178-036c-500d-9c73-2e312127e89b |  | note | RECORD OF CONFORMITY: This ITP signed
label | 95df40be-2565-581f-a82e-913b1eb1387a |  | note | HP*
label | 175600bf-c89a-57a9-829a-ed62cfd1375e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | dc1c1b5e-908d-53c3-98bb-bb81c32d4148 |  | textbox | Date Completed:
checkpoint-group | 6efd4fe2-bc3e-4648-ab49-6f80e86a7796 |  | section | Construction Works
checkpoint-status | fbda8ad6-3ca7-4b61-9c33-d6b699f703d8 |  | checkpoint | 2.1 - Sub Base
label | 8743efbd-bd54-5179-8b2f-1df0f578bd89 |  | note | FREQUENCY: Each Lot
label | 314edfb3-4aba-51cc-87eb-de74e0463355 |  | note | ACCEPTANCE CRITERIA: •Sub grade has been inspected, no visible ponding, springing presence, or visible deformation. •Proof Roll shall be conducted by plant compliant of 173.03
label | 8f3112a7-cfc9-5a7a-b441-6587963245ea |  | note | REFERENCE DOCUMENTS: VicRoads 173.03
label | b305b37b-1a09-5f6f-a2e5-f614f36a9fba |  | note | INSPECTION/TEST METHOD: Inspection / Test Method
label | 70bd699d-d974-54aa-8a71-5c5d6b448c37 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 42ee9c2a-e61f-54b3-9c63-e295db3db12d |  | note | HP
label | 1ff63e5f-82c9-5653-b565-5186bfaed950 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 9d3e2796-84e0-57ac-969b-5709d1c63152 |  | textbox | Date Completed:
holdpoint | b8c5fc30-d268-4d08-b2b8-2dbcedf0ccc9 |  | signoff | Authority holdpoint
checkpoint-status | 87270b10-1274-48fd-b7bc-f7373d27fd8b |  | checkpoint | 2.2 - Moisture Content
label | 8774b2ca-6d58-5916-b9c2-b10080f7702c |  | note | FREQUENCY: Each Lot
label | 738fbb1f-947a-59d9-88ee-a30ac66a036f |  | note | ACCEPTANCE CRITERIA: •Moisture content shall be within 0.5 to 1% percentage of mass during time of spreading and compaction
label | dc7e1006-332f-52e0-89ef-8744e43a6b81 |  | note | REFERENCE DOCUMENTS: Vicroads 306.05
label | aa76258d-15f7-5dec-b42c-8d000b1f4a5e |  | note | INSPECTION/TEST METHOD: Inspection / Test Method
label | 5f91932b-4875-5560-bdd5-a9869ffdc049 |  | note | RECORD OF CONFORMITY: Record of conformity
label | 54061f89-7253-5242-87cd-b09aaae2484c |  | note | IP
label | 81632bd8-3b97-5051-be66-e34577e5530c |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | a42ebae5-9e84-57a4-959f-ea1952ef4851 |  | textbox | Date Completed:
checkpoint-status | be302b2d-928a-4902-9709-149fe1ba3637 |  | checkpoint | 2.3 - Jointing
label | 8410b6d2-8b08-50d8-8b21-9550cbc0b0d8 |  | note | FREQUENCY: Each Lot
label | ec70281c-1174-5ba6-be32-c062064f2b32 |  | note | ACCEPTANCE CRITERIA: •Material shall be spread to minimise number of joins
label | 849bb7e5-af89-56e0-a70a-828ff9135513 |  | note | •transverse joints in adjoining paver runs shall be offset by >2m
label | d3f33619-9214-5996-a66e-d923606a3f5a |  | note | •Longitudinal joints shall be offset from each layer
label | a1d8117e-7b56-5819-b3d5-fb616c61839c |  | note | >150mm
label | a03edf84-9461-5735-a263-c70a6cb41bbc |  | note | •Longitudinal Joins shall be within 300mm from traffic lane lines or centre of traffic lane
label | 730428fc-523c-5400-9e87-3ebd46c0f14c |  | note | REFERENCE DOCUMENTS: VicRoads 306.08
label | 8d3c6204-dec9-58c1-9665-f8a66c52f4fc |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 91adcf2a-309d-54a5-a294-104fc92735a9 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 2e3c665e-54d0-50ea-9039-18d4351d6b72 |  | note | HP*
label | 0b546cc6-aa3e-560d-8106-76caf2c6486e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 62969414-c646-53c4-bb92-381d921ca92c |  | textbox | Date Completed:
checkpoint-status | fc8c2543-06ab-45a7-ac0e-7a1bbc090008 |  | checkpoint | 2.4 - Conformity with Drawings
label | 4b4b77a3-c7a9-58b9-aefd-c89bfa91bd60 |  | note | FREQUENCY: Each Lot
label | 8b372d5e-e242-5122-9cbb-b0f19545ee6f |  | note | ACCEPTANCE CRITERIA: •Pavement sub base shall be finished to smooth and uniform surface
label | e2aecb7e-74d5-575d-ad04-068e1e5ffd29 |  | note | •Surface of sub grade shall not lie more than 12mm below a 3m straightedge
label | e8475bfb-6f18-54d0-b8ce-fafc9416adcd |  | note | •Subgrade height shall lie within +15 to -25mm
label | a95f964e-7b85-561c-8e4d-f428143df434 |  | note | •Sub base height shall lie within +10 to -25mm
label | 90cf01f7-33e1-5262-afe8-1295db124424 |  | note | REFERENCE DOCUMENTS: VicRoads 306.03 306.11
label | ea782bf8-5070-5599-bac2-17bf7c14e333 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | fa89c1cd-6348-534a-bb0c-6acfa5b3e6a6 |  | note | RECORD OF CONFORMITY: This ITP signed
label | d789ab5b-50f9-532b-bbb0-d9c1dc464c82 |  | note | WP
label | 64f8e23e-501e-5278-9110-b5b5e43d3c57 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 0084edbb-1f9b-5765-9706-5c68078b7b57 |  | textbox | Date Completed:
checkpoint-status | 5ebaa305-85a5-4add-bb85-15c93669bb2e |  | checkpoint | 2.5 - Curing
label | 5f8cdfda-3f3d-5f4c-8aaf-e0761736d8ad |  | note | FREQUENCY: Each lot
label | 1831e497-d46a-57d3-81e4-8cbed0a8fe56 |  | note | ACCEPTANCE CRITERIA: •The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane. •As per VicRoads, 4000m2 shall be maximum lot size •No trafficking before 24hrs unless approved by superintendent
label | ab299939-c62e-512a-916f-0d3068515f8f |  | note | REFERENCE DOCUMENTS: VicRoads 306.11
label | 1a7e923d-f8c4-5bf4-a25c-a61cbd2e2580 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 0a05f2f5-9117-52f5-a0fb-f2b8a73d51a9 |  | note | RECORD OF CONFORMITY: This ITP signed
label | b4f63502-ec89-5dea-802d-9cc70976b287 |  | note | IP
label | 4057a548-26d3-5908-a2a6-aade18b7d452 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 6a0f8167-f20a-5236-bdba-03f5fc7bf9f5 |  | textbox | Date Completed:
checkpoint-status | b3fb593c-6e8a-4b00-aefc-72ab6138eef7 |  | checkpoint | 2.6 - Compaction Testing
label | c0653381-983d-5f36-8057-481dc9e54989 |  | note | FREQUENCY: Each Lot
label | d5f02a96-a45d-51d5-9446-c15dd1f8fae4 |  | note | ACCEPTANCE CRITERIA: •CT material shall be placed, trimmed to level and compacted within allowable working time (306.091) •At completion of compaction, any segregation shall be rectified •>500m2 96% modified compaction 6tests <500m2 98% modified compaction 3 tests
label | a51049ac-3b77-5158-a378-627440286866 |  | note | REFERENCE DOCUMENTS: VicRoads 306.09 306.11
label | 4fca6769-a0d3-53f2-bae1-12bd818f2bde |  | note | INSPECTION/TEST METHOD: Visual inspection
label | db02e54a-fc81-5dbe-8be6-2c1c1f295550 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 185b0ca0-212c-595d-9c67-894a76db742a |  | note | WP
label | 875c0d4e-4207-565e-adf9-3faac60282bb |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2779c6ea-8367-5f07-ae42-4f778ebbd858 |  | textbox | Date Completed:
checkpoint-status | c69ab091-cb63-4d3d-905c-d25aeeea708e |  | checkpoint | Final Inspection
label | 98d167ad-83f6-5040-b39f-dcf0a76f0e85 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | bc93a8bf-6f8c-5243-801d-abefbf44d679 |  | textbox | Print Name:
text | 918266b1-a04c-58b4-8e76-defcc838ef5f |  | textbox | Position:
text | 5cc70b78-4fc2-51ca-ab5f-e7df651f4596 |  | textbox | Date:
checklist-sectioned | 727b69dd-b616-4163-8bb7-fdb597ea07f9 |  | checklist | ITP-006 - Track Placement Rev2 |  |  |  |  | Yes | ITP-006 - Track Placement Rev2 | 566c7681-3800-41bc-95eb-09990e7fe12e
checkpoint-group | 8880267c-a095-471a-9fb2-b5e410d97e74 |  | section | Preliminary Works
checkpoint-status | e401a622-281f-4b4e-a278-206d8a46ec72 |  | checkpoint | 1.1 - Check for Correct Documentation
label | cd29fb98-d34a-5d83-b67d-d4b33fd61046 |  | note | FREQUENCY: Prior to Commencing Works
label | 964c440f-9bf0-529d-ab9e-4b6375494ce2 |  | note | ACCEPTANCE CRITERIA: •Ensure that all employees and contractors are using the most current and complete set of drawings
label | 405f74cc-26c0-500b-9a62-a6d76810e729 |  | note | REFERENCE DOCUMENTS: Design Drawings and Register
label | 9be3e37c-2c3c-5298-a0d9-a3c7a29c436f |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 7e901ad5-b7d5-5a50-9e29-46bca7e72f31 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 5e815861-37d7-5c6e-939c-d242661bbe85 |  | note | HP*
label | 2f70d30f-0345-57bf-9c7b-f1fcdedcf44e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 4b6c2314-b0cd-5349-b3b6-5602885559ee |  | textbox | Date Completed:
checkpoint-status | 1b3976e9-5c71-4580-8c72-4d69ccb4ebbd |  | checkpoint | 1.2 - Check Materials
label | 0b610a55-6723-5063-ba69-5697cf1f2c1c |  | note | FREQUENCY: Prior to Commencing Works
label | b657224c-619e-5f44-bec6-1095da352f2a |  | note | ACCEPTANCE CRITERIA: •Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used •Check condition of rail sleepers •Ensure rail jewellery is of sound condition
label | 18386822-fe52-574d-b598-9e655687d446 |  | note | REFERENCE DOCUMENTS: AS 1085
label | 78c574ce-6411-5123-91d2-7ac4a0cd74cf |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | bb98e93b-fd93-579d-aa19-36096a3c1725 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 7646fd20-86a1-5f5b-a71d-a98158afd41e |  | note | HP*
label | e599347c-b5a8-5639-84ee-c52ae83a24f4 |  | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
text | 1874dca2-92d8-5d96-a892-6df537bf2f87 |  | textbox | Date Completed:
checkpoint-status | 9ae86133-3c7b-49cd-a026-3dd54cc2e735 |  | checkpoint | 1.3 - Check Special Works Components
label | a05837b8-43de-57b7-ac96-144b1856913b |  | note | FREQUENCY: Prior to Commencing Works
label | 474de2ce-c6c3-569d-b155-ada77142232b |  | note | ACCEPTANCE CRITERIA: Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending. Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and separate rails. Superintendent to visit yard for initial inspection of the rail and fabrication plans.
label | 25046c45-97b8-5a97-b1ee-b253816a8033 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
label | b4848578-6b52-5c59-9df4-81ef37018436 |  | note | INSPECTION/TEST METHOD: Verify
label | 25358b36-35b1-59ad-a490-44c8057f65d8 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 8eb15827-921f-5dec-b7f7-eb437cedee9f |  | note | IP
label | 818b6dfc-fe63-5a0a-b5b6-f33114de415d |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 44ba37d0-09b1-519d-93a2-de488331cdd0 |  | textbox | Date Completed:
checkpoint-status | cab3bb1f-fe3c-4b73-bb11-11ba60f7af89 |  | checkpoint | 1.4 - Check Curved rail
label | d8d9ede7-59eb-5144-98d8-cbe9133fec94 |  | note | FREQUENCY: Prior to Commencing Works
label | 17560a09-b7af-547d-82d4-fd31a8cb2a60 |  | note | ACCEPTANCE CRITERIA: Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent. Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails. This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
label | 5624175d-8b13-5288-93ad-2f6c5bdd1acf |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
label | 46f3f00a-f241-5e4f-b4ed-652e53db778c |  | note | INSPECTION/TEST METHOD: Verify
label | 796e8825-225f-582b-a9fc-425c8a2a5d81 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | c7b53874-548f-583c-a6e3-dd5cf9394af8 |  | note | HP*
label | 314dfd77-d240-5839-b3bc-5341e0ab6949 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 67209292-68cf-5abd-a0b1-5a80e5fd6d81 |  | textbox | Date Completed:
checkpoint-status | 19d593a2-92c3-4796-a9c8-785fda0b5d29 |  | checkpoint | 1.5 - Welders Qualifications
label | e0e7d274-1fbc-5dd5-bf85-2fcdac646c56 |  | note | FREQUENCY: Prior to Commencing Works
label | 64b0e2a3-5dd5-5ac2-b0a1-0981e4732c06 |  | note | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements; TLIW2012 Grind Rails TLIW3015 Weld Rails using Aluminothermic welding process TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
label | ea8adda3-63fb-5f59-ad0c-e4fd4349e786 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | 6890baf7-b1db-52ae-8fc6-b3f084f8c88f |  | note | INSPECTION/TEST METHOD: Verify
label | 80539802-dd39-52b5-9440-2328a95d320d |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | e8af5b79-190d-5f0a-acf8-878b8da4d60b |  | note | HP*
label | cfbe0754-e9ad-52b6-bbd6-d7292f8a052d |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2d492f74-22fb-5fe6-ba5e-fb6e232c3bed |  | textbox | Date Completed:
checkpoint-status | 4899bd3e-4728-49c9-8db7-10e7744c7ff7 |  | checkpoint | 1.6 - Ultrasonic Testers Qualifications
label | 7d7a4e2f-26d7-576a-8eb5-abd6c83ee16a |  | note | FREQUENCY: Prior to Commencing Works
label | d8971465-e451-51fc-a459-5ee5ffa29b04 |  | note | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing. Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
label | 1acb5bff-9e9d-5b6c-98d2-98c331de6e63 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | ebf347c9-33c6-59f1-8ddf-6c8cba71d1ef |  | note | INSPECTION/TEST METHOD: Verify
label | a4002dbf-9600-5737-a9ce-b8fe15253f85 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | f2cc989a-cf12-5e51-b397-f481d693eae9 |  | note | HP*
label | 3ef36531-d56e-5233-b8ef-1f6c0c3a9805 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | a7d57174-9100-572b-aedf-8b48a3c2fbf9 |  | textbox | Date Completed:
checkpoint-group | ea49d8ff-41bb-4887-9557-ee411727a6cc |  | section | Construction Works
checkpoint-status | 82a6623f-ead1-4f57-ba2e-5a17767688c1 |  | checkpoint | 2.1 - Installation of Sleeper
label | 1af28c5d-5e85-5392-a3f2-7276b93771bd |  | note | FREQUENCY: Each Lot
label | 96620156-a6c6-587b-abb8-5d8d6e3dc570 |  | note | ACCEPTANCE CRITERIA: •Dual block sleepers shall be installed at 700mm intervals, tolerance of +/- 50mm in placement •Dual block sleepers shall also comply with the design offsets at each chainage
label | d3bf5394-99c9-5011-8a1a-320c0bb233f6 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.7.1
label | 9e0723eb-45ae-59b3-bf47-728921b20db9 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f8b5bc31-fbe2-5f96-b851-21ce47bac4e3 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | dac7d3ee-aedc-5d75-8c93-5f1db2c2060d |  | note | IP
label | 78caf6b1-d1d2-5794-84ca-c72246a12d9c |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 1ecc71d6-3820-5fa4-945d-82e6938ca330 |  | textbox | Date Completed:
checkpoint-status | b4313002-f592-46d8-bc80-c2fb194a402b |  | checkpoint | 2.2 - Placement of Rail
label | 9e4882f9-95ed-576b-beb8-91423a4fe3da |  | note | FREQUENCY: Each Lot
label | 81de4f35-0ec9-5fb4-b614-e440666d6b93 |  | note | ACCEPTANCE CRITERIA: •Ensure rail strings conform to rail plan
label | de65fa73-6f41-5de3-a756-9ad7b20704b0 |  | note | All track work, including points and crossings shall conform to alignment, offset, level and Can't as per design drawings and track charts
label | 981ab85f-0749-51e4-9ac7-c2ace21994fd |  | note | •Bottom of rail and bearing surface shall be clean of foreign materials before laying
label | 8fb10fb9-bdb0-586f-831d-7cac9c404e76 |  | note | •Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
label | 19405d0b-67d1-5d59-8bab-27667942c77f |  | note | •Geometry tolerances as follows:
label | 98fc0d85-612b-5263-b8ed-74652c7cd131 |  | note | - Centreline location: +/- 3mm
label | a7d4cfe0-8cec-5cce-90b6-de3bf1d4dce2 |  | note | - Level: +/- 3mm
label | 16e1e851-1d87-56e2-86dd-366c0b925470 |  | note | - Line measured (>10m chord): +/- 3mm
label | 431c5373-d5c1-5bbd-90d0-e3a09db40aa8 |  | note | - Twist (3.5m chord): +/- 2mm
label | 7c96322b-25e7-5583-9442-b2b336132a45 |  | note | - Can't: +/- 3mm
label | d05bf438-e2ac-5f32-a190-9b9d12c17657 |  | note | - Gauge (open track): +3mm, -0mm
label | 4c40abc0-c672-5baf-8a0a-33cac251b69e |  | note | -Gauge,Turnouts (opposite crossings):+2, -0mm
label | 21e310b6-d87c-5063-b917-a002df5a8c3d |  | note | -Gauge, Diamonds and ‘H’ Crossings:+2, -0mm Note: Can't shall be applied uniformly over transitions
label | 20e6cb06-1ef9-5f6c-9023-688f9e9c4111 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
label | ba0b22f6-106a-553f-aadc-f14711e8b518 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 2da2726e-2a7f-5618-a421-49359cde75dc |  | note | RECORD OF CONFORMITY: Completion of track charts
label | 12d24ea5-3bd5-5a03-8140-e32dc1fd656d |  | note | HP*
label | 17b2e038-7a96-5e65-9806-c142ddad861f |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 5e78a8a8-8835-58ce-9dc0-86c8a823770e |  | textbox | Date Completed:
checkpoint-status | b5d082f9-a636-44be-93df-66f796304f70 |  | checkpoint | 2.3 - Placement of Jewellery
label | db7ec983-05bd-5369-9920-18ed1f278787 |  | note | FREQUENCY: Each Lot
label | 494eed0f-a9df-5deb-8dc1-32dad77dbf86 |  | note | ACCEPTANCE CRITERIA: •Each sleeper shall be fastened to track with approved jewellery and rail clips •Clips shall be installed with panpuller or equivalent •All fasteners shall be sealed as per agreed method with Yarra Trams
label | 32f42f5d-e237-535f-b00c-789904d523df |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
label | bce1160d-b5d9-5515-913b-c9534819b257 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | eb193498-4949-54ae-a77c-36777da14e67 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 636ee210-c86b-5509-b9e4-02b7982c18e3 |  | note | WP
label | 9dbb0d67-d5d8-590a-a8d5-60a772a1502a |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | f97de18a-8d57-5b76-bc92-1bdfc0b109f6 |  | textbox | Date Completed:
checkpoint-status | 110bf15f-1fa5-40bc-b29f-c0e355144d63 |  | checkpoint | 2.4 - Rail End Preparation
label | 6104b9aa-139b-52c9-b8b2-d11585fe3d39 |  | note | FREQUENCY: Each Lot
label | 5e2f5c5e-3418-57a7-be92-b75939ed7529 |  | note | ACCEPTANCE CRITERIA: •Rails shall be saw cut or flame cut •Minimum closure length from proximity of welds shall be 2m •Rail end conditions shall match (i.e flame cut - flame cut)
label | a2372a8d-9009-5b53-8cf1-5d3c03e14f5e |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
label | 8390e013-b665-5b70-bc4a-47baa14d1202 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 732e8c69-ef33-57b4-8578-3d11fecfeafe |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | cacab564-386e-50f7-b663-c2dcd3e8cdb2 |  | note | WP
label | cd5d3c55-8e0f-53ae-8bde-f28aac3ec574 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 44dcc52e-22c2-5f2d-b271-efc15d91e30c |  | textbox | Date Completed:
checkpoint-status | cb9bdf51-ed60-406b-b20c-b3d2554ef2ae |  | checkpoint | 2.5 - Welding of Rail
label | 085ca19e-ee90-5b7a-97da-68ff827dd62a |  | note | FREQUENCY: Each Weld
label | 03439012-86e6-5fed-9cb7-7adf8df0c8f7 |  | note | ACCEPTANCE CRITERIA: •Joints shall be square across the track
label | 09e398d6-d71d-54e4-bbc5-b0d624f4cc93 |  | note | •Maximum skew at square joints shall be 65mm
label | a47d6280-bb4b-5e8a-94ad-619801d5a930 |  | note | •Portions shall match rail type (i.e HHR, Ordinary)
label | 1b21b353-c893-50f6-a8c8-dcf5373a6131 |  | note | •Welds shall not be within:
label | 6a223772-158e-5892-9b7a-03485820596e |  | note | - 3m of another weld
label | 1a9200c6-f296-5074-8d7f-d2f482b6e837 |  | note | - 3m of a rail end
label | d55c108e-8df0-579f-82ad-15d24551d9f4 |  | note | - 1.5m of a glued insulation joint assembly
label | 979c87d8-47ec-5e19-b4cf-1f492c4d5f09 |  | note | •Field welds shall be +/- 50mm from centre of bay between sleepers
label | 859ab0a3-f034-5519-b1de-b588eff41ee7 |  | note | •Weld Return forms shall be completed by qualified welder
label | 51879caf-fd2f-5a94-9d21-b0de4e7c5536 |  | note | •Welds shall be grinded after 1 hour
label | b2840a06-bd4a-5e48-8b66-ea6c7acc96c6 |  | note | •Welds shall be free of water
label | 69ad301a-5480-57f4-91da-cfc0931fdc68 |  | note | •Post grinding, welds shall be cleaned for visual inspection
label | 77a27b10-9b9f-58fc-adf1-56a8937a0ba4 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
label | d19dfaa8-fffa-5dd2-b94b-beb24f507615 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 8d27ef80-1755-50a9-838a-161f0a766f2e |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 25f20dd3-680d-56a1-bb6c-766a45cdbff3 |  | note | TP
label | 8c8a9d11-3b1b-55bb-b9ad-90a3a8e96be2 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ae31bbd2-3535-546c-ba33-3e567491aaf0 |  | textbox | Date Completed:
checkpoint-status | a8a7e9fa-2d44-4b24-b4da-d6f11661deb3 |  | checkpoint | 2.6 - Grinding & Cleaning Welds
label | 42f38b73-3bbe-5328-8d15-301b92d305c7 |  | note | FREQUENCY: Each Weld
label | fe6226e5-599b-5a1d-b0e6-12f74a3c8320 |  | note | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld. Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
label | f40d88d2-6be6-51b2-a3a6-8a3edac56835 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | 8257a3d5-91ea-5dfc-8bdd-adfc68fadbd3 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 3e837ce5-809f-5cbe-8357-864f9418656d |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | f0b9a9b9-3834-506c-91a2-7541746fda5f |  | note | IP
label | 6be05ff1-c1a5-54dc-b3fe-2d436b2582fb |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 1b206d17-7851-5c0c-8231-36656b8334e2 |  | textbox | Date Completed:
checkpoint-status | 8e374ad4-0f87-420c-911d-e7553c1fcfb8 |  | checkpoint | 2.7 - Track Adjustment
label | d52394ef-6a66-5064-8c70-c3fa92e7f587 |  | note | FREQUENCY: When required
label | 227a89fc-aa63-5e0c-ad93-557efd7fca8c |  | note | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress. The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths,which shall be measured with an approved type of thermometer. In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep. Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
label | 6b2dbab1-ddf0-522e-ad2b-c951b4e60017 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
label | 7040af63-aeca-5e47-9d60-df450cc0663f |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 82adc131-930c-58d4-892c-96e7167efc2b |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 5f587d22-36af-51ec-a184-1d25812a01e0 |  | note | IP
label | 6ea11ca1-f9cf-515e-ae37-7dd760b43d07 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 7d27f81b-26c7-5941-9008-ec501bbeb88f |  | textbox | Date Completed:
checkpoint-status | 14cb2c02-5d84-4580-bba0-3f7c6409b65e |  | checkpoint | 2.8 - Track Bonds
label | 5975dd3b-dec2-57c0-80c9-ae1b7f325f87 |  | note | FREQUENCY: Each Lot
label | 5de95e3d-1f67-5565-a032-d12dc4ef76b6 |  | note | ACCEPTANCE CRITERIA: • Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications • Ensure bonds are sealed as per agreed method with Yarra Trams
label | 9889d286-ae7d-50c0-9991-39ce083f0147 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4 Appendix C Design Drawings
label | 9debfd48-fb3e-561c-876e-6619de86e594 |  | note | INSPECTION/TEST METHOD: Inspection / Test Method
label | 340bbcd5-17a1-5c10-944f-7bb469086b37 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | adf4ffca-7a9d-50f3-b758-2206898c51ef |  | note | IP
label | 0a8c29c6-b981-55d8-966d-85f05ecb592a |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 0a8cb9a4-9751-5404-a367-f625d5b1c4ed |  | textbox | Date Completed:
checkpoint-group | 013a36bf-2ef1-4221-9de6-0b766c041b65 |  | section | Testing
checkpoint-status | e71cf6f0-3c03-4d02-ba35-4c297feda1e7 |  | checkpoint | 3.1 - Track Testing
label | f82612f6-b828-58a6-ad21-bb1c2e8f9a35 |  | note | FREQUENCY: Each Weld
label | 8e013ac7-2c48-5646-a49c-f7a20c4f2144 |  | note | ACCEPTANCE CRITERIA: • All welds shall be tested by qualified NDT operator • Failed welds shall be cut out and replaced • Testing documentation shall be recorded and supplied to the superintendent
label | c3ddcd00-283b-5c3c-a779-6700f7f6fe9e |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | af6273d3-11e0-51d7-928a-642776e445ea |  | note | INSPECTION/TEST METHOD: Inspection / Test Method
label | 3df59ac5-37a3-5a51-bdcf-4ea290a0d340 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 13bdb075-0886-5f92-a4f9-222340b31820 |  | note | TP
label | 1102627a-fe53-5a67-9460-6bbc450d6eb3 |  | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
text | 8960344a-fe92-5e6d-8ab2-73512c63d8fb |  | textbox | Date Completed:
checkpoint-status | c512471f-d2df-4b17-a9b7-d22552ce20ae |  | checkpoint | Final Inspection
label | 6699681f-4c7a-5d96-9484-aef0f57c74e6 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | f843731e-d52c-5835-a89d-28823de89ec9 |  | textbox | Print Name:
text | 01296558-d969-5629-b097-9b16dbf63a4b |  | textbox | Position:
text | 55e7840c-1f26-51a5-bbda-17567ffd309c |  | textbox | Date:
checklist-sectioned | 0f46140a-27c1-4bbf-937e-4c9ad125191f |  | checklist | ITP-037 - Structural Concrete Construction |  |  |  |  | Yes | ITP-037 - Structural Concrete Construction | 71699595-cfc1-4082-a9a4-3d152fab04a4
checkpoint-group | d575f5c9-a786-44d0-a31d-29a6a1b4e233 |  | section | Design and Submissions
checkpoint-status | da981494-9ad0-4e44-8567-547038f554d0 |  | checkpoint | 1.1 Check for correct documentation
label | 10867538-2aa7-41dc-a905-feb98750ae31 |  | note | FREQUENCY: Prior to commencing any activity
label | 70251ed3-c36b-4277-bd8f-7b0c4ac06a74 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
label | 1a34dcff-ca4c-4da8-a88a-0b9e0aab1f08 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 3e8d9101-7728-465d-adb2-7c76cf5e575d |  | note | INSPECTION/TEST METHOD: Visual inspection
label | dc226a37-d59e-4958-b256-4b8a527e0d3c |  | note | RECORD OF CONFORMITY: This ITP signed
label | 8114c6d4-a80f-40ef-a0da-30b96f57f274 |  | note | HP*
label | 909092ba-a767-4cba-9008-cdec4d57dace |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | d494c5d2-9033-4a1b-8144-95bd559ba962 |  | textbox | Date Completed:
checkpoint-status | 29552d51-0fc2-4088-a3dd-be9c947006b2 |  | checkpoint | 1.2 Implementation of all measures and controls
label | d8f36d48-9962-4c11-8a15-7d999df5ca76 |  | note | FREQUENCY: Prior to commencing any activity
label | 1a98fadb-e11f-4bcc-86af-9cd7bbf83a3a |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | c3b1be3b-1703-493b-936f-dc2f67514e64 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 5a3fb175-cf79-4d83-a4fd-353f6458d1ce |  | note | INSPECTION/TEST METHOD: Visual inspection
label | d59f6772-8936-4438-9d02-ef523eb7656b |  | note | RECORD OF CONFORMITY: This ITP signed
label | 78b91eb9-ca04-466b-b3c7-7122153101fb |  | note | HP*
label | 15846b91-27de-45af-bd9d-0daea8be34d9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | dd645d3e-2497-451d-817e-3ffcc1209b23 |  | textbox | Date Completed:
checkpoint-status | a81ad355-59ed-4d1e-a599-36bba3f5c122 |  | checkpoint | 1.3 Approval of Mix Design
label | 8d91ba3a-9d85-4a85-85ae-680babdbd616 |  | note | FREQUENCY: Prior to the first concrete pour
label | fc25cefd-c662-41a9-b4d0-e769458d7e37 |  | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
label | 6b85be64-be52-463c-b0a5-9f8ffb37041c |  | note | REFERENCE DOCUMENTS: WP 01
label | d5568340-fffb-4d12-a036-97b56a6423c1 |  | note | INSPECTION/TEST METHOD: Verify
label | 8ec1954b-9e02-4d19-8981-f7867be1cc14 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 7d4caa8a-a2aa-43b1-8c38-2f5c58a5930a |  | note | IP
label | 71523cc5-8446-48f4-9720-257e5b2fdfad |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | f210001a-e554-4b5c-8585-7081985ff93c |  | textbox | Date Completed:
checkpoint-status | fa890ebc-d4f8-41f8-aeba-725e6b1649d5 |  | checkpoint | 1.4 Reinforcement schedule
label | 1172d2ac-91f9-4908-b1b8-2b24e80307b4 |  | note | FREQUENCY: Prior to concrete pour
label | 54916229-d0c5-4f70-ba81-1debdd380a5a |  | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
label | 49c4c6a1-e6c8-4328-8a70-e6af441cce5c |  | note | REFERENCE DOCUMENTS: Cl 611.04
label | d3cf1a27-9d7a-43a6-90dc-bb0d48a656f8 |  | note | INSPECTION/TEST METHOD: Verify
label | eb0ef6a7-9a73-4f96-8bb9-e50809857fa6 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 02ba46be-f354-4e8f-8dde-7b625e79350a |  | note | IP
label | 5a7f0fe7-6a20-4dae-b1a5-4c31f53a2587 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 0debaf6f-ccff-4a20-9155-cae027c4bbf0 |  | textbox | Date Completed:
checkpoint-group | 4750ff5e-1315-499a-acc9-e2177c2fadda |  | section | Construction/Erection of Formwork
checkpoint-status | f3259264-ba1d-4c93-a588-fa4217fb2c87 |  | checkpoint | 2.1 Excavation
label | 51e06fc5-ffaf-448f-a38d-a74d37791560 |  | note | FREQUENCY: Prior to concrete pour
label | b5a651dc-36c3-48a1-940e-9a747899b365 |  | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
label | 84618964-c7ba-48b4-abef-8210887395e7 |  | note | REFERENCE DOCUMENTS: WP 01
label | 2e188f4d-254f-4954-9353-6b7f81e3d6bd |  | note | INSPECTION/TEST METHOD: Inspect
label | 9f13ee02-7ac9-4802-8bd4-399943f83c21 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 4de7053c-b08b-48ad-a295-359b08c0bb75 |  | note | IP
label | 57b50d8f-e89f-4815-b41e-9acab9a98b59 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 9fbd4a04-e66b-4cb2-b84b-89265af6b4d0 |  | textbox | Date Completed:
checkpoint-status | f68dae86-0e60-4aca-afb1-9d4a46bce500 |  | checkpoint | 2.2 Construction Methodology
label | c1c38146-ca24-4e3f-9dc2-bce407701d48 |  | note | FREQUENCY: Prior to erection
label | 1b9edb1c-bf60-4bad-b5b1-551e6bb31f17 |  | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
label | 9dcab8ae-c6ca-47bd-b1b0-a98b3e3dcc08 |  | note | REFERENCE DOCUMENTS: 614.04 614.06
label | 45642352-0c3d-4801-9d6d-59b88a8ab8d3 |  | note | INSPECTION/TEST METHOD: Verify
label | 9e1d047e-b6ac-4862-86af-d1c617e869a4 |  | note | RECORD OF CONFORMITY: This ITP signed
label | f892b8f4-de08-4d80-a1ea-f6a2de1dc750 |  | note | IP
label | 37bcfb9f-df1d-4b65-9ed5-97d6816ded81 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 4a31fa64-afb4-4f83-8b9d-f1946f4fb2eb |  | textbox | Date Completed:
checkpoint-group | 50fc99c4-80f2-4d7f-b512-45742ad5d1d6 |  | section | Pre-pour Planning and Inspection
checkpoint-status | 1d777fa8-7d16-4ba4-bbe9-9d358d6feddc |  | checkpoint | 3.1 Excavation/Foundation Blinding, sealing or foundation concrete
label | eb14d022-57f2-4465-8cb4-fc51e87e4011 |  | note | FREQUENCY: Prior to concrete pour
label | 2a0fc54d-4095-476b-9b0f-6badd7c2e79c |  | note | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent. Hold Point released by the Superintendent.
label | 4f66fdef-ee45-4197-9ba4-11650327bc57 |  | note | REFERENCE DOCUMENTS: 602.03
label | 2d2d89cf-74b6-497b-b126-f495719f47fb |  | note | INSPECTION/TEST METHOD: Verify
label | 84230696-cb8d-4b40-8b6d-d8d1d8fd03b2 |  | note | RECORD OF CONFORMITY: This ITP signed
label | f0892976-a7b2-4b72-8624-e9055d9c0894 |  | note | WP
label | b9973106-de6a-4555-aea4-9b8a85bfcbec |  | note | RESPONSIBILITY: Fulton Hogan / Yarra Trams
text | 74cbae5d-c1aa-4cf1-96c1-c0b7b0c3e861 |  | textbox | Date Completed:
checkpoint-status | e296788d-4216-4088-948a-2269204f65be |  | checkpoint | 3.2 Formwork levels and position
label | 199f3526-1b7d-4442-98fa-29aba31201d8 |  | note | FREQUENCY: Prior to concrete pour
label | a27e44bc-39e8-4799-99e0-c63fb6c3c1f6 |  | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
label | 7fb008c3-d125-4812-ab2d-8debe9991bb5 |  | note | REFERENCE DOCUMENTS: 614.06
label | 6b81a006-1e43-40bb-a882-5337385865fc |  | note | INSPECTION/TEST METHOD: Verify
label | 7d580410-24f2-4854-8795-3853bdf0bce8 |  | note | RECORD OF CONFORMITY: This ITP signed
label | cad34c7d-529f-4069-a50e-171ef9a87445 |  | note | SCP HP*
label | 0b611445-ce8b-4d0b-ac64-17675477da5b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 3049e76a-44ec-4296-9301-a7770640d07c |  | textbox | Date Completed:
checkpoint-status | 689ea6a9-4e0e-4397-89bb-b79a64904aa5 |  | checkpoint | 3.3 Location of splices
label | ecbdbc35-07a6-4481-8400-aed20870e310 |  | note | FREQUENCY: Schedule Review
label | 9584ef3c-87d5-4f8f-b49b-619368f06e5c |  | note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained. Where necessary the reinforcement shall be spliced with 40 times nominal diameter of bar.
label | ea35f784-8d4f-439a-bc27-5a8006455aac |  | note | REFERENCE DOCUMENTS: WP 01 Cl6.3
label | df1abb3d-12a1-4382-a527-71401733ebc7 |  | note | INSPECTION/TEST METHOD: Inspect
label | e8d78836-3822-40a4-97bc-69b2d17e4c5d |  | note | RECORD OF CONFORMITY: This ITP signed
label | 5b72d23d-a3bf-463e-9c9c-3d654d6fd56a |  | note | IP
label | f1d95388-0a9a-457d-8848-14eae698e999 |  | note | RESPONSIBILITY: Fulton Hogan
text | ab2d05cc-8862-4548-8bcb-43ee36d108f2 |  | textbox | Date Completed:
checkpoint-status | 0cbf7c38-f6ec-48a0-921e-7c193cacd7bf |  | checkpoint | 3.4 Cleaning formwork
label | 609d0b97-8e68-48fe-84a2-c6b56a260992 |  | note | FREQUENCY: Each concrete pour
label | cb921a9c-c882-42f3-9aa7-1276c6767701 |  | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
label | 4b7b46d3-5874-4041-b667-c26e8812c7da |  | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
label | 601e95a7-8bed-4000-8222-7198f9479f31 |  | note | INSPECTION/TEST METHOD: Verify
label | 3802176b-d9a0-4240-96db-546f21aec767 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 37c3186a-1ff1-4034-969c-18474fd50cdd |  | note | IP
label | 7893a330-8b58-4cbc-9789-3a55a93fa853 |  | note | RESPONSIBILITY: Fulton Hogan
text | b4e7d19f-b8b5-49b6-945b-19e88f5689d1 |  | textbox | Date Completed:
checkpoint-status | 71cbe3f3-f9f7-4be5-b3db-9504310f74e3 |  | checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
label | b748eb38-a56a-4232-b4ee-e61f6c0fc32c |  | note | FREQUENCY: Prior to concrete pour
label | cf625bcb-f0c3-412b-a01c-896a604e5e05 |  | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications. CL01A Pre-pour Checklist completed and signed.
label | 7231ba48-ffdc-440a-9cfe-683b5b8df7ba |  | note | REFERENCE DOCUMENTS: 610.18 (a)
label | 3a18cdd7-19c1-4a24-8154-09856f3ec72b |  | note | INSPECTION/TEST METHOD: Verify
label | 7f75eea5-6be8-408f-9a6c-0ef25179fc4c |  | note | RECORD OF CONFORMITY: This ITP signed and CL01A
label | 950e7515-0e3d-484b-9639-33b1a9980992 |  | note | WP
label | dc1adc95-e5e2-4a74-9fb7-0efa8f8d9054 |  | note | RESPONSIBILITY: Fulton Hogan / Yarra Trams
text | 02c48e7e-68ec-4a65-8993-3134c4042258 |  | textbox | Date Completed:
checkpoint-status | 439e682e-8f3a-44e8-a2cc-559b038ecc67 |  | checkpoint | 3.6 Monitoring weather
label | f37f95db-5b9e-47b6-8155-7a28720f582b |  | note | FREQUENCY: Each concrete pour
label | 9b490dac-4125-4c59-9827-2dde9e7bb6d9 |  | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5�C or > 35�C. All steel components that are in contact with the concrete shall be cooled to below 32�C before concrete is placed
label | 088a0853-b3a2-4656-a0be-5160bd152e9f |  | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
label | 7a3ae2e1-f4c5-4b5b-a833-bb5b4159c392 |  | note | INSPECTION/TEST METHOD: Verify
label | ba5be445-816f-49a7-8344-5425400070f5 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 8d4052a7-fdcc-4bc7-9104-885f089d0abd |  | note | IP
label | 0b87ac01-ca86-4c70-853c-c86b39ef683a |  | note | RESPONSIBILITY: Fulton Hogan
text | ea983163-0d13-4104-90b7-da33d8ff6164 |  | textbox | Date Completed:
checkpoint-group | e9cbbc67-5aa7-45ca-a84b-356066a668e2 |  | section | Placing and Finishing Concrete
checkpoint-status | 74bc0c79-9d18-414e-a2ae-86de5c92a327 |  | checkpoint | 4.1 Carry out sampling of concrete
label | 94210c68-7d71-499e-af95-5cd0588b2330 |  | note | FREQUENCY: Each concrete pour
label | a24dad36-43cb-491e-aaaf-b2b411207e6d |  | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
label | 8aafe55d-2ca0-4868-a43c-8296172e9896 |  | note | REFERENCE DOCUMENTS: 610.16
label | a88874ec-4067-4390-9e8e-a5d0177f051f |  | note | INSPECTION/TEST METHOD: Checklist
label | 9eefb3bc-f6ed-4414-ae41-5c77224600c7 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 2bdcc4f7-7083-4981-9074-430bc84ab5a4 |  | note | IP
label | 2397b2e3-d970-4dff-9661-fa4a8410800f |  | note | RESPONSIBILITY: Fulton Hogan
text | c99380d6-e94b-4da1-8a13-daaa91788992 |  | textbox | Date Completed:
checkpoint-status | ba5cbe3e-f445-40cd-affe-c88199666706 |  | checkpoint | 4.3 Discharge time
label | 4770a92d-e167-43e2-a7c6-25d67c191a31 |  | note | FREQUENCY: Each concrete pour
label | 5a04315d-fa77-4fe9-bf4d-a5d4536bd6b4 |  | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
label | 669fd7d7-f802-43e6-9706-0b029ab00ad6 |  | note | REFERENCE DOCUMENTS: WP 01 Cl 8.2
label | d9007967-9a29-488d-9e4f-6144609c3ba9 |  | note | INSPECTION/TEST METHOD: Checklist
label | 13687bb9-8a77-41bf-a7ac-54447db447de |  | note | RECORD OF CONFORMITY: CL001B
label | 0ccf7d5d-74a6-4be2-8742-c79361f17357 |  | note | IP
label | a23bcec7-2e92-4c96-b326-32b702bb985a |  | note | RESPONSIBILITY: Fulton Hogan
text | 25b5e215-1d65-444b-86a4-23d902ba2eda |  | textbox | Date Completed:
checkpoint-status | dc2eb710-4cae-4dc0-89cc-c9592a559ae4 |  | checkpoint | 4.4 Methodology of placement
label | 99a7812a-bf2f-4f1f-9838-53b73418ddce |  | note | FREQUENCY: Each concrete pour
label | b61867a1-da27-4f05-8029-5ed9cbee6f2a |  | note | ACCEPTANCE CRITERIA: Concrete shall be transported, handled and placed in a manner that will prevent segregation or loss of materials. Concrete shall not be moved horizontally by vibrators. In continuous pours the max. time lag between truckloads on site is 25 minutes
label | a6ba842c-2c3b-4799-97d2-cd5c967bee2e |  | note | REFERENCE DOCUMENTS: WP
label | 2b6dc3ce-ca1f-4b64-afce-2d7df1e7365b |  | note | INSPECTION/TEST METHOD: Verify
label | 52737135-c8d3-429e-a061-9f3e6bad66a7 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 611812ad-6d60-430f-ae18-a5681b743f6b |  | note | IP
label | bcf7f1d2-f359-4ad7-8f55-dda055d7373c |  | note | RESPONSIBILITY: Fulton Hogan
text | 6c276df3-1a46-4bb6-bf38-ce0e33d0edb8 |  | textbox | Date Completed:
checkpoint-group | 846d0d26-bc77-4081-b8fe-d4ae4d9f5578 |  | section | Post-pour Details and Inspection
checkpoint-status | 55fb1338-223d-447d-8fb1-cdfc0abef791 |  | checkpoint | 5.1 Formwork removal
label | fec2e4ec-1278-4ab4-9fdf-921991224a92 |  | note | FREQUENCY: Each concrete pour
label | 6d8f7ea9-34e1-4586-a9f0-8ea0d505fe1d |  | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
label | 4b03cd99-d01b-4c2b-ab11-48df860813ba |  | note | REFERENCE DOCUMENTS: WP01 Cl9.1
label | b8ca32a5-923a-430d-ac1c-b200f3069acf |  | note | INSPECTION/TEST METHOD: Verify
label | 0c722068-a64a-4a30-877b-cf3a3beb8e22 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 6ef0bc97-ad5b-408e-aeb9-e455018b6b49 |  | note | IP
label | fbb9408e-4703-437c-b067-dac0c5df424c |  | note | RESPONSIBILITY: Fulton Hogan
text | 31ef9ff5-b4f0-44df-8f25-1a9701d87fbd |  | textbox | Date Completed:
checkpoint-status | e89fd0a5-ac00-4201-9fb2-247a40befe2b |  | checkpoint | 5.2 Cracks in the concrete
label | 5741c699-a11d-473c-9180-da7b8ba361c3 |  | note | FREQUENCY: Each concrete pour
label | c37d79e2-d266-498b-bdf6-d0a3a47a9e8f |  | note | ACCEPTANCE CRITERIA: Cracks investigated and NCR raised. Repair procedure submitted to the Superintendent.
label | 356e3446-b91e-4da2-801b-539b9b7cf0e8 |  | note | REFERENCE DOCUMENTS: WP01 Cl9.3
label | 6e8b7c51-e079-45d8-8bb3-15471fd8f83a |  | note | INSPECTION/TEST METHOD: Inspect
label | 406d124c-79e5-40fe-b324-57cd3271dd2e |  | note | RECORD OF CONFORMITY: This ITP signed
label | 32440c5d-9a4d-42f7-bf25-8f996affe477 |  | note | IP
label | 33d13f66-98ba-47ff-a88b-abc089727b62 |  | note | RESPONSIBILITY: Fulton Hogan
text | b1db2169-300b-42d2-acd0-951c3b3e97b3 |  | textbox | Date Completed:
checkpoint-status | 0fef7945-b503-45c3-9dcc-c70433c56f61 |  | checkpoint | 5.3 Positional tolerance and dimensions of concrete members
label | 014adbfc-6a2d-42b1-b49f-4d200eca51c2 |  | note | FREQUENCY: Each concrete pour
label | 0c8824eb-91a6-49d1-a342-c00b55705e2d |  | note | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
label | 7f1dbae1-22a8-4c35-ba85-adeebb84fe2d |  | note | REFERENCE DOCUMENTS: AS3600 Cl 17.5
label | 579eb7b6-83d1-403a-8790-f3c3c42c2134 |  | note | INSPECTION/TEST METHOD: Verify
label | 28b64429-f807-4fea-b76e-7d9ba188b694 |  | note | RECORD OF CONFORMITY: CL01C
label | 6b91ffd7-a99c-4a2d-88a1-2be3e5f1cea5 |  | note | IP
label | dc6573ee-4984-4c80-95f2-5c649cc3be04 |  | note | RESPONSIBILITY: Fulton Hogan
text | 1037217d-898e-4636-b9c7-5bcbbf673377 |  | textbox | Date Completed:
checkpoint-status | 5ddc31b1-d05f-4d61-93d9-93b5f1005cde |  | checkpoint | 5.4 As Built Drawings
label | 359350ea-b49e-4f06-9b95-3aed78d5582d |  | note | FREQUENCY: Prior to lot closure
label | e4f658af-cb4d-42c4-a570-a605aec8d134 |  | note | ACCEPTANCE CRITERIA: The location of the footing and centre of pole is recorded on as-built drawings
label | e132c869-780c-4e16-be05-5e4eb3e2dfe0 |  | note | REFERENCE DOCUMENTS: WP 023
label | 1202cc4c-dc63-4e39-b68b-f6be6055f1b4 |  | note | INSPECTION/TEST METHOD: Verify
label | a9903378-0d18-4ec4-9000-7050f1c7da50 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 43864597-a625-47fb-ad47-9bcb6db1f8e2 |  | note | IP
label | 33c3b749-9e66-4cec-bb44-083eea211906 |  | note | RESPONSIBILITY: Fulton Hogan
text | f079d1ac-08e9-498e-9d3f-91686240cc9e |  | textbox | Date Completed:
checkpoint-status | c81776ee-45bd-494f-9911-393ea39e4cee |  | checkpoint | 5.5 Concrete Sampling and Testing
label | a8f956eb-db6b-466c-8fc8-6c5df43a4e1f |  | note | FREQUENCY: Prior to lot closure
label | ffe36561-acf0-4c5a-b82a-9d65e1e8f259 |  | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and slump
label | 9561f75c-0127-4674-b85b-ffd506e252bd |  | note | REFERENCE DOCUMENTS: WP 01 Cl 9.4
label | 62fa0a5d-5498-4fd0-875e-8a406181299f |  | note | INSPECTION/TEST METHOD: Verify
label | ab4d34e2-23ae-4fe7-adf6-59213078752d |  | note | RECORD OF CONFORMITY: This ITP signed
label | e171df6f-eb6e-424d-9626-51309c2bed87 |  | note | TP
label | 53754690-b0d7-4e39-9b33-6213ef7d76dd |  | note | RESPONSIBILITY: Fulton Hogan
text | 0c3226ad-e7c6-43f4-bc82-94e453c8b4cf |  | textbox | Date Completed:
checkpoint-status | 1a5c7f58-ec4d-411d-b6c5-191a69c3b60b |  | checkpoint | 5.6 NCR
label | bfc30203-a341-406d-8b69-b51beaf862a8 |  | note | FREQUENCY: Prior to lot closure
label | 20dbd986-833d-4878-b3c0-42a9e1d67de5 |  | note | ACCEPTANCE CRITERIA: Details of any NCRs to be recorded
label | 4cffa78a-6147-4deb-9b9f-65479b9c4337 |  | note | REFERENCE DOCUMENTS: WP 01 Cl 9.3
label | 083312ee-7d21-4319-82af-e069c75a5a36 |  | note | INSPECTION/TEST METHOD: Verify
label | b45ab1bd-cbc5-4b33-a2be-8d53801f1d1b |  | note | RECORD OF CONFORMITY: This ITP signed
label | 34275254-0e59-49d4-a1d9-48b4d6a1978d |  | note | IP
label | ef85bace-4a80-4c8d-819d-f0274d38cc99 |  | note | RESPONSIBILITY: Fulton Hogan
text | 07b4d4ac-cb4f-407c-8d80-90becfa23adb |  | textbox | Date Completed:
checkpoint-status | b09b4a8f-797d-4f3a-a0e6-648d2c395fc8 |  | checkpoint | Final Inspection
label | 004c51ec-2ac6-4827-88d0-b834bdfe452c |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 6013fef4-8392-4d83-a4bd-4bbd762095f4 |  | textbox | Print Name:
text | 398dd287-ae40-4d1f-ae1c-e085e7608eeb |  | textbox | Position:
text | 3db5451c-d836-4585-8390-c9164ae31227 |  | textbox | Date:
checklist-sectioned | b9a3bbcf-ee0a-4fd2-aa2f-d22e69a2c7eb |  | checklist | ITP-033 - Insitu Concrete Pit |  |  |  |  | Yes | ITP-033 - Insitu Concrete Pit | 79fd6a04-eb61-441c-8505-68aefffef54c
checkpoint-group | 646bbf3b-f00c-4265-9df6-fc3ffe83fa29 |  | section | Preliminary Works
checkpoint-status | 816c912c-71f7-4b5c-a899-47cdacbc53c2 |  | checkpoint | 1.1 Check for correct documentation
label | d2990ba7-ada6-5dff-afab-1ae3beb16e7e |  | note | FREQUENCY: Prior to commencing any activity
label | 63293069-7df6-5ec3-b1dd-751e8b83b91d |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
label | 6d13e60b-beab-5241-9770-0155b4bd607a |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 6f560b21-261e-5e7c-9849-f9b33ccec8bc |  | note | INSPECTION/TEST METHOD: Visual inspection
label | dab88ffd-4497-50e7-a52f-22399e3a2bf6 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 038293bc-89e4-5919-94a5-4827d580315a |  | note | HP*
label | 04f121a8-22a9-5a39-80a3-1e297b31d3b9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | f6480e2b-b21a-5a60-806c-daf90c9e56d3 |  | textbox | Date Completed:
checkpoint-status | d689c02a-55ef-4e47-a8bf-27db1cc06bdb |  | checkpoint | 1.2 Implementation of all measures and controls
label | 638c1463-12a8-5456-8c4c-26eaf673f9df |  | note | FREQUENCY: Prior to commencing any activity
label | aa74b322-eb0e-58c0-92c8-f63b86386a99 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | e8b3c9a0-7217-5b16-994a-3d677aca2c20 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | a38d568b-a126-5a43-b889-068eb26e5c00 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 6bdc116e-84e2-5358-9a2e-5f633e0b4a6d |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 73c4c175-3c36-5b31-9e93-c8779c8a3c29 |  | note | IP
label | 799747d3-09c2-53b1-91d1-e0957c9ae2dd |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 664aa47f-c4b1-5f6d-af37-f745e228ac0c |  | textbox | Date Completed:
checkpoint-status | a2b67dfa-0e67-447e-b0bb-029d77de0c3e |  | checkpoint | 1.3 Pit material classification
label | 52187fa1-7f56-55a4-94d4-b48ae8228cc4 |  | note | FREQUENCY: Each delivery
label | 22f19105-e74c-5056-8576-d521d8d7f2c7 |  | note | ACCEPTANCE CRITERIA: Concrete used shall have a minimum strength of 32MPa and be. Steel fabric shall be SL82 reinforcement and conform with the requirements of AS4671-2001.
label | 7710b1e0-cec9-55dd-8ff4-acf553536261 |  | note | REFERENCE DOCUMENTS: Dwg 1P50318
label | 53d5aa47-b908-5db3-9dbe-4d199c5adc01 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 14d9745e-32a7-5edc-9973-1436e7babc4b |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 5c333421-a415-544b-a03b-344d095a2b64 |  | note | HP*
label | bc70b1dd-d03d-5a1f-a916-586d069a29a4 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 067eb19b-2524-5ce2-8f93-5c85c823c8de |  | textbox | Date Completed:
checkpoint-status | 9b2863ee-4f72-4a12-8c5a-df0fea285b1c |  | checkpoint | 1.4 Backfill and bedding material classification
label | efa19785-4b3d-58a2-af49-1eb78a3b3046 |  | note | FREQUENCY: Prior to start
label | 78e0ca57-8f95-5955-a33d-d040d823cd70 |  | note | ACCEPTANCE CRITERIA: All crushed rock used in the works shall be Class 2, 20mm nominal size. Sand shall conform with the requirements of AS2758 - 1998 and AS1141 - 1997 and shall have grading within the limits as defined in the code.
label | 60adfc2f-6599-5bf8-94e6-90bcb3f4b00d |  | note | REFERENCE DOCUMENTS: Cl 18.0
label | 6e47baed-507d-5f60-adad-af102cdb2e28 |  | note | INSPECTION/TEST METHOD: Verify
label | a6782468-f064-5a2b-a3a1-7d92135769a3 |  | note | RECORD OF CONFORMITY: Test reports from supplier
label | 17dc9f1f-7ef8-5aac-8b3e-26ee4fb88e02 |  | note | HP*
label | e4f4ebae-a019-533f-904d-8283d04ff9c5 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | aae5d3a4-a4e8-57c4-8a21-ed7de60a8747 |  | textbox | Date Completed:
checkpoint-group | 5b76516d-cced-4238-8319-96e7f28760b7 |  | section | Construction Works
checkpoint-status | 12a3c39c-578c-4049-958d-665038e9bdbd |  | checkpoint | 2.1 Set out pit location
label | d01e5ea9-aa28-5be9-9f2d-a789d24b2810 |  | note | FREQUENCY: Prior to backfilling
label | ec261a44-49cb-5c84-9fc5-0c43e11f2dd8 |  | note | ACCEPTANCE CRITERIA: The line, level and location of all pits & structures must be in accordance with the provided design drawings. The position of all pits are to be confirmed with the superintendent if ambiguity arises from the drawings.
label | f6d52be1-d21b-5be8-9efb-308c8eadd428 |  | note | REFERENCE DOCUMENTS: Dwgs Appx 2: Cl 8.0
label | 018895b1-d81b-5534-956a-0e98de49f6f5 |  | note | INSPECTION/TEST METHOD: Survey Conformance Report
label | 8a6617fb-72cc-52c0-8978-22454a04befa |  | note | RECORD OF CONFORMITY: Survey Report. This ITP signed off
label | e8d394bf-a8ad-5102-8af5-09588d3bf89f |  | note | WP
label | 3a8f319a-ae62-5d04-8d41-c6dd1f36b38b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 88edc0e5-f855-58f6-a2a1-049d89444b86 |  | textbox | Date Completed:
checkpoint-status | d16a4fcb-63bc-405a-adf6-0e99543fbd4f |  | checkpoint | 2.2 Excavation
label | edb206f1-efba-51d0-908e-cfb682d5b2c2 |  | note | FREQUENCY: Each trench
label | 04606e24-96a4-5bdd-80ac-e8d90feb1c6c |  | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth greater than 75mm below the specified level of the invert of the pipe to allow for appropriate bedding. Any trench which may have been excavated to a greater depth than necessary shall be filled into the required level with concrete 1:3:6 mix. Any loose material shall be removed. Trench shall be battered, benched or shored in line with WorkSafe code of practice when required by assessment under 1.5m in depth and is mandatory over 1.5m. No stockpiles within 2m of end of the trench to reduce bearing pressure.
label | a24221a7-4bbf-597d-ba7a-f52c128627f2 |  | note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0, Cl 9.0, Cl 11.0
label | bf157885-cdc9-505b-8789-90543c1ab74f |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 4d1ff526-2648-5065-8b6e-f3abf7f10f84 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 14389dbd-f4cd-56cc-b21d-bd56f0ac1e63 |  | note | IP
label | c4ed7ca7-e8d5-5423-8503-281d27c9d29c |  | note | RESPONSIBILITY: Fulton Hogan Foreman
text | 425f52c2-dc6e-5bbd-b448-a1d0a6edbf4a |  | textbox | Date Completed:
checkpoint-status | 2e664806-7cc3-4d6e-8ae3-0540f81e97d5 |  | checkpoint | 2.3 Inspection of trench base
label | ae5fb236-84ad-50db-bda2-052999efbded |  | note | FREQUENCY: Each Lot
label | 55c13594-c890-509c-9e8b-60c301270cd4 |  | note | ACCEPTANCE CRITERIA: Base of the trench shall be inspected prior to placement of bedding.
label | a738f250-d073-5130-8374-fd321a8334f2 |  | note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0
label | b95d1139-9bb2-583b-8452-54c30ba3c6d5 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 21ff7196-04a1-5bd6-8ff5-109925bdc0b8 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 6cb370ec-6a79-5d19-9924-dd36095f07d4 |  | note | IP
label | c501ec82-5ac1-5434-9174-b0c466f2bafb |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 24693771-460f-5093-be28-85a9ee305a42 |  | textbox | Date Completed:
checkpoint-status | 30e06b91-471b-41ec-bd46-8c5f0aa9784d |  | checkpoint | 2.4 Placement of bedding material
label | 26a66305-6d77-5fb2-a77e-6207e18a4384 |  | note | FREQUENCY: Each Lot
label | a605daeb-63fe-5055-a7a4-628c19507a3d |  | note | ACCEPTANCE CRITERIA: A 75mm minimum layer of compacted class 3 crushed rock shall be used under base of pit
label | fd47632d-c7fd-5171-b1ee-8cfc56bec5e6 |  | note | REFERENCE DOCUMENTS: Dwg ELPOD-2021-17
label | 62698e4b-41a3-5ac8-a751-0ac570659e26 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | b3326d67-fb3e-5455-8f15-3d8b73e932ed |  | note | RECORD OF CONFORMITY: This ITP signed off
label | aa46cb81-973b-56ed-814e-eaba03bf59de |  | note | IP
label | 8d4cf218-5f80-5e00-a634-c82cbca04dc9 |  | note | RESPONSIBILITY: Fulton Hogan Foreman
text | 997ef97c-2e67-55bd-868a-dcbd41ad91c3 |  | textbox | Date Completed:
checkpoint-status | 80dc04e1-6994-4848-8319-eaf5ff3bc1af |  | checkpoint | 2.5 Concrete pre-pour inspection
label | ea8c0afe-3f1d-505e-a26d-4e05faeb4137 |  | note | FREQUENCY: Each Lot
label | 449a5ea6-468b-5dc4-b7db-806a8ffc1a47 |  | note | ACCEPTANCE CRITERIA: The site of the concrete pour for the cast in-situ pit shall be inspected by a client supervisor before proceeding. Reinforcement shall be check for correct cover & lap as per drawings
label | 371828bd-af62-571d-8be8-558a2dfcd8a5 |  | note | REFERENCE DOCUMENTS: Dwg ELPOD-2021-17
label | ef24a2ff-6cb0-5e20-baf4-c95246d5d265 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 76118506-9aae-5621-9948-ab7c6ddbc99d |  | note | RECORD OF CONFORMITY: This ITP signed off
label | ff1f006c-76f3-5550-8186-b206a4c9e111 |  | note | WP
label | 12a8556f-1599-5d28-9d68-f50b3b9d0ead |  | note | RESPONSIBILITY: Fulton Hogan Engineer / City of Melbourne Supervisor
text | f5f0cc6e-276e-5ada-9530-79b096e0d367 |  | textbox | Date Completed:
checkpoint-status | 47efbf3e-a587-489c-8cef-40fd5995c832 |  | checkpoint | 2.6 Concrete pour and pit construction
label | 0ff62b93-8da6-5522-be77-2d3704c5d182 |  | note | FREQUENCY: Each Lot
label | def4888d-7ed5-5d92-933a-807141feec8e |  | note | ACCEPTANCE CRITERIA: All pits are to be constructed in accordance with City of Melbourne's Drainage Specification 2012 and Standard Drawing 1P 50318. All pits are to be constructed in accordance with City of Melbourne's Drainage Specification 2012 and Standard Drawing 1P 50318. Pit should also be constructed in accordance with site specific drawings. The walls and slab of the pit shall be 150mm concrete reinforced with SL82 mesh placed centrally. Minimum concrete strength of 32MPa.
label | 4ff4150f-d9fa-52c7-ab18-0284e00abc9b |  | note | REFERENCE DOCUMENTS: Cl 4.1, Dwg 1P50318
label | a6ee1354-8f7c-5207-9c10-4b8166b71b6d |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 1b39a138-b509-5b62-adce-17b399e188e6 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | b6da5a3c-c1d4-5159-8374-354cdeb44198 |  | note | IP
label | 8f4012ec-c34e-52a7-aa3e-2a3cf0d830a5 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | d75493db-4e8f-5fa9-8948-972befe8d8d1 |  | textbox | Date Completed:
checkpoint-status | e8f172e9-04cd-44cf-8d8b-d5840b9edc41 |  | checkpoint | 2.7 Pit base shaped with concrete to match pipe invert
label | f7b0ff29-9899-5709-b2e9-3dbd0cb81ca2 |  | note | FREQUENCY: Each Lot
label | 37e66c5d-6931-5e15-981d-ebcb2a91e20e |  | note | ACCEPTANCE CRITERIA: Construct as shown on Standard Drawing 1P50318
label | 2ecf2ac4-b917-5d2a-863e-b6e1b09d1e95 |  | note | REFERENCE DOCUMENTS: Dwg 1P50318
label | 59638440-a14c-5845-80de-5950a6ddfa17 |  | note | INSPECTION/TEST METHOD: Verify
label | c3a9914b-5bca-5ded-8756-2595a076eba3 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | fccf87b7-b1c6-50e0-9796-88fe7f476534 |  | note | IP
label | 98e4c6d8-3485-5eee-9743-5466adacc5e9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 6ac3f5ba-f4b1-59d8-bbfe-152f301b14aa |  | textbox | Date Completed:
checkpoint-status | 6010dca2-a345-4382-815c-6ffd8d2528c1 |  | checkpoint | 2.8 Placement of pit covers
label | 352f595b-ac23-56ca-8e4a-58a02442e51e |  | note | FREQUENCY: Each Lot
label | 7bbd7b1e-aed8-5e00-abdb-e52c3b8eaafb |  | note | ACCEPTANCE CRITERIA: All pits shall be fitted with standard City of Melbourne covers specified on the drawings of appropriate class.
label | b6412b0a-3e1f-5192-a46a-f9ee4856761d |  | note | REFERENCE DOCUMENTS: Appx 2: Cl 12.4
label | e125a20d-a409-56e5-8b07-0d0d56f98c40 |  | note | INSPECTION/TEST METHOD: Verify
label | 7659c38a-be9d-587f-88b4-9fa9978e5160 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 44e5bb05-8228-53de-b643-c7fda1be682d |  | note | IP
label | fc4d5db1-1238-581c-9415-ba5177d1c0c9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | b307e88c-14d2-5d7f-888d-96f6554592ca |  | textbox | Date Completed:
checkpoint-status | b9ed2fa3-829c-4132-a728-8f41a71a85c4 |  | checkpoint | Final Inspection
label | 7d0e95c0-1c3e-58ba-b54c-befa51eab828 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | f39cbd64-9a05-5b33-b558-cf761ca1fdd9 |  | textbox | Print Name:
text | 5a181708-1c96-5923-9c11-4e97db3564d6 |  | textbox | Position:
text | 0c00c6ee-5226-566c-ac47-8d90c75f7190 |  | textbox | Date:
checklist-sectioned | ecaed04e-332b-4e70-8e7d-0d34d827131e |  | checklist | ITP-005 -Track Drains |  |  |  |  | Yes | ITP-005 -Track Drains | 808a96c1-531a-41c6-8a1c-d7007997738d
checkpoint-group | eac7f392-1c24-451e-bef2-a2ace5255a3b |  | section | Preliminary Works
checkpoint-status | f2051218-07ec-40f1-b3ca-1d75662d25ce |  | checkpoint | 1.1 Check for correct documentation
label | 9e719214-6f4c-522a-a6cd-8392c44ccdb9 |  | note | FREQUENCY: Prior to commencing any activity
label | 139d3e82-c1be-5d58-8955-208cf82d45a6 |  | note | ACCEPTANCE CRITERIA: Drainage design satisfies requirements of all relevant catchment and drainage authorities, a copy of all drainage work approvals are to be forwarded to the superintendent
label | 8f2a61a5-b312-5f92-8888-1b93eb7e5495 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 86c0aaa8-b18d-50b5-8605-5514dd478421 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 86e70454-672b-53a3-8ed7-3869e180b07a |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 47ad83f4-0d5e-550a-b12d-bdf6ac4668c5 |  | note | HP*
label | 44c17bdc-3d8a-5b41-8d12-6f82fb650741 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 7c64b342-81bb-5d5d-b737-3664f9ccfe76 |  | textbox | Date Completed:
checkpoint-status | 0f8b0809-12b8-4d9d-aa84-9c6f757c5bfd |  | checkpoint | 1.3 Materials Check
label | 201b920b-fff7-53fb-a870-f2e6543c6a66 |  | note | FREQUENCY: Prior to commencing any activity
label | 1b3ccf73-4750-56ad-84be-0170f69ad3b9 |  | note | ACCEPTANCE CRITERIA: Ensure drainage pipes are of correct classification and are without damage Check triangle drains are of adequate quality, and are design according Ri57A rail profile Ensure lid and j-bolts being used are in accordance with STD T9022
label | 503fc156-3cab-59f1-aa1b-be63ee508c71 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.1 STD T9021A STD T9020 STD T9022
label | 62c931ab-d295-583c-983f-44dd2009f59d |  | note | INSPECTION/TEST METHOD: Visual inspection Inspection Checklist
label | 2cb56583-da6b-5213-9c22-b0c108412b4e |  | note | RECORD OF CONFORMITY: This ITP signed off Receivable Inspection Checklist
label | 58d8df27-e9ff-5bfa-aa47-909e3008f527 |  | note | HP*
label | 9d48d4d1-305c-57c6-ae7f-418261af225e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | c613a3e8-8884-51fe-87c4-51d2ef2ada77 |  | textbox | Date Completed:
checkpoint-status | 6b955491-33fa-4d74-bd51-491f6c27398a |  | checkpoint | 1.4 Bedding Sand
label | be7f4aa8-56d6-5470-b0ee-e2088df95052 |  | note | FREQUENCY: Prior to commencing any activity
label | 0a61d9ee-c190-52d9-bfdb-20b31ec4de3b |  | note | ACCEPTANCE CRITERIA: The bedding of all pipes shall be in accordance with AS.3500.3-2003 using sand complying to the following: Max. particle size of 5 mm, Not more than 5% by weight passing a 75 micron AS 1152 sieve, Free from organic impurities, Consisting of hard durable particles, and well graded.
label | 12b85dcc-a727-5564-b1ca-04242d428bff |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3
label | 49d72c40-2574-5953-88aa-67494223445a |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 17698916-737c-595e-8736-0cf94fd3fc2a |  | note | RECORD OF CONFORMITY: This ITP signed off
label | f26b99bc-fcd7-5ad0-9536-25fae0c2836b |  | note | HP*
label | dcf78e96-d86b-5266-bdc7-61bb5d8b69dc |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 5b343919-49cc-5fbd-ba3b-98d52a0c3281 |  | textbox | Date Completed:
checkpoint-group | d1d4e554-e4fe-4411-91de-96068a99e672 |  | section | Construction Works
checkpoint-status | 2c85e9c6-3137-4630-ba3c-e1dde5464374 |  | checkpoint | 2.1 Set out drainage
label | caaae469-153e-5cc3-acef-277af5c4474d |  | note | FREQUENCY: Prior to commencing any activity
label | ad9c3afa-56dd-5492-8e71-aaf93898aaa0 |  | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent Track drain locations are to be identified and based off IFC drawings and sections.
label | 9a68a058-3867-5080-9914-5aa1bbdf7b21 |  | note | REFERENCE DOCUMENTS: Design Drawings and Register
label | 064b1ee0-969a-5c23-8298-a379df9fc504 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 245db1aa-66ed-5cac-983d-38884a4e574c |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 425074ba-d042-5055-8167-1925612e9994 |  | note | HP*
label | bb1dbb91-5f3d-507d-aaad-1e4bfc4cf12d |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 01db7acf-86c9-5424-848b-934d6dbea948 |  | textbox | Date Completed:
checkpoint-status | 86ddaf8d-b21d-4bce-89b3-0207d2e63957 |  | checkpoint | 2.2 Excavation (pipes)
label | bf991b72-e9f5-5704-ab45-3b2270b14b48 |  | note | FREQUENCY: Each Trench
label | 7141dcb5-2981-53f6-bcdc-c847bc298ee6 |  | note | ACCEPTANCE CRITERIA: Trenching to allow for minimum clearance depth of 100mm below UPVC pipe, and 15mm from bottom of rail to surface of pipe Track drains usually have invert for pipes at 400mm depth, with floor of pit 10mm deeper.
label | 0005575c-c604-5029-8a8e-a710b26761a6 |  | note | REFERENCE DOCUMENTS: STD T9021 CE-021-ST-0044 cl 4.3
label | 298cb14e-25f3-5992-b46e-cff5236cfceb |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 34067c0e-3af7-5e54-8198-2bfb5e571e8b |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 049e91f2-9006-573a-b4d9-3522339d240d |  | note | IP
label | 400cdc14-1eb5-5cdb-b30b-abdc5b532723 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | e53e65d6-3f8c-5b04-9f51-3fb137c6a005 |  | textbox | Date Completed:
checkpoint-status | ceae9883-25a2-462b-ac45-ab3d538284f5 |  | checkpoint | 2.3 Bedding
label | 73c9f0d8-b0bb-5508-81fc-60e8ae3c0a0f |  | note | FREQUENCY: Each lot
label | b2ce27e0-5219-5f2d-b51f-57e4b990dd9d |  | note | ACCEPTANCE CRITERIA: Class 2 crush rock shall be compacted to refusal of 100mm minimum thickness
label | 7f2bc204-3460-5ca9-bcda-a544d15b1647 |  | note | REFERENCE DOCUMENTS: STD T9021A
label | 0687c0d7-ff21-519f-8601-7c9730189f4e |  | note | INSPECTION/TEST METHOD: Visual inspection
label | a2edf9f4-6b0c-5c5b-9eba-b35fd6d744bc |  | note | RECORD OF CONFORMITY: This ITP signed off
label | ad361632-a777-5d09-bc13-2b473ab9bef6 |  | note | IP
label | c32c9e71-a5da-5238-8370-7f0395f44ee7 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | fd377ac5-3462-58d7-9325-b7c7059a283e |  | textbox | Date Completed:
checkpoint-status | 038769a5-34f1-4317-9f47-f4cbcb11d8f1 |  | checkpoint | 2.4 Joining
label | a94f0cdc-9b05-5d9b-a208-2de8953bacac |  | note | FREQUENCY: Each lot
label | 79f92300-c431-5b2d-880b-2d0916abf8dc |  | note | ACCEPTANCE CRITERIA: All UPVC pipes shall be joined utilising 'male' to 'female' ends. UPVC pipes shall be joined using appropriate plumbing adhesive immediately prior to connection.
label | 4b4afdd1-c36b-54d7-8dc5-1fcad749e3f4 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
label | a5b02335-b8ab-5e24-ae7a-edabbf4aa38c |  | note | INSPECTION/TEST METHOD: Verify
label | e3c9e811-2635-515f-b699-d5f5f7fc6df6 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 0a1eb945-08ac-5d4d-8419-b374df341353 |  | note | IP
label | b7ee8190-0104-5e7d-9f61-fe91f31e1f6a |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | bcdf340a-0c97-5499-bcf1-73c35e1d851c |  | textbox | Date Completed:
checkpoint-status | 7404b6b8-f380-44b6-8893-86e9ae3d5771 |  | checkpoint | 2.5 Track Drain Installation
label | bcb9e419-0c30-58e2-a589-911be6f63c8a |  | note | FREQUENCY: Each Lot
label | 60775f54-b8b5-5e44-9f11-378cdc08e3fb |  | note | ACCEPTANCE CRITERIA: Track drains shall be welded to designated positions, and cleaned of all weld splatter . Weld shall be sealed after installation Rectangular 300 x 450mm junction pit & lid shall be used with 4 x j-bolts secured as per STD T9022
label | af44239c-bc5a-5595-8463-f5e0465063f1 |  | note | REFERENCE DOCUMENTS: STD T9021A STD T9022
label | 17397136-4493-5a90-863b-4cc6073c7c5a |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 40d3ddd1-703b-5466-8cc0-e9748af75f69 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 7712113a-ee3e-5cc8-ae7d-fc28660963f4 |  | note | IP
label | cff7c239-1375-5488-889d-acbc26e26f4a |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 04e22a8e-dbe6-5ea4-af6c-61d4fa3f8460 |  | textbox | Date Completed:
checkpoint-status | 85285304-8566-4134-a131-ff0b566340b7 |  | checkpoint | 2.6 Points Drainage
label | fbd7ddc6-4b76-5d56-939b-a9497f761e8b |  | note | FREQUENCY: Where required
label | 4fccfa6e-7221-5447-a2aa-4b4ffe8e22a7 |  | note | ACCEPTANCE CRITERIA: The road motor box pit for automatic points shall be drained separately to the normal switch drain and care shall be taken to ensure that water cannot flow into the road motor box pit. Points drainage shall be constructed as shown on Standard Drawing STD_T0304, with 100mm dia UPVC pipe.
label | 8e137636-5107-5c62-8a9b-b5840eaa00b6 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3 STD T0304 STD T0305
label | fc87165e-8a07-53a6-a3a0-a3c04a4b3b6a |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 6d521cb0-cc98-5d40-b5de-d8192ef268ad |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 8e64e7f8-a85b-5db2-9a34-6f6d5a717f80 |  | note | IP
label | aef69ae8-9e63-59b0-a6f4-2a0837003fd7 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 62b33a48-1ead-5979-b570-1158f4a4ff71 |  | textbox | Date Completed:
checkpoint-status | 3a851b00-e731-45bc-84ec-31257adfb249 |  | checkpoint | 2.7 Concrete Pour
label | b0f20b78-72e1-5c15-b42c-20412d0cdc86 |  | note | FREQUENCY: Each Lot
label | 5b83efcd-c52c-5e90-a3ce-8e2e42be8687 |  | note | ACCEPTANCE CRITERIA: Ensure correct heights of sub grade, as to allow for minimum thickness 150mm concrete, to be poured in same period as track slab
label | a91e4d76-8c95-5912-a0e3-137ceaad966d |  | note | REFERENCE DOCUMENTS: STD T9021A
label | ba9b49a0-0288-577a-a42d-1ba812e56b5f |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 7de4930a-a1f4-5d1c-9d6e-829361583ee6 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 5d59bb42-4d3c-573a-97bf-b143f9e147d1 |  | note | IP
label | 20ca46b3-6049-5f3c-8e6b-06ff285f9fd4 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 635780ce-b909-5130-b541-a1e26f8c15fd |  | textbox | Date Completed:
checkpoint-status | 8d012a0c-1f5e-4070-be78-d5e006f4ff97 |  | checkpoint | 2.8 Connection to local drainage
label | 305ef7df-44af-5943-a00a-71b7279fa183 |  | note | FREQUENCY: Each Lot
label | cd115ee8-3add-5d8f-abd0-e570dc7d2a7e |  | note | ACCEPTANCE CRITERIA: Drainage shall be connected to existing Principal’s, VicRoads or the Local Authority's storm water drainage system using either UPVC pipe or reinforced concrete pipes, or an alternative approved by the relevant authority. The minimum pipe size shall be 150 mm.
label | cae01919-f869-5ebc-8777-eca12e7fe323 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
label | d79f1177-d76d-50df-8fd4-49977bd413b3 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 2ac641e7-770a-5b33-9f41-0431d6fd0644 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 6bda4e3c-2d2e-584e-bb67-b8d1c8e77017 |  | note | IP
label | 8c4fc595-790b-578a-aefc-5aaedb4a854c |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 087dcad1-d2f7-503d-971e-45f7e1db9f50 |  | textbox | Date Completed:
checkpoint-status | 81b2f811-b347-4215-b94a-a67a53782d71 |  | checkpoint | Final Inspection
label | 1bbceff5-f8d0-58c7-b622-91d67342ba2a |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 9cb10ab5-7b2a-5756-b173-077872aa5869 |  | textbox | Print Name:
text | 23931154-332b-5613-8fa5-5dee83d1ee32 |  | textbox | Position:
text | 965abdee-ad61-53de-b310-88c0839c6fad |  | textbox | Date:
checklist-sectioned | 7e65a7e5-d482-41a6-99d8-29409d589aca |  | checklist | FHC-ITP-007 - General Demolition Rev1 | itp |  |  |  | Yes | FHC-ITP-007 - General Demolition Rev1 | 87a42c89-e8d2-4972-bbf6-2c60c4ab4d23
checkpoint-group | debcca96-6870-4024-8e76-4f712e75f78e |  | section | 1 - Preliminary Works
checkpoint-status | 8d3a6e5d-2184-4646-8936-cde6f2473701 |  | checkpoint | 1.1 Check for correct documentation
label | df6012eb-90d8-578a-a14e-e4ff0b7fc480 |  | note | FREQUENCY: Prior to commencing any activity
label | 597e5149-918d-5ffa-8294-01257c2e61b9 |  | note | – – – – – – – – –
label | a08c2ad1-8e96-5ea3-b856-b25c5ba5c733 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 52c16e84-73f5-5171-aa4c-b116a74852ca |  | note | – using the correct and complete set of drawings
label | 03acd100-5975-5275-8cb4-6a2bfa2aac22 |  | note | – all drawings are the latest revision
label | 0fbff04b-1d0d-589b-96f5-21ca69f0eb61 |  | note | – – – – – – – – –
label | 5514b563-ff63-5656-ae25-8fa8a2b465eb |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 9121c074-aae7-5df2-b252-d09964df6ec0 |  | note | – – – – – – – – –
label | e6f53646-eef1-52a3-90c1-9715f4d14dc4 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | bd7877ac-023e-5a8e-8f34-07bd8586ce84 |  | note | – – – – – – – – –
label | 50852312-2e56-501c-97d0-99c88668a14b |  | note | RECORD OF CONFORMITY: This ITP signed
label | bb07ad05-2b78-5609-95b1-bb07d1ebb3ae |  | note | – – – – – – – – –
label | 552aaf4b-31ab-5ea0-b962-a13dfe20db14 |  | note | HP*
label | c42d969b-c983-5f23-8ab3-99f29176ab09 |  | note | – – – – – – – – –
label | bc147509-bc74-5c27-856d-4f5a88943091 |  | note | RESPONSIBILITY: Site Engineer/ Site Foreman
label | b760f9ee-9c08-579f-94a3-5576983b6c34 |  | note | – – – – – – – – –
text | 750f67fe-048c-59b5-9901-40f9492837dd |  | textbox | DATE:
checkpoint-status | b9021a4f-23f5-4371-a586-f066c07d15af |  | checkpoint | 1.2 Implementation of all measures and controls
label | 3f157a80-4b3c-5e09-956d-90174093ffd2 |  | note | FREQUENCY: Prior to commencing any activity
label | f40c649a-aa79-5603-8623-ec5c4867b53c |  | note | – – – – – – – – –
label | cdb1f75c-b8bd-5369-9769-6cd46525f410 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 4b15cce4-21b1-517d-86e9-9ed8ed48fc14 |  | note | – – – – – – – – –
label | 8e3a6076-441a-51ab-a2a2-1bb1ac334733 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 8494aa4f-676f-59aa-b090-48a3e3c68aac |  | note | – – – – – – – – –
label | def16d3a-697c-50fe-b77a-3161f06f5f54 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 121d3109-dc0d-5239-a058-221cd0ea5bb2 |  | note | – – – – – – – – –
label | 6d4c2168-7e94-52a3-b966-fcf3ccd9f2a9 |  | note | RECORD OF CONFORMITY: This ITP signed
label | c6e4b942-d1d0-5514-9868-2b52ad76332c |  | note | – – – – – – – – –
label | 39a7d4e9-6d9b-5d6e-a472-206e2e390623 |  | note | HP*
label | d428a88c-bbab-54c6-8edd-8166b961346a |  | note | – – – – – – – – –
label | be7be447-b29f-51d4-8154-be64adc65d0d |  | note | RESPONSIBILITY: Site Engineer/ Site Foreman
label | ae17996c-7529-56a0-b3b1-9483c93ff714 |  | note | – – – – – – – – –
text | 89f5945a-1176-5080-9e3a-de60b3af7077 |  | textbox | DATE:
checkpoint-status | 877c5abf-0715-4661-9780-b28f1ba6a43e |  | checkpoint | 1.3 Service Identification
label | a669f715-54c5-55bd-af60-823806b96bf3 |  | note | FREQUENCY: Prior to start
label | bf45c9ef-c6ad-59e2-874b-44620dbd9171 |  | note | – – – – – – – – –
label | 8fa82c07-1c42-5db4-9f5c-a82a43c517fd |  | note | ACCEPTANCE CRITERIA: Services within vicinity of area to be demolished should be identified and marked, and all services to be retained shall be protected
label | d31140b0-f219-5761-a670-225281b5af1b |  | note | – – – – – – – – –
label | e7779ca6-c1ec-5026-97ea-a134f58dd100 |  | note | REFERENCE DOCUMENTS: ITP sign off
label | c15fc12c-d20f-5c12-858f-a57ece666502 |  | note | – – – – – – – – –
label | b58e406a-d431-5252-8954-eb1178e594fb |  | note | INSPECTION/TEST METHOD: Verify
label | 5484943b-9935-5885-a082-b086affe6d36 |  | note | – – – – – – – – –
label | 793e7e3e-47e6-5be3-b9e7-f4c9b28b3d4f |  | note | RECORD OF CONFORMITY: This ITP signed
label | 987641a3-566a-577a-bbc2-a407afa54202 |  | note | – – – – – – – – –
label | 9cd54f6e-aa05-5f60-ad65-6f8ab9f41033 |  | note | HP*
label | 453c1f05-9ddc-57ba-aa55-754374bc1138 |  | note | – – – – – – – – –
label | 8525759e-4f70-5675-becb-a840bcde690d |  | note | RESPONSIBILITY: Site Engineer
label | df6001f8-e7ff-55ef-9228-5954dd79c4d7 |  | note | – – – – – – – – –
text | bc340cc3-2e3a-5523-ab5c-bf3248e505ba |  | textbox | DATE:
checkpoint-group | e3292e98-9bb7-4b31-85fa-ac1135bd6c05 |  | section | 2 - Construction Works
checkpoint-status | 14b66475-10e4-458b-8013-0a388d21837a |  | checkpoint | 2.1 Saw cutting
label | 727daec6-5eed-5736-8cc3-3b2798186985 |  | note | FREQUENCY: Where required
label | 9693ac95-5907-56ab-baa6-f42b227d1b06 |  | note | – – – – – – – – –
label | ead4b070-dae9-5501-bbb2-42b960bdb031 |  | note | ACCEPTANCE CRITERIA: Extent and location of cuts to be clearly set out and checked prior to saw cutting
label | e7c7243e-f9cc-5b7b-9cc6-0555b6fb8284 |  | note | – – – – – – – – –
label | 92cb0043-0c5c-5480-bb9e-5a6af32b86fd |  | note | REFERENCE DOCUMENTS: ITP sign off
label | c7b0a1e8-7d97-58cd-a39c-1f9063da4b8a |  | note | – – – – – – – – –
label | 8dc05b7d-20b8-5080-b4bc-49ba69d2b317 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 125ec3ff-0cc4-550f-bf01-890178f3ac34 |  | note | – – – – – – – – –
label | 3310c1ac-86da-558e-aa6d-ae9077098848 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 8aacc636-807d-5d9d-a6a4-8ee36e4ad7f1 |  | note | – – – – – – – – –
label | e55c8fd1-ddc6-5844-8774-eca692eb4d9b |  | note | WP
label | 89081531-3e9f-57a1-9f3d-a3158c5ed296 |  | note | – – – – – – – – –
label | dcbc86f5-d080-5a3f-8251-7618893f8c09 |  | note | RESPONSIBILITY: Site Engineer
label | 779f61c3-b20a-5451-bbbb-f30c6c16ccf3 |  | note | – – – – – – – – –
text | 227d9c3d-0ad9-5feb-8a18-e1b2bf4f142b |  | textbox | DATE:
checkpoint-status | 1a68c326-710d-4fc7-a3d7-9133a1ea96ee |  | checkpoint | 2.2 Excavation Permit
label | 0685f7c7-c41d-5b57-b2a0-613ffb04d61e |  | note | FREQUENCY: During excavation
label | d46bef5a-f8fb-589f-9417-b5ec8fbf7283 |  | note | – – – – – – – – –
label | 9c4b8328-df8e-5534-afe8-24217a367567 |  | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | fa2efc0a-d754-5b8c-899a-55593cd2eab2 |  | note | • Plant and equipment shall be appropriate for the task
label | bb6bc2b3-72ff-5259-9567-7ffc3bf98af9 |  | note | • Excavation operations shall not disturb areas outside the limit of excavation
label | 3113516d-f65b-5097-b2c6-313ef624bddc |  | note | – – – – – – – – –
label | a1518f87-ef3d-55b8-905a-684331b3c66d |  | note | REFERENCE DOCUMENTS: VicRoads 204.06
label | 1bfd7064-6869-5a66-866b-39b396096dbc |  | note | – – – – – – – – –
label | 90007c2d-53c9-5d41-8856-283771962c3b |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 606311c9-448f-55db-9493-dc0dff861d79 |  | note | – – – – – – – – –
label | c8be3115-8385-51bf-a376-6519d8956191 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 92acbd21-96b1-5eb4-b078-0c592eee8382 |  | note | – – – – – – – – –
label | 76507a6c-970e-5ab3-9bd7-02f3901c557d |  | note | HP*
label | 1460fe9d-a81b-5a98-84ea-1690c0fc50b2 |  | note | – – – – – – – – –
label | ef1c3eb9-408a-5f6b-b062-b293ff8259b4 |  | note | RESPONSIBILITY: Site Engineer
label | 385f222b-84d4-58a9-a1a6-b42ed23aa6fd |  | note | – – – – – – – – –
text | 1d6d3a3f-a570-582c-bf53-80699b506b8a |  | textbox | DATE:
checkpoint-status | 800a5694-e03b-4120-b9d0-bfa0fe2af0ba |  | checkpoint | 2.3 Redundant Pits
label | e4778281-ee8b-50d4-96ad-403645e4658a |  | note | FREQUENCY: After clearing
label | e3c830d6-f4f5-588e-a3ff-e547cc09b138 |  | note | – – – – – – – – –
label | b53114d2-2a14-5c91-8fbf-3704b360719a |  | note | ACCEPTANCE CRITERIA: Any redundant pits, are to be removed to a depth no less than 0.3m below the stripped surface or no less than 0.6m below finished subgrade (wichever is lesser)
label | 2153616e-fc39-5d3e-a43b-0ee2318d0dcb |  | note | • Seal any pipe openings with concrete and backfill pit area with material and compact to a density ratio of 95% (standard compactive effort)
label | 06385c25-a0d4-56bb-b702-387f603e7a48 |  | note | – – – – – – – – –
label | 7c48c1d4-9ed0-553c-b7e5-f5d88ddc3adc |  | note | REFERENCE DOCUMENTS: 201.05
label | 0a303729-db6e-5d31-b7e2-8ac48f1326d6 |  | note | – – – – – – – – –
label | e111603c-9dbb-57d9-90a2-946a538003bc |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 7a75ef14-ac91-5eb3-9680-412e7918bb64 |  | note | – – – – – – – – –
label | 312571b1-0e79-50bb-bd74-edf045772242 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 57f334da-edaa-5cbe-9202-089be0994c02 |  | note | – – – – – – – – –
label | e668d7dd-7cc6-597a-8724-0ffc700213a9 |  | note | IP
label | ff45c08b-f710-5976-8743-ffca18365cca |  | note | – – – – – – – – –
label | ace237ca-d4e9-510f-8c09-6d88bf7ec78e |  | note | RESPONSIBILITY: Site Engineer
label | 301b3fbb-7a4c-587c-bacb-fee71a0e564a |  | note | – – – – – – – – –
text | 00293c63-2d0d-5bdc-8666-9379f942845b |  | textbox | DATE:
checkpoint-status | 48054a26-24ea-4bda-92d2-14aab1066642 |  | checkpoint | 2.4 Disposal of Material
label | ad0aa656-2e53-516b-9e08-2173f6d60fd2 |  | note | FREQUENCY: All times
label | 74a44bd5-3655-5614-b249-1e374ab22750 |  | note | – – – – – – – – –
label | d2f2ca37-322b-5586-8ce5-5746c600c896 |  | note | ACCEPTANCE CRITERIA: Surplus material, debris and demolished material are to be sorted and transported off site. Material to be kept in condition for re-use where possible.
label | f70db071-1240-5e62-a8dc-afca0cf91a7b |  | note | – – – – – – – – –
label | f0978719-2755-54b0-ab5c-6c1f4548f0b4 |  | note | REFERENCE DOCUMENTS: ITP sign off
label | b4bdc89c-1c46-58e1-bee8-d5785f1da137 |  | note | – – – – – – – – –
label | 45da89af-2f48-5ea9-b6b2-6bd468b29072 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | abd4e96d-c0df-52b0-9c54-9af5de0eef22 |  | note | – – – – – – – – –
label | 0a3b6125-0485-59d2-8189-291ceebdd7f5 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 610df51f-bd81-5fb4-b384-b4e2bf41eadd |  | note | – – – – – – – – –
label | 4c3d4887-aab9-561c-aa8b-92ed648da9c6 |  | note | WP
label | 9fc922f3-890f-5128-854e-68524c24bc89 |  | note | – – – – – – – – –
label | 1cb9b201-8a42-51a4-9898-61d4a8e3b73e |  | note | RESPONSIBILITY: Site Engineer/ Site Foreman
label | 9063200a-3a87-5e32-a29c-fc1fee865a1a |  | note | – – – – – – – – –
text | 0d5b66dd-3496-5691-a067-13bff9281e25 |  | textbox | DATE:
checkpoint-status | 8f82c5e2-07b1-4fa0-bc57-f97d0a519488 |  | checkpoint | 2.5 Maintaining cleanliness of site
label | 0b525960-4620-527d-ac8c-ecc5fe7df4b1 |  | note | FREQUENCY: All times
label | d54bb11a-8022-5ae8-a1ad-89bb00bfbd19 |  | note | – – – – – – – – –
label | 2c8959b3-afe8-54cf-9c06-714e8c47c060 |  | note | ACCEPTANCE CRITERIA: Site and surrounding environment are to be maintained at a good standard of cleanliness
label | 689ecdef-b563-565f-add9-078fbfb81894 |  | note | – – – – – – – – –
label | 1cbc5927-6e3f-5da8-a3e2-763fa8418433 |  | note | REFERENCE DOCUMENTS: ITP sign off
label | 9b623fe5-39c5-5f78-b88b-4e123883fb3a |  | note | – – – – – – – – –
label | 2f809241-68b4-54b7-930d-b88b8105f5fc |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d7576e9a-0cf1-50c3-8d3a-e841cc38eb9e |  | note | – – – – – – – – –
label | e9236435-c2f5-5f6e-8c55-76b4224123c0 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 086a39ec-b509-5c1d-8512-c1aae7aa5876 |  | note | – – – – – – – – –
label | 9dde9364-66ef-57a3-8ea9-df735ead8986 |  | note | WP
label | 1c22771b-f83a-584b-9c31-042be18ee7b4 |  | note | – – – – – – – – –
label | 0e320487-f627-5be1-b34a-da952ff4eacd |  | note | RESPONSIBILITY: Site Engineer/ Site Foreman
label | f05d5fbc-e001-562e-be00-4e5a44b8b431 |  | note | – – – – – – – – –
text | 1dc3ee7e-2160-5af9-8d1b-bd06195d22a9 |  | textbox | DATE:
checkpoint-status | 887194a3-4d74-44b0-a08e-fd90c2077e65 |  | checkpoint | Final Inspection
label | 2139fa7c-c198-5879-81c4-07cd5b142c7e |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 668c4a4e-961b-5c48-8503-f99336c42a9f |  | textbox | Print Name:
text | 2efe18cd-257c-554e-92c2-f19f63ed6d06 |  | textbox | Position:
text | 7f6e2996-d6db-51bb-97f8-a644809f941e |  | textbox | Date:
checklist-sectioned | 76779e58-1098-478f-a652-5807cc405494 |  | checklist | ITP-029 - TGSI Installation |  |  |  |  | Yes | ITP-029 - TGSI Installation | 8c0340f6-99e6-4833-81fb-381efe190eaa
checkpoint-group | 9d5f2181-a699-437b-9014-e9af1562ebe8 |  | section | Preliminary Works
checkpoint-status | 72dec241-57cb-4be8-8df1-8997ab41ea73 |  | checkpoint | 1.1 Check for Correct Documentation
label | 58512ea7-b77d-5e20-8a7b-475aeeafb400 |  | note | FREQUENCY: Prior to Commencing Activity
label | 26a879f6-047e-591d-b091-6bea99caefdc |  | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | d8a5b310-bb4d-5a9b-a73a-ff0a13699629 |  | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | eebee218-17ad-58a8-9eae-3dfd95b70389 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 3c0a9ed6-5091-57b2-81a7-639ad953fe84 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 0fb1f4d3-102e-5c60-a055-e8253610859e |  | note | HP*
label | 50546b5b-7f3f-5967-bdad-49d9aec1b90f |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 73d98214-a900-568a-b724-26a5e8ab3999 |  | textbox | Date Completed:
checkpoint-status | 054b5a87-a7c5-4727-8954-c54572c54629 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 040389a3-a39b-5d7e-87dd-cf3a8c928630 |  | note | FREQUENCY: Prior to Commencing Activity
label | 74fbdbfe-2296-5d74-830c-17feae25274c |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | 850dea4a-3ce9-58a2-b077-07e0c1d65952 |  | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | f040fcf1-e4f3-5314-bf50-eec8ac9ece07 |  | note | INSPECTION/TEST METHOD: Inspection
label | 17074e00-8c2b-5829-a082-2c9b0aa1ad65 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 9cd76f2f-69f6-56c2-94e4-acdd4a66b2fb |  | note | IP
label | 22b0733f-a1c9-5bbc-8610-d3c973b5f7fa |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 93786f4c-b348-52a9-9717-6ab2aae0ddc2 |  | textbox | Date Completed:
checkpoint-status | f5f47abd-4aae-4fdf-9719-e35a2a415e49 |  | checkpoint | 1.3 Check Materials
label | fc43b9d8-4a85-5760-a5c8-afaadb1d36b6 |  | note | FREQUENCY: Prior to Commencing Activity
label | 58d25e05-90bd-5d00-935d-9f5818a6fa3f |  | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage. Tactiles in paved areas shall be Versatac Bluestone / Granite Tactiles. Tactiles in asphalt areas shall be Pandatac Granite Tactiles.
label | 708a5c66-ebfb-5386-bb52-e446a7b1eb7d |  | note | REFERENCE DOCUMENTS: Receivable Inspection List
label | dc14ded3-3911-5dce-bfa3-6abe545a9f77 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 7a2f3996-490e-51d8-8a7a-afd3380a1b1b |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 050b8703-726a-55da-8263-610f63e7bd56 |  | note | HP*
label | 7cb5ad01-8613-595c-b057-98adcbc89700 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 80156d47-4943-54c0-bf0c-f36d15ea9cf4 |  | textbox | Date Completed:
checkpoint-status | 92b9f671-f9e9-40b6-8b55-fd56429eceea |  | checkpoint | 1.4 Setting out
label | 5c0690fc-fb8d-5252-83c2-7908c174a6f5 |  | note | FREQUENCY: Each Lot
label | f29f5923-6b5e-5350-8d3a-5c71d05f596a |  | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels. Line and level of bluestone pavers, tactiles and granite inlay shall be set out according to design levels to suit new kerb heights.
label | 185241d9-34a4-57e4-903b-cc38d329f1db |  | note | REFERENCE DOCUMENTS: Work Procedure
label | 8873ab8a-58d4-581f-8fbc-231a17c26ca5 |  | note | INSPECTION/TEST METHOD: Inspection
label | 98a06d18-bca3-583c-9cde-e79b235320a9 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | d003c7a7-c5f5-5cc2-80ed-487e2c5d3a01 |  | note | WP
label | 4176e7be-6c24-523e-80c2-6230ce466a55 |  | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
text | 844d0cd3-0a9d-59a8-a2f1-6b7732e9732e |  | textbox | Date Completed:
checkpoint-group | b5f632f7-d226-44c9-b023-d04adca08381 |  | section | Construction of Access Ramp Bluestone Footpath
checkpoint-status | 63ed54f7-5f8a-4844-b14a-b3d4e897f19e |  | checkpoint | 2.1 Base preparation
label | bc295a75-ca07-5c7c-bb3b-d950a1849cd7 |  | note | FREQUENCY: Each lot
label | 026356d3-860e-5bf7-88c3-f807c21faf54 |  | note | ACCEPTANCE CRITERIA: Sound base should be achieved with 50-100mm for bedding materials
label | 9a6d7c68-2897-5bd5-8b7b-5e610dc5d830 |  | note | REFERENCE DOCUMENTS: Dwg 1P50201
label | 5ab8edea-1529-5cef-aebc-7ee1cb0a4b12 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9aeeed16-682a-53c5-81fd-fc422cb53b41 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | f9b7b0d8-129c-5f22-a7d8-e71a0f11965e |  | note | IP
label | 745c0ee7-5d55-5fc1-9f5e-2a1999ea132d |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 970d87b0-c72e-5592-be1b-ab9e699dd0d4 |  | textbox | Date Completed:
checkpoint-status | 0001697c-1d7a-4335-8f76-0bec0e304d44 |  | checkpoint | 2.2 Placement of bluestone pavers on mortar bed
label | 142277e1-b7c3-562d-ba06-a975d6757590 |  | note | FREQUENCY: Each lot
label | fb029f77-0549-5f7c-b4c6-232eb3a47b31 |  | note | ACCEPTANCE CRITERIA: Pavers shall be placed in accordance with Dwg 1P50402 on average 30mm thick mortar bed of sand & cement mixture. All pavers shall be coated in mortar slurry on rear face before laying. Kerb access ramp wings shall be at an angle of 45° or as per design and the ramp gradient shall not exceed 1:8. Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
label | 3cff16c3-a237-5170-8713-68c87968756f |  | note | REFERENCE DOCUMENTS: Dwg 1P50402 Dwg 1P50201
label | f0b2a502-3a56-5470-ae1e-488939f79a3d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 6218e6eb-ff61-5258-9d83-99501f514ad2 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | bf02fa11-c03e-58f7-8f86-8df634856b9d |  | note | HP
label | f1f0efad-cb76-54eb-973c-c429564e3a27 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 812fbfd2-bd44-54ec-8a31-2f52c034580c |  | textbox | Date Completed:
holdpoint | fe0e76c9-6bc6-4b8f-8aef-b5d256eed844 |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status | d3ba9b27-d408-4820-bcbf-d59897a9a2b6 |  | checkpoint | 2.3 Curing
label | eafb2a3e-8d65-5689-97db-1d3856a63489 |  | note | FREQUENCY: Each lot
label | 697d9fb7-53cb-50d0-9836-9fff5997f247 |  | note | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic. Where required, ply shall be laid over area of works
label | 018244ae-13e0-56c7-a0cb-00fb585d21b5 |  | note | REFERENCE DOCUMENTS: Manufacturers Specifications
label | ae6191c5-b455-5596-9c1c-da2f30b1d483 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 66a69c17-6945-58e0-9b14-836394f552fc |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | fb919fdd-51a1-50a6-8b39-ba4a30885ac3 |  | note | IP
label | 3f475cb3-ec35-5e5a-bedc-85916a133eb1 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 5329c1e4-4b54-565d-9b5a-a88de1f51bc5 |  | textbox | Date Completed:
checkpoint-status | 71b4ee5f-e481-4883-8714-4be2c8f9e29b |  | checkpoint | 2.4 Grouting
label | 624d0230-f2ee-5d4d-b2ca-97774ce6a563 |  | note | FREQUENCY: Each lot
label | 0410b7ca-d319-575a-a538-9d789043b9f4 |  | note | ACCEPTANCE CRITERIA: Pavers shall be grouted using Lanko Durabed to specified mixture content. Grout shall be spread & clean appropriately as required.
label | 2ac2d53e-425a-57ef-aa9c-8a50eb21cf13 |  | note | REFERENCE DOCUMENTS: Manufacturers Specifications
label | 0013bf4b-96ad-520d-9459-d33d207f0dae |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | af2e5ce4-6b9d-5f8c-9752-00f05614ff0c |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 317ba425-7186-54c1-a058-38eea202305c |  | note | HP*
label | e013bb63-1cb3-5764-9992-e926b6d0de98 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 38609131-229b-5e95-b11c-3a08fd974abe |  | textbox | Date Completed:
checkpoint-status | 2dddb408-4816-4aa0-a6cf-2c93686f9c1b |  | checkpoint | 2.5 Installation of Versatac Granite Tactiles and Granite Inlay
label | d2e20344-0a4f-5c08-b52f-761db9b6d38e |  | note | FREQUENCY: Each Lot
label | 5b46034a-c1f4-5b7b-986a-a2ad9155b12e |  | note | ACCEPTANCE CRITERIA: Granite tactiles and inlay shall be placed in accordance with Standard Drawing 1P50201 with surface deviation of under 5mm. Tactile Pavers shall be placed on average 30mm thick mortar bed of sand & cement mixture. All pavers shall be coated in mortar slurry on rear face before laying. Tactiles shall be cut with a diamond blade and allow a 5mm grout.
label | 5996e517-121a-5436-92f6-bda4c207319b |  | note | REFERENCE DOCUMENTS: Dwg 1P50201
label | d4e16df7-8a3d-5fbf-8c65-4b2fee305e75 |  | note | INSPECTION/TEST METHOD: Verify
label | 5d57676b-5612-5bf0-8317-ad2d4a804c5c |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 6f395c1f-bbad-57ae-ad12-3eff1bf7704d |  | note | HP
label | e5bd8232-8f33-573f-acf1-a05a38306b7e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | cb41ed74-357c-5781-a1ed-baf819222a11 |  | textbox | Date Completed:
holdpoint | 76c39ebc-62d0-4c3d-be2b-25f0c5964a49 |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-group | 2c2f50b5-bb9a-4e45-9ba2-91ce89116d77 |  | section | Completion
checkpoint-status | ee7535d6-fbb5-4a6f-8fd4-5783b14a88ff |  | checkpoint | 3.1 Completion
label | 382d5dd1-9e0b-53b0-93f5-1b3e3766919c |  | note | FREQUENCY: Each lot
label | 5642da93-e1b9-5f43-ba90-7de163daf3d7 |  | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste. Bluestone pavement is free of mortar stains and cleaned to satisfaction
label | 77b89f3a-6712-5853-8e3d-e75aa01021cb |  | note | REFERENCE DOCUMENTS: Visual Inspection
label | b33e71e0-fbc5-51f4-9e9b-f853da82e949 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 4c407344-98db-5b2d-b9af-994897943ec1 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | eac5c9f3-89e9-509b-9737-7d2845ff7085 |  | note | IP
label | 70e307a4-fced-5f79-b6f9-be82596888d7 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 494d6bc7-7028-5fd9-807b-8116c1ac1716 |  | textbox | Date Completed:
checkpoint-status | fc4c4352-1444-4831-947b-04ed65da7e5a |  | checkpoint | Final Inspection
label | 920badbf-d7cf-5263-a798-b907ed9a2c10 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | da5e0cbb-0608-5ba6-9d86-0fecb14305cc |  | textbox | Print Name:
text | 9b7aa94a-118f-508d-be5f-eaed31536ef4 |  | textbox | Position:
text | 3aedafbd-670b-5dee-89aa-3d6f4d1f5fe2 |  | textbox | Date:
checklist-sectioned | 80871329-bdcd-4bec-bc5b-7dbcc7b3791d |  | checklist | ITP-031 - Precast Stormwater Pipe Installation |  |  |  |  | Yes | ITP-031 - Precast Stormwater Pipe Installation | 8cf2513f-6855-4b7b-a912-77dea5c3fa5c
checkpoint-group | cb43fa44-2e2f-4f09-a104-2dc9bfefd580 |  | section | Preliminary Works
checkpoint-status | a2a3d341-e729-4e40-ad3a-6323202934eb |  | checkpoint | 1.1 Check for correct documentation
label | cdb385f3-3512-50b9-b475-c64ebf73e732 |  | note | FREQUENCY: Prior to commencing any activity
label | 3223ec45-8b20-503c-be2e-f8e99623ea65 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
label | 344bc3b2-8cf7-59ad-ad94-75c86b12ef54 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 485dd589-3c0b-543a-952e-a853f08dfe6d |  | note | INSPECTION/TEST METHOD: Visual inspection
label | a0eb09eb-9b24-5853-85dc-efcb2842ef6a |  | note | RECORD OF CONFORMITY: This ITP signed off
label | bc3de693-93aa-589b-bfa6-acf051b58987 |  | note | HP*
label | 1b6d53a8-7c69-5bc2-a9ed-af1c5a97a653 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 941b4ab1-2373-515d-a94c-eaaf196f9890 |  | textbox | Date Completed:
checkpoint-status | 8b90be19-3f22-4b8e-ab5a-1a5838fa4d0e |  | checkpoint | 1.2 Implementation of all measures and controls
label | e546188b-8d64-593b-97d4-f1330b917fbf |  | note | FREQUENCY: Prior to commencing any activity
label | fe58b9cd-e1e4-5bb9-96ff-68562039ffaa |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | e0e5ea83-5b98-5c82-b570-3f1963bf0fb9 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 9c55124e-7aed-533e-bc2c-5c601641be2a |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 07202c91-1ef7-50c2-870d-214470a7cb75 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 3381c12c-3b65-5811-9468-e12bedf3932c |  | note | IP
label | d51edbab-c0dc-5806-9d8d-aba7630aafda |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 84074ef2-79a1-5e06-9502-20202539d8ec |  | textbox | Date Completed:
checkpoint-status | 7451c7b7-9a9e-400f-8582-b9b4ee6c91f5 |  | checkpoint | 1.3 Pipe classification and delivery
label | 6636086a-ff0a-5815-886c-3934b91f8126 |  | note | FREQUENCY: Each delivery
label | d8457e97-33d1-5fdc-81cb-81edd352653c |  | note | ACCEPTANCE CRITERIA: Pipes shall be of the size specified on the drawings and either: Socketed reinforced concrete to comply with AS 4058 - 2007, with rubber ring joints complying with AS1646 - 2007, or Fibre reinforced concrete including fittings, to comply with AS4139 - 2003. Condition and compliance of the pipe is to be inspected upon delivery.
label | 4ad543a7-5c1c-5a36-9153-08a8179fd4de |  | note | REFERENCE DOCUMENTS: Cl 4.1; Appx 2: Cl 7.0; Dwg 1P50318
label | d731092f-ba4e-572d-9a53-99dadb855cc4 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f8f56355-9f3e-5db8-9c85-0f268b41da80 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 28613be2-7be2-50af-9b7f-130945927c20 |  | note | IP
label | 810da3be-fd16-5996-9fc6-8777f77746ce |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | e2f36268-4752-5449-b990-874e5978eb43 |  | textbox | Date Completed:
checkpoint-status | 8c14e83e-996b-4c28-89c5-1f0b86aff113 |  | checkpoint | 1.5 Backfill and bedding material classification
label | e28d78de-a8b0-5334-97a7-1d3e7b80ea31 |  | note | FREQUENCY: Prior to start
label | 0ddb8a98-ced0-5ee7-b65f-dafcc28fd861 |  | note | ACCEPTANCE CRITERIA: All crushed rock used in the works shall be Class 2, 20mm nominal size. Sand shall conform with the requirements of AS2758 - 1998 and AS1141 - 1997 and shall have grading within the limits as defined in the code.
label | 09477858-8880-57d1-b01e-1baea9e7059a |  | note | REFERENCE DOCUMENTS: Cl 18.0
label | 6adb6493-bb3d-5675-8f7a-d08296b5bad5 |  | note | INSPECTION/TEST METHOD: Verify
label | 1e3fb593-8b99-56e4-bb31-eb319f2b8fcf |  | note | RECORD OF CONFORMITY: Test reports from supplier
label | a5fd55e8-1d1c-5c45-a3dd-c19bd608ee9e |  | note | IP
label | 54cc624b-4aac-5c79-97da-2e1579f73a0e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 6e5f7b57-9f3b-58fc-9d21-ccc1d78a944e |  | textbox | Date Completed:
checkpoint-group | 1652d220-3d6d-413f-9016-05fdfd080820 |  | section | Construction Works
checkpoint-status | c9dfcfed-faa1-478a-8a40-b4aa15fe3807 |  | checkpoint | 2.1 Set out drainage
label | 3ade98a2-a1f1-5962-96c6-24143585ab97 |  | note | FREQUENCY: Prior to backfilling
label | 8ebe8b22-50a9-5660-8108-0e355db0a2a4 |  | note | ACCEPTANCE CRITERIA: The line and level of all drainage lines and pits must be in accordance with the provided design drawings. The position of all drainage lines and pits are to be confirmed with the superintendent if ambiguity arises.
label | 7f59848e-fcd8-5819-a790-806ae318cb3d |  | note | REFERENCE DOCUMENTS: Design Drawings Appx 2: Cl 8.0
label | 1dbc62af-ede6-5d19-999f-db4c5072208a |  | note | INSPECTION/TEST METHOD: Survey Conformance Report
label | bef5083d-01e0-51bd-bbf0-44391cd55b75 |  | note | RECORD OF CONFORMITY: Survey Report. This ITP signed off
label | d5efc9ec-1fd1-5641-bb73-25ab44d9ec21 |  | note | SCP
label | 09f4a1c6-f2e4-5e6e-9684-bc84b2741af7 |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Survey
text | 283fa5a1-3d5e-5f25-ba55-15d07724b473 |  | textbox | Date Completed:
checkpoint-status | a97767c5-9bf1-4b3a-99fb-7d2767b2a5a6 |  | checkpoint | 2.2 Excavation
label | 29979228-4ba5-59d5-aa15-c5431eb5b241 |  | note | FREQUENCY: Each trench
label | d15de657-eefb-5b55-b411-79be71ad78d3 |  | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth greater than 75mm below the specified level of the invert of the pipe to allow for appropriate bedding. Any trench which may have been excavated to a greater depth than necessary shall be filled into the required level with concrete 1:3:6 mix. Any loose material shall be removed. Trench shall be battered, benched or shored in line with WorkSafe code of practice when required by assessment under 1.5m in depth and is mandatory over 1.5m. No stockpiles within 2m of end of the trench to reduce bearing pressure.
label | dfdff10a-bf31-5740-b6ff-568f0525f657 |  | note | REFERENCE DOCUMENTS: Appendix 2: Cl 8.0, Cl 9.0, Cl 11.0
label | 376f4c1c-184d-5aa7-badd-196a474956ae |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e14fb186-30d6-555a-89a4-cf9f4ee492df |  | note | RECORD OF CONFORMITY: This ITP signed off
label | c16ecb21-eb9e-5b00-b2b1-a28f72944a0c |  | note | IP
label | 30cf57c3-f7fb-508e-a143-4cdbc726b2ab |  | note | RESPONSIBILITY: Fulton Hogan Foreman
text | 66ea3e69-e808-5bf1-911d-f613dbae3f18 |  | textbox | Date Completed:
checkpoint-status | 0b96481b-6cff-4f9f-8320-aaf6b4111b90 |  | checkpoint | 2.3 Inspection of trench base
label | a5f6937d-9830-5a89-b76d-2ba4dbb060f2 |  | note | FREQUENCY: Each Lot
label | 69b780c8-bb58-52ca-8015-55e547b04015 |  | note | ACCEPTANCE CRITERIA: Base of the trench shall be inspected prior to placement of bedding.
label | fffe9e58-2185-5f52-8cc6-748167e45cbe |  | note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0
label | d2995ae2-9497-5c33-9a30-fd59c5104be5 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | cc89e7d0-d6b2-5986-bf70-79dd231a6ccb |  | note | RECORD OF CONFORMITY: This ITP signed off
label | c43cff28-f122-5889-b092-abfd6fee1dd7 |  | note | IP
label | 8404bc4a-4f50-5b16-ae22-f372a2214498 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ccef1801-bf59-5aca-9f3d-bd75e78aeebe |  | textbox | Date Completed:
checkpoint-status | aa14746f-b4ac-44c6-ae43-e93fc970384f |  | checkpoint | 2.4 Placement of bedding material
label | bbe7347d-de94-50b0-81a8-b855607480c1 |  | note | FREQUENCY: Each Lot
label | 9e147125-8df4-5016-8200-00f6db8b5206 |  | note | ACCEPTANCE CRITERIA: A 75mm minimum layer of consolidated sand shall be used to bed the pipes of the diameter specified on the drawings.
label | ad6afd50-f18d-55a7-b673-a0f6802cf2e8 |  | note | REFERENCE DOCUMENTS: Appx 2: Cl 9.0
label | 9561e6f9-a877-5153-8e47-da823440fa48 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 056fb510-f9e5-5c6c-b736-6184d2dc948f |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 9fe5f03f-dd59-502e-94b1-1905b78a1405 |  | note | IP
label | 4b9686e5-24c9-5ee8-aaaa-5e8fd24a2506 |  | note | RESPONSIBILITY: Fulton Hogan Foreman
text | 4ffd3a91-b584-51d3-8c47-03af5d0567d0 |  | textbox | Date Completed:
checkpoint-status | dfdb1146-6342-4482-be2e-57b1e39aeb5e |  | checkpoint | 2.5 Placement of pipes
label | 1847c87e-05eb-5a46-9b5e-61591b6f1cf1 |  | note | FREQUENCY: Each Lot
label | 78db297f-9736-5dbc-b6de-df49dd95d25c |  | note | ACCEPTANCE CRITERIA: The pipes of the diameter specified on the drawings shall be laid on the bedding firmly for their entire length. All pipes shall be laid true to lines, level and grades, and shall be butted tightly together with lips. Rings must be in place between pipes and not dropped to be visible.
label | d3889d01-1343-56ec-913d-61852363bf69 |  | note | REFERENCE DOCUMENTS: Appx 2: Cl 9.0
label | 6b959ded-69f6-539d-9996-03b9c12eceb7 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 3449efcf-80c3-5a6e-8aaa-0e392dc21a30 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 62329db1-ded9-5bf4-8aba-367c89ce692d |  | note | IP
label | 1268ef48-a80c-59bd-9d6c-990503fc0d24 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | fe2e1a0d-8e05-5690-905c-54fd924f7d54 |  | textbox | Date Completed:
checkpoint-status | c5c21459-0294-4516-9404-c9714f85b0ce |  | checkpoint | 2.6 Sealing
label | a3bc3b0e-3c25-58a0-a4d2-1544ad711a27 |  | note | FREQUENCY: Each Lot
label | f58738ea-fcf8-50f4-bce4-03a839bcc261 |  | note | ACCEPTANCE CRITERIA: All pipes connections to pits shall be neatly made, and the ends of all pipes properly trimmed off and stopped with cement mortar.
label | d8e5e53b-17d0-5a6e-93de-968cc2f1bb8a |  | note | REFERENCE DOCUMENTS: Appx 2: Cl 12.0
label | ff9113be-1dc7-5dba-92bc-c02698608d15 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 5f0a78a4-48dc-534b-81bd-23938637dd2c |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 2535a53d-ab42-52e6-b267-30991bebe6c3 |  | note | IP
label | 3ee4f68c-9bd7-5aa0-84b8-015514975287 |  | note | RESPONSIBILITY: Fulton Hogan Foreman
text | f10727f6-d36c-5e8b-a901-32b692034e99 |  | textbox | Date Completed:
checkpoint-status | ccdb1fc8-038a-47b6-bd26-af6a42bf7357 |  | checkpoint | 2.7 Bandage Joint
label | c623ab40-df90-5c8d-8279-ae53ad4c9bd1 |  | note | FREQUENCY: Each Lot
label | f5e6bced-f5d5-586e-aa46-846778ab981e |  | note | ACCEPTANCE CRITERIA: Construction bandage must be constructed where 750mm pipe connects to existing in accordance with Melbourne Water standard 7251/08/420 with SL82 mesh and 40MPa concrete.
label | a1ad2f94-249c-5e36-ba40-80d67d7ce3d9 |  | note | REFERENCE DOCUMENTS: Melbourne Water Standard Drawing 7251/08/420
label | bc1edb9d-a705-53e9-be68-a8fd08baeb54 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 0b5aa4e3-585d-5281-9327-fcdba8313a28 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | caa311c7-185e-5ad7-85fd-eae1cf9bb93a |  | note | IP
label | b0617a17-ab1d-55c3-adcb-a2ff980b69af |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 0ee28f16-a922-578d-ab73-63c46a772df6 |  | textbox | Date Completed:
checkpoint-status | 9c3e2911-c2c4-4d8d-8ca1-bf1524d8daf9 |  | checkpoint | 2.8 Inspection of Pipe Installation
label | 350a1c87-2100-5cba-bd6f-1ff110ec486c |  | note | FREQUENCY: Each Lot
label | 9ea370c5-ca53-5c78-b967-bef1e625ca7b |  | note | ACCEPTANCE CRITERIA: No further backfilling shall be done until the Council's Supervisor has inspected the work.
label | 8b325c9f-b4e1-5448-a5cd-80a7a67cb9c4 |  | note | REFERENCE DOCUMENTS: Appx 2: Cl 18.0
label | a63ca885-f223-5ffc-b872-a7a8da4a4506 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | d4d7d5ba-9824-5438-8ff6-63081657a092 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 5e014a38-e8d0-5272-a8a4-27d642c48893 |  | note | HP
label | 6de879cd-f08a-59f6-9174-8ba2649ed7e1 |  | note | RESPONSIBILITY: Fulton Hogan Engineer / City of Melbourne Supervisor
text | bf3e9c8e-4144-5759-b858-65d2af2c03a2 |  | textbox | Date Completed:
holdpoint | a86a5ca1-724c-44cf-afd7-a2cea166302f |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-group | acca8e23-d483-4d37-86d4-952e4aa8a6bc |  | section | Testing
checkpoint-status | 52af1f48-fac3-4548-b40e-b605207c3272 |  | checkpoint | 3.1 Crushed Rock Placement & Compaction
label | d550144e-abb4-5ebc-b5fb-5ad940bf7087 |  | note | FREQUENCY: Each Lot
label | 1acbdd59-fec3-5d30-9ae7-0dad2f55866a |  | note | ACCEPTANCE CRITERIA: The trench shall be backfilled with Class 2 crushed rock to the springing line of the pipes immediately after completion of laying. Further backfilling shall be with layers of crushed rock, Class 2, no thicker than 150mm compacted to 95% Modified Relative Compaction.
label | acfa716b-e823-5685-916d-400da1bc343c |  | note | REFERENCE DOCUMENTS: Appx 2: Cl 18.0
label | ae0cc798-69a0-5a82-be68-2317dfbb4cb6 |  | note | INSPECTION/TEST METHOD: Verify
label | d9356e2d-5908-5af6-87b3-f683a990f847 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 14ae4068-d88a-5818-82dc-c06e9ef412bd |  | note | TP
label | 33d10156-f16e-5610-be03-e42c64707863 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ac201eb2-56cb-55b2-8637-e60dc118db93 |  | textbox | Date Completed:
checkpoint-status | 0dc87804-d4fe-4ff7-b887-513f06582e0b |  | checkpoint | 3.2 CCTV Inspection
label | 11116eba-1ffe-5657-a4ea-dfdc706aadd3 |  | note | FREQUENCY: Each Lot
label | a3af7d5d-1d63-5f14-80b3-f278b2ccde80 |  | note | ACCEPTANCE CRITERIA: All drainage lines constructed beneath pavements are to be inspected by CCTV.
label | ae940c40-b7df-5357-8fa6-a468f0e93763 |  | note | REFERENCE DOCUMENTS: Appx 2: Cl 18.0
label | 751d2cde-3587-549a-91e0-aab80be65f3d |  | note | INSPECTION/TEST METHOD: Verify
label | 709f5b6a-a5fb-5d2e-8ef1-090a285630f1 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 8638d594-d8b6-5831-804f-5e4f6a18982b |  | note | TP
label | 4d2da017-a61c-57a9-8fd6-d0b792a150cb |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | d6207561-9220-5a5e-a4f2-a885ede980fa |  | textbox | Date Completed:
checkpoint-status | 98bce6ce-fec3-47bb-9fa4-13a9f670efb4 |  | checkpoint | Final Inspection
label | b70a0e05-4f4b-564f-9faa-aca495cc2f70 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 0355a40b-3d40-579a-a7d4-b951aacc73a4 |  | textbox | Print Name:
text | ff00e4c4-80f0-5e54-8c32-af0b733f9f11 |  | textbox | Position:
text | 9f74a7a5-a468-55ec-972f-d221dca76024 |  | textbox | Date:
checklist-sectioned | c363c2e6-1b72-4efc-aacc-74b399d8031c |  | checklist | ITP-015 - Energy Absorbing Bollards |  |  |  |  | Yes | ITP-015 - Energy Absorbing Bollards | 8d242957-4bf0-4675-8654-9c07a3a2301d
checkpoint-group | e172fd22-06cb-44ba-8172-b884fd33bfe2 |  | section | Preliminary Works
checkpoint-status | 36af9d91-ee2e-4bad-b057-7e9ed21d4953 |  | checkpoint | 1.1 Check for Correct Documentation
label | 9f4f69df-d072-5720-bce3-18d43ae69cc8 |  | note | FREQUENCY: Prior to Commencing any Activity
label | 1d44aacb-ef88-5260-aef7-c196b15acf73 |  | note | ACCEPTANCE CRITERIA: All employees and subcontractors shall have the most current and complete set of drawings
label | f351a2fb-d004-56f1-bca4-0da3b9ad82ea |  | note | REFERENCE DOCUMENTS: Design Drawings and Register
label | 0aa4c29f-3be2-50b3-b4c8-f8a4b36afd58 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | efdfe11a-9fb4-51eb-87bc-3df25a98e36d |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 9b72c6e9-1439-5aee-af89-7847f77b83da |  | note | HP*
label | 233b1c24-0237-5b79-a574-55e4e7d0900e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | d5237858-faa4-5dc4-948d-d487d64d946a |  | textbox | Date Completed:
checkpoint-status | 75824eca-e856-4de3-83ff-0d1a349ccaf2 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 38b41293-ac5b-58af-aae7-5eaf7571a213 |  | note | FREQUENCY: Prior to Commencing any Activity
label | 5b764db0-ba0b-5269-8f66-edb9836a1604 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including; EMP, TMP, PSP, JSEA, SWMS & WP
label | dd875f2a-fe79-552e-90ba-d3109a820ad8 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 503b4015-7efc-5282-a49b-1e12122f2dfb |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | aae83b35-00ab-5779-9504-be57d00e846a |  | note | RECORD OF CONFORMITY: This ITP signed off
label | a82a5ae0-a06a-5b9d-9d99-cba2ab3a83ad |  | note | IP
label | 57439984-5d45-5a2a-8935-af9daebfdf9b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | d82630c6-39b4-5301-ad86-05c5be65a069 |  | textbox | Date Completed:
checkpoint-status | f9a5c7d5-fee2-42cd-b7df-1f9b646d67ce |  | checkpoint | 1.3 Service Proving
label | 310b8360-2283-58d5-bc5b-4ad38a579b8b |  | note | FREQUENCY: Prior to Commencing any Activity
label | 659eb53a-0546-5c1d-a74c-fc192fb9a18c |  | note | ACCEPTANCE CRITERIA: Service locating shall be conducted in form of DBYD and service location
label | 51d6886c-9b3e-5dc9-b52f-703e66043ddc |  | note | REFERENCE DOCUMENTS: DBYD Service Locator
label | 3da7bbb6-5e16-5375-b114-91ca50519bc8 |  | note | INSPECTION/TEST METHOD: Verify
label | 0ab53de5-6821-599f-9446-0092238049b2 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | a6c79647-ce42-5a78-af67-068648b758d2 |  | note | HP*
label | 8a3681c6-be37-5594-bc57-0cb2b085355f |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 18477a0a-3d4c-5baf-8b89-40b59560cc37 |  | textbox | Date Completed:
checkpoint-status | 13be9a81-02f4-4ccd-a262-57793fbe58d6 |  | checkpoint | 1.4 Excavation Permit
label | 540277f4-580d-595d-a8d1-18229d3536f9 |  | note | FREQUENCY: Prior to Commencing any Activity
label | c5cc9e19-28cd-5dce-93d0-60a790e6d11c |  | note | ACCEPTANCE CRITERIA: Ensure excavation permit has been obtained for the specified tasks
label | af6bca3d-8ce3-56d7-bc5b-9ed38a087347 |  | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
label | dc4883ba-38a4-5b69-b6bb-a9ba7784ba17 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | bdd2fca9-92f7-5a0b-89b0-50d8be919953 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | d8d8b0d9-f291-5832-be15-0b2dac49a5a9 |  | note | HP*
label | 9ed95b37-6804-5a34-afa0-194134e0f1cc |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ffa8b8dc-8600-538a-bcaf-e62c629b380c |  | textbox | Date Completed:
checkpoint-status | 26848522-0c60-4e59-8c27-9e19938b02e7 |  | checkpoint | 1.5 Materials
label | b13102e7-4d36-5218-923a-5c11c326ba75 |  | note | FREQUENCY: Prior to Commencing any Activity
label | 593d62ec-a13c-5915-bd08-06521e2e41d4 |  | note | ACCEPTANCE CRITERIA: All materials shall comply as per technical specification Ensure materials are not damaged
label | 72fa504b-f5e3-549a-8332-0e4ddad1618a |  | note | REFERENCE DOCUMENTS: ASE TS
label | 089f9c08-bd4a-581f-832e-3a1fea469878 |  | note | INSPECTION/TEST METHOD: Verify
label | 1f4793b8-f897-55b9-aca5-118aa61d26a6 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | e35374a2-214a-576d-84f6-dfea4624de7d |  | note | IP
label | 11018413-7491-51e1-8546-4527280ab0f4 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2acae374-2ff7-5781-beef-698295de090b |  | textbox | Date Completed:
checkpoint-status | 774823cb-bdec-4943-b97c-4c9a47726737 |  | checkpoint | 1.6 Setting Out
label | fea5aac5-e7c2-59e0-a0dd-0736823bae40 |  | note | FREQUENCY: Prior to Commencing any Activity
label | af697200-8074-53cd-883c-981d10865b5b |  | note | ACCEPTANCE CRITERIA: Ensure location of bollards conforms to design drawings Mark hole centre position at location
label | 6d3088ce-4520-5ee4-9dec-0684d335221e |  | note | REFERENCE DOCUMENTS: ASE TS cl1.1
label | f506c76e-6b9e-5b39-83cd-873be1a6deb4 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 1e42c83e-a96d-566d-a186-a2e9783dd786 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 49f6d2a7-1d57-583d-8af7-9ba7ae117d82 |  | note | WP
label | 33510672-4bef-5f96-8279-4e56adf14fb9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 52b275a4-e79f-55f2-be3f-8491ea1bce0e |  | textbox | Date Completed:
checkpoint-group | 9b0e8397-283d-493b-ac3c-ac3352b91ac5 |  | section | Construction Works
checkpoint-status | 8655134f-3589-4149-997e-21c6fd8926ea |  | checkpoint | 2.1 Excavation
label | 00174762-ad83-5413-812c-8b9ead00993d |  | note | FREQUENCY: Each lot
label | 370141b6-755e-579f-b616-edadc853d745 |  | note | ACCEPTANCE CRITERIA: Care shall be taken in excavation Hole shall be minimum 600mm dia and 1000mm in depth
label | 17baf021-ffe4-5760-a160-683bc0b82d8a |  | note | REFERENCE DOCUMENTS: ASE TS 2.2
label | 569adde8-a081-5db3-81ce-2f577e456ac6 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | cef3e82b-1b36-53bf-b7b7-1b4185ce74ef |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 7ba44245-6fb6-554f-9899-aa7afefdc168 |  | note | IP
label | 89ff7549-db8c-5d9c-a4fb-8e5c2c2fbc42 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 41b8231c-27e4-5398-b35b-5af7e88dab46 |  | textbox | Date Completed:
checkpoint-status | 2045e5aa-ff2e-429d-b9ec-3b257e810bd2 |  | checkpoint | 2.2 Placement of block
label | 81780c18-7125-548f-af38-61247c8f6c3b |  | note | FREQUENCY: Each lot
label | 42567b17-2afb-5ff4-86c1-deb15e6007c8 |  | note | ACCEPTANCE CRITERIA: Block (brick, wood, foam) shall be placed at hole base Ensure base is supported by solid ground, and block is level
label | 63a81bd0-3717-51c2-abe0-51dfbc5d7c7d |  | note | REFERENCE DOCUMENTS: ASE TS 3.1
label | b8366b6e-f659-5039-a335-9c635b7d7903 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9dafcee9-94fa-5f35-b15d-c5010dba393e |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 20f050ab-a20f-5965-824f-fca56436b3c0 |  | note | WP
label | f2667b32-edfd-5396-9a4a-0bbcb81c2028 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | e1880d0b-4cc8-5fed-bc5d-319e71fe9e8f |  | textbox | Date Completed:
checkpoint-status | a0be6617-409e-4f22-ab8b-134c8baf4246 |  | checkpoint | 2.3 Installation of Cartridge
label | 3b51db39-f597-57fc-9011-6abf4a4c3233 |  | note | FREQUENCY: Each lot
label | 66f31a3e-9259-5529-ba32-d592314cda8f |  | note | ACCEPTANCE CRITERIA: EAB cartridge shall be placed on level block
label | ad5bf4e1-eaef-5dd2-bde3-53088542a664 |  | note | REFERENCE DOCUMENTS: ASE TS 4.1
label | 83e9fac4-276c-5f21-8901-1208684807c2 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 51741062-097f-56a1-a03e-5d4c91db5954 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 5cdb81ea-bc49-50c2-a48f-c5d7e61c7d9d |  | note | WP
label | 2c3c11b4-273d-5d5d-9ad4-10795cff31d9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ef580cfb-01d3-5468-a57b-682a50142882 |  | textbox | Date Completed:
checkpoint-status | 07ba979b-1ff8-47f4-aad9-7e9bc6a5dbdc |  | checkpoint | 2.4 Pre Pour Checklist
label | 0d45af90-3c30-5030-9619-575a3c2dfc90 |  | note | FREQUENCY: Each lot
label | a5ea5f5b-b0e4-517c-b44f-fe4eedc336f6 |  | note | ACCEPTANCE CRITERIA: Ensure minimum clearances are provided, no foreign materials are present, and EAB cartridge is level
label | 837ab97c-4e35-500d-b482-0a6d55035269 |  | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
label | 7f2a32ec-6f0e-5e71-a1a3-0a168ee13b20 |  | note | INSPECTION/TEST METHOD: Verify
label | fb7afaa3-2e52-5ac7-8e0f-1645b6c1c51c |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 72fc6f3f-adeb-545f-ba34-5d90d58fe230 |  | note | IP
label | 0a02357a-35c5-5605-9720-298398a04cf6 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 029f52f6-60c5-556e-83aa-9aead1095319 |  | textbox | Date Completed:
checkpoint-status | 4dafe5d7-c730-44fb-b28b-75f784334d3e |  | checkpoint | 2.5 Installation of Concrete
label | 0fa2d619-5293-5fdd-9e0d-d17b46a4c8a3 |  | note | FREQUENCY: Each lot
label | c54d81ac-2a54-5aa4-8d0b-60b2e871cc06 |  | note | ACCEPTANCE CRITERIA: 32MPa concrete shall be placed to cover reinforcement cartridge and fill hole Concrete shall be compacted by use of vibrator If surface pavers are to be used, allow 25mm gap from finished surface Ensure cartridge is level post compaction
label | ab12431b-8fc6-58e4-88a3-30042e5977f5 |  | note | REFERENCE DOCUMENTS: ASE TS 4.2
label | cde6445a-577f-5463-8d3a-f4a05b8b0012 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 7e920cdd-8ee2-5061-9a6f-f52227d0c293 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | b8a1e715-2e58-58c0-b79a-ebd6d95c7c27 |  | note | IP
label | 7920b3b1-9149-5fa5-9dd7-73d8fe2ed545 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | a54fc4b9-8ed7-5948-ac35-24d297e063d7 |  | textbox | Date Completed:
checkpoint-status | b39c109d-3d50-4ab4-9af8-36dcc6944d78 |  | checkpoint | 2.6 Installation of Bollard
label | a310f99c-5879-5dec-b737-b189b1d3adf0 |  | note | FREQUENCY: Each lot
label | 62a59d39-edb9-5d22-8801-e762cdef7b11 |  | note | ACCEPTANCE CRITERIA: Ensure bollard is installed, and bolts are tightened adequately Concrete, pavers or bitumen shall be finished to specified requirements
label | 313f1b56-8b5c-5ddb-a49f-399a63a99d4b |  | note | REFERENCE DOCUMENTS: ASE TS 5.2
label | be9a29a2-b3f0-5911-a802-15d84f418bb0 |  | note | INSPECTION/TEST METHOD: Verify
label | b05a7ffb-3323-5830-b1ad-f8d1bb6e864a |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 44bdfa7f-602e-5d44-b4fa-6cdd8b5c121b |  | note | IP
label | c07446a4-7162-5267-a3ea-163668b807cd |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 106a18d8-2d93-5d12-83ed-c6efa7cf83ee |  | textbox | Date Completed:
checkpoint-status | f8408594-98b4-4b76-8a4b-7d901849428e |  | checkpoint | Final Inspection
label | 7ddcd1ca-83e4-5c71-b725-aaaaffb44c48 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | f8b1c20a-0f3a-5521-952f-4a1243a20c09 |  | textbox | Print Name:
text | 2631b7fc-a95b-5d75-98a0-468fcabd2099 |  | textbox | Position:
text | dce930d2-37dd-5911-9be8-198c0c293b8e |  | textbox | Date:
checklist-sectioned | 26cb2541-6f44-4ead-8bce-fc05ea3994db |  | checklist | ITP-035 - Kerb Access Ramp Asphalt Footpath |  |  |  |  | Yes | ITP-035 - Kerb Access Ramp Asphalt Footpath | 8dcd654b-1ffd-48b2-b4d0-98c6082bc738
checkpoint-group | ee591d63-d5a1-4949-b367-249005efe442 |  | section | Preliminary Works
checkpoint-status | dcf7ea66-bf3d-4c2e-8c00-b5f6e55cc594 |  | checkpoint | 1.1 Check for Correct Documentation
label | 269c50c5-4335-55f2-ac6f-ce08f4fc37a2 |  | note | FREQUENCY: Prior to Commencing Activity
label | 77af6e24-9151-5d13-ba57-c42ac783f492 |  | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | 30618744-9a56-51fa-8182-80a91779a366 |  | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | f4df79ce-43a3-5c8e-81b8-cfee3e0fcae5 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 0619d166-deb3-5e8a-9fc3-5e55dbe86675 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | c123da8e-0eff-5219-b590-f52f8f9e8bf5 |  | note | HP*
label | f4def454-72c7-5039-9f1a-0f57a352cfaf |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | da10a0da-6aa5-5e2d-a744-634ade79f635 |  | textbox | Date Completed:
checkpoint-status | ade28501-ab03-49e7-9912-5bb448d38aad |  | checkpoint | 1.2 Implementation of all measures and controls
label | aeba95b4-3a17-5c88-b544-fbb6234856b2 |  | note | FREQUENCY: Prior to Commencing Activity
label | 343a329a-9a31-56ce-96a2-f657c5dd77b5 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | e65b2830-cef6-51d8-8f5f-98ff17f8f2ad |  | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | 7ff5a8e8-2a99-5c4e-92b4-31e3fe65dfeb |  | note | INSPECTION/TEST METHOD: Inspection
label | 0f546919-5ade-53d4-85cd-2fbad021a06e |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | ba3b6931-2be4-5426-9415-d3739884af79 |  | note | IP
label | 327739f9-5412-5552-a528-197f83a088dd |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | c101e5b4-b4c4-5c0d-aaed-b62c6fd09001 |  | textbox | Date Completed:
checkpoint-status | c43b00d1-6ee1-434d-aee5-a4197382f1fd |  | checkpoint | 1.3 Existing Bluestone Kerb Demolition / Removal
label | 63aa5d71-12ae-5a19-8194-f94d650ff5d1 |  | note | FREQUENCY: Each Lot
label | 199e214c-c1f2-574f-af9c-cbbd6c150192 |  | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone (if applicable) Bluestone shall be salvaged and re-used in new kerb alignment where possible
label | c8d82dc9-03c2-540d-9bc4-d2a7c8330b67 |  | note | REFERENCE DOCUMENTS: Work Procedure
label | 6f01147f-870f-5f04-a732-dfd276ee9907 |  | note | INSPECTION/TEST METHOD: Inspection
label | b30ccc84-9218-5fc3-a506-d4cad5c29c2c |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | ebd94304-45e5-50c4-a673-25dc975d69dc |  | note | IP
label | a271eb68-6ef4-5bc0-990c-9ebc1b654b7d |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 30e9c808-b302-5c4f-840e-ab577a607ea4 |  | textbox | Date Completed:
checkpoint-status | 3a4b20fa-2c0f-4abb-9e47-b27afb48e5d3 |  | checkpoint | 1.4 Check Materials
label | 17bc89cb-f743-5d0a-8870-73a92af336d2 |  | note | FREQUENCY: Prior to Commencing Activity
label | 10e3a094-a533-5662-807c-1833997a6f61 |  | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage. Tactiles in paved areas shall be Versatac Granite Tactiles. Granite inlay shall be 50mm wide x 40mm thick Spring White Granite Inlay.
label | 8d676394-9d79-5f49-a4c8-472e57c25ea4 |  | note | REFERENCE DOCUMENTS: Receivable Inspection List
label | 7442db3b-e6bf-5e0b-9606-258528ab1f27 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | a135e28d-9746-5571-9ae5-91d641514379 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 3d5801e0-0b5c-55f0-96ae-e54787c86615 |  | note | HP*
label | 53a2386f-cac4-5db7-9c76-a7c5524c69d9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 0fb8885a-5876-5074-bd8a-7740ad45997b |  | textbox | Date Completed:
checkpoint-status | e0ffc64d-1f7b-482c-92e8-514375da89c5 |  | checkpoint | 1.5 Setting out
label | 3db4c3c4-8cab-5611-9d7a-2c6b11eb71ec |  | note | FREQUENCY: Each Lot
label | ae527ad0-9330-57bd-a3ca-5429f47629ee |  | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels. Line and level of bluestone pavers, tactiles and granite inlay shall be set out according to design levels to suit new kerb heights.
label | 73ef6965-526b-5b66-b8ea-c746597e9646 |  | note | REFERENCE DOCUMENTS: Work Procedure
label | fcef10d2-ebe5-569e-b6ba-5328c590dfec |  | note | INSPECTION/TEST METHOD: Inspection
label | de6f5fb2-8d39-59d9-8abd-f7d55d42f20d |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | df210f57-6257-5faa-83f1-cd086162390b |  | note | WP
label | 4c183b5d-2855-5068-989a-846d983c870b |  | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
text | a2e69996-dca1-5a08-a190-5b69839b60bb |  | textbox | Date Completed:
checkpoint-group | b1444a37-4b0f-4003-b880-5fc71fd49574 |  | section | Construction of Access Ramp Asphalt Footpath
checkpoint-status | 68e7085c-a8f2-40b0-9482-bb0eedb7e5b7 |  | checkpoint | 2.1 Re-levelling of bluestone kerbing and ramp
label | 2cc31c67-71d9-5ffe-8afd-5d88d3a41105 |  | note | FREQUENCY: Each Lot
label | efec4ea2-75c5-549b-b2be-cf455fbaed8a |  | note | ACCEPTANCE CRITERIA: Bluestone kerbing to be re-installed to new design levels. Bluestone kerb shall be placed on a bed of low slump 20MPa concrete, minimum 75mm thickness. Formed groove of 10x25mm in concrete face shall be filled with caulk
label | ec0ca6b0-02e7-5205-b77e-cfe202aa76ae |  | note | REFERENCE DOCUMENTS: Dwg 1P50201
label | 8981377f-f8f7-544a-b319-27ac1327632a |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d8f9045b-0ca2-5126-a21b-13a406077acc |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | ffdb29a2-bb86-5657-8c6e-bc431105b9bf |  | note | IP
label | d79a940e-8808-572c-b08e-f1645fe02782 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | e64188b9-5608-5e5d-b587-358f4c3bdcc4 |  | textbox | Date Completed:
checkpoint-status | f1ab9b20-1f03-41dd-aaf7-dc82de986846 |  | checkpoint | 2.2 Base preparation
label | a78f242e-276c-5cbf-b6f8-f067beead71b |  | note | FREQUENCY: Each lot
label | 79801543-d9a5-5a97-8e02-a3bce7cab18d |  | note | ACCEPTANCE CRITERIA: Sound base should be achieved with 50-100mm for bedding materials
label | 78aa16c9-ef2c-5b7f-9108-869532fce6e7 |  | note | REFERENCE DOCUMENTS: Dwg 1P50201
label | 7b09f44a-565c-575b-b899-f38531ba83a7 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 331a8893-dd6e-5474-9806-68b9476597ca |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 20a9d807-5e8b-5bfd-8671-fb64209c1b07 |  | note | IP
label | fba4ff62-cca0-5e3a-ab73-b309a6eb52bb |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 5bbcbd19-4182-5772-97a8-681d6023473f |  | textbox | Date Completed:
checkpoint-status | b47cedcf-ada7-45e3-9674-7d41a61bda12 |  | checkpoint | 2.3 Installation of Kerb & Gutter Blustones
label | 47da9a64-ee82-58a9-b014-aab198dc4806 |  | note | FREQUENCY: Each lot
label | bf5e0ba8-97b9-5f18-ac49-397e5bef506e |  | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness Gaps of >10-30mm< shall be provided and filled with mortar.
label | bacfed7c-16c6-5d83-95e5-abb0ae0480df |  | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
label | 7521dc29-fbd2-5066-92ba-0bee7084d7de |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | ef3d88fd-327f-5924-96ef-e0a4d0b42aaa |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 70e7f742-7b14-5493-9f07-340adefdf355 |  | note | IP
label | bbd3f038-93f9-54c3-b32a-3790b11babd2 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | a82d928f-9e2b-55e8-a259-d2af5adf4dd4 |  | textbox | Date Completed:
checkpoint-status | 845e7533-ab04-485f-8a4c-4ec0e91f84ca |  | checkpoint | 2.4 Asphalt placement
label | 3ae8f9ac-ca4c-50fe-9ea3-305d8b264a0b |  | note | FREQUENCY: Each Lot
label | 2482b55c-510f-5ea2-9133-e1d03bc5c413 |  | note | ACCEPTANCE CRITERIA: Asphalt ramp to match adjoint asphalt footpath and sit flush with channel at grade of ramp using 7mm type N hot mix asphalt. Kerb access ramp wings shall be at an angle of 45° and the ramp gradient shall not exceed 1:8.
label | f4648241-1193-5d13-a6ed-3ed43f209c8f |  | note | REFERENCE DOCUMENTS: Dwg 1P50200
label | 39db275a-08f4-5014-92a7-f5428c9cdc32 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 6697926c-8549-5892-a76c-4a289c043502 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | a9a9a300-6586-5bb3-afec-d038e6d28f72 |  | note | IP
label | 40ca199a-74c9-5f0b-a5b5-b5565dd13ec1 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | aaab07b5-21f2-5661-99ae-2754b67ef078 |  | textbox | Date Completed:
checkpoint-status | dab9ad62-4b20-42c8-a898-301463f72471 |  | checkpoint | 2.5 Installation of Pandatac Granite Tactiles
label | 8b7e0cb1-d6a5-595b-bafc-875a14b170e7 |  | note | FREQUENCY: Each Lot
label | 4822926b-103f-5c48-9722-54682465514b |  | note | ACCEPTANCE CRITERIA: Granite tactiles shall be placed in accordance with Standard Drawing 1P50200 & drawings.
label | dd1903fa-2b65-57bb-acfe-5663594b9917 |  | note | REFERENCE DOCUMENTS: Dwg 1P50200
label | 9d260bbd-3dce-5ba5-b926-c89f26867d51 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 468145c9-e7aa-5afd-88c4-d3fd4734d987 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 47f67a6d-ded6-5e3a-ae4d-748891b5e7fb |  | note | IP
label | 4367f07a-bc04-5ec9-87b3-6f1ff9c39752 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 4ce9a59a-0d13-53cd-a8bc-f26b7e2af66a |  | textbox | Date Completed:
checkpoint-group | bde4f4d3-6719-4e2a-82f9-514aa749ba74 |  | section | Completion
checkpoint-status | f72ab9ba-4731-4772-b832-c19688e50dee |  | checkpoint | 3.1 Completion
label | 0388b6d0-5435-5b26-8347-ca86f4aec718 |  | note | FREQUENCY: Each lot
label | e4a3ee74-3488-5af5-a222-3d0ed3b96b3d |  | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste Bluestone kerb is free of mortar stains and cleaned to satisfaction.
label | 3a97c709-a75f-547b-ab0f-f4e61204e75f |  | note | REFERENCE DOCUMENTS: Visual Inspection
label | 0f546ba3-764c-5859-948c-b19dafff4dfd |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 7bc8ea4d-fa3a-5c4f-a81b-3ed78e126645 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | a27f3b59-e2d1-5890-be1e-dcc0d5c08573 |  | note | IP
label | 14bd36d8-a664-5bdf-bf6e-9640e862fe9b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 34028fe8-e367-5e02-9460-fd8ff6c26f4d |  | textbox | Date Completed:
checkpoint-status | 8e042ab4-897b-4c7e-9d1c-d9a731260d9e |  | checkpoint | Final Inspection
label | 6285094f-aacd-5f3d-9b4f-1d2e792c841c |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | be1085f2-e4d7-579c-9d5d-5205917669a2 |  | textbox | Print Name:
text | 7f8a57c8-06e5-5cc6-93c1-f3df770ae309 |  | textbox | Position:
text | e8f5ee14-63a2-530b-a9ce-127c470f5a85 |  | textbox | Date:
checklist-sectioned | cf5d8f67-c4f7-4f90-8e94-28e1fd95058d |  | checklist | ITP-041 Platform Bonding |  |  |  |  | Yes | ITP-041 Platform Bonding | b1d09002-7c08-4dfd-84c7-445c5c6997ff
checkpoint-group | 1e6336db-7636-4cf7-897f-0fbc25b5669b |  | section | Preliminary Works
checkpoint-status | 65bba1f0-86fd-4d41-8b81-24ed89d546d6 |  | checkpoint | 1.1 Check for correct documentation
label | f0d695f3-e2c9-599f-b2d7-a68c7b35b268 |  | note | Frequency: Prior to commencing any activity
label | 408d8b8d-702b-5fa9-9579-30443ecf3990 |  | note | Acceptance Criteria: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
label | 0a7c81a4-9cf5-5e8f-8df1-34783a288cad |  | note | Reference Documents: Drawings and drawing registers
label | 05f021e5-50a8-5f40-a7c2-0370470e9781 |  | note | Inspection / Test Method: Visual inspection
label | 27791457-c17c-5076-8d14-c794e7ed01c3 |  | note | Record of conformity: This ITP signed off
label | f5ee5d25-b9b1-51ac-a144-e72b9a80ffb6 |  | note | HP*
label | 0cbcc85b-0fde-50db-9757-24fbe5171fb8 |  | note | Responsibility: Fulton Hogan Engineer
text | 6949b7ce-6331-5fc1-a294-a024ed9fce25 |  | textbox | Date Completed:
checkpoint-status | 46fbf62a-88a8-49d9-a9ad-7646d1fb3b39 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 070861e3-a6b2-553e-bfb6-f92738a5820d |  | note | Frequency: Prior to commencing any activity
label | fba398d7-a525-5406-a07c-2c9e556cb3c8 |  | note | Acceptance Criteria: •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | 75d5f00b-37c2-5ae0-a54d-017949ee2c18 |  | note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
label | 2465b4db-cdb4-5eca-81f4-de05bca12be2 |  | note | Inspection / Test Method: Visual Inspection
label | 169e46be-a6d4-5ec5-87be-d018f403fe6d |  | note | Record of conformity: This ITP signed off
label | ef5064d6-dae1-5efd-8431-48f916405eef |  | note | HP*
label | 695ca31c-3f5f-564c-b0f0-94636162e3c9 |  | note | Responsibility: Fulton Hogan Engineer
text | 983c934b-0624-5ff6-b46d-92f61d19859c |  | textbox | Date Completed:
checkpoint-status | 1178249e-6d8c-4173-9d98-0d496b617116 |  | checkpoint | 1.3 Check Materials
label | 27f701d4-cda7-58ab-83f6-26b3cd475152 |  | note | Frequency: Prior to commencing any activity
label | 3e8b6e8d-b4d9-527e-9360-d7c65ed961bf |  | note | Acceptance Criteria: •Confirm bonding cable material & size is correct and in accordance with design drawings. •Confirm correct mould type and size is used for required CAD weld connections.
label | a45389dd-cb1f-5f9f-a37a-28147b66b220 |  | note | Reference Documents: Construction Drawings
label | 7cb87a0e-de6a-5784-b8cc-01a2ed7ad447 |  | note | Inspection / Test Method: Verify
label | 08bc3802-cd39-5e9b-81a9-f62f9b95caf2 |  | note | Record of conformity: This ITP signed off
label | 09c38494-1f7d-5bde-8dfc-2dfdcb5dca3d |  | note | HP*
label | 1b184c99-0ada-5a99-be99-d29481f632a0 |  | note | Responsibility: Fulton Hogan Engineer
text | ff056964-54d4-5104-8414-4e745996102c |  | textbox | Date Completed:
checkpoint-status | 97ced493-05f4-4b9b-9fa7-f09e5d5acfdd |  | checkpoint | 1.4 Bond setout
label | 1ee10d2e-d9ab-5020-8d8d-fd1b82599a83 |  | note | Frequency: Prior to commencing any activity
label | c1dc2204-0c6a-5231-9b92-a5fcc42be3be |  | note | Acceptance Criteria: •Confirm bonding loop and connections are positioned in accordance with the most current and updated set of construction drawings. Ensure that all locations are reviewed by a Fulton Hogan engineer.
label | 8344c9e0-5e6c-544e-ae83-3cbad8d2932f |  | note | Reference Documents: Construction Drawings
label | 1521a5bd-11dc-5343-a398-fda096154edc |  | note | Inspection / Test Method: Verify
label | 443c5621-ac2e-5a00-bdda-c849edc75142 |  | note | Record of conformity: This ITP signed off
label | b8886ebe-5ef9-520b-ae6c-786e3b58a6c8 |  | note | HP*
label | e796c78f-aff1-5272-ad28-8a76412eb71d |  | note | Responsibility: Fulton Hogan Engineer
text | aa639460-caf7-55be-b55c-5bff4d13858f |  | textbox | Date Completed:
checkpoint-group | fc792f1c-0397-4525-8257-952255aedbf4 |  | section | Construction Works
checkpoint-status | cda5ac32-8f9b-4d81-8c1c-c46f56fdbd90 |  | checkpoint | 2.1 Laying of Bonding Loop
label | f5c9fd36-7a73-5562-bce6-f6658481cd05 |  | note | Frequency: Prior to Asphalt
label | 79c1d320-3e33-521e-a0d5-9f1d05ac3785 |  | note | Acceptance Criteria: Lay bonding loop in accordance with construction drawings such that it connects to the electric cabinet correctly.
label | 10a774a4-ed22-5514-86f9-5e6fb11dd194 |  | note | Reference Documents: Construction Drawings
label | 74056e8d-b4b6-5c03-9e0e-d9a20308d9b1 |  | note | Inspection / Test Method: Visual inspection
label | 00231cda-a0b0-50db-b4eb-16f2feaa101b |  | note | Record of conformity: This ITP signed off
label | 98eedbbd-35cc-5470-bf3b-c4d40b095048 |  | note | IP
label | 7028de1d-d8f6-5542-bc0c-b572f13ff587 |  | note | Responsibility: Fulton Hogan Engineer
text | 0d018288-6b48-57ac-9fb2-f239ee04c6b4 |  | textbox | Date Completed:
checkpoint-status | 71cecf00-013f-4900-9e92-2d49a8f5bc9b |  | checkpoint | 2.2 Laying of Bonding Furniture Connections
label | bb8078a2-57d5-52c0-8f82-44938be8de15 |  | note | Frequency: Each Lot
label | f31c0c8c-8fed-54f1-b9c6-cd432403a34e |  | note | Acceptance Criteria: Ensure furniture connections align correctly with structure and are positioned in accordance with the design drawings.
text | f478eae6-a4d9-56e1-9593-4a971526b247 |  | textbox | No. of Furniture Connections:
text | 33ce6aa3-5eb9-5d2e-ac49-58d1d686264d |  | textbox | Furniture Connection Cable Size:
label | b44beb1c-1309-55ec-b25d-10d15f1270f5 |  | note | Reference Documents: Construction Drawings
label | 1ec69e40-1365-5626-a737-2abb1b64da97 |  | note | Inspection / Test Method: Visual inspection
label | 1ff1e675-5957-5495-9215-b4879662568e |  | note | Record of conformity: This ITP signed off
label | 26fb6910-8954-58d5-af60-f178dc0bcb76 |  | note | IP
label | f28393ee-3e32-51ef-bf69-00c7b511e52e |  | note | Responsibility: Fulton Hogan Engineer
text | d74e7d06-f5ca-5a80-967a-68288fa28bb2 |  | textbox | Date Completed:
checkpoint-status | 4a9f7b31-e13c-447a-9856-07fac159dd96 |  | checkpoint | 2.3 CADWELD Furniture Connections to Bonding Loop
label | 3227895b-1285-5000-89f8-13617925f5da |  | note | Frequency: Each Lot
label | 2ae6e3da-32c1-561a-b53d-461de8ea749f |  | note | Acceptance Criteria: Ensure correct mould is used when CAD welding furniture connections to bonding loop.
text | 84400cc3-a5e0-5c87-ae4e-2cb64f8fadcc |  | textbox | CAD Weld Mould Dimensions:
label | dec004e2-1ff3-573c-844a-b484f94de38d |  | note | Reference Documents: Eritech CADWELD Exothermic Welding Manual
label | 9c38a405-c160-5853-a74e-6469ed31499e |  | note | Inspection / Test Method: Visual inspection
label | c844bd46-a958-5af1-814b-0ea39ae082af |  | note | Record of conformity: This ITP signed off
label | 3b9ba9d4-718f-57cd-8630-cee855114410 |  | note | IP
label | af490d01-b97f-5e49-9775-625d4b1d3f70 |  | note | Responsibility: Fulton Hogan Engineer
text | d8695058-8268-52b6-939f-8407e43bae60 |  | textbox | Date Completed:
checkpoint-group | ef5a68df-e283-47b1-8292-a1212a3595d1 |  | section | Construction Works
checkpoint-status | a649df79-c25b-4c4c-9baf-109787494da4 |  | checkpoint | 2.3 Weld Review
label | 1c2d0163-3522-541b-8e2b-a04ed7155703 |  | note | Frequency: Each Lot
label | d871c010-c72b-560f-a151-531ef514342a |  | note | Acceptance Criteria: Ensure each weld is inspected and that a quality connection has been made. All welds shall be inspected by a Fulton Hogan engineer.
label | ab9a4223-7bc4-52ba-9b88-e6edbafc022f |  | note | Reference Documents: Eritech CADWELD Exothermic Welding Manual
label | 406c20ea-ec97-5be2-a7f1-b559a9e03d43 |  | note | Inspection / Test Method: Visual inspection
label | f4698237-90bf-517c-9bf8-d1e1e98d7aa5 |  | note | Record of conformity: This ITP signed off
label | 7a0a7fa2-4019-5505-8f55-4fc653c643eb |  | note | TP
label | d1c5225c-a2e6-5dd9-9869-ed7b13e1b080 |  | note | Responsibility: Fulton Hogan Engineer
text | 1fe9b24e-d706-519c-80cc-157f4bfce62b |  | textbox | Date Completed:
checklist-sectioned | c5c88ae7-98b9-4060-a672-3dd414d8ef27 |  | checklist | ITP-032 - Orca Island Installation |  |  |  |  | Yes | ITP-032 - Orca Island Installation | b2b3366d-2ef2-45c3-abe6-93f88aa11b89
checkpoint-group | 85cf0213-5784-4b70-8a66-549d5f606344 |  | section | Preliminary Works
checkpoint-status | a7a6e5fc-0ece-47b6-9fa2-4a489c493b68 |  | checkpoint | 1.1 Check for Correct Documentation
label | 59cfbaa8-a8b8-52cc-984e-418aa3abab55 |  | note | FREQUENCY: Prior to Commencing Activity
label | de752495-8dbe-5ce0-87e1-a214fcb25283 |  | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | 50739957-d3b7-5213-b2ac-6a55c57a6042 |  | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | f051c969-1b2e-51a9-8e32-bbc81da0c353 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e2561d01-0e6e-5723-8dd7-16cd6801f121 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 2b91a9dc-5f6e-527f-94ed-3df5bb0b7b36 |  | note | HP*
label | 9d7a9c82-b320-54cd-8721-7022bd92d0c5 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | daa30b17-1d35-5595-be4d-b98c19223f63 |  | textbox | Date Completed:
checkpoint-status | 2c4f5d3e-e19a-4d76-aa8f-e4e72a16bdb6 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 18892569-6400-5e8e-bb15-8543283ff710 |  | note | FREQUENCY: Prior to Commencing Activity
label | 7f5fcadd-e5e0-50e1-8af5-94146e8d3758 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | 7b93c346-79ba-5028-a300-5d0a83c46dd4 |  | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | a099a9a4-c5c5-58fd-b572-1bd66339343d |  | note | INSPECTION/TEST METHOD: Inspection
label | cc182ecc-16ab-5a93-b63b-fe364238659f |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 9f57672d-303c-5434-b77a-1476ca4f6e20 |  | note | IP
label | d0072b76-bb7d-5738-98bc-36749a1027f2 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 84731356-2d73-58f0-b197-bbb78e5cfb27 |  | textbox | Date Completed:
checkpoint-status | 6c9c5be7-7b5b-4092-87f7-ebc12396b499 |  | checkpoint | 1.3 Check Materials
label | ab3bb1d0-5e1f-5ddc-be71-53f460185139 |  | note | FREQUENCY: Each Delivery
label | af0b7a77-2f2b-5ff7-b246-daf2154649a7 |  | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
label | 105381bf-c010-5bc1-afa7-841aab593d59 |  | note | REFERENCE DOCUMENTS: Receivable Inspection Checklist
label | c74c084a-5fbc-54bd-b858-f3c3725644ce |  | note | INSPECTION/TEST METHOD: Inspection
label | 3bc0eaae-005d-54e2-8810-b2733cfe41a9 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 0c368bf9-522d-5cff-8be5-480fdcb7b9a4 |  | note | IP
label | a09df259-f857-5138-88b6-d246bb2f7afe |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 9f6b177f-7e9a-5ac6-9ac4-911b2682be50 |  | textbox | Date Completed:
checkpoint-status | ad863e19-1786-446c-85a6-f5500dec3653 |  | checkpoint | 1.4 Setting out
label | 8363cd56-0c35-5fd4-9628-2e9389e84b0b |  | note | FREQUENCY: Each Lot
label | e35f60c7-5ba7-5436-818a-8f8a58359ef6 |  | note | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans Alignment of new separation kerb and islands shall be marked out using string line
label | 609681cb-f391-53ee-b5e7-b0fe6ea37bf8 |  | note | REFERENCE DOCUMENTS: Work Procedure
label | e55fb4aa-546f-5a72-9747-077e2a8d7531 |  | note | INSPECTION/TEST METHOD: Inspection
label | 3f21009f-a27a-53ed-8b6a-1b5f6d86c61d |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | b7b83f67-5d8e-54e4-95fc-2fad2bd30483 |  | note | WP
label | 4804fdc3-9edc-513e-b639-a7b775cd4426 |  | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
text | 75fb96ee-80a6-5dbf-bb87-17dac0f4538e |  | textbox | Date Completed:
checkpoint-group | bddce686-383c-4e55-98ee-f10f01ee2c68 |  | section | Construction Works
checkpoint-status | 91905c5a-b9b7-4914-a5c2-2595b0671442 |  | checkpoint | 2.1 Base Preparation
label | 8c9a7879-2992-5855-a24a-85c5f715dcf4 |  | note | FREQUENCY: Each Lot
label | 6c4e87ab-04a9-5db9-8793-719843610c6a |  | note | ACCEPTANCE CRITERIA: Concrete base shall be inspected to be free of foreign loose materials and water pooling. IF required glue foam tape to the road where channel will be placed to ensure containment of adhesive.
label | a897b5f9-184b-5e23-809e-12896cc2ca7e |  | note | REFERENCE DOCUMENTS: Orca Installation Guide
label | 2f1ed3a6-dd2b-57b7-bd91-311d8b401644 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | ee121277-4464-51fb-a579-9d93956ec3b4 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | cc3d8ec2-59ea-59c0-a2c5-a24f46bb5dc3 |  | note | IP
label | 4552939d-5805-5fd5-9343-366dd5f1f8f2 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 638befcd-3f0b-5cd2-87d8-d7ccee31caac |  | textbox | Date Completed:
checkpoint-status | b3d49de4-d310-4462-9188-ef57e778a2e4 |  | checkpoint | 2.2 Preparation of Orca Polurethane (Adhesive Agent)
label | 2426beb4-a069-589f-97d0-07ac63a56746 |  | note | FREQUENCY: Each Lot
label | 9e61fb96-8f08-5768-b1c1-1059b835114d |  | note | ACCEPTANCE CRITERIA: Mix Orca Polyurethane as follows: - 2 parts of Part B Polyol Black - 1 part of Part A MDI Using a paint stirrer in a drill, stir for a minimum of 4 minutes. Once Part A & B have been mixed, add 1:1 Part C Rubber Compound in the mixed A+B compound and stir again for 2 minutes. Ensure even mix throughout the adhesive.
label | 308d4521-d8d7-53e5-92ec-493f57ef816d |  | note | REFERENCE DOCUMENTS: Orca Installation Guide
label | d1956aef-160d-5e21-81b0-d9c6286274eb |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 4ed7fec6-570b-51df-8146-841ab259ead4 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 3d6c3a94-8c20-5a9d-882d-1dffcf3891c0 |  | note | IP
label | a69cf8bc-1d2e-556d-b01f-52779f5da28c |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | b1adbf5b-413a-5118-9492-deae056494f3 |  | textbox | Date Completed:
checkpoint-status | a22e4f17-81a1-41ee-8a4f-5df05d5b498c |  | checkpoint | 2.3 Placement of Orca Polyurethane
label | 3f93e246-1555-5ba5-b798-53dc8c80b7a5 |  | note | FREQUENCY: Each Lot
label | 318cdded-0d31-5371-9830-88432aede8cf |  | note | ACCEPTANCE CRITERIA: Pour the Orca Polyurethane compound onto the road, spreading to a thickness of approximately 2mm.
label | ebb14c76-76a5-5f3c-9158-33b230ca9edc |  | note | REFERENCE DOCUMENTS: Orca Installation Guide
label | dfdcb997-e5bc-5f82-a102-ee5769427b95 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c5784f2e-74fc-5be7-bcd2-63dbda4fd356 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | af043eca-3f1f-56dd-8a2a-6f4d08d15fdc |  | note | IP
label | 30aa9523-c787-5d64-bf2b-53721d91f8a3 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 8650bab4-bfe4-5567-bb11-0609e03c1bae |  | textbox | Date Completed:
checkpoint-status | e824f497-e4d6-4bd4-983f-d79a772833b9 |  | checkpoint | 2.4 Placement and Securement of Orca Island
label | 2cd0053c-bd8d-5426-ad86-af06edf33814 |  | note | FREQUENCY: Each Lot
label | 712e9f31-5a40-5aff-b5c5-d072b442d033 |  | note | ACCEPTANCE CRITERIA: Lay the island on the polyurethane material. Drill holes through island fixing hole into road surface, then screw island down securely with 12mm x 150mm coach screws and mudguard washer. Ensure screws are all the way down to secure island. Plastic plugs to be put in bolt holes.
label | 2794af55-5736-5c9f-a490-38c5a376b4fd |  | note | REFERENCE DOCUMENTS: Orca Installation Guide
label | 549d46d8-a420-5860-a7f5-84a95554dee5 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 6aed28a8-b3c6-5827-afe7-0fa44c7ffb48 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | d43ccbd0-db13-5199-aeab-a7eda4fcb2ac |  | note | IP
label | 9f8345b7-a2ff-5f64-b712-470b59091b81 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | bbe7fe02-d3cf-59ff-aba1-9c9dfadd0363 |  | textbox | Date Completed:
checkpoint-status | 9d07b370-f253-4724-b615-ee430c262e98 |  | checkpoint | Final Inspection
label | 31d3b027-31ec-5a5c-9892-35cd1a8c0dca |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 8bac44dd-5e18-5316-8fc2-ded1d7d59227 |  | textbox | Print Name:
text | 93da29e9-afd7-5b14-88c3-f97695f4ebb1 |  | textbox | Position:
text | bfef5598-cac3-5682-bc07-3481aacfd539 |  | textbox | Date:
checklist-sectioned | 5602779b-0511-465c-93a1-d01ac8cae3a0 |  | checklist | FHC-ITP-001 - Clearing & Grubbing Rev1 | itp |  |  |  | Yes | FHC-ITP-001 - Clearing & Grubbing Rev1 | b4c10e08-0957-48ab-b550-649e50b6f452
checkpoint-group | 5056e0ef-7061-42ad-8bf0-973f310f7146 |  | section | 1 - Preliminary Works
checkpoint-status | e0d7666c-e451-4d5b-8f6b-7ee897a228d6 |  | checkpoint | 1.1 Check for correct documentation
label | 85790e24-e5f5-591f-b3a3-3f5e86f337bf |  | note | FREQUENCY: Prior to commencing any activity
label | 6237e5a7-ad59-5eaa-ab85-c3260b2dc761 |  | note | – – – – – – – – –
label | abebb59d-b410-5d90-94ef-37586b937b96 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 86444a8f-8739-512a-8dad-ab52b734b9fa |  | note | – using the correct and complete set of drawings
label | a63d38e8-baeb-5ce0-9973-3d5635cb06bd |  | note | – all drawings are the latest revision
label | 52249fc6-5811-58da-87a7-8c02d92be099 |  | note | – – – – – – – – –
label | ccfdb724-6465-5242-a029-a4c507df34db |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | f150e617-4d82-57e2-835f-be5b013a3320 |  | note | – – – – – – – – –
label | 26e34435-0075-5ce2-b013-c7726e283c42 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | fa249159-2648-5af9-bf05-aed619d60b61 |  | note | – – – – – – – – –
label | 61f7bc0b-8ebb-5ad4-a5db-8d68182659f3 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 5490a368-000a-51b8-8279-843701f0c71e |  | note | – – – – – – – – –
label | a5c1ad82-aad7-5479-b301-df256929c818 |  | note | HP*
label | a7acbb5f-493c-5717-ac16-7523579e095d |  | note | – – – – – – – – –
label | 577e7277-ed6a-5672-8c69-68b23b8fa016 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 9917db73-a554-5b63-aa11-382746f99e04 |  | note | – – – – – – – – –
text | b7e761f5-a1fd-51c0-8471-0ffff56e7f90 |  | textbox | DATE:
checkpoint-status | 927f1bc9-a3f6-41d4-b623-d4e814c8785e |  | checkpoint | 1.2 Implementation of all measures and controls
label | 44d15383-15a6-57ae-ad5d-374e5fdb7bae |  | note | FREQUENCY: Prior to commencing any activity
label | 435e5912-d4b4-52a8-b314-4b1ef1b19a2e |  | note | – – – – – – – – –
label | b92bc0a6-9993-5135-8d1c-b71e661dc224 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 8f1bf357-c2b1-5e08-8b59-9cefb5bc2469 |  | note | – – – – – – – – –
label | 08eb87f1-b3fd-500d-8d7a-b651ae30dff0 |  | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | e259b134-da3a-5105-95d5-4880d19957ab |  | note | – – – – – – – – –
label | fc8810e8-537f-56a4-b3e6-db1ac69d85db |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 764730c3-c3b6-55ea-8bf6-86a2a5fa672d |  | note | – – – – – – – – –
label | dbd0cbe9-2625-57c5-9189-ab272076e778 |  | note | RECORD OF CONFORMITY: This ITP signed
label | d8f13ad2-7e54-592e-8661-3df9c2b519f1 |  | note | – – – – – – – – –
label | 001a64b6-a1d8-5779-b03f-23c4a6aa5e51 |  | note | HP*
label | 1c9ce619-25e3-5bda-9fa9-4aad509f6281 |  | note | – – – – – – – – –
label | 2cb675ce-dcd1-58e3-977b-8778e7a1eed8 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 31b69d4a-6ecf-5fab-b75b-8c789af30a36 |  | note | – – – – – – – – –
text | f30115ea-0347-563d-b240-b9d14c351b1b |  | textbox | DATE:
checkpoint-status | 12000731-0940-4642-a714-09a90a46c876 |  | checkpoint | 1.3 Flora & Fauna
label | 751a4507-09a8-5d6f-b469-668ab7ecf5cc |  | note | FREQUENCY: Prior to commencing clearing
label | 01d1e9ac-3a4b-5c92-80dd-22088218a16d |  | note | – – – – – – – – –
label | bf11dd2c-30ad-533e-8294-6bb0eaea5f0f |  | note | ACCEPTANCE CRITERIA: A qualified ecologist and/or botanist has examined trees to be removed and/or any fallen logs affected by works and provided written clearance for removal; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
label | 0a95ae53-8388-56f3-a690-9debc7401015 |  | note | – – – – – – – – –
label | 338b8cc5-7971-551c-b806-36d0b1ed7d71 |  | note | REFERENCE DOCUMENTS: EMP, ECP
label | 7de4000d-3c8e-58ab-8ce4-b724b9ebf686 |  | note | – – – – – – – – –
label | 3e9de13a-258a-55b5-88e6-312895651758 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | b3fb69a3-a124-5e56-8cfe-b7ba72862920 |  | note | – – – – – – – – –
label | 0bbac84f-8def-50d8-980e-daddb542569f |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 63d4cc05-58fb-5bcc-abc5-360756fb166e |  | note | – – – – – – – – –
label | 4e0d30dd-641e-5e5f-b1fa-20163ac09663 |  | note | IP
label | fc1cdf62-09f5-5057-8485-68c69be0c545 |  | note | – – – – – – – – –
label | 6d7d6c1a-7cce-5a60-bbbf-d912b09d2f70 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 1e4a3e19-728a-5fed-8366-aea7a007f8ea |  | note | – – – – – – – – –
text | a7486b63-c5fa-578e-8c60-f366b3460bc0 |  | textbox | DATE:
checkpoint-status | 93fb3c2f-ce4a-477f-b513-f3e5bef63ed1 |  | checkpoint | 1.4 Permit to distrurb flora & fauna
label | 25e72b6e-b3a2-5879-ba45-27f0f635841a |  | note | FREQUENCY: Prior to commencing clearing
label | d8b26a07-13d6-5f5d-82a9-b2bfdff50a41 |  | note | – – – – – – – – –
label | 8eefd7b8-e81a-528f-8a4d-4467f8b0a6c4 |  | note | ACCEPTANCE CRITERIA: MRPA has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
label | e612aaa3-b64d-5ece-8b8b-a6bbbb62e47d |  | note | – – – – – – – – –
label | f1d6ecbf-4f99-517e-836d-e69d721b286d |  | note | REFERENCE DOCUMENTS: EMP, ECP
label | 7550b470-c3d0-5f0f-a87f-7ed91b2e96a0 |  | note | – – – – – – – – –
label | 281ea013-b6b0-5458-bff7-27b691b1fa83 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 271a2bd9-c3c2-5642-8244-7cd1b65b1a5a |  | note | – – – – – – – – –
label | cc7789a3-e786-5635-bcca-225cb9caa916 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 9e525d43-8aa1-572d-bed5-de8b8cc29fc8 |  | note | – – – – – – – – –
label | 3341d8c9-dc01-56f2-9e06-5328d9d1b705 |  | note | IP
label | 2cd9525d-4ca1-5aeb-b5d9-96cebdee56cf |  | note | – – – – – – – – –
label | b1baabaa-5a6e-52a6-bb1e-f81d2df948f0 |  | note | RESPONSIBILITY: Project Engineer
label | b850d379-72d3-5720-99c6-05963751f118 |  | note | – – – – – – – – –
text | 6c656bb8-3e10-511d-8364-1f225979167f |  | textbox | DATE:
checkpoint-group | 9b4e55e8-9db6-4a30-acb2-acec7ee03724 |  | section | 2 - Clear & Grub
checkpoint-status | 11f21b79-5d9d-4434-962c-46b01c3226f8 |  | checkpoint | 2.1 Define work area
label | 9ed3ed3b-8a65-5bbb-ae5f-aa70529b956a |  | note | FREQUENCY: Prior to commencing clearing
label | e1a00a1a-3171-5904-b674-5c131f9c3793 |  | note | – – – – – – – – –
label | c881ea3c-6edf-52ec-8345-95f029a9d897 |  | note | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
label | 1601715c-b3d2-544e-ae13-21894dee7771 |  | note | – – – – – – – – –
label | e1cfe4c3-c44e-5e80-a9a1-49cdba9aebf8 |  | note | REFERENCE DOCUMENTS: 201.03
label | 5a4795cf-856f-5f46-b86b-5e30e59052c5 |  | note | – – – – – – – – –
label | 80cad0b8-8db8-52f2-9a49-2e32530ef343 |  | note | INSPECTION/TEST METHOD: Inspect
label | d756d229-797c-54b2-b17c-09a1564d334c |  | note | – – – – – – – – –
label | 0bdbc982-d1fd-5669-b32f-cd4569f2bc3c |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 185efeb4-ba5b-54c9-8650-b8b65baa94bd |  | note | – – – – – – – – –
label | 460e19a1-4c4b-5fb7-9f1c-92058cd06a6b |  | note | WP
label | 054ceee9-967f-57cd-a00e-20700bed7fc1 |  | note | – – – – – – – – –
label | be7fa55c-d394-5157-9684-f12028878cb9 |  | note | RESPONSIBILITY: Project Engineer/ Superintendent
label | f6ce5360-185f-5614-8126-823f1dd8ff60 |  | note | – – – – – – – – –
text | 35e7d0ce-ec1b-55f9-b959-5d7be48da89f |  | textbox | DATE:
checkpoint-status | b255148f-c197-40f0-ac0d-f958d9fc8e66 |  | checkpoint | 2.2 Joint Inspection to Mark vegetation or habitat to be removed
label | 0d943b94-53b0-5cd5-a968-57ad8528adc7 |  | note | FREQUENCY: Prior to commencing clearing
label | 6152291b-d316-526b-a351-b1eaeca877df |  | note | – – – – – – – – –
label | c3955192-f2df-5a1c-b5bc-31243fd9aec8 |  | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent to confirm and clearly identify and mark trees to be removed, consistent with Appendix O Tree Assessment Report.
label | a6f26ba7-ae10-544a-9039-82339ed39fc2 |  | note | – – – – – – – – –
label | 65b602fc-70bc-5e1c-ba6d-0fa35431b07e |  | note | REFERENCE DOCUMENTS: Drawings 201.10
label | ca4f7b91-f662-5551-81a0-dcb92efa8aa2 |  | note | – – – – – – – – –
label | a7f5eeab-debb-5a0b-8cad-843b20915375 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 7bc754ef-fa51-5b03-a343-6d7da2552baa |  | note | – – – – – – – – –
label | 9fbc7c4c-b6ac-5676-aade-464608621e20 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 86435fbc-6849-5550-93d7-b4bd5e7d3cd3 |  | note | – – – – – – – – –
label | 4516dc5d-936e-5116-acd2-c54f5add8543 |  | note | HP
label | 2d94bb62-6865-5184-8343-af99bf05b89e |  | note | – – – – – – – – –
label | 347c7647-c27f-563d-a9f2-aadf2a0707d7 |  | note | RESPONSIBILITY: Project Engineer/ Superintendent
label | 3ad58c1c-0b7d-5c93-85a2-01f95575d999 |  | note | – – – – – – – – –
text | 19d36c41-4d69-5d77-b8eb-f75dda87d9a5 |  | textbox | DATE:
holdpoint | 26010539-0e24-45fb-b50e-afd2086ccf98 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | bad90f2d-cfdb-468b-a5c7-e0f34b7c28d9 |  | checkpoint | 2.3 Identify No-go Zones
label | 143ea1b6-7ee6-509c-a798-6d4475e1df91 |  | note | FREQUENCY: Prior to commencing clearing
label | 89000ed6-b0c4-598a-beac-5d4aa203ffc8 |  | note | – – – – – – – – –
label | 22d3b077-9da1-5a57-95a6-8ff8d1b1f9f2 |  | note | ACCEPTANCE CRITERIA: Existing vegetation and native fauna habitat identified in the Contract to be retained, shall be identified as ‘No-Go Zones’ and protected by temporary fencing, consisting of, as a minimum, star pickets,wire support and parawebbing.
label | 1853b644-9cf8-5dec-a1f7-86d6f1e1c821 |  | note | • Signage shall be erected outside the limit of the of the vegetation or the habitat site, at intervals no less than 20 metres apart or as per the SSEMP
label | 7e2da812-d0a7-5f52-a9a5-e1b512a6d882 |  | note | • Prior to any work onsite the contractor shall fence and sign all no go zone sites as per the EMP.
label | aa19df41-efd1-5abf-9a48-3324359e0a73 |  | note | • Any works required inside TPZ shall be completed under the supervision of an Arborist
label | 1e47b39e-65aa-5a0b-b287-1c393cd9c578 |  | note | – – – – – – – – –
label | 43d1f34a-5e07-524a-b895-df0558da9c04 |  | note | REFERENCE DOCUMENTS: Drawings 201.10
label | aeeb6fa4-a44c-5d9f-9ecd-62e844947a63 |  | note | – – – – – – – – –
label | af82a7b8-f34e-58ee-b236-2097261b0f33 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 3031c5e8-137a-5ba5-8eb6-88ad658c3f92 |  | note | – – – – – – – – –
label | 38ace839-c42c-5ef0-9ec7-9a3221f64a02 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | d6af50ae-0c83-5e1c-9d5c-430fbd1b8f90 |  | note | – – – – – – – – –
label | 0bef3e61-ab7b-55d5-8655-732d3f439910 |  | note | HP
label | 6091a22f-3380-5ba2-9132-f72a506d832c |  | note | – – – – – – – – –
label | 90d97e82-6575-52e0-ad8f-6fdfdd704a64 |  | note | RESPONSIBILITY: Project Engineer/ Superintendent
label | 42d23c91-3002-5711-9f07-311b20b13ef8 |  | note | – – – – – – – – –
text | 58a55d3c-2122-5a84-9486-df7596abcbf9 |  | textbox | DATE:
holdpoint | 876fcf1b-b5a4-48aa-811d-d0ee41246053 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 2e95ab62-f165-46ff-9cc4-6aee6ced7d80 |  | checkpoint | 2.4 Clear felling distances of trees are adequate.
label | 2cca8de8-2709-5bcd-addf-0208f8e86dd7 |  | note | FREQUENCY: Prior to commencing clearing
label | 75a0424c-c3b5-5a1b-a23f-ac22bfc67938 |  | note | – – – – – – – – –
label | 0139f76a-6950-531c-b093-7c6885b60ae6 |  | note | ACCEPTANCE CRITERIA: Ensure the clear distances are adequate and signage is inplace as planned. Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared.
label | 4f6c28a5-45ad-52f5-99fa-325fef38a6d6 |  | note | – – – – – – – – –
label | 1fd1282c-47e7-50f3-b57f-9ac451ee8f95 |  | note | REFERENCE DOCUMENTS: 201.04
label | 61aef769-0bd5-5cad-ab1f-39e0ff0457f6 |  | note | – – – – – – – – –
label | 6b60750a-90f4-5f09-baae-53d78ae02995 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 25cd2178-11d9-5250-8598-a8cc9ea15a32 |  | note | – – – – – – – – –
label | 89f9438a-2518-543a-9c74-e9187d8216d8 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 45b43b96-8b44-55f2-a33e-cadb0cf092d0 |  | note | – – – – – – – – –
label | 6a942206-e8ec-5c0a-90e4-0257599229d0 |  | note | IP
label | 529de333-2b96-5340-9c7d-eebc4e3179dd |  | note | – – – – – – – – –
label | b9341aab-1618-5eb2-b9e4-ef8a524ff653 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | c5774739-e2ca-57f4-87d1-88948a88f1e6 |  | note | – – – – – – – – –
text | 5a702f82-1d4b-5bd5-94dd-a64ab31784db |  | textbox | DATE:
checkpoint-status | 77502b3e-ffe9-4362-b68e-5d0a91c77b44 |  | checkpoint | 2.5 Clear and grub trees and vegetation
label | 336ab5ff-475a-5629-9a25-ef0e19adfdf2 |  | note | FREQUENCY: After clearing
label | 83cc3712-e8d2-56fd-9c04-440ba12d2507 |  | note | – – – – – – – – –
label | c4fdea82-cff4-5c94-b934-87fbe65a2b46 |  | note | ACCEPTANCE CRITERIA: Vegetation in areas of site excavation have been cleared and grubbed to at least 0.3m below subgrade, all other vegetation and obstructions cleared to natural surface level
label | 8a681883-37c0-5068-bfc8-e468f837585e |  | note | • Tree branches extending over the carriageway shall be trimmed to provide minimum clearance of 6m above the carriageway surface.
label | c2ad1d6d-9b31-5c74-9765-3ff35697ac5b |  | note | – – – – – – – – –
label | 3f281082-2131-50b3-8302-22d174ea807c |  | note | REFERENCE DOCUMENTS: 201.04, 201.05, 201.06
label | 8af60a35-c258-57d7-b5bb-b1362d9199c9 |  | note | – – – – – – – – –
label | eb68580e-2a94-5746-a8d4-a17b7fbe7f9e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9c9481cc-3c5e-5651-a2d4-bbdf4287ab2f |  | note | – – – – – – – – –
label | f602f990-08d3-53d1-aca7-8f8289e17c0d |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 9aab7197-ee1b-5a37-a97b-8262077191c7 |  | note | – – – – – – – – –
label | b3db9ffa-1ac5-5cf9-a3be-67c07ba9e75e |  | note | IP
label | db14b33f-4608-5538-932a-500b1761883f |  | note | – – – – – – – – –
label | 4adc3f6f-8765-5ee0-93bc-f383b88277d0 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | cb900f33-60d7-57b1-a4cd-84711fd04a60 |  | note | – – – – – – – – –
text | 0556e71e-c703-5814-8991-ae9435b80e8a |  | textbox | DATE:
checkpoint-status | 7518fa77-d771-4fb4-a887-26df387bb2a7 |  | checkpoint | 2.6 Backfill holes
label | de2e72ba-f0cf-52bc-a382-cb0f68144041 |  | note | FREQUENCY: After clearing
label | a18dd509-3df2-5f74-bf34-54b9b2cdba8f |  | note | – – – – – – – – –
label | c7293d85-593f-5eee-accb-2a039cac0422 |  | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material to the sorrounding material and compacted to the same degree to the sorrounding material.
label | 19e5e9f5-a936-5150-9d04-8d611ecbd106 |  | note | – – – – – – – – –
label | 97bf45b1-a2dd-51aa-985e-83050ef6f55e |  | note | REFERENCE DOCUMENTS: 201.05
label | 39b45a35-f8a0-5108-83e3-3b7589414de5 |  | note | – – – – – – – – –
label | 9a6f1b90-06cb-57ad-b67f-d5b38d540459 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 2f703398-80a9-5c43-9291-86e0fde779db |  | note | – – – – – – – – –
label | 0eca8b64-d84f-5619-a564-59caa62cc17c |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 86998011-a3a6-5679-852b-ca4f30550cbf |  | note | – – – – – – – – –
label | cb82b229-8236-51e9-b2aa-2dba61623116 |  | note | IP
label | ba6592ab-816d-57dc-bf04-8a17c84081be |  | note | – – – – – – – – –
label | c58f7cf4-93b5-580e-b752-4e78789bffc6 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | e4845189-2256-5587-9029-c6ebb6d9330b |  | note | – – – – – – – – –
text | 7da7683b-e0ec-5cb4-aa79-edad0a100fa6 |  | textbox | DATE:
checkpoint-status | c9a31d02-29a4-4ff1-b997-be292c2c13f8 |  | checkpoint | 2.7 Dispose of Trees and vegetation
label | 6cfbade4-4f60-5d34-84e9-9faff42244e4 |  | note | FREQUENCY: After clearing
label | 618a3da8-65ea-5048-a79d-43d7b65c7bc6 |  | note | – – – – – – – – –
label | 21fc9df9-fd3f-5c60-8b39-3368e5947003 |  | note | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works.
label | bc629063-4cdd-568e-a102-d7f6d1cf7fe4 |  | note | • Noxious weeds shall not be mulched.
label | ec790847-bb29-508c-ac85-ce8491ebc79f |  | note | – – – – – – – – –
label | 6506ff5c-6d13-5d94-8bcb-a637506c1262 |  | note | REFERENCE DOCUMENTS: 201.07
label | 171180cd-92a1-5807-85d3-ee1e05525951 |  | note | – – – – – – – – –
label | 1e57c38d-f6e6-5826-b990-fc6431f27fc1 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | eed09962-0bab-50b9-b240-9214aecc755a |  | note | – – – – – – – – –
label | e5a56c3f-7cd9-5159-a994-7b2692a831af |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | da79d145-ddbe-59ac-a314-1d1fdc9ec87b |  | note | – – – – – – – – –
label | 4924d4d0-4411-58ee-89ec-2cbae9254a03 |  | note | IP
label | 8aa8be68-8ce1-52d0-a549-5b0c39fd286f |  | note | – – – – – – – – –
label | eae6f1bb-907a-539a-b08f-f1645b895650 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 27045c5b-5ec5-5415-86c8-120bc413ceaa |  | note | – – – – – – – – –
text | 41a58957-2fb5-5aab-b6d3-0818821dec4f |  | textbox | DATE:
checkpoint-status | c593b093-df4c-4bae-8d70-a440dedcf9dd |  | checkpoint | 2.8 Dispose of concrete, bituminous and other recyclable materials.
label | f2e1bc67-dd0f-5006-9edc-716e3bb862ba |  | note | FREQUENCY: After clearing
label | abe6ecc4-401f-5397-b41f-fdbd387f6763 |  | note | – – – – – – – – –
label | 065f4676-5fba-5b90-bc34-83da07ead8ca |  | note | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
label | 212f83b7-8fdd-57d2-be8f-56a723a1f47b |  | note | – – – – – – – – –
label | fad89740-36bd-596c-969f-2414a83a3741 |  | note | REFERENCE DOCUMENTS: 201.07
label | 895393ff-4dd7-5437-89a7-96b83dd81114 |  | note | – – – – – – – – –
label | 9e8f2b02-f9d6-58ea-ace9-af459c339595 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9b9440e3-d4bc-57e2-8e6d-74b1b6d9ab14 |  | note | – – – – – – – – –
label | 43446636-86a3-543e-9a91-c7c702ea41c6 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 048b9b23-debf-5a68-bddd-ca71fd02e2eb |  | note | – – – – – – – – –
label | 0e54203a-65b1-51c1-b029-d6caf85d6174 |  | note | IP
label | cdc3665a-f8cf-5ddf-a8c1-3d5068a4605a |  | note | – – – – – – – – –
label | d086f342-659c-56a6-95d6-bcc219e13c86 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | c2011e36-927e-5e63-a7e4-19be5f141815 |  | note | – – – – – – – – –
text | 613e1b20-d5c2-5851-a1fa-348ce5538c18 |  | textbox | DATE:
checkpoint-status | 7225dbae-6537-4eb3-95ca-e0723a277510 |  | checkpoint | Final Inspection
label | a60cb05c-cae3-5325-a94c-c4cbf755ddd4 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | fa47f71b-eb28-5f2d-8193-f13984ae029d |  | textbox | Print Name:
text | b1a1fce5-a4b3-50e5-9742-01cf394174e5 |  | textbox | Position:
text | b3f8d783-9a63-5356-8747-94d6fd38b7e0 |  | textbox | Date:
checklist-sectioned | 5dad7ec0-5a2a-44e1-8e93-4b0f83edd146 |  | checklist | ITP-002 - Feeder conduits and pits Rev2 |  |  |  |  | Yes | ITP-002 - Feeder conduits and pits Rev2 | c246bb66-3150-4c0f-8594-ee66056babe4
checkpoint-group | 8aef01c2-8302-4b66-aaa0-7cfc9e3ea3f3 |  | section | Preliminary Works
checkpoint-status | 078b9a38-5f90-4077-8609-dfd03d43bf0b |  | checkpoint | 1.1 - Check for correct documentation
label | d51dd484-9c6d-5853-b8aa-b9db28924a95 |  | note | FREQUENCY: Prior to commencing any activity
label | d9a1b59a-b349-594e-84d5-f8d76dafd64f |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
label | bd529b6a-8653-58b5-9f43-5b588c99c963 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 6dfac36e-0b0a-5f25-9daf-d74ce2720bb5 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 43c464c7-ca22-5ee3-8d5a-e8eccaf7aa1f |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 85ebb617-aae5-5c30-9e46-1fa332216229 |  | note | HP*
label | c920840b-32a8-58c2-94e3-b2da315adcfe |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 25cc67f6-8fa8-543b-ab4f-28a618b7ff52 |  | textbox | Date Completed:
checkpoint-status | 905f422e-df0e-477a-a591-6cd067bb2239 |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 27e5a31c-f489-5daa-afda-a574f4f0fc05 |  | note | FREQUENCY: Prior to commencing any activity
label | 3a037c4e-663e-5ab4-a5f0-2b809d2383b0 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | 75c43fb9-f7c8-55c6-8a40-a869e21e7cce |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 03c168b1-b530-5624-b639-2ee34ec329b0 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 1178321b-b6b1-5494-a825-d516a2740650 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | d86abb2f-af58-5e6b-9b24-9dde622bdd27 |  | note | HP*
label | 9fdf781a-7964-56b1-9b78-d02d90c81bf9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | fb4bd187-bf60-5262-aa0b-3992c55f2233 |  | textbox | Date Completed:
checkpoint-status | 0f9645e0-e9ad-40ac-87ad-b552f95a4dbd |  | checkpoint | 1.3 - Materials
label | f3233e4b-fed9-5267-b276-e798ead44f25 |  | note | FREQUENCY: Per Batch
label | 80f2cc42-40a0-5877-a6dd-f2c93f08f382 |  | note | ACCEPTANCE CRITERIA: • Electrical supply conduit to be Orange • Heavy Duty 100mm diameter UPVC •Modula Stakka pits to be used for feeder pit, entry for conduits to be cut with hole saw •All pit covers to be class D or greater and installed in accordance with manufacturer requirements.
label | 57429af1-2504-55d4-bac6-79e8c8376bf0 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4 AS 2053
label | 97ece864-7cdc-5590-972e-9fbf88d4159d |  | note | INSPECTION/TEST METHOD: Verify
label | 3aeebf58-74e5-521d-b3ed-5e5800b830a3 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 5e399b9b-85d8-52cc-8162-89589d9a1853 |  | note | HP*
label | c886d838-6476-5d54-af10-1dfb8f175886 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 23606c3b-7e04-5583-b276-e7abd00b490e |  | textbox | Date Completed:
checkpoint-group | e1b57d4d-6752-4528-9434-ff0322f14be6 |  | section | Construction Works
checkpoint-status | f26712d4-8a67-488a-bc16-4a4fb2783da5 |  | checkpoint | 2.1 - Survey set-out
label | d4621f17-83dc-5ec3-8be0-d5c5bff87a0a |  | note | FREQUENCY: As required
label | b40990ca-90d0-58aa-a302-ec08ea1b45d2 |  | note | ACCEPTANCE CRITERIA: • Work is set out in accordance with drawings. • Ensure that pits are placed as shown on drawings and shall align with overhead poles which are suitable for connection with infrastructure from pits
label | acc81278-9c82-5777-8604-6356d9730b40 |  | note | REFERENCE DOCUMENTS: Work procedure
label | 6fb1735a-c1a5-5ff6-8a23-0174678b6489 |  | note | INSPECTION/TEST METHOD: Verify
label | 47ffc079-c89c-56fc-b657-8f0446d83d78 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 51c8e4df-01c7-50a3-8b7a-1692369bd1e1 |  | note | HP*
label | aa92b1c7-6f58-5f34-b2f9-863393a3b7fd |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 3617d15f-48c3-5141-8207-8ea4ad584e80 |  | textbox | Date Completed:
checkpoint-status | 5c3b09f9-5694-4f4d-a5d8-b9d0250297f0 |  | checkpoint | 2.2 - Excavation and Trenching
label | 5195388b-b415-583d-9f8a-1075787dab9c |  | note | FREQUENCY: Prior to Installation
label | 5a3b164e-f14f-5cbd-beea-53935f060e54 |  | note | ACCEPTANCE CRITERIA: • Minimum cover for underground conduits shall be 600mm • Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track • Trench shall maintain a minimum clearance of 300mm from all existing services where possible
label | 9bfae568-b3b6-5ede-ac29-ae153a04cdce |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
label | 1381b0c0-64c8-5f2e-a2f2-89363b1de9b1 |  | note | INSPECTION/TEST METHOD: Verify
label | da1bedd7-9329-56a6-b52b-f231955e9274 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 714b1fa0-5d96-5b53-a09e-0a83e8ac4067 |  | note | WP
label | e43c850e-a56d-5c21-9858-cf22d41c80cd |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 80a407f1-269a-523f-a35e-9819efd7ac47 |  | textbox | Date Completed:
checkpoint-status | c18b7741-da4c-486f-86f1-8c9a5dbdba56 |  | checkpoint | 2.3 - Installation of Conduits and pits
label | 59f317ee-f69b-5cfb-bc33-c4ffef6a2cfb |  | note | FREQUENCY: Each Lot
label | 705c6f9c-f73f-50a5-ac7d-34f7bd058c06 |  | note | ACCEPTANCE CRITERIA: • Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
label | 7864db51-ed20-5439-9338-91188ee2452a |  | note | Conduit shall be embedded in not less than 50mm sand and covered by
label | 4644165f-7ef7-5db6-9d8e-9a53adf7c186 |  | note | >50mm - 75mm< sand
label | a5576bc8-a83d-505b-8414-82ef7b0572c1 |  | note | • Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
label | 6e519764-3a05-5565-a93a-9dd19fb666a0 |  | note | • Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
label | f5b40ae3-3e12-5116-b6c6-a18a868bc205 |  | note | • Conduits shall not be subject to construction loadings
label | f2865fcf-3759-599b-9659-fe56c93ac02b |  | note | • Pits shall be constructed as to allow for class D rated covers
label | bd1ae1a6-99fa-5aca-90b4-d6b1e3a1a053 |  | note | • Bottom of lowest conduit shall maintain a minimum 100mm above pit floor, a 50mm gap between conduits shall be maintained as they enter pit face.
label | b6079c11-5857-5d94-9a64-418cd2d23f2c |  | note | • Conduits exiting the pit as 'stub ends' shall extend a minimum of 50mm beyond the pit face and shall be fitted with a spigot end and capped with UPVC electrical caps to prevent contamination to internal surface.
label | 79ad57fe-6052-5d9a-9d54-404aea514051 |  | note | • Conduits shall be placed a minimum of 100mm above pit floor
label | b40bd866-6d16-55b4-b9a2-2cdc30d2a02e |  | note | • Conduits installed for future connections shall be installed to the track Margin
label | a25b6ab1-4553-5bf2-bc83-c1d11185d972 |  | note | • 100mm of concrete around and under pit lid
label | 5a7e9c26-2e6f-5fb1-a867-9fc91beb85da |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
label | bdb991ef-92df-5cb4-9ce1-dbefe7bf031e |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 96907488-a721-5a3a-895f-997e61564d9e |  | note | RECORD OF CONFORMITY: This ITP signed
label | 367ef7dc-f8b3-5821-ba9c-fbb3220785b9 |  | note | WP
label | 37a4b8a1-58f1-5d4a-a021-f7f441232491 |  | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
text | fb223460-d9b5-5582-8acb-d579847aed2f |  | textbox | Date Completed:
checkpoint-status | b3f383df-aa05-4b2b-bdf2-c9e47e93b19b |  | checkpoint | 2.4 - Inspection of conduit installation
label | 7eeea24d-5f10-5a2f-88e0-e4243a7d1a4e |  | note | FREQUENCY: Each Lot
label | 5ce68162-4e36-5a8a-9d69-580608fcd6b7 |  | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
label | a2976cf9-6bda-5f2e-a37a-15104961d302 |  | note | REFERENCE DOCUMENTS: Work procedure
label | 32abdd24-8ce1-5851-b2eb-3856299d993f |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 44823288-e7af-5497-9420-7619cf4a1a62 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | fdef59a4-c710-593d-999b-fe39b7f05707 |  | note | *HP
label | 2c5acbe8-ace8-571b-875a-9289025cc9ea |  | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
text | 5d3d0e3c-6c18-52c5-9471-3ea1a2cfe6ef |  | textbox | Date Completed:
checkpoint-status | 56aa524c-0e02-4ee9-83ee-20cac1859af8 |  | checkpoint | 2.5 - Backfill of Trenches
label | ec1541c4-c2a8-5294-950d-ca3d8a447c7b |  | note | FREQUENCY: Each Lot
label | d386fbc1-cc06-5bff-bac5-f52649917a27 |  | note | ACCEPTANCE CRITERIA: • Backfilling (Only to be used for road crossing trenches) - conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction
label | 734bf98c-f71d-5686-8029-66df36e4e2ed |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
label | 21afa69d-217f-5a08-89d4-53415482fdc2 |  | note | INSPECTION/TEST METHOD: Verify
label | d7d35586-77a0-5504-bc20-b4e3132a5367 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 4256365c-84e6-5a58-99cc-e94700b7972e |  | note | WP
label | fa636460-20bf-5746-8f95-25840d46ba5b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 59b9d26d-1034-50e0-a21f-399cc1d329be |  | textbox | Date Completed:
checkpoint-status | 1350a87e-99e1-4b8e-99f2-a961540213d4 |  | checkpoint | 2.6 - Installation of Draw Cords
label | e4264c8c-2c06-5553-b9f0-4e0deb2ed7ec |  | note | FREQUENCY: Each Lot
label | 92764ba0-38df-5353-9b65-62d03a243064 |  | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit. Material shall be 6mm 'telstra rope'
label | 39d907d1-de65-5bca-80f4-4e37faff9aa1 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
label | 6d7a2af3-0330-5af2-86de-98656a29f440 |  | note | INSPECTION/TEST METHOD: Verify
label | 71fdc941-35c3-585c-9ea8-68253dd4656f |  | note | RECORD OF CONFORMITY: This ITP signed
label | cd070514-a63e-5273-8452-f565b2eec374 |  | note | WP
label | 8d3e36bb-f303-5fa3-ba8b-90b24c065af5 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | c35af4aa-28b5-52da-92aa-2870d0b3f634 |  | textbox | Date Completed:
checkpoint-status | c97c5d79-e370-46bb-9b2f-1f2df001dcc0 |  | checkpoint | 2.7 - Compaction
label | 79ec26a0-8d61-5b17-bce7-5f0b49dd4e88 |  | note | FREQUENCY: Each Lot
label | 4cbb1931-060b-5e0d-8153-28848408f7e4 |  | note | ACCEPTANCE CRITERIA: • Bedding and backfill material to be compacted using mechanical plant During compaction optimum moisture content of bedding and select fill is within 85% to 115%
label | 8ccd19af-2f12-56fc-bd46-34f0b00bc6c7 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
label | bebcea1d-c15a-524d-93c3-1dc3e4068bff |  | note | INSPECTION/TEST METHOD: Verify
label | 7b629d97-6a0e-5eeb-aac0-064529a370c4 |  | note | RECORD OF CONFORMITY: This ITP signed
label | f643d678-fd04-581a-ad48-f84f8486438e |  | note | IP
label | 3f92c428-d6c8-58db-9470-dfbc2e44184c |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | e83d6940-d37c-5b8c-883f-27df6430c8bf |  | textbox | Date Completed:
checkpoint-status | c4f33e45-de55-44a6-8c32-6d0b8e912850 |  | checkpoint | 2.8 - Feeder Pits & Pit Lids
label | 2eff92ae-1e2c-532b-9a12-f14a64a3a23e |  | note | FREQUENCY: Each Lot
label | 3b4a4b01-a703-578f-8e3e-70e839873e57 |  | note | ACCEPTANCE CRITERIA: • Feeder Pits constructed and installed as per drawings
label | 0943805a-59b5-52e5-b08d-4e0fa3be7a95 |  | note | • All conduit connections to cable pits shall be neatly made and ends of conduit trimmed off and the area between the conduit and pit wall stopped with cement mortar
label | 9378cceb-3f25-5740-92e6-db4e73c9a47f |  | note | • Pits shall be constructed such that the level of the top of the pit lid matches surrounding finished surface level, top of pit wall is finished so that lid fits without movement
label | 420676b4-90f8-5ecf-a24f-5ad57d6714ef |  | note | • Gatic pit lids shall be filled with structural grade concrete.
label | e8b57501-98d0-58be-9f08-13586c50f3d4 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.7
label | 38888b6f-ed35-5855-af46-c722d56f4597 |  | note | INSPECTION/TEST METHOD: Verify
label | bb5f0b9a-82f9-5207-8af1-c60b85e7e64c |  | note | RECORD OF CONFORMITY: This ITP signed
label | 7e6e3025-7f8d-58fc-b14a-e6b911d3b4f0 |  | note | WP
label | 448a0cdd-d744-5cd2-bd05-b5e342ac6fb9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 8f616542-944d-57fd-88a8-6e5f13899074 |  | textbox | Date Completed:
checkpoint-status | b5b069e0-627c-4ece-bb90-ffd38e39ca68 |  | checkpoint | Final Inspection
label | c830c928-6a42-50e5-bf4f-a3ad780a3359 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 3d46f1f4-facf-568e-8c10-8ac93b238201 |  | textbox | Print Name:
text | 705c52d1-f37a-5f5d-8226-cc38137ef254 |  | textbox | Position:
text | 92527a12-74dd-58d9-bad4-efeb991d8dd5 |  | textbox | Date:
checklist-sectioned | b314e121-8c94-48c9-bbe8-c6f019a8f561 |  | checklist | ITP-001 - Subgrade Preparation Rev2 |  |  |  |  | Yes | ITP-001 - Subgrade Preparation Rev2 | c5c9a695-d5fb-4302-ab6e-f4bd34fdce9d
checkpoint-group | 92735ee7-00d4-4047-b531-1157dd1ffab2 |  | section | Preliminary Works
checkpoint-status | 8aa120f7-5d64-41d8-a81c-d1dee6f35f05 |  | checkpoint | 1.1 - Check for correct documentation
label | 45188c88-c52b-57af-b3b7-03ffb2fa8f30 |  | note | FREQUENCY: Prior to commencing any activity
label | 55e0b00f-b175-5332-9d35-8d2ea8fd0fda |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
label | 43ba18bb-5e67-5b1d-a0d6-f4dfd23fa27d |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | cae04579-468a-5bb0-bcbb-188f602e5329 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 15d4dbc5-9fd7-5653-89ab-df14a395fcae |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 44705a3e-a804-5ef6-bd00-c3a1b5801b76 |  | note | WP
label | 77cc26f7-3555-5973-83aa-3e09b928ae51 |  | note | RESPONSIBILITY: Fulton Hogan
text | b0ce8c95-decf-5071-bb9c-7112e16c0c02 |  | textbox | Date Completed:
checkpoint-status | c1deca52-bf51-465b-a0ca-c6f0eaa74d09 |  | checkpoint | 1.2 - Implementation of all measures and controls
label | bba017b4-8f81-5c61-8c44-f5d8cb094182 |  | note | FREQUENCY: Prior to commencing any activity
label | 9120371d-d575-5d35-babf-69ea8bded992 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | aa908750-6bad-52a7-b547-cbbaf48c1487 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | b5e9cb4f-3b12-5054-a26b-6a13f91dfa58 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 874839a3-bf07-5f70-aee1-bd340fd598a7 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 88e4c18a-b299-5358-b7b1-f0d3ddf5adc1 |  | note | WP
label | 87f0a977-25a9-5acb-b28a-466cc1433823 |  | note | RESPONSIBILITY: Fulton Hogan
text | 751321f2-27c7-51ae-9c8f-a44d48accc4c |  | textbox | Date Completed:
checkpoint-status | 7e640079-d376-4885-9402-3fa9ad0544c7 |  | checkpoint | 1.3 - Selection and approval of Disposal Site
label | 9cb26a5b-8903-5b22-9685-09c730343609 |  | note | FREQUENCY: Prior to commencing any activity
label | 67c61ce2-8eac-5a1a-9265-4122e349bae2 |  | note | ACCEPTANCE CRITERIA: Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements & in accordance with Yarra Trams site classification report. It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the Authorities controlling disposal of material at that location.
label | 5ed4e0c4-0358-592c-ab96-6b7db0e4f962 |  | note | REFERENCE DOCUMENTS: Site Classification Report, CE-019- ST-0033 CL. 4.2.1.5.
label | a91157d9-da51-5096-b8d9-f25d2a95b07d |  | note | INSPECTION/TEST METHOD: Verify
label | 840d1327-464c-5e0f-bf9c-0b174666cae7 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | b1d0dc7a-d5d3-58a7-bcb8-10f370d9d38b |  | note | WP
label | 53c3aeff-b9eb-552f-9fa7-fa7614d171b2 |  | note | RESPONSIBILITY: Fulton Hogan
text | 416f0ccd-cc2e-5d38-b3bc-6ec260c9f0b7 |  | textbox | Date Completed:
checkpoint-group | 4dd63ab3-dd6b-4529-9b9b-dd6f5f3c7794 |  | section | Construction Works
checkpoint-status | a0b41a9b-f81b-4ed8-b6cd-3dbd76ae77bd |  | checkpoint | 2.1 - Excavation
label | 5dafd1cc-eb05-5463-a582-b13de1af5907 |  | note | FREQUENCY: Each lot
label | a338bb55-9b70-51b0-ad00-da39de2e595f |  | note | ACCEPTANCE CRITERIA: Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of works
label | bf0d3fa9-f92b-5dd5-8c6e-ff8e54386b6f |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3. , 4.2.4. Subgrade Preparation Work Procedure
label | bc767fb1-3969-50a2-b592-64172ca170ea |  | note | INSPECTION/TEST METHOD: Verify
label | 77f22b39-80c6-532b-8add-3c3a0073877d |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 3240cc15-9d09-54aa-86f3-87a34ff7ba81 |  | note | IP
label | 2bf90b48-ba07-57d7-9dfb-23536a96f782 |  | note | RESPONSIBILITY: Fulton Hogan
text | 6da904e9-ee0a-5b76-ac22-f75341946855 |  | textbox | Date Completed:
checkpoint-status | 0207bb47-3385-4a28-a899-6f3a63f201ee |  | checkpoint | 2.2 - Reinstatement of bonds
label | 96e709ff-698e-5f3e-8024-5af4d199a873 |  | note | FREQUENCY:
label | d84ba202-6a80-507e-ac30-7e6e715dda43 |  | note | ACCEPTANCE CRITERIA: Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables. All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
label | eb176fda-5b9a-522e-9824-b0cb052f5bf5 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.4.1.
label | 212381da-8a54-561b-8012-27623ff5f5c4 |  | note | INSPECTION/TEST METHOD: Verify
label | 3d6cd25a-a502-53c7-acbd-84fb464c4175 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 9fe48eaf-dfd2-53d4-a56c-5787003855b0 |  | note | IP
label | 6e521760-12a5-566c-a298-7e6113cd9f22 |  | note | RESPONSIBILITY: Fulton Hogan
text | a4d2f4b7-c5d2-53f8-a65e-e823ddfab736 |  | textbox | Date Completed:
checkpoint-status | 616761f3-455c-4949-85c9-645e8d1dfd16 |  | checkpoint | 2.3 - Inspection of Subgrade Material
label | 576eb2d8-a672-5a4f-9081-312eb8e5fc3e |  | note | FREQUENCY: Each lot
label | 2d2796c2-c1ed-5a62-aa52-9ce2626eda06 |  | note | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the Standard.
label | 047d2ad4-f790-5158-a697-a0cb0123e5f7 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
label | 35a3a40a-bd2d-5df2-bd64-6fe6802f96d8 |  | note | INSPECTION/TEST METHOD: Verify
label | 3a007820-922f-57b9-9070-a9892866b1a2 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 8e7fff5c-a388-5e73-af58-37279c679e42 |  | note | HP
label | c2abe582-1979-5c5d-984d-f454996ca911 |  | note | RESPONSIBILITY: Fulton Hogan Engineer & Yarra Trams Superintendent
text | b56f1584-fd36-5878-940d-7f33e1d23eaa |  | textbox | Date Completed:
holdpoint | 67fb1652-94c5-4358-922a-2618c31553a4 |  | signoff | Authority holdpoint
checkpoint-status | bcd29c89-3f91-4435-87a7-bc7878d471e7 |  | checkpoint | 2.4 - Width and Level conformity
label | 4e71c4f6-a39e-5344-945d-99f2452efa35 |  | note | FREQUENCY: Each Lot
label | 752dc8fe-1994-5dc5-9516-3f518929d091 |  | note | ACCEPTANCE CRITERIA: The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings. No point in the general surface shall vary more than 12mm from a 3m straight edge. Finished formation widths shall not vary more than - 0 mm, + 50mm from dimensions shown on the Drawings
label | 659f292c-4e11-58f6-87c5-625d56098bea |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
label | d306a058-1fa8-5b7d-aa90-2f7a27fc7a14 |  | note | INSPECTION/TEST METHOD: Survey Report
label | 2552991b-495c-57e1-a371-4ca5a52bd262 |  | note | RECORD OF CONFORMITY: Survey Record
label | 54cc9d94-6e86-534f-89ee-f5d16efaacba |  | note | IP
label | fccf15a3-d2b7-5ff9-972c-d9dda69557f8 |  | note | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
text | 442e49be-7cbb-532c-b42d-621f0ccc41c3 |  | textbox | Date Completed:
checkpoint-status | 50d8f268-73e5-4b7f-ac48-71a44a9a7497 |  | checkpoint | Final Inspection
label | 75654e3b-f502-5dbd-af74-d2dc98ede34a |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | a69e878b-32cf-5909-b04e-d062802050ec |  | textbox | Print Name:
text | 36759aa4-7b2a-5d81-8b7c-d0fcc420108b |  | textbox | Position:
text | a1625a23-a2b3-58ac-a423-4d707d7d2454 |  | textbox | Date:
checklist-sectioned | 47906b50-33c5-4d76-a8c1-d5539885dce7 |  | checklist | ITP-003 - Electrical and Communication Conduit Rev2 |  |  |  |  | Yes | ITP-003 - Electrical and Communication Conduit Rev2 | d28f2450-748b-4848-9c99-d960ce312d30
checkpoint-group | 31176222-5868-42a6-bb6f-70b3fa7bc207 |  | section | Preliminary Works
checkpoint-status | c4076e9f-5b28-437a-aa27-ae85b621c52f |  | checkpoint | 1.1 - Check for correct documentation
label | f37cf723-2f76-53d9-94e9-2e96fff13d88 |  | note | FREQUENCY: Prior to commencing any activity
label | ae645317-a5ad-589f-905a-71c064836b2a |  | note | ACCEPTANCE CRITERIA: Employees and subcontractors shall be issued with the most current and complete construction drawings
label | a50bafcc-8b88-5fe0-afe0-a620d24bb08a |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 74d178c9-73e1-5003-8b2b-93943c629d79 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | a068f500-591b-5867-853b-ad3090b869f6 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | b37978f2-6fa2-53cb-abd9-d5776574be22 |  | note | HP*
label | 82064103-dee7-567e-85ea-c82a8b233bff |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | da404d0c-65f9-5333-ba6a-b33234c60693 |  | textbox | Date Completed:
checkpoint-status | 69c305eb-d475-4543-9b12-45328c843a66 |  | checkpoint | 1.2 - Implementation of all measures and controls
label | ae913ecc-9439-5ad4-9a0a-027f004c3416 |  | note | FREQUENCY: Prior to commencing any activity
label | 8574ffb5-8b67-5cf0-8efb-268d21f481ad |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | aa8c78e1-e348-5e3a-a8fd-6db13c054eb1 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | bd534ec6-fa6c-5d01-8507-9a37bba98e63 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c39abd1a-9de1-5533-84ff-a29f3e6277c4 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 937796af-5546-5fbe-92ed-09ffc2513c2d |  | note | HP*
label | b22b05e2-8a17-5fcf-90b3-99535c764dd8 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | a0cb0867-664b-5a56-8dcb-926d53c9c6d8 |  | textbox | Date Completed:
checkpoint-status | 9eb92c43-4630-4ea5-ae2b-f7e214a055db |  | checkpoint | 1.3 - Materials
label | dc176250-0282-5527-af6b-0055d60ed351 |  | note | FREQUENCY: Per Batch
label | b1913a11-7022-5da0-a291-1f77b0f15742 |  | note | ACCEPTANCE CRITERIA: • Electrical supply conduit to be Orange and rigid HD UPVC of sizes as required. • Communications conduit to be White and rigid UPVC of either 32 or 50mm size or larger as required.
label | 5928abd0-863d-583e-bc69-3ca4dd91da16 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.1 AS 2053
label | 6e77ad37-ef14-5bac-9031-5e1f7dfd7b6f |  | note | INSPECTION/TEST METHOD: Verify
label | 911b61fd-3340-58ac-8390-b7b975cab988 |  | note | RECORD OF CONFORMITY: This ITP signed
label | e12ca152-124e-5c61-883f-228b0edfbaab |  | note | HP*
label | 080f4a39-e2ab-517e-9775-b1bc89c2285d |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 013729c2-7255-56a0-a988-f7273795f1fb |  | textbox | Date Completed:
checkpoint-group | 8f8dad74-0b7f-4230-92a1-d59f9f1bc4d2 |  | section | Construction Works
checkpoint-status | 159bdd7b-b662-4a7a-a299-3a4c728efc71 |  | checkpoint | 2.1 - Survey set-out
label | 60d591cb-05a7-5cf2-9f0d-64252dccf918 |  | note | FREQUENCY: As required
label | b2c92a45-2d8a-507a-83dc-4a62bbe33d6b |  | note | ACCEPTANCE CRITERIA: • Work is set out in accordance with drawings.
label | b80e7a36-72f3-5606-9cb0-99534f07df78 |  | note | REFERENCE DOCUMENTS: Work procedure
label | dae80f44-de96-5808-b6bc-3caa90fb1eb2 |  | note | INSPECTION/TEST METHOD: Verify
label | 799ab4c8-6484-51b5-aed3-dc59e36e9198 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 6adaf214-c4a7-5836-9915-aa873f33cb9b |  | note | HP*
label | cbf7c7fe-53a3-53e7-b632-1f3e4c968129 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | c00cf6e3-28c4-51b9-bcf4-5653a40fe34b |  | textbox | Date Completed:
checkpoint-status | 507a3076-d057-42e7-b6a2-f1193eaf3dd5 |  | checkpoint | 2.2 - Excavation and Trenching
label | 35447bc8-77dc-5774-8394-590bc5ad78f6 |  | note | FREQUENCY: Prior to Installation
label | b56623b1-ce6f-5d67-bf05-87746c51be9e |  | note | ACCEPTANCE CRITERIA: • Minimum cover for underground conduits shall be 600mm • Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track • Trench shall maintain a minimum clearance of 300mm from all existing services where possible
label | 84d38c2b-edeb-5fb7-8ee2-b6adf38a1050 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
label | ee7ce9e2-79e2-58f3-9dad-5135a2b0f85f |  | note | INSPECTION/TEST METHOD: Verify
label | 23afe5bd-1722-533a-84f4-4beeb3fe80e4 |  | note | RECORD OF CONFORMITY: This ITP signed
label | ae99b891-6b48-5254-afda-942081f0bf53 |  | note | WP
label | e76fe0b8-541f-5d1a-8f0a-8ec87117c0fd |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 7f3920c8-7c54-5e4a-b6d9-1a21c5ea977e |  | textbox | Date Completed:
checkpoint-status | a2e74203-22e8-4fad-a248-ebbefc8fce75 |  | checkpoint | 2.3 - Installation of Conduits and pits
label | b40e944e-dfc4-530e-8b33-02f0e89515d4 |  | note | FREQUENCY: Each Lot
label | d9043b88-a333-5e2f-b1d9-b7774872441e |  | note | ACCEPTANCE CRITERIA: • Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
label | a7d158d7-6b4d-585d-9ea6-cd77a1c454f2 |  | note | Conduit shall be embedded in not less than 50mm sand and covered by
label | cd52ca9e-13ac-507b-8ea9-1bf86352807c |  | note | >50mm - 75mm< sand
label | 023cd43d-5c8e-51fc-b26e-36c8f6cb33d2 |  | note | • Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
label | 6d837a21-8ea3-5e12-be7e-c63b46deed3b |  | note | • Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
label | ab1979e5-c80c-5c01-bd97-4ae0e9ba776c |  | note | • Conduits shall not be subject to construction loadings
label | f5afc207-2756-5e47-bf7f-08f577e10c7e |  | note | • Bottom of lowest conduit shall maintain a minimum 100mm above pit floor
label | dcf0571d-1608-5677-8491-bb35d544fd70 |  | note | • Conduits shall be capped with UPVC electrical caps
label | 81847ff6-2342-5bbb-ab13-7b7ba57d21a2 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
label | 0b03f992-28dc-508b-b642-98740e54a9e5 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 4972551c-b706-512a-a01e-f5d680e7d8cf |  | note | RECORD OF CONFORMITY: This ITP signed
label | ce55d0e6-3eda-5d45-a9b9-8d1583abf411 |  | note | WP
label | 8c4e53d4-4f65-5b9d-b012-356dc59f8e7c |  | note | RESPONSIBILITY: Fulton Hogan Engineer/ YT
text | 385fa5e9-e597-5960-bc0c-8b25cceb837d |  | textbox | Date Completed:
checkpoint-status | 1ac0b196-096a-4e8f-99cb-89e32ff4e5ff |  | checkpoint | 2.4 - Inspection of conduit installation
label | bdaa746e-a432-51ab-a931-840fc43f6791 |  | note | FREQUENCY: Each Lot
label | 69d453be-573c-598d-845e-95b7efaad486 |  | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
label | 3edd8ea6-d590-5bfc-952d-242663fb550c |  | note | REFERENCE DOCUMENTS: Work procedure
label | f8f08e89-f712-56da-849e-28563f6fb8e8 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9c654764-ecca-5323-8240-2b169b3ab393 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 66a072a3-6977-5c71-9e5e-ad9624d525ff |  | note | *HP
label | abfd7e95-0bf6-5027-a6f4-c83f14e18476 |  | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
text | 35494e49-1d21-5a9a-9a17-37272c298f28 |  | textbox | Date Completed:
checkpoint-status | fb1d7401-50d1-414a-b0f7-3ee86dd4e8ec |  | checkpoint | 2.5 - Backfill of Trenches
label | db9899f3-a206-55d3-9e9b-071958316181 |  | note | FREQUENCY: Each Lot
label | eca85508-0a4a-5cce-983d-729edd60ad9b |  | note | ACCEPTANCE CRITERIA: • Backfilling (for trenching or road crossings) - conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction using handheld mechanical plant
label | 64016342-46c1-5f7d-a686-34e7563db3a8 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
label | 66ab2d74-64e6-5164-9ee1-9f4973ea3b47 |  | note | INSPECTION/TEST METHOD: Verify
label | 0d91d238-b4ce-5903-bce2-c7c44f2f19de |  | note | RECORD OF CONFORMITY: This ITP signed
label | eee7953d-a751-5398-80bd-c400383657fd |  | note | IP
label | d243be8e-4e36-5cc7-848b-e056fdfcaefe |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | cb574033-cbc4-5a9c-ad03-71a398cf2618 |  | textbox | Date Completed:
checkpoint-status | dadde7ac-36de-4ff7-8e37-74bf8d880fd4 |  | checkpoint | 2.6 - Installation of Draw Cords
label | 3656be04-ed75-5de1-91b1-a734d9bdde60 |  | note | FREQUENCY: Each Lot
label | 5b6e178a-9419-56f6-a88c-6d3e3d309614 |  | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit, material to be used shall be 6mm 'telstra rope'
label | 97ef5f82-d9b8-582c-9600-70b4f8fd90fd |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
label | 93007efc-86a5-5a3e-9d28-c7e23bc4cae1 |  | note | INSPECTION/TEST METHOD: Verify
label | cd8e3906-b84c-565b-b574-0a0d761e2f8e |  | note | RECORD OF CONFORMITY: This ITP signed
label | 8452fc5c-cd0c-5ec9-bee0-22ad94954821 |  | note | IP
label | 777b7c52-4da8-56ff-908c-79a98ff1d2e4 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ffe26cc6-1bd4-542e-b7fe-6c8d804154b6 |  | textbox | Date Completed:
checkpoint-status | 38a5c65a-99d4-4a15-b1ba-20091fa98c60 |  | checkpoint | 2.7 - Compaction
label | d26efa9a-710c-580a-a6e0-1381a2b1ed36 |  | note | FREQUENCY: Each Lot
label | f199c0c6-7ddd-5f98-84ff-3acc41d92a08 |  | note | ACCEPTANCE CRITERIA: During compaction optimum moisture content of bedding and select fill is within 85% to 115% as provided by suppliers
label | 0e7898a2-ba62-5def-b2c7-0b567f51f71d |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
label | 241c05f9-45af-5382-9ac5-552c469484b3 |  | note | INSPECTION/TEST METHOD: Verify
label | 7f6171fa-4efd-5595-9f2d-82095df6d6f2 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 43a0280e-d7bf-57c3-b278-537d3bdfe116 |  | note | HP*
label | bb277407-16c6-578f-96d2-607e81a90df8 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 0c9d4779-cf39-5a1e-a6ba-f2a69a952eba |  | textbox | Date Completed:
checkpoint-status | 71feae13-4c38-4bef-ba49-95dfcf092fba |  | checkpoint | Final Inspection
label | 4f331889-36c4-5a9e-bc2f-7a66ecd1d5af |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 18d00a23-909a-5255-846d-69678ec738a3 |  | textbox | Print Name:
text | f726574b-0634-56b8-b804-75d6385ae977 |  | textbox | Position:
text | 4bfa6c5e-99c8-5d4c-8cd3-dacd49324069 |  | textbox | Date:
checklist-sectioned | 6fb24073-4612-4e53-8bc1-d451785fe85e |  | checklist | FHC-ITP-009 - Profiling Rev1 | itp |  |  |  | Yes | FHC-ITP-009 - Profiling Rev1 | e5d0165e-3044-4b97-89cd-04699cbba583
checkpoint-group | 69f0293d-4635-46f1-8bcd-b93e795a0081 |  | section | 1 - Preliminary Works
checkpoint-status | f9462b4b-0c95-4003-b344-278d8cc6284a |  | checkpoint | 1.1 Check for correct documentation
label | 330e73e9-3a0a-50ff-858c-91fe2bee6161 |  | note | FREQUENCY: Prior to commencing any activity
label | 436a1692-04d7-514b-aa97-f748641d3dd5 |  | note | – – – – – – – – –
label | a674625f-1804-584b-81b1-e535203d77c3 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 7c9e3791-1683-5b53-a7eb-83f186e7ba13 |  | note | – using the correct and complete set of drawings
label | 1979f499-a2aa-5f44-992c-16b86bfc22bc |  | note | – all drawings are the latest revision
label | a7047f78-a862-55c4-9367-686c83872a10 |  | note | – – – – – – – – –
label | 4c3503d9-e137-5521-8477-f3a84e0a0541 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 2782aec6-348b-5982-b8d6-e9194016748d |  | note | – – – – – – – – –
label | d2678a9e-092e-5a54-b586-013b9df9d148 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | eed79a5e-b7b0-5510-9469-6f800aa581f2 |  | note | – – – – – – – – –
label | b3f175bf-4246-545c-94e5-d5c6aa772289 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 8c5652af-818b-5997-abfe-259ec6e1d6fc |  | note | – – – – – – – – –
label | 689c0d58-134c-510a-92e3-219fce98e990 |  | note | HP*
label | da354b42-c5d2-5cc5-9d87-71a5ebf1709d |  | note | – – – – – – – – –
label | f8c18ddb-4cee-56ee-a5cc-be7d8ef4d949 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 50acbc34-65a2-5982-9895-9e62d6c3261a |  | note | – – – – – – – – –
text | db13739a-5f85-5f87-8a51-15071c2274d2 |  | textbox | DATE:
checkpoint-status | 6688f0da-5bc8-4378-b2aa-45fd4bda636b |  | checkpoint | 1.2 Implementation of all measures and controls
label | fd492931-8b69-5702-bb10-b6d3f1f9ff9f |  | note | FREQUENCY: Prior to commencing any activity
label | 43c62598-86ca-5b36-af4b-0ac1546fa700 |  | note | – – – – – – – – –
label | 2c953f87-ed6a-5589-bfdc-5b7b0b7d54a1 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 37a2b6d3-c77f-5670-a0aa-be21cc4d74e1 |  | note | – – – – – – – – –
label | 65b1cc13-2b72-5932-8ff8-11331e2d3115 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | bafe42c4-42e0-5c43-81bd-f7c6bbd2c5e6 |  | note | – – – – – – – – –
label | 7dcbf39d-4583-5078-bf75-aea6278732ee |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f44bd40c-d8f9-5d9d-a3c6-2824a2a43691 |  | note | – – – – – – – – –
label | 38a2886d-a5ee-5507-8c5e-9603771ca57a |  | note | RECORD OF CONFORMITY: This ITP signed
label | 68d113d1-6714-51b5-af9d-69a76dccb495 |  | note | – – – – – – – – –
label | 8424fa29-2e3b-5cb1-84ce-d73ed94d7e0b |  | note | HP*
label | f5c82f50-2d4c-5770-aec5-24d70a336dd3 |  | note | – – – – – – – – –
label | d51793c1-e4c0-5c61-91ff-ad596c823e92 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 1aab2079-fb1f-5b0a-8b4e-dadfade1b441 |  | note | – – – – – – – – –
text | 6e0fb8be-b955-5d8e-a28a-85459f78fd1a |  | textbox | DATE:
checkpoint-group | 85a8660c-2a3d-4dae-955f-21cbcb909db5 |  | section | 2 - Construction Works
checkpoint-status | 4796cf22-ed2e-479b-8402-8be986da596b |  | checkpoint | 2.1 Profiling Works
label | 1099a73f-f8df-5a38-b456-af924cb9adbd |  | note | FREQUENCY: Each lot
label | eba0cee0-e7d0-5506-a953-a07d6b08be97 |  | note | – – – – – – – – –
label | 6c9d8c5d-9bb8-56d7-bf59-1686505aab9c |  | note | ACCEPTANCE CRITERIA: Cold planing shall be carried out in a manner such that a uniform surface is present on a plane parallel with the ultimate finished surface of the pavement
label | 858d2199-b576-502f-86b9-c025b58b442a |  | note | – – – – – – – – –
label | 51e73baf-4958-5d4c-a603-e5a2a92ba936 |  | note | REFERENCE DOCUMENTS: 402.02
label | d82fd3fc-1446-56fa-b540-8829ee591de1 |  | note | – – – – – – – – –
label | 03a36cac-941a-50dd-9233-843217778010 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9db6c544-741b-5b70-b096-d01eeb360802 |  | note | – – – – – – – – –
label | 55237a5a-a01f-5f2a-9590-e498f3b1588d |  | note | RECORD OF CONFORMITY: This ITP signed
label | 24d3cefc-3a5d-51b1-97b4-4064bf1bc704 |  | note | – – – – – – – – –
label | acf8bc04-837c-59dd-9974-62e065c22628 |  | note | WP
label | 0f631d12-de5d-5562-9fa2-e1ebd7459390 |  | note | – – – – – – – – –
label | cc6c07ec-fc6e-5def-b383-399fb119d95d |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
label | b0a12475-9c04-52c3-852b-ec3a1bc37242 |  | note | – – – – – – – – –
text | fcced668-bedd-5aab-be64-dd48b3cd6f59 |  | textbox | DATE:
checkpoint-status | 08cc5710-5798-4737-a485-566410dbcd6b |  | checkpoint | 2.2 Depth check
label | db73131a-0be9-5764-9b28-ebf5f40e02de |  | note | FREQUENCY: Each lot
label | 1d449daa-13fb-5891-a95e-85e3c4d6dcdf |  | note | – – – – – – – – –
label | d33f41aa-2c5f-52d2-8927-a9b8f5742cac |  | note | ACCEPTANCE CRITERIA: Average depth of pavement to be removed shall be 40mm ensuring that all Wearing Course is removed.
label | b54af1ee-b7b9-56c4-96c4-5a4346687e81 |  | note | • After planing, no point on the planed surface shall be positioned more than 15 mm below a 3 m straightedge placed on the planed surface in any direction.
label | 947d74c8-86e6-5ac0-96a5-de021771c5dc |  | note | – – – – – – – – –
label | 7f3e3edd-d3bd-58b0-8e3d-fbd3cb058fb8 |  | note | REFERENCE DOCUMENTS: 402.02
label | 5cab79fa-8bf8-5d0a-a342-44a9ae256175 |  | note | – – – – – – – – –
label | c1d316b9-ebaf-5e6b-b6c1-454904832541 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 78316e38-f1e4-5d20-bb30-1d1f46f92978 |  | note | – – – – – – – – –
label | c889a62b-d843-5458-857b-78445d87db74 |  | note | RECORD OF CONFORMITY: This ITP signed
label | ba7cece8-da6d-51db-8c46-49627d2b7762 |  | note | – – – – – – – – –
label | e6e23a33-4516-569c-ba72-078b17a3e2eb |  | note | WP
label | 3b6c6ef7-500c-568f-8fef-b837cd5ec4e4 |  | note | – – – – – – – – –
label | ab6ab7c4-9d09-5e5b-9fc0-3d280795ac92 |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
label | 56d609fc-71c6-5bb0-a008-839e2e0fa4da |  | note | – – – – – – – – –
text | 2aaac270-526b-587a-9f17-bf3dc64525db |  | textbox | DATE:
checkpoint-status | 87c5738b-b219-4759-8f8e-8ba2a88535d9 |  | checkpoint | 2.3 Temporary ramping (longitudinal)
label | 95f9611a-2744-58e2-8751-5cea3490aeb8 |  | note | FREQUENCY: Longitudinal edges
label | 1b02d0c6-0376-5f01-a096-807c5d502735 |  | note | – – – – – – – – –
label | 126efb32-049a-54cf-a7fa-25ceb8cd99f6 |  | note | ACCEPTANCE CRITERIA: Any exposed longitudinal edges within the trafficked area shall be ramped down at a slope no steeper than 5 horizontal to 1 vertical.
label | 27ad8924-5830-5eb1-a8f6-b81a6a7c2ee4 |  | note | – – – – – – – – –
label | 183faba7-98d5-5681-ae9b-11d8b912a4df |  | note | REFERENCE DOCUMENTS: 402.05
label | 28911900-541a-52c8-9345-ca1f93526f81 |  | note | – – – – – – – – –
label | 8ca7c42a-678c-5826-b78a-5935d46f3a1d |  | note | INSPECTION/TEST METHOD: Verify
label | 3275999c-b207-5b94-8db7-4386c1871565 |  | note | – – – – – – – – –
label | d45150d0-3fd0-5c02-9989-ace3f297c87c |  | note | RECORD OF CONFORMITY: This ITP signed
label | f044c9f0-33b6-5e74-836f-677b035f0108 |  | note | – – – – – – – – –
label | dde62919-9e4b-517d-815e-a75689870931 |  | note | WP
label | a36f7cbf-b241-5396-be5a-1355b16c8575 |  | note | – – – – – – – – –
label | 862610d9-fcca-5856-bbb3-db31c453d37c |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
label | 82ac1268-8993-5f39-b71e-7c53384916c8 |  | note | – – – – – – – – –
text | 65ba2c93-b804-5988-8231-614cecfff502 |  | textbox | DATE:
checkpoint-status | d22bc193-13ab-4c4c-832e-993b0272dbe1 |  | checkpoint | 2.4 Temporary ramping (transverse)
label | b6fc80eb-2dd5-5c31-8d5c-5ee490c71c99 |  | note | FREQUENCY: Transverse Edges
label | bd35881b-db54-5eb9-bbda-a08734fb57d1 |  | note | – – – – – – – – –
label | cd53f918-c4d1-5545-bc73-53d50152dd0a |  | note | ACCEPTANCE CRITERIA: Temporary ramping shall not be steeper than 20 horizontal to 1 vertical for traffic speeds of more than 75 km/h or 10 horizontal to 1 vertical for traffic speeds of 75 km/h or less
label | 0d1810fa-6109-546a-8c7e-0f32c92d8dcc |  | note | – – – – – – – – –
label | 6df580de-3b43-55d8-8b39-5cc266ab6211 |  | note | REFERENCE DOCUMENTS: 402.05
label | f2adb7ba-2103-5c0e-849d-8e1159deeda8 |  | note | – – – – – – – – –
label | daacf506-7554-5142-8ad7-bd23157f7b06 |  | note | INSPECTION/TEST METHOD: Verify
label | 979e5616-bb44-5356-a456-01d193cae829 |  | note | – – – – – – – – –
label | 1375c4cb-9c1d-5108-a9a6-097999148834 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 4ae697ca-7547-5d8a-ad3b-18342d4bda37 |  | note | – – – – – – – – –
label | af4a53f0-f023-58bd-b00c-12f09d725bab |  | note | WP
label | f93ec3ae-3a21-521b-8829-c7b75746876a |  | note | – – – – – – – – –
label | 816a18fc-eab0-51a8-b38b-156f9c26964c |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
label | a5d460e0-16b3-5bce-93f9-a44e76096c36 |  | note | – – – – – – – – –
text | 92ed54b5-1194-5690-88db-cc1fb74d4c21 |  | textbox | DATE:
checkpoint-status | 4941292c-e115-448c-a512-46682f548f38 |  | checkpoint | Final Inspection
label | e0084c6e-5f02-55b6-90ad-16cf17b68313 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 580e4567-0788-5ecd-90b8-362b27cf218d |  | textbox | Print Name:
text | 3bb2df73-9caa-5b44-a4b6-d04880d828a6 |  | textbox | Position:
text | b29fb01c-6e2f-58b2-8921-55f4e92c402c |  | textbox | Date: