## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | FHC-ITP-008 - Stormwater Drainage Rev3 | itp |  |  |  |  | FHC-ITP-008 - Stormwater Drainage Rev3
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.3 Precast Materials acceptance
note | FREQUENCY: Each Delivery
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be accepted on the basis of full compliance with the requirements of this section and AS/NZS 4058.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl. 701.05e
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed, Receival and Inspection Checklist
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.4 Precast Pipe & Culvert Compliance
note | FREQUENCY: Prior to Commencing
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619.
note | Precast Reinforced Concrete (Portland) Pipes shall comply with requirements of AS 4058
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: VicRoads Spec.
note | • Cl.619
note | • Cl. 701.04
note | • Cl. 701.05(a)
note | • AS4058
note | • AS4680
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Document review & Site inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.5 Precast Drainage Pit Compliance
note | FREQUENCY: Prior to Commencing
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: VicRoads Spec.
note | • Cl.610
note | • Cl. 705.04
note | • AS5100
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Document Review
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.6 Bedding material classification
note | FREQUENCY: Prior to start
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Test Reports from supplier
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.7 Backfill material Classification
note | FREQUENCY: Prior to start
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 701.09(d), 701.091
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Test Reports from supplier
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.8 Mortar material classification
note | FREQUENCY: Prior to start
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 610.33
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Test Reports from supplier
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Excavation Permit
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
note | • Plant and equipment shall be appropriate for the task.
note | • Excavation operations shall not disturb areas outside the limit of excavation
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Excavation permit
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.2 Set out drainage
note | FREQUENCY: Prior to backfilling
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Drawings 701.10
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Superintendent
note | – – – – – – – – –
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Excacation (pipes)
note | FREQUENCY: Each Trench
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical
note | ○ Depth of trench:
note | • > 100mm below underside of pipe (for pipe width < 1500 mm)
note | • > 200mm below underside of pipe (for pipe width > 1500 mm)
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 701.151, 701.15
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.4 Excacation (pits)
note | FREQUENCY: Each Pit
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: A minimum clearance of 400mm is required around the external faces of precast pits.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 705.05b
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.5 Compact base of trench
note | FREQUENCY: Each Trench
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 701.15
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.6 Place bedding material & compact
note | FREQUENCY: Each Trench
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
note | • Bedding shall be compacted to refusal using hand held mechanical equipment.
note | • Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 701.20, 701.20a
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.7 Place pipes & precast pits
note | FREQUENCY: Each Line/Pit
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.8 Jointing pipe sections
note | FREQUENCY: Each Line
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All interlocking (flush) joint reinforced concrete pipes shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 701.18
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.9 Sealing - for joining culvert sections and pipe penetrations in pits
note | FREQUENCY: Each Pit
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Contact areas between top and bottom sections of box culverts to be mortared.
note | • The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 610.32, 701.17c
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.10 Survey of laid pipe or pit
note | FREQUENCY: Prior to backfilling
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The location of each run of drainage has been verified prior to backfilling and conforms to the following tolerances: (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
note | (c) invert level of pipes at pits ±50 mm
note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 701.1
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Survey Conformance Point
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | SCP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Surveyor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.11 Haunching & compaction of bedding material
note | FREQUENCY: each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Height of additional bedding material = 30% of nominal pipe diameter or culvert height.
note | • Loose layer thickness <=150mm
note | • Compacted to refusal using hand held mechanical equipment.
note | • 1 lot = 150mm layer
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 701.16, 701.20
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.12 Place & compact backfill material over pipes
note | FREQUENCY: each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Backfill under paved area:
note | • fill trench with selected back fill material to subgrade level
note | ○ Backfill under area not paved:
note | • Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
note | • Loose layer thickness <= 150mm.
note | • 1 lot = 150mm layer
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 701.19, 701.20
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.13 Place & compact backfill material around pits
note | FREQUENCY: Each Pit
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Loose layer thickness <= 300mm. Compacted to refusal using hand held mechanical equipment.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 705.18
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.14 Backfilling with cement stabilised sand
note | FREQUENCY: Each culvert
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Where approval is given from superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% stabilised sand with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.19(a)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Site Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Superintendent approval, ITP signed
note | – – – – – – – – –
note | AP
note | – – – – – – – – –
note | RESPONSIBILITY: Project Engineer / Superintendent
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.15 Install step irons
note | FREQUENCY: Each Pit
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: For pits > 1m deep.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 705.12
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.16 Pit base shaped with concrete to match pipe invert
note | FREQUENCY: Each Pit
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: As shown on Standard VicRoads drawing - Pit & Pipe Invert levels SD 1002
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Standard VicRoads drawing SD 1002
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Enginer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.17 Place pit covers
note | FREQUENCY: Each Pit
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Covers must be set to within ±10mm of the design levels shown on the drawings
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 705.17
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.18 Repairs to damaged pipes and box culverts
note | FREQUENCY: Each damaged pipe or culvert
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
note | • All repair procedures undertaken in accordance with Cl 701.25
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 701.31a
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Superintendent
note | – – – – – – – – –
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing & Completion
checkpoint | 3.1 Compaction and moisture content of backfill & bedding material
note | FREQUENCY: at least 20% of all lots
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 97% using standard compactive effort.
note | • Bedding shall be compacted to refusal using hand held mechanical equipment.
note | • Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 701.20a, 701.20b
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Test Reports
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.2 CCTV inspection
note | FREQUENCY: each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 701.3
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: CCTV Report
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Superintendent
note | – – – – – – – – –
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 Flushing of pipes
note | FREQUENCY: Each line
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All pipes to be flushed clean upon completion
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 701.28
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: