## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-0388-ITP-005 Gabions [B] | itp |  |  |  |  | SYM-0388-ITP-005 Gabions [B]
section | 1.0 Material
checkpoint | 1.1 - Gabions
note | Ref docs - TfNSW R55 Cl 2.1, IFC Drawing
note | Acceptance criteria - Gabions must have a nominal mesh size of 80 mm x 100 mm. The minimum diameter of mesh wire must be 2.7 mm.
note | • The minimum diameter of galvanized selvedge wire must be 3.4 mm. The mesh is flexible, woven, galvanized and PVC coated when required as per IFC drawings.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 1.2 - Selvedges
note | Ref docs - TfNSW R55 Cl 2.3
note | Acceptance criteria - All edges of the gabions must be selvedged with a continuous wire in accordance with ASTM A975-97.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 1.3 - Lacing and Connecting Wire
note | Ref docs - TfNSW R55 Cl 2.5
note | Acceptance criteria - Materials must conform to ASTM A975-97.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Alternative fastener systems such as “C” clips in place of lacing and connecting wire are permitted but must conform to the requirements of ASTM A975-97.
checkpoint | 1.4 - Rock Fill - Strength
note | Ref docs - TfNSW R55 Cl 2.6
note | Acceptance criteria - At least 100 kN and a maximum wet/dry strength variation of 35% when tested in accordance with Test Method TfNSW T215.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 1.5 - Rock Fill - Size
note | Ref docs - TfNSW R55 Cl 2.6
note | Acceptance criteria - For gabions, the minimum and maximum rock size must be 100 mm and 250 mm respectively
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Gabion Installation
checkpoint | 2.1 - Material Inspection
note | Acceptance criteria - The gabions shall be visually inspected to ensure that they are free from defects such as cracks, splits, or punctures.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 2.2 - Set out
note | Ref docs - IFC Drawings
note | Acceptance criteria - Setout of gabion location and level.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 2.3 - Foundation Inspection
note | Ref docs - IFC Drawings
note | Acceptance criteria - Backfill material is compacted in layers to the required density, loose material has been removed.
note | • Geotextile is placed as per the IFC drawings.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Assembly
note | Ref docs - TfNSW R55 Cl 4.1
note | Acceptance criteria - Visual inspection of the gabion boxes to ensure they are free from kinks and bends.
note | • Measurement of the gabion boxes and mattresses to ensure they meet the design specifications.
note | • Lacing are securely fastened.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 2.5 - Erection
note | Acceptance criteria - Only assembled boxes or groups of boxes are positioned in the structure.
note | • The side, or end, from which work is to proceed, must be secured either to the completed work, or by galvanized star pickets driven into the ground at 1 m spacing. The star pickets must be firmly embedded in the ground and reach at least to the top of the gabion box.
note | • Measurement of the gabion boxes and mattresses to ensure they meet the design specifications.
note | • Lacing are securely fastened.
note | • If further gabion boxes positioned in the structure are required.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 2.6 - Stretching
note | Ref docs - TfNSW R55 Cl 4.3
note | Acceptance criteria - Verification that the gabion units have been supplied and assembled in accordance with specification requirements.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Carry out final stretching of the gabion boxes using a pull-lift of at least one tonne capacity.
checkpoint | 2.7 - Pipe Culvert Within Gabion Structures
note | Ref docs - IFC Drawings
note | Acceptance criteria - Mesh is cut and laced as per the IFC Drawings.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 2.8 - Filling
note | Ref docs - TfNSW R55 Cl 4.4
note | Acceptance criteria - Gabion boxes shall be filled with rocks only while under tension and the rocks shall be placed by hand packing to produce a neat face free from excessive bulges, depressions and voids.
note | • Internal bracing wires shall be provided to prevent distortion of the gabion units during filling and in the completed structure.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Mechanical filling equipment may be used provided that adequate precautions are taken to protect any PVC coating from abrasion during filling operations.
checkpoint | 2.9 - Final Lacing
note | Ref docs - TfNSW R55 Cl 4.5
note | Acceptance criteria - Gabion boxes and mattresses are finally laced and secured through each mesh along all edges, ends and diaphragms.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
section | 3.0 Subsoil
checkpoint | 3.1 - Subsoil Drainage Pipe
note | Ref docs - IFC Drawings
note | Acceptance criteria - DN100 Socked Subsoil Drainage Pipe installed at base of wall before backfill.
note | • Discharge through face of wall at 25m centres
note | ○ Provide clear out riser to surface
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 3.2 - Subsoil Aggregate
note | Ref docs - IFC Drawings
note | Acceptance criteria - Install subsoil layer min. 200mm wide from rear face of wall before backfill.
note | • Aggregate to be nominal 20mm in dimension.
note | ○ Wrapped in approved Geotextile.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - S
textbox | Shoalhaven City Council: Sign Date
checkpoint | 3.3 - Rock fill material behind the gabion
note | Ref docs - IFC Drawings
note | Acceptance criteria - Backfill behind the gabions by compacting in 200mm layers to at least 98% of standard maximum dry density
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
section | 4.0 Conformance check
checkpoint | 4.1 - Tolerances
note | Ref docs - IFC Drawings
note | Acceptance criteria - Surface Level: the top surface level must be as per design levels or as approved.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - S
textbox | Shoalhaven City Council: Sign Date
checkpoint | Works complete (sign SS)
textbox | Name:
textbox | Position:
textbox | Date works complete:
signoff | Sign ITP
checkpoint | Site conforms (sign PE)
textbox | Name:
textbox | Position:
textbox | Date works complete:
signoff | Sign ITP
checkpoint | Lot conforms
textbox | Name:
textbox | Position:
textbox | Date Site closed:
textbox | NCR no. raised:
textbox | Date NCR closed for this Site:
signoff | Sign ITP
checkpoint | Site acceptance - Symal Infrastructure
textbox | Symal Infrastructure representative name:
signoff | Symal Infrastructure representative signature
checkpoint | Site acceptance - Shoalhaven City Council
textbox | Shoalhaven City Council representative name:
signoff | Shoalhaven City Council representative signature