## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-0388-ITP-007 Structural Concrete Works [B] | itp |  |  |  |  | SYM-0388-ITP-007 Structural Concrete Works [B]
section | 1.0 – PRELIMINARIES
checkpoint | 1.1 - Submit details of each concrete mix and proposed curing regime, together with a certificate stating that the nominated mix, its constituents and the proposed curing regime
note | Ref docs - TfNSW R53 Cl 2.4.3
note | Acceptance criteria - Submit at least 5 working days before the concrete mix is proposed to be used for the concrete mix.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Designate concrete truck washout area (s)
note | Acceptance criteria - Designate a washout bay for the cleaning of concrete trucks
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
section | 2.0 – CONCRETE WORKS
checkpoint | 2.1 - SWMS and Induction
note | Acceptance criteria - Ensure Symal SWMS in place for current works and all personal inducted to site
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 2.2 - Submit formwork design documentation & certification
note | Ref docs - TfNSW R53 Cl 3.1 AS 3610.1
note | Acceptance criteria - Submission of Formwork design if required, Submit 5 working days before placing of reinforcement
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Determine Extent of the Site
note | Ref docs - IFC Drawings
note | Acceptance criteria - Survey work is performed by qualified surveyor using appropriate surveying equipment to determine extent of the site.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Set out the structural element
note | Ref docs - IFC Drawings
note | Acceptance criteria - Centre and Invert of Pit or Stormwater Line set out by Survey
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 2.5 - Weld Testing Results Prior to Delivery
note | Ref docs - IFC Drawings
note | Acceptance criteria - Weld testing results are sent to the client prior to delivery.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 2.6 - Reinforcement
note | Ref docs - TfNSW R53 Cl3.2, IFC Drawings
note | Acceptance criteria - IFC Drawings
note | • Refer CC0388 Pre-Pour Checklist
note | 1. Lapped splices length as per drawings & Specs (400mm)
note | 2. Bar sizes correct
note | 3. Bar spacing correct
note | 4. Chairs adequate & correct type
note | 5. Reinforcement secure
note | • Cover to formwork faces is 50mm unless shown on the drawings
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Headed Anchor and Anchor Blocks
note | Ref docs - IFC Drawings, Manufacturer's Specifications
note | Acceptance criteria - The anchor is installed in the correct alignment.
note | • The lockshear bolts is tightened appropriately.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 2.8 - Concrete Joints
note | Ref docs - TfNSW R53 Cl3.3.9
note | Acceptance criteria - Joints constructed to prevent loss of mortar.
note | • If it’s an adjoining concrete, roughen the surface of constructions joints to expose coarse aggregate.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 2.9 - Formwork
note | Ref docs - TfNSW R53 Cl3.1 AS 3610.1
note | Acceptance criteria - IFC Drawings
note | – Formwork in the correct position and level
note | – Embedment in correct position and level
note | – Formwork is clean, oiled and free from grease, adequately supported in place with no movement.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
section | 3.0 – CONCRETE PLACEMENT
checkpoint | 3.1 - Pre pour planning
note | Ref docs - TfNSW R53 Cl3.3.1 Cl3.3.2 Cl3.3.3
note | Acceptance criteria - Ensure the following:
note | 1. Areas free of water
note | 2. Construction debris removed
note | 3. Concrete temperature at the point of discharge is <32°C except for precast concrete members.
note | 4. Air temperature at the point of discharge is between 5°C and 35°C.
note | 5. Rain not forecasted
note | 6. NATA lab arranged
note | • Concrete pump or crane / kibble arranged (where required)
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 3.2 - Intention to place concrete in the Works
note | Ref docs - TfNSW R53 Cl3.3.1
note | Acceptance criteria - Submit checklists for verifying conformity of the following:
note | – Nominated Concrete Mix
note | – Formwork
note | – Reinforcement
note | – Embedment’s and other relevant details
note | – Intention to place concrete in the Works.
note | • Submit ≥2 working days before commencement.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Pour in Progress Inspections
note | Ref docs - TfNSW R53
note | Acceptance criteria - Ensure the following:
note | 1. Adequate resources are onsite for works
note | 2. Adequate vibrators are available as necessary
note | 3. Record Times
note | • Concrete is being compacted adequately
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 3.4 - Concrete Slump/Strength Field Testing
note | Ref docs - TfNSW R53 Cl4.1, Annex B53/L
note | Acceptance criteria - Slump Test 1 per first 3 batches
note | • Strength test, Concrete Cylinder set of 7,28,28 days every 100m3
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 – AFTER CONCRETE POUR
checkpoint | 4.1 - Curing
note | Ref docs - TfNSW R53 Cl2..6 Cl3.4
note | Acceptance criteria - Apply approved concrete curing compound in line with specification
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 4.2 - Stripping of Formwork
note | Ref docs - TfNSW R53 Cl3.3.7
note | Acceptance criteria - Stripping of Concrete
note | • External surfaces – 2 days
note | • Permanently Hidden Surface – 1 day
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 4.3 - Inspection of Concrete Surface Finish/Class
note | Ref docs - TfNSW R53 Cl4.2 Cl3.3.8
note | Acceptance criteria - Inspect for
note | 1. Compliance with specified surface finish;
note | 2. Check for extent of any cracking after 21 days (Cracks are less than 0.2 mm)
note | • are repairs required, specify repair methods
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 4.4 - Tolerance
note | Ref docs - TfNSW R53 Cl4.3 AS3610.1
note | Acceptance criteria - Within tolerance set out in R53
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 4.5 - Test Results
note | Ref docs - TfNSW R53
note | Acceptance criteria - Test certificates received, reviewed and conforming to requirements.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | Works complete (sign SS)
textbox | Name:
textbox | Position:
textbox | Date works complete:
signoff | Sign ITP
checkpoint | Site conforms (sign PE)
textbox | Name:
textbox | Position:
textbox | Date works complete:
signoff | Sign ITP
checkpoint | Lot conforms
textbox | Name:
textbox | Position:
textbox | Date Site closed:
textbox | NCR no. raised:
textbox | Date NCR closed for this Site:
signoff | Sign ITP
checkpoint | Site acceptance - Symal Infrastructure
textbox | Symal Infrastructure representative name:
signoff | Symal Infrastructure representative signature
checkpoint | Site acceptance - Shoalhaven City Council
textbox | Shoalhaven City Council representative name:
signoff | Shoalhaven City Council representative signature