## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-0388-ITP-008 Stormwater Drainage [B] | itp |  |  |  |  | SYM-0388-ITP-008 Stormwater Drainage [B]
section | 1.0 Preliminaries
checkpoint | 1.1 - Set out
note | Ref docs - Construction Drawings TfNSW R11
note | Acceptance criteria - Is the position of the culverts in accordance with the drawings?
note | • Confirm location with the superintendent.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Submission of Conformance Documentation
note | Ref docs - Construction Drawings TfNSW R11
note | Acceptance criteria - Full set of certified product drawings submitted prior to installation
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Drainage structure confirmation
note | Ref docs - Construction Drawings
note | Acceptance criteria - Has the correct class & type of drainage structure been supplied and free of defects?
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Excavation and bedding
checkpoint | 2.1 - Excavation
note | Ref docs - TfNSW R11
note | Acceptance criteria - The minimum width of vertically sided trenches shall be the outside diameter plus 30mm or 600mm total, whichever is greater?
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 2.2 - Minimum Grade Requirements
note | Ref docs - TfNSW R11
note | Acceptance criteria - Where 0.5% gradient not achievable with sections of open drain, notification to be issued to client
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Material
note | Ref docs - IFC Drawings
note | Acceptance criteria - Material for stormwater drainage to comply with requirements of the IFC Drawings
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 2.4 - Bedding material
note | Ref docs - TfNSW R11
note | Acceptance criteria - Is the Bedding material placed the full width of the trench and not less than:
note | • 100mm where D<1500mm
note | • 200mm where D>1500mm
note | Where D is the nominal pipe diameter or culvert height.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
section | 3.0 Culvert Installation
checkpoint | 3.1a - Culvert under paving
note | Ref docs - TfNSW R11
note | Acceptance criteria - Has trench been backfilled to design subgrade level with select backfill material?
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 3.1b - Culvert not under paving
note | Ref docs - TfNSW R11
note | Acceptance criteria - Has trench been backfilled to 0.3m above the top of the culvert with select backfill material?
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 3.2 - Jointing
note | Ref docs - TfNSW R11
note | Acceptance criteria - Has jointing been installed to specifications?
note | • Have holes provided for lifting and handling purposes been plugged?
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 3.3 - Compaction
note | Ref docs - TfNSW R11
note | Acceptance criteria - Backfill under pavements shall be compacted to a dry density ratio if not less than 95% modified compactive effort. General Fill shall be compacted to a dry density ratio of not less than 98% using standard compactive effort.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Drop Inlet Installation
checkpoint | 4.1 - Drop Inlet Position
note | Ref docs - IFC Drawing
note | Acceptance criteria - The drop inlet structure is installed at the correct location, depth, and size per IFC Drawings
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 4.2 - Connection
note | Ref docs - IFC Drawing
note | Acceptance criteria - The drop inlet structure is properly aligned and connected to the storm drain system.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 4.3 - Drop Inlet Gate
note | Ref docs - IFC Drawing
note | Acceptance criteria - Drop inlet grate is installed securely and flush with the surrounding pavement surface
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 4.4 - Compaction
note | Ref docs - IFC Drawing
note | Acceptance criteria - Backfill material is properly compacted in layers per the IFC Drawing / manufacturer specifications. Verify the grading is level and slopes away from the drop inlet structure to ensure proper drainage.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
section | 5.0 Rip Rap
checkpoint | 5.1 - Rip rap
note | Ref docs - IFC Drawing
note | Acceptance criteria - The rip rap is installed at the correct location and orientation per the project specifications.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 5.2 - Geotextile
note | Ref docs - IFC Drawing
note | Acceptance criteria - The geotextile is installed as per the spec.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 5.3 - Shotcrete
note | Ref docs - IFC Drawing
note | Acceptance criteria - The shotcrete is applied as per the spec.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
section | 6.0 Conformance check
checkpoint | 6.1 - Survey pick up
note | Ref docs - TfNSW R11
note | Acceptance criteria - Has an As-constructed survey must be completed by a licenced or competent surveyor of the stormwater drainage system?
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
textbox | Surveyor
textbox | Date picked up
checkpoint | Site acceptance - Symal Infrastructure
textbox | Symal Infrastructure representative name:
signoff | Symal Infrastructure representative signature
checkpoint | Site acceptance - Shoalhaven City Council
textbox | Shoalhaven City Council representative name:
signoff | Shoalhaven City Council representative signature