## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-0388-ITP-010 Guardrail [B] | itp |  |  |  |  | SYM-0388-ITP-010 Guardrail [B]
section | 1.0 Preliminaries
checkpoint | 1.1 - Survey set-out
note | Ref docs - Construction drawings
note | Acceptance criteria - Has the work area been set out for line and level?
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
section | 2.0 Installation of guard rail
checkpoint | 2.1 - Location and length
note | Ref docs - Construction drawings
note | Acceptance criteria - Has length and location been confirmed with the Superintendent?
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Material
note | Ref docs - Construction drawings
note | Acceptance criteria - Galvanised steel components are compliance with the requirements of AS/NZS 4680.
note | • Manufacturer certificates are provided to the client.
note | • Visual inspection.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
tickbox | Material certificates
checkpoint | 2.3 - Install
note | Ref docs - Construction drawings
note | Acceptance criteria - Has the guard rail run been installed as per the relevant specifications and drawings?
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
tickbox | Subcontractors ITP
section | 3.0 Completion
checkpoint | 3.1 - Tolerances
note | Ref docs - TfNSW D&C R132
note | Acceptance criteria - Has the guard rail been installed to the specified tolerances?
note | (a) For height of barrier: ± 20 mm;
note | (b) For line of safety barrier system: ± 20 mm in plan view; and
note | (c) For departures from the upright axis (vertical or normal to the surface as applicable - see Clause 4.1): ± 15 mm at the top of the barrier.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Certificate of compliance
note | Ref docs - TfNSW D&C R132
note | Acceptance criteria - Has a safety barrier compliance audit taken place with records of findings available?
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
tickbox | Compliance certificate
checkpoint | Site acceptance - Symal Infrastructure
textbox | Symal Infrastructure representative name:
signoff | Symal Infrastructure representative signature
checkpoint | Site acceptance - Shoalhaven City Council
textbox | Shoalhaven City Council representative name:
signoff | Shoalhaven City Council representative signature