## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 5642e4fd-f1d1-4925-bf87-f02aae745228 |  | checklist | Roof Readiness Checklist - Membrane |  |  |  |  | Yes | Roof Readiness Checklist - Membrane | 7d35fe86-1a83-4a70-b5bf-52f31997ea3a
checkpoint-status | a4b3b847-30a2-468d-aeaa-8de075b8f1ad |  | checkpoint | Area ready?
checkpoint-status | 16a1682f-c042-4b78-952f-80d110233dbc |  | checkpoint | CCA H3.2 treated plywood sheets used
label | 98e063d6-a5d7-596f-a70a-6f1c6e552aa3 |  | note | 17mm thick for roofs, 20mm thick for decks
checkpoint-status | 826ba90a-e34d-430c-85e0-73a6ce688342 |  | checkpoint | Plywood sheets supported by joists and nogs at maximum 400mm centers in both directions, unless specified otherwise
checkpoint-status | 774f0d50-a2bb-4ff7-853e-d6a361d2a35d |  | checkpoint | Sheets stagger lay (fully offset) with the face grain at right angles to the primary supports
checkpoint-status | 36eadc95-37a0-4da3-b3a7-df5a14ec6735 |  | checkpoint | All sheet edges supported by nogs, fixed 100mm on edges and 200mm through girth, edges butt-jointed with no gaps except at abutments
checkpoint-status | a8df693b-bc20-432d-972d-84be8d5c7f36 |  | checkpoint | Sheets glued in place and then fixed using 316 grade Stainless Steel 10 gauge countersunk screw fixings
checkpoint-status | e157546c-e3ef-46e5-81b3-99c7657adb36 |  | checkpoint | All decks and gutters have correct falls once installed
checkpoint-status | 2e996499-057f-4bbe-b9e7-320b0191c442 |  | checkpoint | Fillets installed to all internal junctions and neatly fitted with mitres neatly formed
checkpoint-status | 80419d17-12cd-4edc-9732-9eb5475c132c |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status | 5393304a-f7c1-48d6-9d9f-243bc2f45761 |  | checkpoint | 5mm clearances from all abutments, 5mm radius to all exposed edges
checkpoint-status | af80f707-3c79-4cca-9314-09873d029325 |  | checkpoint | Sharp edges and lips removed and cavities filleted. All joints flush
checkpoint-status | 5a358506-1c77-414a-9ea0-37b524fce430 |  | checkpoint | Substrate dry, clean, firm and suitable condition for laying
holdpoint | d5423695-297e-42ae-83a8-0e0dfca81e86 |  | signoff | signed by Titus
checklist-flat | 85932ddd-77fb-4940-9531-4887accfd279 |  | checklist | New Concrete Substrate Readiness Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | New Concrete Substrate Readiness Checklist - Nuraply 3PM Membrane | 1964fb73-2f72-43c5-a917-8f89a0de7a13
checkpoint-status | ed93ddaa-6294-43fe-b858-272e3e4ca93c |  | checkpoint | Area ready?
checkpoint-status | cdaa0f4c-3884-4a4b-b930-df909bdbfd5c |  | checkpoint | Structure complies to the New Zealand Building Code and concrete complies with NZS 3101 (2006)
checkpoint-status | c156c578-e062-4a0f-ae0f-3839eae9d790 |  | checkpoint | Concrete cured with curing membranes removed. Concrete substrate contains less than 5% moisture content
checkpoint-status | abd0834d-8205-4015-8c5c-98d170ab8a4a |  | checkpoint | Surface smooth and clean with falls as per plan
checkpoint-status | 708347e5-8422-4ddf-a247-95e01f1e616a |  | checkpoint | Cavities and cracks filled with repair mortar, flushed off and cured
checkpoint-status | 89c68cb9-d9a1-4341-a181-267a783adebd |  | checkpoint | Concrete surface firm with any soft concrete or laitance removed
checkpoint-status | cf999c81-6c00-41da-bd0a-b75c5d85f92d |  | checkpoint | Ponding areas removed
checkpoint-status | c898bd6d-cb52-431b-a3fa-2725fb763c6f |  | checkpoint | Roof drains and overflow recesses formed to fit rebated outlets
checkpoint-status | 8d72b061-f4f9-4ed5-b25d-6a93d081fcb1 |  | checkpoint | Mortar or Profili Bitumen fillets to all upstands and smooth 5mm radius to all external edges
checkpoint-status | b133f1ce-2110-4db3-9676-793716a91660 |  | checkpoint | If terminating into a chase, pre-form the chase and ensure it is straight and 20mm deep
checkpoint-status | 494368b3-02cf-47b4-bff3-cdb4019d4e3d |  | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures
checkpoint-status | 941dfb9d-da4d-4a45-9236-9360e2f93310 |  | checkpoint | Construction joints incorporated in slab as per designers specification
checkpoint-status | 17fff8e8-cc1a-4b9a-89f3-9fc820f1781b |  | checkpoint | Substrate dry, clean, firm and suitable condition for laying
holdpoint | 19b28c2b-419c-4f91-bf7f-ed140fa340fa |  | signoff | Signed by Titus
checklist-flat | 3e41ab98-0333-474e-b740-c800ce738faa |  | checklist | Roof Readiness Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | Roof Readiness Checklist - Nuraply 3PM Membrane | 19c1dc5d-5e30-47a1-88cf-a69d3618fab7
checkpoint-status | 37fc76ff-ae40-4390-b45f-35cb37fb2857 |  | checkpoint | Area ready?
checkpoint-status | d77d6aa0-ebac-4f57-88e7-8cc7f7baef5c |  | checkpoint | CCA H3.2 treated plywood sheets used
label | f5d7585c-740a-5681-b87e-674b405b9a82 |  | note | 17mm thick for roofs, 20mm thick for decks
checkpoint-status | 897e4e95-c1b0-4566-89fa-2c9a617098d7 |  | checkpoint | Plywood sheets supported by joists and nogs at maximum 400mm centers in both directions, unless specified otherwise
checkpoint-status | b1741b12-bba7-4657-bc6f-5a48aa3d63c3 |  | checkpoint | Sheets stagger lay (fully offset) with the face grain at right angles to the primary supports
checkpoint-status | e17212f8-2454-4938-9869-91d2e1cedc0f |  | checkpoint | All sheet edges supported by nogs, fixed 100mm on edges and 200mm through girth, edges butt-jointed with no gaps except at abutments
checkpoint-status | 5760ddb0-9bc5-423a-a501-47bc94fe8c52 |  | checkpoint | Sheets glued in place and then fixed using 316 grade Stainless Steel 10 gauge countersunk screw fixings
checkpoint-status | f7035316-9f53-43ed-9990-c0b0cd78e80d |  | checkpoint | All decks and gutters have correct falls once installed
checkpoint-status | ced1d0a4-53c7-4b2b-aaf4-0e6cb316bf7e |  | checkpoint | Fillets installed to all internal junctions and neatly fitted with mitres neatly formed
checkpoint-status | 952937e9-f07a-4996-b862-3947e1d9c6d8 |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status | 512e8abc-de5a-4027-bf82-d48c6ba4de18 |  | checkpoint | 5mm clearances from all abutments, 5mm radius to all exposed edges
checkpoint-status | 56d0a0f3-7cbf-4371-9f43-aad1aec7f370 |  | checkpoint | Sharp edges and lips removed and cavities filleted. All joints flush
checkpoint-status | cff6b4e8-6d04-47cd-b4db-a282567f9d5f |  | checkpoint | Substrate dry, clean, firm and suitable condition for laying
holdpoint | f05665c0-93cf-446b-b795-6df6032c5fd9 |  | signoff | signed by Titus
checklist-flat | cc2cf5a7-575f-4c50-a70f-560073f619ca |  | checklist | New Plywood Substrate Readiness Checklist - Membrane |  |  |  |  | Yes | New Plywood Substrate Readiness Checklist - Membrane | beb33168-4586-4e5c-b4f7-e406c69b7e5a
checkpoint-status | d66212f9-ee1c-454a-a8e9-42a85208f58a |  | checkpoint | Area ready?
checkpoint-status | 3ad981d4-5f82-40a2-a15d-d9d13123b344 |  | checkpoint | Structure complies to the New Zealand Building Code and plywood complies with AS/NZ 2269
checkpoint-status | 64763699-a143-4439-8847-8d0e8a521541 |  | checkpoint | CCA H3.2 treated plywood sheets used
label | b00cbda9-ba8d-5d40-81a9-65ec98289a88 |  | note | 17mm thick for roofs, 20mm thick for decks
checkpoint-status | 6f702b53-13d8-4168-8d8e-0cbdef4dc41a |  | checkpoint | Plywood sheets supported at 600mm centred rafters and nogs for roofs and decks, unless otherwise specified
checkpoint-status | bbf63397-532e-4232-bd85-60f181d5c193 |  | checkpoint | Sheets stagger lay (fully offset) with falls as per plan
checkpoint-status | ba6b9bc1-815a-436c-9879-1d6537d78307 |  | checkpoint | 5mm clearances from all abutments, 5mm radius to all exposed edges
checkpoint-status | b646d57c-c391-40ef-ac7a-54b929a92364 |  | checkpoint | All sheet edges supported, fixed 150mm on edges and 200mm through girth, edges butt-jointed with no gaps except at abutments
checkpoint-status | 7a419060-1f4e-47b0-9ee5-53bd7e201cd3 |  | checkpoint | Sheets fixed by gluing and Stainless Steel countersunk screw fixing
checkpoint-status | 3859dbb2-b98d-4b4f-b7f5-7c566267eecc |  | checkpoint | Fillets installed to all internal junctions and neatly fitted
checkpoint-status | 20255191-3cbc-49e0-b58d-7914e39e50a3 |  | checkpoint | Mitres neatly formed
checkpoint-status | b34c8a6d-464c-4b67-a35a-5ad96fe55b19 |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status | 61fba1ea-d14e-4566-92d9-95e8de2075e3 |  | checkpoint | Sharp edges and lips removed and cavities filleted. All joints flush
checkpoint-status | a2754a25-4cd4-4c65-ba9c-6cb5a751f351 |  | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures
checkpoint-status | 9a25a33e-ab7f-4439-a8b6-caa9dc3c38bd |  | checkpoint | Substrate dry, clean, firm and suitable condition for laying
checkpoint-status | d64ea2cc-1427-49f0-a6ec-ca32ef2ffc4d |  | checkpoint | When substrate is ready complete send this as report to membrane applicator
holdpoint | f21b34ff-ce03-40b8-bdd5-41da17bb7125 |  | signoff | Signed by head contractor
checklist-flat | 27d66028-c3b8-4352-ae76-b37bde70f13e |  | checklist | Allco Warranty Checklist - Projects Under 200m² |  |  |  |  | Yes | Allco Warranty Checklist - Projects Under 200m² | 1fc92e7c-5605-4847-b953-85f8a386d6f4
checkpoint-status | 37349276-a015-4344-beb3-a8e7b9b5e664 |  | checkpoint | Must notify Allco of project a minimum of 7 days prior to starting the project using Allco’s Applicator Portal.
checkpoint-status | e9fe1637-eb43-40e8-8a72-255a7bddcea6 |  | checkpoint | Must follow job specification, or in the absence of one, follow detail provided by Allco.
checkpoint-status | 3aa75a47-a9a3-47da-94c3-1755a14fb956 |  | checkpoint | Must follow Allco QA requirements using either CONQA, Allco’s QA manual forms or a pre-approved 3rd party QA System.
checkpoint-status | 687d8441-a326-46b1-9a87-4f2d1439fe82 |  | checkpoint | An adequate collection of photos showing pre, during & post installation details.
checkpoint-status | e717bd52-4bfa-4439-a969-85c3ac73b9ec |  | checkpoint | Photos must clearly show all products used in installation.
checkpoint-status | 6eec3e3a-ab09-4e5f-beeb-1710bdfc4c49 |  | checkpoint | All applicators on site are Allco Approved, trained and licensed applicators and are employees of the Approved Applicator at time of installation.
checkpoint-status | 82e1a6df-264d-457f-943d-9b8855811d3f |  | checkpoint | Complete and submit a Warranty Request Form.
checkpoint-status | 9c03a3f1-663d-4aea-82cd-d2e85d06311d |  | checkpoint | Applicator will hand over Warranty Documents and Care and Maintenance Plan to the Building Owner.
checklist-flat | 7e10f655-a457-4f9d-b852-2451e2d98644 |  | checklist | New ENERTHERM Substrate Readiness Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | New ENERTHERM Substrate Readiness Checklist - Nuraply 3PM Membrane | fbe196c5-f0df-4688-96a1-fa82ce91763b
checkpoint-status | 4f5debc8-9caf-4a9f-8566-f4453c0dbfda |  | checkpoint | Area ready?
checkpoint-status | de944c84-5556-4585-b380-80662623f635 |  | checkpoint | Structure complies to the New Zealand Building Code
checkpoint-status | 97f5cb6b-ba18-46d1-8533-5948dcdf02bb |  | checkpoint | Sheets stagger lay (fully offset)
checkpoint-status | 93b3bb16-35d9-402f-977b-eeaafdb1dbcb |  | checkpoint | Confirm the substrate slope complies with plans
checkpoint-status | 8c24b641-77aa-47fb-8f16-56f171ae8e51 |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status | 27775442-5338-47a3-b133-845f90a9e1c6 |  | checkpoint | Ensure only approved accessories to be used for drainage and venting
checkpoint-status | 3e0d3320-d091-48b3-aca0-fd4170d1dbac |  | checkpoint | Review penetrations to minimize number and complexity
checkpoint-status | 92ccd33e-6619-44be-8476-4a9728f98aee |  | checkpoint | Any gaps in the insulation filled to prevent thermal bridging
checkpoint-status | 8e33f1db-af56-46f6-af02-520da1428309 |  | checkpoint | Material fastened with the correct quantity of IKOfix Telescopic Fixing Plates and Fixing Screws
label | 6e71481f-2d39-582a-a1b6-8a20ebc59ebb |  | note | 5 per sheet normally, 10 per sheet in extra high wind zones
checkpoint-status | b3d117c7-4287-4724-9a95-284d62473a8e |  | checkpoint | Edges of insulation supported by metal sheet ridges
checkpoint-status | be8f823d-70f3-4edf-b6f8-921cea6b6cb7 |  | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures
checkpoint-status | f8003102-dbd3-4360-ab96-cecf7072af76 |  | checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite systems
checkpoint-status | 36712004-be7c-4d31-8cef-90bfcb8c3a8b |  | checkpoint | When substrate is ready complete send this as report to Nuralite applicator
holdpoint | 983f7903-338d-4416-870e-ed421ef59f7d |  | signoff | Signed by head contractor
checklist-flat | 380c45b4-8b72-41e4-ae5d-15dba63a3b40 |  | checklist | Allco Warranty Checklist - Projects Over 200m² / Liftpits / Hydrostatic |  |  |  |  | Yes | Allco Warranty Checklist - Projects Over 200m² / Liftpits / Hydrostatic | 4d47b94a-71f6-4d4f-b6c3-baeed69f63a7
checkpoint-status | 917bda5f-6ae2-4f9d-8888-4e38dcc97487 |  | checkpoint | Must notify projects with a minimum of 2 weeks prior to starting the project using Allco’s Applicator Portal.
checkpoint-status | df3e5f9f-cf6f-4f9c-a629-1ef38cc0fe5d |  | checkpoint | Must arrange pre-install meeting with relevant parties including contractor, applicator, steel fixers, concreter and an Allco TA representative.
checkpoint-status | 017cac68-59be-4ae8-9ee8-c95b6a1709ad |  | checkpoint | If site is hydrostatic, adequate water control measures must be in place during construction.
checkpoint-status | 7e7f2903-cb08-421d-b824-64917ae229bc |  | checkpoint | Must follow specification or in the absence of a one, follow detail provided by Allco.
checkpoint-status | 2a678551-a4ae-420c-b77c-cbdd144fc67e |  | checkpoint | Must follow Allco QA requirements using either CONQA, Allco’s QA manual forms or a pre-approved 3rd party QA System.
checkpoint-status | 96a15f10-45cb-4e5f-bb27-ee9912912670 |  | checkpoint | An adequate collection of photos showing pre, during & post installation details.
checkpoint-status | 9af41a7e-2341-438a-813b-2fded5e7b8bc |  | checkpoint | Photos must clearly show all products used in installation.
checkpoint-status | 037b0cc3-bff2-451b-b302-999d8275a204 |  | checkpoint | All applicators on site are Allco Approved, trained and licensed applicators and are employees of the Approved Applicator at time of installation.
checkpoint-status | 117c62e2-f0b1-4476-864f-1677ba224449 |  | checkpoint | Allco TA must be notified at least 48 hours before any major steps throughout the project so site visits can be arranged.
checkpoint-status | 9555f7de-d753-46be-8b55-bee453fcd193 |  | checkpoint | If walls are shotcrete then water control is required during and post construction (non-hydrostatic).
checkpoint-status | dff0a985-493b-4470-b67f-d023f60cede9 |  | checkpoint | Complete and submit a Warranty Request Form.
checkpoint-status | b733f027-dda5-4448-8b00-3397f0060f52 |  | checkpoint | Applicator must hand over Warranty and Care and Maintenance Plan to the Building Owner.
checklist-flat | 13a94e53-6fa3-4feb-9c18-b47ce5718df6 |  | checklist | Allco Warranty Checklist - Small Lift Pits |  |  |  |  | Yes | Allco Warranty Checklist - Small Lift Pits | a080d3ce-e639-4e12-a7a2-91c10e8eac3a
checkpoint-status | 3074f478-0ee2-42c2-82fc-a808fefa79f3 |  | checkpoint | Work must only be carried out by an Allco pre-approved applicator.
checkpoint-status | 379e9c08-5e41-4dad-a1a0-164018f4a248 |  | checkpoint | Applicator must notify Allco a minimum of 1 week prior to starting the project using Allco’s Applicator Portal.
checkpoint-status | a244f2ed-6a7f-40ed-a620-fd2276126c2c |  | checkpoint | Site presence by an Allco TA representative is at the discretion of Allco.
checkpoint-status | 8b336035-42d6-45d0-906d-354dab5a0c46 |  | checkpoint | If site is hydrostatic, adequate water control measures must be in place during construction.
checkpoint-status | f082bdbf-7b68-4957-a3d1-0cb9d910be7e |  | checkpoint | Full encapsulation; footings, under-slab & walls, including Waterstop RX in all cold joints.
checkpoint-status | 98d6c697-2d77-4af2-90f3-fc39bee1b810 |  | checkpoint | Have followed specification or in the absence of a specification, followed detail provided by Allco.
checkpoint-status | 509290f7-af86-422e-9c40-9b77d726752c |  | checkpoint | Followed Allco QA requirements using either CONQA, Allco’s QA manual forms or a pre-approved 3rd party QA System.
checkpoint-status | a9e890d5-8e2e-45c0-b38a-49f0cba98bab |  | checkpoint | An adequate collection of photos showing pre, during & post installation details.
checkpoint-status | ca94bef3-bae7-435c-86fa-ec10a5b0e356 |  | checkpoint | Photos must show all products used in installation. (Failure to do so will mean that the project will be ineligible for a System Warranty.)
checkpoint-status | 3e46c7f9-10e9-498a-81e2-3f0ae84970c2 |  | checkpoint | At least one Allco Approved, trained and licensed applicators who are employee of the Approved Applicator at time of installation.
checkpoint-status | 46e6aff8-4c51-4f4b-8f97-1182fa9ccf81 |  | checkpoint | Complete and submit a Warranty Request form via Allco Applicator Portal.
checkpoint-status | b7c5cd7c-83ab-4827-8d68-12f8eb61b41c |  | checkpoint | Applicator will supply copies of the Workmanship Warranty*, Allco Warranty Document and appropriate Care and Maintenance Plan to the Building Owner.
label | 89997685-c97a-592c-9bf4-5fa4c1b2d691 |  | note | *Under System Warranty, the Workmanship Warranty (also known as Certificate of Work) must be of at least 5 years in the case of commercial buildings and as required by consumer law applicable at the time for residential buildings.
checklist-flat | 7d04096e-9ccd-4ae2-acb8-84c085693ddd |  | checklist | Project Sign Off Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | Project Sign Off Checklist - Nuraply 3PM Membrane | 06828ce3-e556-462e-8ed0-7673f0fc109f
checkpoint-no-status | 56bfab15-b3d1-438a-811d-324080d434a0 |  | checkpoint | Products used
text | 75cdaedd-80a0-5ccc-87ff-cd727c99f6a4 |  | textbox | Products used
checkpoint-status | 071ecc87-2f6b-4329-8395-157bcf5d9f51 |  | checkpoint | Substrate readiness checklist completed
checkpoint-status | bb8271e8-a31e-4de4-8109-fe45407877a6 |  | checkpoint | Under Flashings installed to all corners and upstands
checkpoint-status | 80e06550-b0f0-413f-a51e-e7c57a55993b |  | checkpoint | Gutters correctly and neatly installed, particularly the internal corners
checkpoint-status | 0b5a4aed-1d71-4b85-80db-955849e39f74 |  | checkpoint | Roof drains & overflows installed to specification and watertight
checkpoint-status | 77cdfa90-adac-47f2-9621-1d8ab5ba9141 |  | checkpoint | Membrane fully adhered to substrate with no evidence of bubbles or lifting. Correct quantities of primer/adhesive used as per specification
checkpoint-status | 7dadebd8-d717-4ff0-9a7a-5f0bc0ed61d5 |  | checkpoint | Cap sheet and basesheet fully bonded together, no areas of delamination
checkpoint-status | c1e4149d-6966-461b-9573-8d25f7a64d62 |  | checkpoint | Cap sheet side laps 80mm and end laps 100mm fully welded and tidily seamed off
checkpoint-status | fe12c38f-0128-471b-86a7-e34487dec4ee |  | checkpoint | No sign of overheating/excessive bitumen bleed from laps (over 2-3mm)
checkpoint-status | f0dec2e4-cd10-4180-92b6-7a151d1c2c37 |  | checkpoint | Cap sheet and base sheet laps offset satisfactorily. No three layer lap build-ups
checkpoint-status | 53653cf4-5c97-449f-9685-0f9533432c45 |  | checkpoint | Overall installation free of wrinkles, creases and splits
checkpoint-status | a550c01a-b68f-4f07-b319-48eade88aee3 |  | checkpoint | Nuravents installed to specification (one every 20m²)
checkpoint-status | 8b15ae87-f5b1-4ede-b4c4-00dacaec74f8 |  | checkpoint | All penetration details completed to specification including under/over flashing
checkpoint-status | 6ee6317e-53e5-4d18-bd01-53727b004676 |  | checkpoint | Standard details used throughout including at upstands, parapets, construction joints
checkpoint-status | dfbdb211-365d-45a0-8d0c-4cf14d7cb5a3 |  | checkpoint | All non standard details installed as per pre-approved specifications (attach approved drawing)
checkpoint-status | 6bf0c406-f5e1-439b-920c-5d72a9336a79 |  | checkpoint | Gutters and outlets have been flood tested
checkpoint-status | 48eed571-6c48-4af0-98d5-ba2378dec0d0 |  | checkpoint | Any damage to cap sheet repaired to specification
checkpoint-status | 4e35b159-0bd8-44a3-b4e2-d8c8b4ebb33a |  | checkpoint | Sand finished cap sheets have Nura Colour applied to specification. Surfaces thoroughly cleaned before coating
checkpoint-status | 862113a3-05ed-4ab9-8e1f-e196ae3a2a51 |  | checkpoint | Remedial action required?
holdpoint | 38cea451-b6cc-4aeb-ac8a-5132b02a3ad1 |  | signoff | Signed by Builder & Applicator
checklist-sectioned | 9553c0df-60f2-4899-a901-4e1daef87a24 |  | checklist | Grouting QA Form |  |  |  |  | Yes | Grouting QA Form | 7245b2e0-401c-4460-820e-26aa1fb5cb9b
checkpoint-group | 7603511a-9c10-4e47-b349-27226e660334 |  | section | Preparation
checkpoint-status | 35fd9cc2-07bc-4f3b-8c6d-470ef886d0ab |  | checkpoint | Concrete checked and confirmed as clean
checkpoint-status | bc15cbbe-3d01-4c2b-9e35-60815401cdd9 |  | checkpoint | Concrete surface tensile strength (if required)
text | dbb3b309-c275-5490-a12f-ccf2ea339bf6 |  | textbox |  | Mpa
checkpoint-status | af1f0ce7-3162-4300-abdd-2ab1f8184d95 |  | checkpoint | Concrete confirmed as watertight (if using formwork)
checkpoint-status | b6c011df-0863-4feb-b2c3-8ba288f59c07 |  | checkpoint | Concrete and other porous surfaces thoroughly soaked with water and at Saturated Surface Dry condition when grouting commences
checkpoint-group | 04c49726-bb11-4767-9549-304e5f6efc2e |  | section | Ambient conditions during mixing
checkpoint-status | 1cfa2bf7-3c1a-451e-a52f-ebddc6e3fe41 |  | checkpoint | All conditions recorded
text | 600d5ff8-e3ae-5d76-9b26-1875f1e45f39 |  | textbox | Temperature (ambient & substrate) + Time
text | 7dcca1ab-85f3-540f-b997-e20242c07756 |  | textbox | Humidity (ambient) + Time
text | f1373ccf-6c12-51e0-88c7-ca02d66d2874 |  | textbox | Weather during application + Time (e.g. record time of rain, snow, hail, etc.)
checkpoint-group | 403f232b-fb6e-4b15-9af7-5c5b2c23b16b |  | section | Ambient conditions during placement
checkpoint-status | 5f9c5370-b4b4-40c2-9b56-ce343a047370 |  | checkpoint | All conditions recorded
text | e8453e44-6567-5fd7-86b0-ba6b00a77a21 |  | textbox | Temperature (ambient & substrate) + Time
text | ce961cca-76d5-5d7e-87ef-459461a6bbc6 |  | textbox | Humidity + Time
text | e1e8256d-af89-5c1a-a673-59d557513ca6 |  | textbox | Weather during application + Time (e.g. record time of rain, snow, hail, etc.)
checkpoint-group | 2b2267b5-ac9c-48cb-a635-1179f68614a5 |  | section | Ambient conditions during early curing
checkpoint-status | a9bd1145-632d-4cb7-a3d9-53f3c4cdd399 |  | checkpoint | All conditions recorded
text | 99f2099f-3bf6-5549-aae4-586d2477c5a4 |  | textbox | Temperature (ambient & substrate) + Time
text | bd3b3c84-47d5-5614-8329-1b5294b6991e |  | textbox | Humidity + Time
text | ead8da98-3893-5451-97ec-b52f51f5c5e2 |  | textbox | Weather during application + Time (e.g. record time of rain, snow, hail, etc.)
checkpoint-group | 0f6cd13e-5e47-4f7e-997d-56045599c16e |  | section | Product Consumption
checkpoint-status | 3465e396-591a-48d6-a8ff-ba732506f96f |  | checkpoint | Complete details below
text | baee857f-f18f-5bfb-bf97-3b2e3ebc4124 |  | textbox | Name of grout used
text | 10bc531a-e6e2-58ba-9b55-7bc696b06c83 |  | textbox | Batch number
text | db2e79c2-b46c-5827-bb95-8b2a1c7c84b1 |  | textbox | Number of bags used
text | c4da80ec-baf1-5fca-b883-2a955a2b3909 |  | textbox | Volume of mix water used
text | e9ecd9fe-5101-53c2-928a-383351419ed0 |  | textbox | Mixer for grout mixing
checkpoint-status | f027798d-34c6-4faa-b8fb-7d66aea84c96 |  | checkpoint | Grout flow test results (if required)
text | 7e34389d-b098-5d18-bf78-4128a397e936 |  | textbox | Grout flow test method used (if applicable) e,g, NZS3112
text | 7951cbc8-c255-5e69-baf4-d36eacbad31d |  | textbox | References of compressive strength cubes cast (if any)
checkpoint-group | 8c8ca040-27c3-4d6b-9ecc-0477e650093d |  | section | After Completion
checkpoint-status | d8392e8b-364f-4ce9-a079-fb6e907adbe9 |  | checkpoint | Compressive strength results (cube reference numbers and strength).
text | 31aab300-ac27-51e7-9ccd-f43ccee5373f |  | textbox
checkpoint-status | c2af7dba-8f61-4999-b814-34ba6663ece5 |  | checkpoint | Visual examination of completed works
holdpoint | 76fb60b3-b345-438c-80b0-2cbe8b31fdb4 |  | signoff | Signed by installer
checkpoint-status | e5d5f4d9-fa34-4e2a-b170-19eee492a523 |  | checkpoint | Contractor signoff
holdpoint | 9f1014a7-3e1e-4544-b750-4d6031fafcc0 |  | signoff | Signed by contractor
checklist-flat | c76a9f67-6713-406c-a256-45b282f718dd |  | checklist | New Plywood Substrate Readiness Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | New Plywood Substrate Readiness Checklist - Nuraply 3PM Membrane | a8674115-e84f-454a-99b0-1ca330877034
checkpoint-status | 56c6f6db-168a-4d9e-bd04-b70b8c9364e8 |  | checkpoint | Area ready?
checkpoint-status | 5b2c7281-172b-4699-b626-f02f4f2ed443 |  | checkpoint | Structure complies to the New Zealand Building Code and plywood complies with AS/NZ 2269
checkpoint-status | 658aab08-27a3-4bfa-95db-646cf44a2826 |  | checkpoint | CCA H3.2 treated plywood sheets used
label | 1921163b-055d-5d54-98db-c8761a30cbb3 |  | note | 17mm thick for roofs, 20mm thick for decks
checkpoint-status | a3ea0a01-ec8d-4604-a162-7e2194ac8969 |  | checkpoint | Plywood sheets supported at 600mm centred rafters and nogs for roofs and decks, unless otherwise specified
checkpoint-status | 8b760178-fcca-498f-a40a-890b54a760ad |  | checkpoint | Sheets stagger lay (fully offset) with falls as per plan
checkpoint-status | c708fce4-f325-48de-a99c-f1b9759e9181 |  | checkpoint | 5mm clearances from all abutments, 5mm radius to all exposed edges
checkpoint-status | f989ef67-33f7-4e2f-9692-736c2d585453 |  | checkpoint | All sheet edges supported, fixed 150mm on edges and 200mm through girth, edges butt-jointed with no gaps except at abutments
checkpoint-status | 2a9ddb85-ebd1-4543-9591-4f95587e2d93 |  | checkpoint | Sheets fixed by gluing and Stainless Steel countersunk screw fixing
checkpoint-status | d1d5915e-43bb-416f-ad30-e9eacd00c530 |  | checkpoint | Fillets installed to all internal junctions and neatly fitted
checkpoint-status | bfa81b0a-1938-4267-bd27-1a177c3a1a71 |  | checkpoint | Mitres neatly formed
checkpoint-status | ae733f10-7c5a-4fe0-9ac5-080c8838e433 |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status | 276d8be6-0bac-438c-a33a-e49bdda478f0 |  | checkpoint | Sharp edges and lips removed and cavities filleted. All joints flush
checkpoint-status | 6c00e913-22b8-467b-91a7-c2b2dbd3c10f |  | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures
checkpoint-status | 48e59c3b-0850-4dc8-b355-ad577e629313 |  | checkpoint | Substrate dry, clean, firm and suitable condition for laying
checkpoint-status | 8ae0315d-93a6-4808-ba24-73934307d1dc |  | checkpoint | When substrate is ready complete send this as report to Nuralite applicator
holdpoint | 52d40977-0304-4eee-be17-970bd4e159ae |  | signoff | Signed by head contractor
checklist-flat | 650969e1-8bbe-42d0-b375-de63c7ccc4d0 |  | checklist | Existing Roof Substrate Readiness Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | Existing Roof Substrate Readiness Checklist - Nuraply 3PM Membrane | ae5b95ca-677a-4158-ac7d-dbebe6f52e8c
checkpoint-status | e6333d44-befa-4dce-8745-63ddcb3559ad |  | checkpoint | Area ready?
checkpoint-status | ba6e22c1-fdfd-40c7-9b8a-ae130af62907 |  | checkpoint | Confirm the substrate is suitable with no signs of deterioration in the form of rust or rot
checkpoint-status | 4898784e-86dd-430d-8d6d-288c5455b05b |  | checkpoint | Cladding, doors and windows removed to allow upstands to be formed
checkpoint-status | a3161a42-764a-49d0-8148-c0959d3131f4 |  | checkpoint | Confirm the substrate slope exceeds minimum requirements unless approved by Nuralite for this specific project
checkpoint-status | 142c9ab1-9900-4acd-ab0d-6f610a6d2ee1 |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status | 43e5bc51-fdcc-421c-a74f-103a5dfd1f15 |  | checkpoint | Ensure only approved accessories to be used for drainage and venting
checkpoint-status | 49cf1cb5-9e1c-472c-b9e9-53a18b80899b |  | checkpoint | Review penetrations to minimize number and complexity
checkpoint-status | a0be767d-6cbd-46fc-b300-0c4202d2e148 |  | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures
checkpoint-status | 48f526b5-2a2f-4e83-a962-9467e8e1bbb2 |  | checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite systems
checkpoint-status | 6b0f32f6-386f-490a-82f3-231ba28bc6ee |  | checkpoint | When substrate is ready complete send this as report to Nuralite applicator
holdpoint | 0ded08ba-5f6a-47da-883f-1d1700e1ea75 |  | signoff | Signed by head contractor
checklist-flat | 022376d5-9825-4c76-9f98-22a818c68e04 |  | checklist | Allco Warranty Checklist - Projects Over 200m² / Full Encapsulation |  |  |  |  | Yes | Allco Warranty Checklist - Projects Over 200m² / Full Encapsulation | c06dce7f-b4be-4474-85f6-bfbbc433087f
checkpoint-status | 8d1b34e7-1cc5-4ca5-aa49-1d0195ddc903 |  | checkpoint | Project must be at least 200m2 of Allco supplied products.
checkpoint-status | c614fbc1-1eea-4014-b22c-e1d4bcb6147d |  | checkpoint | Work must only be carried out by an Allco pre-approved applicator.
checkpoint-status | d62d3a97-8572-42d4-9344-8960fa8807ea |  | checkpoint | Applicator must notify Allco a minimum of 2 weeks prior to starting the project using Allco’s Applicator Portal.
checkpoint-status | b913ef86-0a09-4917-94d1-bf666302b852 |  | checkpoint | Specification must be assessed by Allco prior to pre-install meeting with TA team representative.
checkpoint-status | 5af625d4-3478-44b1-bc3f-1bbf539e3f65 |  | checkpoint | Pre-install meeting with relevant parties including contractor, applicator, steel fixers, concreters and an Allco TA representative.
checkpoint-status | ed8a280a-ee24-4c03-9b02-7dfeac1574af |  | checkpoint | If site is hydrostatic, adequate water control measures must be in place during construction.
checkpoint-status | 8602199f-4753-47a1-ba88-037677199690 |  | checkpoint | Full encapsulation; footings, under-slab & walls, including Waterstop RX in all cold joints.
checkpoint-status | f0b39e31-d635-430d-995d-a1d21d0b1f95 |  | checkpoint | Have followed specification or in the absence of a specification, followed detail provided by Allco.
checkpoint-status | 9c44f347-1e61-49d7-aadf-9d377f5b317c |  | checkpoint | Followed Allco QA requirements using either CONQA, Allco’s QA manual forms or a pre-approved 3rd party QA System.
checkpoint-status | 50cab3f3-39ba-4a77-880e-b929a0255a6f |  | checkpoint | An adequate collection of photos showing pre, during & post installation details.
checkpoint-status | 84d80d60-2936-4cca-9b5d-3dc50ba2f71e |  | checkpoint | Photos must show all products used in installation. (Failure to do so will mean that the project will be ineligible for a System Warranty.)
checkpoint-status | ba53796e-05b1-4ed0-9eb1-fcfc1d0b690c |  | checkpoint | All applicators on site are Allco Approved, trained and licensed applicators and are employees of the Approved Applicator at time of installation.
checkpoint-status | 8475ab46-a17e-4809-8d4e-c12703de6357 |  | checkpoint | Allco TA must be notified at least 48 hours before any major steps throughout the project.
checkpoint-status | 8ca159e7-7d98-4297-a804-7521b7b1bef7 |  | checkpoint | If walls are shotcrete then water control is required during and post construction (nonhydrostatic).
checkpoint-status | f51f4548-b300-4b35-b9a3-e42183e786ef |  | checkpoint | Complete and submit a Warranty Request form
checkpoint-status | 3ce7e7a8-519f-4bce-b8ff-1e3ee48135bb |  | checkpoint | Applicator will supply copies of the Workmanship Warranty*, Allco Warranty Document and appropriate Care and Maintenance Plan to the Building Owner.
label | 5c61378f-86c9-5d1b-892e-bf043f9011d5 |  | note | *Under System Warranty, the Workmanship Warranty (also known as Certificate of Work) must be of at least 5 years in the case of commercial buildings and as required by consumer law applicable at the time for residential buildings.
checklist-flat | e9036c57-d961-4427-b936-efa0b4f551cf |  | checklist | SEALCO TPO - Plywood Substrate Readiness Checklist |  |  |  |  | Yes | SEALCO TPO - Plywood Substrate Readiness Checklist | 27b25526-5faa-4955-a507-fd277ac6fb1f
checkpoint-status | 31fa97e8-b6e3-4f52-88f0-53197adccb9e |  | checkpoint | Architect and builder are responsible for correct design, including falls, constructions and detailing of substrate.
checkpoint-status | 31864342-5747-49bd-aa91-7cfaa43064ea |  | checkpoint | CD Structural Grade H3.2 CCA treated Kiln Dried and min. 17mm thick.
checkpoint-status | a2952714-0d3a-4214-ba73-3dc93f937a28 |  | checkpoint | Use only square edged construction plywood with all edges fully supported with timber battens. (T&G plywood not acceptable)
checkpoint-status | 57da27e6-a673-49ff-bfc1-cfce790b170d |  | checkpoint | Sheets stagger laid (fully offset brick bond pattern), tight butted, with sanded C-face upwards and face grain at right angles to supports or crossmembers.
checkpoint-status | 2ee8dd04-80c1-458f-9b9e-58ea36c32387 |  | checkpoint | Plywood glued and screwed, fixed 150mm on edges and 200mm through girth.
checkpoint-status | e1785cb1-c216-407c-9c58-f03855645112 |  | checkpoint | Grade 316 stainless steel counter sunk screw fixing, min. 10-gauge x 50mm or a length 3 times that of the plywood thickness.
checkpoint-status | 8977213c-2112-41ee-918f-de73fe040c8b |  | checkpoint | Plywood installed with correct falls and no ponding.
checkpoint-status | c1c2f824-bf53-4f83-a390-c143ad667ab9 |  | checkpoint | No fillets required; all internal angles formed at 90 degrees.
checkpoint-status | 0b04a87c-1015-4179-900d-8ddec17ce858 |  | checkpoint | 3 - 5mm clearances from all abutments.
checkpoint-status | bad99a4a-4b83-45a4-8ea3-0daa3c105fb1 |  | checkpoint | Pre-inspection of all penetrations and details.
checkpoint-status | 3a083e89-a523-4b9c-8fcb-49fdaf1dd6b1 |  | checkpoint | 5mm radius to all external corners.
checkpoint-status | 58b271fb-815e-4561-86d8-ff5a52482b1e |  | checkpoint | Using a moisture measure ensure moisture content at the time of installation is below 20%.
checkpoint-status | c4769908-564e-483c-bc50-2a66bf1bd436 |  | checkpoint | Rainwater outlets and overflow recesses formed in substrate to fit propriety outlets.
checkpoint-status | facbdc04-285f-4e91-be01-6222c78a07eb |  | checkpoint | Sharp edges and lips removed, and cavities filled. All joints flush.
checkpoint-status | fea64e6e-7500-42d1-8604-af0f09d1fd82 |  | checkpoint | Substrate is clean, firm, and suitable condition for laying.
checkpoint-status | 0a7525c9-bbce-4911-8587-59bd81b88b50 |  | checkpoint | Plinths formed for any exterior ventilation, fixtures or similar.
checkpoint-status | 9bd8b618-b687-4741-8465-fe8fdbdf2043 |  | checkpoint | Builder has installed flashings and tapes that are compatible with system
checklist-sectioned | fe0329bc-589c-4551-91c7-9a3fa0e4fa35 |  | checklist | SEALCO TPO - Quality Control Checklist |  |  |  |  | Yes | SEALCO TPO - Quality Control Checklist | 945ab0d7-5468-4ef2-9727-944479317b70
checkpoint-group | c8af95f2-1cca-467b-8558-5edb7eb22c0a |  | section | QA Checks
checkpoint-status | 24d80fb3-2de9-4b7d-a332-96431fed5a60 |  | checkpoint | Plywood substrate stagger-bond laid with each sheet offset at least 300mm and edges supported.
checkpoint-status | f96008b8-7272-4c5a-8862-203e24c60d65 |  | checkpoint | Plywood substrate s/s screw fixed to E2/AS1 specification, no loose/drummy sheets or delamination. (
checkpoint-status | b3e3858d-b705-434d-84e4-40fdc7a45868 |  | checkpoint | Plywood sheets to be tight butted and 3mm gap to all abutments. (No T&G sheet joints)
checkpoint-status | 3268eb0f-2a45-4771-bd92-8490c044942b |  | checkpoint | Substrate clean, dry and free from foreign matter and sharp edges - Plywood moisture tested with moisture meter and is below 20%. Any holes or indentations filled with builders’ bog and flushed off smooth.
checkpoint-status | 8a385952-146b-4360-af6d-b13de6cb8dc1 |  | checkpoint | All soft areas in concrete filled and cracks repaired with non-shrink mortar. Any curing compounds removed. Maximum moisture of relative humidity 75% - verified using an approved method.
checkpoint-status | 44900fa2-0825-46b2-93c1-d77a23f0bc53 |  | checkpoint | All external corners chamfered 5mm radius.
checkpoint-status | 60faa7d9-ad26-4fd8-9b25-571c37e83d61 |  | checkpoint | 36mm PVC tapes to plywood sheet joints. For concrete, install grid tapes if concrete surface is to be vented.
checkpoint-status | e67d2cac-2449-4731-bbaf-b0710c94815e |  | checkpoint | Movement joints identified and installed to approved specification / detail (attach detail drawings)
checkpoint-status | 9ff2301b-0a6c-44f7-9c28-23fea5f2a244 |  | checkpoint | Pipe penetrations and rainwater outlets detailed as per Sealco specification.
checkpoint-status | b163ce27-2040-4e4f-adaf-bf0661e89e6c |  | checkpoint | Gutters correctly and neatly installed, particularly the internal corners - ensure laps above roof line.
checkpoint-status | 238ef09e-2faa-41d5-8472-29aebbaef675 |  | checkpoint | DrainRITE® roof drains installed to Sealco specification.
checkpoint-status | b2e3d81f-e87e-4e0c-9e31-7a9de7c6962a |  | checkpoint | VentRITE® overflows installed to Sealco specification.
checkpoint-status | 568883f6-70a8-474f-8272-057ccecef4f5 |  | checkpoint | EcoTUFF® adhesive within shelf life and correctly mixed.
checkpoint-status | f6550a35-52bf-4a21-92c2-6f46ba007cdc |  | checkpoint | EcoTUFF® installed to Sealco specification, ensuring adhesive applied to substrate and membrane at correct rate.
checkpoint-status | 25d4ab02-fde4-48f4-b0a5-f064c20071b1 |  | checkpoint | All laps minimum 40mm. Lap tested and watertight
checkpoint-status | c0500c23-1e3f-4fd5-98ca-f0019b9f5269 |  | checkpoint | No air entrapment or foreign matter contamination under the EcoTUFF® membrane.
checkpoint-status | bbc133b0-82e7-4a31-9e6c-983d1096af79 |  | checkpoint | EcoTUFF® sheets laid across the roof slope, so water runs over the laps rather than down lap edge
checkpoint-status | 729571ae-c92d-4992-97e6-cfc1b5fec5b4 |  | checkpoint | Membrane termination completed to Sealco approved detail.
checkpoint-status | 084c0a9a-30c5-4a65-82f7-0271f9a51792 |  | checkpoint | EcoTUFF® roof vents installed to specification (min. two vents / roof area, with one every 90m²)
checkpoint-status | fae32406-3b38-4a8d-b13c-18f41e58bc2b |  | checkpoint | All penetration details completed to Sealco specification including EcoTUFF® over flashing.
checkpoint-status | 14b706a1-93dc-4df8-a999-71dd8b76b6d4 |  | checkpoint | All non-standard details installed as per pre-approved specifications (attached approved drawings).
checkpoint-status | 6c4a85ca-2de0-45a8-9f4f-69ece14118f6 |  | checkpoint | Any mechanical damage to EcoTUFF® repaired to Sealco specification
checkpoint-status | 1c2c508d-a2be-4aa6-b127-667c9851d2d1 |  | checkpoint | Overall installation free of wrinkles, creases and splits, with no air or foreign matter entrapped.
checkpoint-status | 7cfe69ac-6a2e-4f38-bfb6-69fb80613c2b |  | checkpoint | Job sheets completed recording area installed, date of installation, membrane batch numbers etc.
checkpoint-status | 36f9f2dd-03c3-4115-862d-0ef9cc15d18f |  | checkpoint | Remedial action required? If yes, attach photos of damaged areas repaired.
checkpoint-group | 9d6d60c9-db29-4e8e-aaac-afa57327742d |  | section | Priming coverage calculation
checkpoint-no-status | 5867312c-4230-460a-9082-780cd1eb6249 |  | checkpoint | Calculation
text | 31548e5b-0cdc-5f2f-a255-7fee3f79134f |  | textbox | Installation Area (M²)
text | 88ce8cf4-3b63-5a43-8042-01b76d43ebcc |  | textbox | Coverage (ltr/M²)
text | 0c0ffa69-7ac2-5533-b9b6-dbb85ecaf321 |  | textbox | Litres required
text | fd1c4c8e-751f-5ad1-bc87-1c10c1ac9c53 |  | textbox | Pails required
text | 088d3c7b-3ca3-56a2-b582-f1a0c8dc8983 |  | textbox | Pails used
checklist-flat | c40a6251-63e1-4706-9885-46fba73ff455 |  | checklist | Project Sign Off Checklist - Membrane |  |  |  |  | Yes | Project Sign Off Checklist - Membrane | 96cd194e-6b0d-4863-a044-a9f599a94d4f
checkpoint-no-status | 0b942e33-fb19-4d55-9ecd-612bceca5d38 |  | checkpoint | Products used
text | ec8a6bdf-c732-5577-aa6b-8cd0a6221de7 |  | textbox | Products used
checkpoint-status | ab10ff47-98fb-41aa-866a-b7600f81da34 |  | checkpoint | Substrate readiness checklist completed
checkpoint-status | 367547ff-b5ef-4820-8110-c86022a7702a |  | checkpoint | Under Flashings installed to all corners and upstands
checkpoint-status | 3c43ac70-f0cb-4c8c-9afd-c3e7ac0ce96f |  | checkpoint | Gutters correctly and neatly installed, particularly the internal corners
checkpoint-status | b6629b26-dfbd-4418-9298-4da5fd363e2e |  | checkpoint | Roof drains & overflows installed to specification and watertight
checkpoint-status | f203444e-f939-43a2-a97f-1008dc9f93b3 |  | checkpoint | Membrane fully adhered to substrate with no evidence of bubbles or lifting. Correct quantities of primer/adhesive used as per specification
checkpoint-status | e1047b72-04cd-4558-a43a-2509f5a62054 |  | checkpoint | Cap sheet and basesheet fully bonded together, no areas of delamination
checkpoint-status | de8a8892-8b32-4b51-9279-683f517a26b6 |  | checkpoint | Cap sheet side laps 80mm and end laps 100mm fully welded and tidily seamed off
checkpoint-status | 5b140c7c-9de9-427b-9447-eafe7a2c39b4 |  | checkpoint | No sign of overheating/excessive bitumen bleed from laps (over 2-3mm)
checkpoint-status | 369689b7-09b3-4aa1-a2a1-118690167a5b |  | checkpoint | Cap sheet and base sheet laps offset satisfactorily. No three layer lap build-ups
checkpoint-status | 444cf754-1619-4554-b812-f654822f7d59 |  | checkpoint | Overall installation free of wrinkles, creases and splits
checkpoint-status | ab457e33-9a73-40f5-ad98-7a078ba0383d |  | checkpoint | Vents installed to specification (one every 20m²)
checkpoint-status | a2b2a527-1065-4ebb-ac4a-872ce15748eb |  | checkpoint | All penetration details completed to specification including under/over flashing
checkpoint-status | 8589d4f2-3c93-4366-85b5-e6a6a569cf3e |  | checkpoint | Standard details used throughout including at upstands, parapets, construction joints
checkpoint-status | 8a304abb-a119-40c1-8d5f-eb25ee5d9520 |  | checkpoint | All non standard details installed as per pre-approved specifications (attach approved drawing)
checkpoint-status | 87f629e8-a92b-4b66-9538-c8de9fb689e4 |  | checkpoint | Gutters and outlets have been flood tested
checkpoint-status | c0110aa8-0d71-410f-8555-02cc053ba55c |  | checkpoint | Any damage to cap sheet repaired to specification
checkpoint-status | 29352747-d081-4335-a68a-b4ece50a74e9 |  | checkpoint | Sand finished cap sheets have gel applied (if applicable). Surfaces thoroughly cleaned before coating
checkpoint-status | 22ad6dab-c804-443c-bcbb-c584b964a527 |  | checkpoint | Remedial action required?
holdpoint | 45804454-e164-48f7-974e-04cca5ff1989 |  | signoff | Signed by Builder & Applicator