## EVENTS KITCHEN QA
TRANSPLUMB EVENTS KITCHEN QA
|  |  | CLOSE OUT | ATTACH PHOTOS OR FILE | COMMENTS AND SIGNATURE
CLIENT xxx AREA xxx NAME xxx DATE xxx
ITEM 1 | Take 5/SWMS/Inductions been completed before works start |  | YES/NO | YES | YES
ITEM 2 | Kitchen layout is correct as per current drawings issued by client |  | YES/NO | YES | YES
ITEM 3 | Has a gas test been completed |  | YES/NO | YES | YES
ITEM 4 | Do all gas appliances have the minimum 500mm clearnace from combustable surfaces? |  | YES/NO | YES | YES
ITEM 5 | Do all gas appliances have an isolation valve installed and is valve in good condition? |  | YES/NO | YES | YES
ITEM 6 | Have all gas appliances been fixed in position? |  | YES/NO | YES | YES
ITEM 7 | Are gas flexable hoses installed off the floor? |  | YES/NO | YES | YES
ITEM 8 | Are the gas LPG bottles installed with the minimum 1500mm clearance from an ignition sorce and secured to the base plate with chain? |  | YES/NO | YES | YES
ITEM 9 |  |  | YES/NO | YES | YES
ITEM 10 | Have all water and waste pipes been installed neatly? |  | YES/NO | YES | YES
ITEM 11 | Is hotwater unit connected and working as required? |  | YES/NO | YES | YES
ITEM 12 | Is macerator unit connected and working as required? |  | YES/NO | YES | YES
ITEM 13 | Are sullage tanks and sewer connections in place and connected as required? |  | YES/NO | YES | YES
ITEM 14 | Is water live to kitchen and has all water and waste been checked for leaks and repaired if required |  | YES/NO | YES | YES
ITEM 15 | Have all appliances been commissioned? Are they working as intended? |  | YES/NO | YES | YES
ITEM 16 | Area Clean |  | YES/NO | YES | YES
ITEM 17 | SIGN OFF
C

## FIX 1
TRANSPLUMB FIX 1 QA
|  |  | CLOSE OUT | ATTACH PHOTOS OR FILE | COMMENT & SIGNATURE
CLIENT xxx AREA xxx NAME xxx DATE xxx
ITEM 1 | Are you working to an approved drawing |  | YES/NO/NA | YES | YES
ITEM 2 | Setout is correct as per current approved drawings |  | YES/NO/NA | YES | drawing number
ITEM 3 |  |  | YES/NO/NA
ITEM 4 | Check for no cross-connection on all water lines |  | YES/NO/NA | YES | YES
ITEM 5 | Support and fixings checked (water hammer/silicone) |  | YES/NO/NA | YES | YES
ITEM 6 | are all lines new and existing capped for testing? |  | YES/NO/NA | YES | YES
ITEM 7 | Pressure test Waterlines 1500KPA |  | YES/NO/NA | YES | YES
ITEM 8 | fixture waste points heights and centres doubled checked before wall sign off |  | YES/NO/NA | YES | YES
ITEM 9 | all suspended drainage has been supported as per AS.3500 requirements |  | YES/NO/NA | YES | YES
ITEM 10 | all suspended drainage been flow tested for leaks |  | YES/NO/NA | YES | YES
ITEM 11 | Please supply photos of all water and waste completetd installations |  | YES/NO/NA | YES | YES
ITEM 12 | Area clean |  | YES/NO/NA
ITEM 13 | Final Sign off - Pass when happy to proceed |  | YES/NO | YES | YES
ITEM 10
ITEM 9
ITEM 10
ITEM 11
ITEM 12
ITEM 13
ITEM 14
ITEM 15
ITEM 16
ITEM 17
ITEM 18
ITEM 19
ITEM 20
Pumpline installed correctly and fixings checked

## FIX 2
TRANSPLUMB FIX 2 QA
|  |  | CLOSE OUT | ATTACH PHOTOS OR FILE | COMMENT & SIGNATURE
CLIENT xxx AREA xxx NAME xxx DATE xxx
ITEM 1 | Only approved fixtures to be installed |  | YES/NO/NA | YES | YES
|  |  | YES/NO/NA | YES | YES
ITEM 2 | Check products for imperfections |  | YES/NO/NA | YES | YES
ITEM 3 | Fixtures installed as per approved drawing locations |  | YES/NO/NA | YES | YES
ITEM 4 | Check for no cross connections/leaks |  | YES/NO/NA | YES | YES
ITEM 5 | Hot water correct temperature & Hot water tempering valve set to 50c +/-5c) |  | YES/NO/NA | YES | YES
|  |  | YES/NO/NA | YES | YES
ITEM 6 | DDA Hot water correct temperature & Hot water tmv set to 42c +/-2c) |  | YES/NO/NA | YES | YES
ITEM 7 | Water pressure acceptable 350kpa - 500kpa |  | YES/NO/NA | YES | YES
ITEM 8 | Check all drainage is working correctly wth no leaks |  | YES/NO/NA | YES | YES
ITEM 9 | Clean out all strainers |  | YES/NO/NA | YES | YES
ITEM 10 |  |  | YES/NO/NA | YES | YES
ITEM 10 | Commission all fixtures |  | YES/NO/NA | YES | YES
ITEM 12 |  |  | YES/NO/NA | YES | YES
ITEM 11 | Final check for any leaks |  | YES/NO/NA | YES | YES
ITEM 14 |  |  | YES/NO/NA | YES | YES
ITEM 12 | Area clean and photos of all fixtures |  | YES/NO/NA | YES | YES
ITEM 16 |  |  | YES/NO/NA | YES | YES
ITEM 13 | Final Sign off - Pass when happy to proceed |  | YES/NO/NA | YES | YES
ITEM 18 | Final Sign off - Pass when happy to proceed |  | YES/NO/NA | YES
ITEM 19 |  |  | YES/NO/NA | YES
ITEM 20 |  |  | YES/NO/NA | YES
ITEM 21 |  |  | YES/NO/NA | YES
ITEM 22 |  |  | YES/NO/NA | YES
ITEM 23 |  |  | YES/NO/NA | YES
ITEM 24 |  |  | YES/NO/NA | YES
ITEM 25 |  |  | YES/NO | YES
ITEM 26 |  |  | YES/NO | YES
ITEM 27 |  |  | YES/NO | YES
ITEM 28 |  |  | YES/NO | YES
ITEM 29 |  |  | YES/NO | YES
ITEM 30 |  |  | YES/NO | YES
ITEM 31 |  |  | YES/NO | YES
ITEM 32 |  |  | YES/NO | YES
ITEM 33 |  |  | YES/NO | YES
ITEM 34 |  |  | YES/NO | YES
ITEM 35
ITEM 36
ITEM 37
ITEM 38 |  | Final fit-off inspection on all items
ITEM 39
ITEM 40
ITEM 41 |  | Check for no cross connections/leaks
ITEM 42

## PRESTART
Take 5 Pre-Start Safety Checklist
This checklist will help workers and contractors who are working on new or external worksites reduce their exposure to health and safety risk and hazards. It should take 5 minutes to complete.
site location and job number
name: |  |  |  |  | date: |  | task:
If you answer “no” to any of the questions below, you should make yourself acquainted with the site requirements before starting work
1. Have you completed a site induction? | Yes ☐ | No☐ |  | N/A☐
2. Do you know the site’s health and safety rules? | Yes ☐ | No☐
3. Are you familiar with security arrangements and the
system for reporting incidents, near misses and hazards? | Yes ☐ | No☐
4. Are you familiar with the emergency facilities and evacuation
procedure/route for the site? | Yes ☐ | No☐
5. Do you have access to appropriate emergency and
first aid equipment? | Yes ☐ | No☐
6. Have you asked the person in charge about all relevant
hazards? | Yes ☐ | No☐
If you answer “no” to any of the questions below, you may need to follow up with the person in charge before you start work to ensure your safety.
1. If the work involves a high risk task (such as work at
heights, hot-work, confined spaces), has a safe work method
statement or job safety analysis been completed? | Yes ☐ | No☐ | N/A☐
2. Do you have the correct procedures, equipment and PPE to
do the work safely? | Yes ☐ | No☐ | N/A☐
3. Has equipment that requires a lock/tag-out and/or power
that requires isolation/containment been completed? | Yes ☐ | No☐ |  | N/A☐
4. Is there appropriate separation of vehicles and people
during the proposed work? | Yes ☐ | No☐ | N/A☐
5. Is all required electrical/mechanical equipment in a safe
condition? | Yes ☐ | No☐ | N/A☐
6. Are all hazardous and/or dangerous goods/substances used
and stored according to their material safety data sheets? | Yes ☐ | No☐ | N/A☐
7.
Have you consulted with all fellow workers about the task to
be completed and the safe way to do it? | Yes ☐ | No☐ | N/A☐
8. Have you got a safe way of getting in and out of your work | Yes ☐ | No☐ |  | N/A☐
area?
9. Have any manual handling risks been identified and assessed? | Yes ☐ | No☐ |  | N/A☐
10. ARE THERE ANY ADDITIONAL SITE SPECIFC HAZARDS OR REQUIREMENTS |  | Yes ☐ | No☐ |  | N/A☐
COMMENTS:
print name: sign:
HAZARD LIST
HAZARD | EXAMPLE
A. ENTANGLEMENT | Limbs, hair, clothing, jewellery.
B. CRUSHING | Plant falling, moving, collapsing, contact with moving parts, trapped between.
C. CUTTING, STABBING & PUNCTURING | Contact with sharp, moving parts. Parts ejected, disintegrated.
D. SHEARING | Caught between two parts of equipment or plant structure.
E. FRICTION | Contact of moving parts, surfaces or materials.
F. STRIKING | Struck by or against, movement of parts/materials, ejection, structures.
G. HIGH PRESSURE FLUID | Hydraulic oil under pressure.
H. ELECTRICAL | Shock or burns in contact with electrical conduits, near conductors, circuit overload, leads/cables/switches etc. Damaged switches/leads/tools.
I. EXPLOSION | Gases, vapours, liquids, dust triggered by equipment.
J. SLIPPING, TRIPPING, FALLING | Surfaces uneven, slippery, obstacles, stairs, ladders, guardrails, holes.
K. ERGONOMIC | Poorly designed, seating, repetitive, posture, effort, lighting, mental, psychological, human error, behaviour.
L. MANUAL HANDLING | Too heavy/too extended or cramped causing stress/strain/fatigue.
M. ASPHYXIATION | Due to lack of oxygen, atmospheric contamination.
N. FIRE OR HIGH TEMPERATURE | Contact objects at high temperature. ie hot water/steam or injury due to fire.
O. TEMPERATURE | Ill health or injury due to exposure to high or low temperatures.
P. EXPOSURE | Exposure to chemicals, toxic gases/vapours/fumes, dust, noise, vibration, radiation, x-ray, bacteria or pressure.
Q. IMPROPER TOOLS | Incorrect tools available.
R. LAYOUT/SITING | Inability to access equipment.
S. PROCESS UPSETS | Operations goes outside normal limits.
T. EXTRAS | Communication, emergency, understanding/experience with procedures.

## ROOF QA
TRANSPLUMB ROOFING QA
|  |  | CLOSE OUT | ATTACH PHOTOS OR FILE | COMMENT & SIGNATURE
CLIENT xxx AREA xxx NAME xxx DATE xxx
ITEM 1 | Job Name/Number |  | YES/NO/NA | YES | YES
|  |  | YES/NO/NA | YES | YES
ITEM 2 | Job Description |  | YES/NO/NA | YES | YES
ITEM 2 | Are you trained in Working at Heights |  | YES/NO/NA | YES | YES
ITEM 3 | Take 5/SWMS/Inductions/Permits been completed before works start |  | YES/NO/NA | YES | YES
ITEM 4 | Are you working to an approved drawing |  | YES/NO/NA | YES | YES
ITEM 5 | Only approved materials to be installed |  | YES/NO/NA | YES | YES
|  |  | YES/NO/NA | YES | YES
ITEM 6 | Are all fixings correctly install as per AS 3500 |  | YES/NO/NA | YES | YES
ITEM 7 | Boxgutters/sump/downpipes installed and clipped correctly as per AS 3500 |  | YES/NO/NA | YES | YES
ITEM 8 | Flashings installed correctly and siliconed |  | YES/NO/NA | YES | YES
ITEM 9 |  |  | YES/NO/NA | YES | YES
ITEM 10 |  |  | YES/NO/NA | YES | YES
ITEM 10 |  |  | YES/NO/NA | YES | YES
ITEM 12 |  |  | YES/NO/NA | YES | YES
ITEM 11 | Carry out testing were possible |  | YES/NO/NA | YES | YES
ITEM 14 |  |  | YES/NO/NA | YES | YES
ITEM 12 | Area clean |  | YES/NO/NA | YES | YES
ITEM 16 |  |  | YES/NO/NA | YES | YES
ITEM 13 | Final Sign off |  | YES/NO/NA | YES | YES
ITEM 18 | Final Sign off - Pass when happy to proceed |  | YES/NO/NA | YES
ITEM 19 |  |  | YES/NO/NA | YES
ITEM 20 |  |  | YES/NO/NA | YES
ITEM 21 |  |  | YES/NO/NA | YES
ITEM 22 |  |  | YES/NO/NA | YES
ITEM 23 |  |  | YES/NO/NA | YES
ITEM 24 |  |  | YES/NO/NA | YES
ITEM 25 |  |  | YES/NO | YES
ITEM 26 |  |  | YES/NO | YES
ITEM 27 |  |  | YES/NO | YES
ITEM 28 |  |  | YES/NO | YES
ITEM 29 |  |  | YES/NO | YES
ITEM 30 |  |  | YES/NO | YES
ITEM 31 |  |  | YES/NO | YES
ITEM 32 |  |  | YES/NO | YES
ITEM 33 |  |  | YES/NO | YES
ITEM 34 |  |  | YES/NO | YES
ITEM 35
ITEM 36
ITEM 37
ITEM 38 |  | Final fit-off inspection on all items
ITEM 39
ITEM 40
ITEM 41 |  | Check for no cross connections/leaks
ITEM 42

## VARIATIONS
TRANSPLUMB VARIATIONS
|  |  | CLOSE OUT | ATTACH PHOTOS OR FILE | COMMENT & SIGNATURE
CLIENT xxx AREA xxx NAME xxx DATE xxx
ITEM 1 | Variation Name |  | YES/NO/NA | YES | YES
|  |  | YES/NO/NA | YES | YES
ITEM 2 | Variation Description |  | YES/NO/NA | YES | YES
ITEM 3 | Materials & Labour Breakdown (Names, Hours & Materials Quantities) |  | YES/NO/NA | YES | YES
ITEM 4 | Client Signature/Reference Mail |  | YES/NO/NA | YES | YES
ITEM 5 |  |  | YES/NO/NA | YES | YES
|  |  | YES/NO/NA | YES | YES
ITEM 6 | Photos |  | YES/NO/NA | YES | YES
ITEM 7 | Transplumb Final Sign-off |  | YES/NO/NA | YES | YES
ITEM 8 |  |  | YES/NO/NA | YES | YES
ITEM 9 |  |  | YES/NO/NA | YES | YES
ITEM 10 |  |  | YES/NO/NA | YES | YES
ITEM 10 |  |  | YES/NO/NA | YES | YES
ITEM 12 |  |  | YES/NO/NA | YES | YES
ITEM 11 |  |  | YES/NO/NA | YES | YES
ITEM 14 |  |  | YES/NO/NA | YES | YES
ITEM 12 |  |  | YES/NO/NA | YES | YES
ITEM 16 |  |  | YES/NO/NA | YES | YES
ITEM 13 |  |  | YES/NO/NA | YES | YES
ITEM 18 | Final Sign off - Pass when happy to proceed |  | YES/NO/NA | YES
ITEM 19 |  |  | YES/NO/NA | YES
ITEM 20 |  |  | YES/NO/NA | YES
ITEM 21 |  |  | YES/NO/NA | YES
ITEM 22 |  |  | YES/NO/NA | YES
ITEM 23 |  |  | YES/NO/NA | YES
ITEM 24 |  |  | YES/NO/NA | YES
ITEM 25 |  |  | YES/NO | YES
ITEM 26 |  |  | YES/NO | YES
ITEM 27 |  |  | YES/NO | YES
ITEM 28 |  |  | YES/NO | YES
ITEM 29 |  |  | YES/NO | YES
ITEM 30 |  |  | YES/NO | YES
ITEM 31 |  |  | YES/NO | YES
ITEM 32 |  |  | YES/NO | YES
ITEM 33 |  |  | YES/NO | YES
ITEM 34 |  |  | YES/NO | YES
ITEM 35
ITEM 36
ITEM 37
ITEM 38 |  | Final fit-off inspection on all items
ITEM 39
ITEM 40
ITEM 41 |  | Check for no cross connections/leaks
ITEM 42

## GENERAL WORKS
TRANSPLUMB GENERAL WORKS QA
|  |  | CLOSE OUT | ATTACH PHOTOS OR FILE | COMMENT & SIGNATURE
CLIENT xxx AREA xxx NAME xxx DATE xxx
ITEM 1 | Job Name/Number |  | YES/NO/NA | YES | YES
|  |  | YES/NO/NA | YES | YES
ITEM 2 | Job Description |  | YES/NO/NA | YES | YES
ITEM 3 | Take 5/SWMS/Inductions been completed before works start |  | YES/NO/NA | YES | YES
ITEM 4 | Has the client been notified of works to be carried out |  | YES/NO/NA | YES | YES
ITEM 5 | Do any of the works require pressure testing on completion |  | YES/NO/NA | YES | YES
|  |  | YES/NO/NA | YES | YES
ITEM 6 | Have all requested works been completed |  | YES/NO/NA | YES | YES
ITEM 7 |  |  | YES/NO/NA | YES | YES
ITEM 8 |  |  | YES/NO/NA | YES | YES
ITEM 9 |  |  | YES/NO/NA | YES | YES
ITEM 10 |  |  | YES/NO/NA | YES | YES
ITEM 10 |  |  | YES/NO/NA | YES | YES
ITEM 12 |  |  | YES/NO/NA | YES | YES
ITEM 11 |  |  | YES/NO/NA | YES | YES
ITEM 14 |  |  | YES/NO/NA | YES | YES
ITEM 12 | Area clean |  | YES/NO/NA | YES | YES
ITEM 16 |  |  | YES/NO/NA | YES | YES
ITEM 13 | Final Sign off |  | YES/NO/NA | YES | YES
ITEM 18 | Final Sign off - Pass when happy to proceed |  | YES/NO/NA | YES
ITEM 19 |  |  | YES/NO/NA | YES
ITEM 20 |  |  | YES/NO/NA | YES
ITEM 21 |  |  | YES/NO/NA | YES
ITEM 22 |  |  | YES/NO/NA | YES
ITEM 23 |  |  | YES/NO/NA | YES
ITEM 24 |  |  | YES/NO/NA | YES
ITEM 25 |  |  | YES/NO | YES
ITEM 26 |  |  | YES/NO | YES
ITEM 27 |  |  | YES/NO | YES
ITEM 28 |  |  | YES/NO | YES
ITEM 29 |  |  | YES/NO | YES
ITEM 30 |  |  | YES/NO | YES
ITEM 31 |  |  | YES/NO | YES
ITEM 32 |  |  | YES/NO | YES
ITEM 33 |  |  | YES/NO | YES
ITEM 34 |  |  | YES/NO | YES
ITEM 35
ITEM 36
ITEM 37
ITEM 38 |  | Final fit-off inspection on all items
ITEM 39
ITEM 40
ITEM 41 |  | Check for no cross connections/leaks
ITEM 42

## DRAINAGE BG
TRANSPLUMB DRAINAGE BG
|  |  | CLOSE OUT | ATTACH PHOTOS OR FILE | COMMENT & SIGNATURE
CLIENT xxx AREA xxx NAME xxx DATE xxx
ITEM 1 | Job Name/Number |  | YES/NO/NA | YES | YES
|  |  | YES/NO/NA | YES | YES
ITEM 2 | Job Description |  | YES/NO/NA | YES | YES
ITEM 3 | Take 5/SWMS/Inductions/Permits been completed before works start |  | YES/NO/NA | YES | YES
ITEM 4 | Are you working to an approved drawing |  | YES/NO/NA | YES | YES
ITEM 5 | Setout is correct as per current approved drawings |  | YES/NO/NA | YES | YES
|  |  | YES/NO/NA | YES | YES
ITEM 6 | Pipe bedding materials comply (as per AS 3500) |  | YES/NO/NA | YES | YES
ITEM 7 | Grades, fittings & joints installed to standards |  | YES/NO/NA | YES | YES
ITEM 8 | Inspection & Testing prior to backfill |  | YES/NO/NA | YES | YES
ITEM 9 | Seal any open ends |  | YES/NO/NA | YES | YES
ITEM 10 |  |  | YES/NO/NA | YES | YES
ITEM 10 | Backfill & compact trenches to code requirements |  | YES/NO/NA | YES | YES
ITEM 12 |  |  | YES/NO/NA | YES | YES
ITEM 11 | CCTV on completion |  | YES/NO/NA | YES | YES
ITEM 14 |  |  | YES/NO/NA | YES | YES
ITEM 12 | Area Clean |  | YES/NO/NA | YES | YES
ITEM 16 |  |  | YES/NO/NA | YES | YES
ITEM 13 | Final Sign off |  | YES/NO/NA | YES | YES
ITEM 18 | Final Sign off - Pass when happy to proceed |  | YES/NO/NA | YES
ITEM 19 |  |  | YES/NO/NA | YES
ITEM 20 |  |  | YES/NO/NA | YES
ITEM 21 |  |  | YES/NO/NA | YES
ITEM 22 |  |  | YES/NO/NA | YES
ITEM 23 |  |  | YES/NO/NA | YES
ITEM 24 |  |  | YES/NO/NA | YES
ITEM 25 |  |  | YES/NO | YES
ITEM 26 |  |  | YES/NO | YES
ITEM 27 |  |  | YES/NO | YES
ITEM 28 |  |  | YES/NO | YES
ITEM 29 |  |  | YES/NO | YES
ITEM 30 |  |  | YES/NO | YES
ITEM 31 |  |  | YES/NO | YES
ITEM 32 |  |  | YES/NO | YES
ITEM 33 |  |  | YES/NO | YES
ITEM 34 |  |  | YES/NO | YES
ITEM 35
ITEM 36
ITEM 37
ITEM 38 |  | Final fit-off inspection on all items
ITEM 39
ITEM 40
ITEM 41 |  | Check for no cross connections/leaks
ITEM 42

## HYD PRESSURE TEST
Hydraulic Pressure Test Record Checklist
|  |  | CLOSE OUT | ATTACH PHOTOS OR FILE | COMMENT & SIGNATURE
CLIENT xxx AREA xxx NAME xxx DATE xxx
ITEM 1 | Name of Tester |  |  |  | YES
YES
ITEM 2 | Site Location |  |  |  | YES
ITEM 3 | Description of system being tested |  |  |  | YES
ITEM 4 | Nominal Working Pressure (KPA) |  |  |  | YES
ITEM 5 | Max Test Pressure (KPA) |  |  |  | YES
YES
ITEM 6 | Test Type (Hydro/Air) |  |  |  | YES
ITEM 7 | Gauges Calibration |  |  |  | YES
ITEM 8 | Time at test |  |  |  | YES
ITEM 9 | Time at test completion |  |  |  | YES
ITEM 10 |  |  |  |  | YES
ITEM 10 | Pressure at completion |  |  |  | YES
ITEM 12 |  |  |  |  | YES
ITEM 11 | Duration of Pressure Test |  |  | YES | YES
ITEM 14 |  |  |  | YES | YES
ITEM 12 | Transplumb Sign-off |  |  | YES | YES
ITEM 16 |  |  |  | YES | YES
ITEM 13 | Witness Sign-off |  |  | YES | YES
ITEM 18 | Final Sign off - Pass when happy to proceed |  | YES/NO/NA | YES
ITEM 19 |  |  | YES/NO/NA | YES
ITEM 20 |  |  | YES/NO/NA | YES
ITEM 21 |  |  | YES/NO/NA | YES
ITEM 22 |  |  | YES/NO/NA | YES
ITEM 23 |  |  | YES/NO/NA | YES
ITEM 24 |  |  | YES/NO/NA | YES
ITEM 25 |  |  | YES/NO | YES
ITEM 26 |  |  | YES/NO | YES
ITEM 27 |  |  | YES/NO | YES
ITEM 28 |  |  | YES/NO | YES
ITEM 29 |  |  | YES/NO | YES
ITEM 30 |  |  | YES/NO | YES
ITEM 31 |  |  | YES/NO | YES
ITEM 32 |  |  | YES/NO | YES
ITEM 33 |  |  | YES/NO | YES
ITEM 34 |  |  | YES/NO | YES
ITEM 35
ITEM 36
ITEM 37
ITEM 38 |  | Final fit-off inspection on all items
ITEM 39
ITEM 40
ITEM 41 |  | Check for no cross connections/leaks
ITEM 42
ONLY THE 1 OPTION YES/NO/N/A CLOSE OUT ON THIS CHECKLIST

## SWMS
TRANSPLUMB SWMS
|  |  | CLOSE OUT | ATTACH PHOTOS OR FILE | COMMENT & SIGNATURE
CLIENT xxx AREA xxx NAME xxx DATE xxx
ITEM 1 | HAS A SWMS DOC BEEN UPLOADED |  | YES/NO |  | YES
|  |  | YES/NO/NA | YES | YES
ITEM 2 | DO YOU AGREE TO FOLLOW ALL PROCEDURES OUTLINED WITHIN THE ATTACHED SWMS |  | YES/NO |  | YES
ITEM 3 | ARE THERE ANY SITE SPECIFIC ADDITIONS OR OMISSIONS TO ADD TO THIS SWMS |  | YES/NO |  | YES
ITEM 4 | HAVE YOU SIGNED INTO THE ATTACHED SWMS |  | YES/NO |  | YES
ITEM 6
ITEM 7 |  |  | YES/NO/NA | YES | YES
ITEM 8
ITEM 9 |  |  | YES/NO/NA | YES | YES
ITEM 10 |  |  | YES/NO/NA | YES | YES
ITEM 11 |  |  | YES/NO/NA | YES | YES
ITEM 12 |  |  | YES/NO/NA | YES | YES
ITEM 13 |  |  | YES/NO/NA | YES | YES
ITEM 14 |  |  | YES/NO/NA | YES | YES
ITEM 15 |  |  | YES/NO/NA | YES | YES
ITEM 16 |  |  | YES/NO/NA | YES | YES
ITEM 17
ITEM 18 |  |  | YES/NO/NA | YES | YES
ITEM 19
ITEM 20 | Final Sign off - Pass when happy to proceed |  | YES/NO/NA | YES
ITEM 21 |  |  | YES/NO/NA | YES
ITEM 22 |  |  | YES/NO/NA | YES
ITEM 23 |  |  | YES/NO/NA | YES
ITEM 24 |  |  | YES/NO/NA | YES
ITEM 25 |  |  | YES/NO/NA | YES
ITEM 26 |  |  | YES/NO/NA | YES
ITEM 27 |  |  | YES/NO | YES
ITEM 28 |  |  | YES/NO | YES
ITEM 29 |  |  | YES/NO | YES
ITEM 30 |  |  | YES/NO | YES
ITEM 31 |  |  | YES/NO | YES
ITEM 32 |  |  | YES/NO | YES
ITEM 33 |  |  | YES/NO | YES
ITEM 34 |  |  | YES/NO | YES
ITEM 35 |  |  | YES/NO | YES
ITEM 36 |  |  | YES/NO | YES
ITEM 37
ITEM 38
ITEM 39
ITEM 40 |  | Final fit-off inspection on all items
ITEM 41
ITEM 42
ITEM 43 |  | Check for no cross connections/leaks
ITEM 44
ITEM 45

## TOOLBOX
TRANSPLUMB TOOLBOX MEETING
|  |  | CLOSE OUT | ATTACH PHOTOS OR FILE | COMMENT & SIGNATURE
CLIENT xxx AREA xxx NAME xxx DATE xxx
ITEM 1 | SITE FOREMAN/SUPERVISOR |  | YES/NO | YES | YES
ITEM 2 |  |  | YES/NO | YES | YES
ITEM 3 |  |  | YES/NO | YES | YES
ITEM 4 | SUBJECT |  | YES/NO | YES | YES
ITEM 5 | COMMENTS AND POINTS RAISED |  | YES/NO | YES | YES
ITEM 6 | CORRECTIVE ACTION REQUIRED |  | YES/NO | YES | YES
| IF YES, ACTION BY |  | YES/NO | YES | YES
ITEM 8 | ACTION COMPLETE |  | YES/NO | YES | YES
ITEM 9 | PERSONS PRESENT |  | YES/NO | YES | YES
ITEM 10 |  |  | YES/NO/NA | YES | YES
ITEM 11 |  |  | YES/NO/NA | YES | YES
ITEM 12 |  |  | YES/NO/NA | YES | YES
ITEM 13 |  |  | YES/NO/NA | YES | YES
ITEM 14 |  |  | YES/NO/NA | YES | YES
ITEM 15 |  |  | YES/NO/NA | YES | YES
ITEM 16 |  |  | YES/NO/NA | YES | YES
ITEM 17 |  |  | YES/NO/NA | YES | YES
ITEM 12
ITEM 16 |  |  | YES/NO/NA | YES | YES
ITEM 13
ITEM 18 |  |  | YES/NO/NA | YES
ITEM 19 |  |  | YES/NO/NA | YES
ITEM 20 |  |  | YES/NO/NA | YES
ITEM 21 |  |  | YES/NO/NA | YES
ITEM 22 | Final Sign off - Pass when happy to proceed |  | YES/NO/NA | YES
ITEM 23 |  |  | YES/NO/NA | YES
ITEM 24 |  |  | YES/NO/NA | YES
ITEM 25 |  |  | YES/NO | YES
ITEM 26 |  |  | YES/NO | YES
ITEM 27 |  |  | YES/NO | YES
ITEM 28 |  |  | YES/NO | YES
ITEM 29 |  |  | YES/NO | YES
ITEM 30 |  |  | YES/NO | YES
ITEM 31 |  |  | YES/NO | YES
ITEM 32 |  |  | YES/NO | YES
ITEM 33 |  |  | YES/NO | YES
ITEM 34 |  |  | YES/NO | YES
ITEM 35
ITEM 36
ITEM 37
ITEM 38
ITEM 39
ITEM 40
ITEM 41
ITEM 42 |  | Final fit-off inspection on all items
Check for no cross connections/leaks

## PLANT INTRODUCTION
TRANSPLUMB PLANT INTRODUCTION
|  |  | CLOSE OUT | ATTACH PHOTOS OR FILE | COMMENT & SIGNATURE
CLIENT xxx AREA xxx NAME xxx DATE xxx
ITEM 1 | SITE REPRESENTATIVE |  | YES/NO | YES | YES
ITEM 2 |  |  | YES/NO | YES | YES
ITEM 3 |  |  | YES/NO | YES | YES
ITEM 4 | INDEPENDENT CONTRACTOR |  | YES/NO | YES | YES
ITEM 5 | ITEM OF PLANT |  | YES/NO | YES | YES
ITEM 6 | HAZARD CHECKLIST BEEN COMPLETED |  | YES/NO | YES | YES
ITEM 7 | HAS A SWMS BEEN PROVIDED AND SIGNED FOR THE TASK |  | YES/NO | YES | YES
ITEM 8 | LOG BOOK PROVIDED |  | YES/NO | YES | YES
ITEM 9 | MAINTENANCE LOG BOOK |  | YES/NO | YES | YES
ITEM 10 | OPERATOR'S MANUAL |  | YES/NO | YES | YES
ITEM 11 | CERTIFICATION OF OPERATOR |  | YES/NO | YES | YES
ITEM 12 | NOISE LEVEL - OPERATIONAL |  | YES/NO | YES | YES
ITEM 13 | Final Sign off |  | YES/NO | YES | YES
ITEM 14 |  |  | YES/NO/NA | YES | YES
ITEM 15 |  |  | YES/NO/NA | YES | YES
ITEM 16 |  |  | YES/NO/NA | YES | YES
ITEM 17 |  |  | YES/NO/NA | YES | YES
ITEM 12
ITEM 16 |  |  | YES/NO/NA | YES | YES
ITEM 13
ITEM 18 |  |  | YES/NO/NA | YES
ITEM 19 |  |  | YES/NO/NA | YES
ITEM 20 |  |  | YES/NO/NA | YES
ITEM 21 |  |  | YES/NO/NA | YES
ITEM 22 | Final Sign off - Pass when happy to proceed |  | YES/NO/NA | YES
ITEM 23 |  |  | YES/NO/NA | YES
ITEM 24 |  |  | YES/NO/NA | YES
ITEM 25 |  |  | YES/NO | YES
ITEM 26 |  |  | YES/NO | YES
ITEM 27 |  |  | YES/NO | YES
ITEM 28 |  |  | YES/NO | YES
ITEM 29 |  |  | YES/NO | YES
ITEM 30 |  |  | YES/NO | YES
ITEM 31 |  |  | YES/NO | YES
ITEM 32 |  |  | YES/NO | YES
ITEM 33 |  |  | YES/NO | YES
ITEM 34 |  |  | YES/NO | YES
ITEM 35
ITEM 36
ITEM 37
ITEM 38
ITEM 39
ITEM 40
ITEM 41
ITEM 42 |  | Final fit-off inspection on all items
Check for no cross connections/leaks

## PUMP PLANT REPORT
TRANSPLUMB PUMP / PLANT REPORT
|  |  | CLOSE OUT | ATTACH PHOTOS OR FILE | COMMENT & SIGNATURE
CLIENT xxx AREA xxx NAME xxx DATE xxx
ITEM 1 | Has a Take 5/SWMS been completed before works start |  | YES/NO/NA | YES | YES
|  |  | YES/NO/NA | YES | YES
ITEM 2 | pump / plant location and description |  | YES/NO/NA | YES | YES
ITEM 3 | control board clean and sealed from water ingress |  | YES/NO/NA | YES | YES
ITEM 4 | check operation of all controls |  | YES/NO/NA | YES | YES
ITEM 5 | check indicator and alarm light operations |  | YES/NO/NA | YES | YES
|  |  | YES/NO/NA | YES | YES
ITEM 6 | pump 1 working as intended including amp and motor continuity test. |  | YES/NO/NA | YES | YES
ITEM 7 | pump 2 working as intended including amp and motor continuity test. |  | YES/NO/NA | YES | YES
ITEM 8 | check system pipework, manifolds, hoses and related service lines |  | YES/NO/NA | YES | YES
ITEM 9 | pump well clean and free of forien objects |  | YES/NO/NA | YES | YES
ITEM 10 |  |  | YES/NO/NA | YES | YES
ITEM 10 | pump well access stepsd and pump guiderails in good condition |  | YES/NO/NA | YES | YES
ITEM 11 |  |  | YES/NO/NA | YES | YES
ITEM 11 | comments |  | YES/NO | YES | YES
ITEM 14 |  |  | YES/NO/NA | YES | YES
ITEM 12 | Area Clean |  | YES/NO/NA | YES | YES
ITEM 16 |  |  | YES/NO/NA | YES | YES
ITEM 13 | Final Sign off |  | YES/NO/NA | YES | YES
ITEM 18 | Final Sign off - Pass when happy to proceed |  | YES/NO/NA | YES
ITEM 19 |  |  | YES/NO/NA | YES
ITEM 20 |  |  | YES/NO/NA | YES
ITEM 21 |  |  | YES/NO/NA | YES
ITEM 22 |  |  | YES/NO/NA | YES
ITEM 23 |  |  | YES/NO/NA | YES
ITEM 24 |  |  | YES/NO/NA | YES
ITEM 25 |  |  | YES/NO | YES
ITEM 26 |  |  | YES/NO | YES
ITEM 27 |  |  | YES/NO | YES
ITEM 28 |  |  | YES/NO | YES
ITEM 29 |  |  | YES/NO | YES
ITEM 30 |  |  | YES/NO | YES
ITEM 31 |  |  | YES/NO | YES
ITEM 32 |  |  | YES/NO | YES
ITEM 33 |  |  | YES/NO | YES
ITEM 34 |  |  | YES/NO | YES
ITEM 35
ITEM 36
ITEM 37
ITEM 38 |  | Final fit-off inspection on all items
ITEM 39
ITEM 40
ITEM 41 |  | Check for no cross connections/leaks
ITEM 42

## BACKFLOW TESTING
TRANSPLUMB BACKFLOW TESTING
|  |  | CLOSE OUT | ATTACH PHOTOS OR FILE | COMMENT & SIGNATURE
CLIENT xxx AREA xxx NAME xxx DATE xxx
ITEM 1 | Has a Take 5/SWMS been completed before works start |  | YES/NO/NA | YES | YES
|  |  | YES/NO/NA | YES | YES
ITEM 2 | OWNER/CLIENT |  |  | YES | YES
ITEM 3 | LOCATION OF DEVICE (INSERT MAPS LOCATION SCREENSHOT) |  |  | YES | YES
ITEM 4 | METER NUMBER |  |  | YES | YES
ITEM 5 | MAKE/SIZE/MODEL/SERIAL NO |  |  | YES | YES
ITEM 6 | DEVICE TYPE (RPZD, DOUBLE CHECK VALVE,SINGLE CHECK VALVE) |  |  | YES | YES
ITEM 7 |  |  | YES/NO/NA | YES | YES
ITEM 8 | INSTALLATION COMPLIES WITH AS/3500 |  | YES/NO/NA | YES | YES
ITEM 9 | PERMISSION RECEIVED TO ISOLATE WATER |  | YES/NO/NA | YES | YES
ITEM 10 | STRAINER INSTALLED AND CLEANED |  | YES/NO/NA | YES | YES
ITEM 11 | FIRST CLOSED TEST RESULT (KPA) |  | YES/NO/NA | YES | YES
ITEM 12 | SECOND CLOSED TEST RESULT |  | YES/NO/NA | YES | YES
ITEM 13 | SECOND CLOSED TEST RESULT (KPA) |  | YES/NO/NA | YES | YES
ITEM 14 | FIRST CLOSED TEST RESULT |  | YES/NO/NA | YES | YES
ITEM 15 | THIRD CLOSED TEST RESULT (KPA) |  | YES/NO/NA | YES | YES
ITEM 16 | FOURTH OPEN TEST RESULT (KPA) |  | YES/NO/NA | YES | YES
ITEM 17 | TEST EQUIPMENT USED TO COMPLETE RESULTS |  | YES/NO/NA | YES | YES
ITEM 18 | DEVICE TEST COMPLETED |  | YES/NO/NA | YES | YES
ITEM 19 | COMMENTS |  | YES/NO/NA | YES | YES
ITEM 20 |  |  | YES/NO/NA | YES/NO/NA | YES
ITEM 21 |  |  | YES/NO/NA | YES/NO/NA | YES
ITEM 22 |  |  | YES/NO/NA | YES/NO/NA | YES
Final Sign off
ITEM 18 | Final Sign off - Pass when happy to proceed |  | YES/NO/NA | YES
ITEM 19 |  |  | YES/NO/NA | YES
ITEM 20 |  |  | YES/NO/NA | YES
ITEM 21 |  |  | YES/NO/NA | YES
ITEM 22 |  |  | YES/NO/NA | YES
ITEM 23 |  |  | YES/NO/NA | YES
ITEM 24 |  |  | YES/NO/NA | YES
ITEM 25 |  |  | YES/NO | YES
ITEM 26 |  |  | YES/NO | YES
ITEM 27 |  |  | YES/NO | YES
ITEM 28 |  |  | YES/NO | YES
ITEM 29 |  |  | YES/NO | YES
ITEM 30 |  |  | YES/NO | YES
ITEM 31 |  |  | YES/NO | YES
ITEM 32 |  |  | YES/NO | YES
ITEM 33 |  |  | YES/NO | YES
ITEM 34 |  |  | YES/NO | YES
ITEM 35
ITEM 36
ITEM 37
ITEM 38 |  | Final fit-off inspection on all items
ITEM 39
ITEM 40
ITEM 41 |  | Check for no cross connections/leaks
ITEM 42

## FIRE PLUG QA
TRANSPLUMB FIRE PLUG QA
|  |  | CLOSE OUT | ATTACH PHOTOS OR FILE | COMMENT & SIGNATURE
CLIENT xxx AREA xxx NAME xxx DATE xxx
ITEM 1 | Has a Take 5/SWMS been completed before works start |  | YES/NO/NA | YES | YES
ITEM 2 |  |  | YES/NO/NA | YES | YES
ITEM 3 | Fire Plug Number |  | YES/NO/NA | YES | YES
ITEM 4 | Fire Plug Location IB or OB (Insert Maps Location Screenshot) Photo Required |  | YES/NO/NA | YES | YES
ITEM 5 | Fire Plug Isolation Valve Location (Insert Maps Location Screenshot) Photo Required |  | YES/NO/NA | YES | YES
ITEM 6 | Is the current hydrant cover adequately sized and positioned for maintanance (Photo Required) |  | YES/NO/NA | YES | YES
ITEM 7 | Has any maintenance works been completed |  | YES/NO/NA | YES | YES
ITEM 8 |  |  | YES/NO/NA | YES | YES
ITEM 9 |  |  | YES/NO/NA | YES | YES
ITEM 10 |  |  | YES/NO/NA | YES | YES
ITEM 11 |  |  | YES/NO/NA | YES | YES
ITEM 12 |  |  | YES/NO/NA | YES | YES
ITEM 13 | SECOND CLOSED TEST RESULT |  | YES/NO/NA | YES | YES
ITEM 14 |  |  | YES/NO/NA | YES | YES
ITEM 15 | FIRST CLOSED TEST RESULT |  | YES/NO/NA | YES | YES
ITEM 16 |  |  | YES/NO/NA | YES | YES
ITEM 17 |  |  | YES/NO/NA | YES | YES
ITEM 18 |  |  | YES/NO/NA | YES | YES
ITEM 19 |  |  | YES/NO/NA | YES | YES
ITEM 8 | COMMENTS |  | YES/NO/NA | YES | YES
ITEM 20 |  |  | YES/NO/NA | YES/NO/NA | YES
ITEM 21 |  |  | YES/NO/NA | YES/NO/NA | YES
ITEM 22 |  |  | YES/NO/NA | YES/NO/NA | YES
Final Sign off
ITEM 18 | Final Sign off - Pass when happy to proceed |  | YES/NO/NA | YES
ITEM 19 |  |  | YES/NO/NA | YES
ITEM 20 |  |  | YES/NO/NA | YES
ITEM 21 |  |  | YES/NO/NA | YES
ITEM 22 |  |  | YES/NO/NA | YES
ITEM 23 |  |  | YES/NO/NA | YES
ITEM 24 |  |  | YES/NO/NA | YES
ITEM 25 |  |  | YES/NO | YES
ITEM 26 |  |  | YES/NO | YES
ITEM 27 |  |  | YES/NO | YES
ITEM 28 |  |  | YES/NO | YES
ITEM 29 |  |  | YES/NO | YES
ITEM 30 |  |  | YES/NO | YES
ITEM 31 |  |  | YES/NO | YES
ITEM 32 |  |  | YES/NO | YES
ITEM 33 |  |  | YES/NO | YES
ITEM 34 |  |  | YES/NO | YES
ITEM 35
ITEM 36
ITEM 37
ITEM 38 |  | Final fit-off inspection on all items
ITEM 39
ITEM 40
ITEM 41 |  | Check for no cross connections/leaks
ITEM 42

## EVENTS ASSET I.D
TRANSPLUMB EVENTS ASSET I.D
|  |  | CLOSE OUT | ATTACH PHOTOS OR FILE | COMMENT & SIGNATURE
CLIENT xxx AREA xxx NAME xxx DATE xxx
ITEM 1 | ASSET NO# |  |  | YES | YES
|  |  | YES/NO/NA | YES | YES
ITEM 2 | Asset Description |  |  | YES | YES
ITEM 3 | Asset Serial Number |  | YES/NO/NA | YES | YES
ITEM 4 | Damage or Missing Parts |  | YES/NO/NA | YES | YES
ITEM 5 | Current Location |  | YES/NO/NA | YES | YES
|  |  | YES/NO/NA | YES | YES
ITEM 6 | Staff Sign Out |  |  |  | YES
ITEM 18 | Final Sign off - Pass when happy to proceed |  | YES/NO/NA | YES
ITEM 19 |  |  | YES/NO/NA | YES
ITEM 20 |  |  | YES/NO/NA | YES
ITEM 21 |  |  | YES/NO/NA | YES
ITEM 22 |  |  | YES/NO/NA | YES
ITEM 23 |  |  | YES/NO/NA | YES
ITEM 24 |  |  | YES/NO/NA | YES
ITEM 25 |  |  | YES/NO | YES
ITEM 26 |  |  | YES/NO | YES
ITEM 27 |  |  | YES/NO | YES
ITEM 28 |  |  | YES/NO | YES
ITEM 29 |  |  | YES/NO | YES
ITEM 30 |  |  | YES/NO | YES
ITEM 31 |  |  | YES/NO | YES
ITEM 32 |  |  | YES/NO | YES
ITEM 33 |  |  | YES/NO | YES
ITEM 34 |  |  | YES/NO | YES
ITEM 35
ITEM 36
ITEM 37
ITEM 38 |  | Final fit-off inspection on all items
ITEM 39
ITEM 40
ITEM 41 |  | Check for no cross connections/leaks
ITEM 42