## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Fix 2 ITP |  |  |  |  | Yes | Fix 2 ITP | 29ba4acd-0561-48b8-b4b3-f18c63ea23b2
checkpoint-status |  |  | checkpoint | Only approved fixtures installed
checkpoint-status |  |  | checkpoint | Products checked and have no imperfections
checkpoint-status |  |  | checkpoint | Fixtures installed as per approved drawing locations
checkpoint-status |  |  | checkpoint | No cross-connection on all water lines
checkpoint-status |  |  | checkpoint | Hot water correct temperature & Hot water tempering valve set to 50c +/-5c)
checkpoint-status |  |  | checkpoint | DDA Hot water correct temperature & Hot water tmv set to 42c +/-2c)
checkpoint-status |  |  | checkpoint | Water pressure acceptable 350kpa - 500kpa
checkpoint-status |  |  | checkpoint | Checked all drainage is working correctly wth no leaks
checkpoint-status |  |  | checkpoint | Cleaned out all strainers
checkpoint-status |  |  | checkpoint | Commissioned all fixtures
checkpoint-status |  |  | checkpoint | Final check for any leaks
checkpoint-status |  |  | checkpoint | Area clean - sign off and photos attached below
checklist-flat |  |  | checklist | Hydraulic Pressure Test Record Checklist |  |  |  |  | Yes | Hydraulic Pressure Test Record Checklist | 3ecd9d11-3f1f-4425-8ba4-54a0bac6b37f
checkpoint-status |  |  | checkpoint | Details entered below
text | 982a52a1-0844-5cc3-af72-d59c7b4e10d0 |  | textbox | Description of system being tested
text | 8190c82e-c7f3-5ff3-887f-023ce31d065d |  | textbox | Nominal Working Pressure (KPA)
text | 4cc2967a-b9bb-5182-ba24-f1dddfd0544c |  | textbox | Max Test Pressure (KPA)
text | 07cea4ae-66a3-5a28-b8bb-0a26ba80dd54 |  | textbox | Test Type (Hydro/Air)
text | ddb3401a-15c6-54cf-b56d-2ce4be82c7c6 |  | textbox | Gauges Calibration
text | bd2d9802-8c39-5c1a-be3a-cd6b0cae101f |  | textbox | Time at test
text | 418aa139-ae5d-5be7-8247-d88a7a40596b |  | textbox | Time at test completion
text | 7774688a-c716-566b-bcad-546efe2ec962 |  | textbox | Pressure at completion
text | 2e5347b4-65df-52e9-b972-03bcc0df3f51 |  | textbox | Duration of Pressure Test
checkpoint-status |  |  | checkpoint | Transplumb and witness signoff attached below
holdpoint |  |  | signoff | Request signoff
checklist-flat |  |  | checklist | Events Kitchen QA |  |  |  |  | Yes | Events Kitchen QA | 48b64997-4b49-4f95-821d-0acc0e897db4
checkpoint-status |  |  | checkpoint | Take 5/SWMS/Inductions been completed before works start
checkpoint-status |  |  | checkpoint | Kitchen layout is correct as per current drawings issued by client
checkpoint-status |  |  | checkpoint | Do all gas appliances have the minimum 500mm clearance from combustible surfaces?
checkpoint-status |  |  | checkpoint | Do all gas appliances have an isolation valve installed and is valve in good condition?
checkpoint-status |  |  | checkpoint | Have all gas appliances been fixed in position?
checkpoint-status |  |  | checkpoint | Are gas flexible hoses installed off the floor?
checkpoint-status |  |  | checkpoint | Are the gas LPG bottles installed with the minimum 1500mm clearance from an ignition source and secured to the base plate with chain?
checkpoint-status |  |  | checkpoint | Have all water and waste pipes been installed neatly?
checkpoint-status |  |  | checkpoint | Is hot water unit connected and working as required?
checkpoint-status |  |  | checkpoint | Is macerator unit connected and working as required?
checkpoint-status |  |  | checkpoint | Are sullage tanks and sewer connections in place and connected as required?
checkpoint-status |  |  | checkpoint | Is water live to kitchen and has all water and waste been checked for leaks and repaired if required
checkpoint-status |  |  | checkpoint | Have all appliances been commissioned? Are they working as intended?
checkpoint-status |  |  | checkpoint | Area Clean
holdpoint |  |  | signoff | SIGN OFF
checklist-flat |  |  | checklist | Blank Canvas Checklist |  |  |  |  | Yes | Add Blank Canvas Checklist | 5121e442-5978-4e51-b54c-efbb5e954dd6
checkpoint-status |  |  | checkpoint | Add Comments, Files or Signatures here
checklist-flat |  |  | checklist | Fix 1 ITP |  |  |  |  | Yes | Fix 1 ITP | 70dc899a-3a05-4b1c-a846-125d701b876a
checkpoint-status |  |  | checkpoint | Working to an approved drawing
checkpoint-status |  |  | checkpoint | Setout is correct as per current approved drawings
text | 14ada7dc-95c4-5fa9-927e-5862e6e87f44 |  | textbox | Drawing no. & Revision
checkpoint-status |  |  | checkpoint | No cross-connection on all water lines
checkpoint-status |  |  | checkpoint | Support and fixings checked (water hammer/silicone) and in order
checkpoint-status |  |  | checkpoint | All lines new and existing capped for testing
checkpoint-status |  |  | checkpoint | Pressure tested waterlines 1500kpa for 30 mins with start photo attached below
checkpoint-status |  |  | checkpoint | Pressure tested waterlines 1500kpa for 30 mins with finish photo attached below
checkpoint-status |  |  | checkpoint | Fixture waste points heights and centres doubled checked before wall sign off
checkpoint-status |  |  | checkpoint | All suspended drainage has been supported as per AS3500 Requirements
checkpoint-status |  |  | checkpoint | All suspended drainage been flow tested and has no leaks
checkpoint-status |  |  | checkpoint | Please supply photos of all water and waste completetd installations
checkpoint-status |  |  | checkpoint | Area clean & works signed off below
checklist-flat |  |  | checklist | Transplumb General Works ITP |  |  |  |  | Yes | Transplumb General Works ITP | 741a66c9-ae76-4858-bae9-53c6f1b71632
checkpoint-status |  |  | checkpoint | Take 5/SWMS/Inductions been completed before works start
checkpoint-status |  |  | checkpoint | Client notified of works to be carried out - description of works in comments below
button | 08508840-f388-5a53-9ffd-e0077bd878f8 |  | button | Do any of the works require pressure testing on completion | Yes,No
checkpoint-status |  |  | checkpoint | All requested works completed
checkpoint-status |  |  | checkpoint | Area clean & works signed off below
checklist-flat |  |  | checklist | Transplumb Roofing ITP |  |  |  |  | Yes | Transplumb Roofing ITP | 8123b463-0ed0-4b87-8ea9-683864bc8a48
checkpoint-status |  |  | checkpoint | Take 5/SWMS/Inductions been completed before works start
label | e145d2b8-915c-5fda-b759-e80e7f8af7ef |  | note | Worker is qualified to work at heights
checkpoint-status |  |  | checkpoint | Working to an approved drawing - description of works entered in comments below
checkpoint-status |  |  | checkpoint | Only approved materials installed
checkpoint-status |  |  | checkpoint | All fixings correctly installed as per AS 3500
checkpoint-status |  |  | checkpoint | Boxgutters/sump/downpipes installed and clipped correctly as per AS 3500
checkpoint-status |  |  | checkpoint | Flashings installed correctly and siliconed
checkpoint-status |  |  | checkpoint | Testing carried out where possible
checkpoint-status |  |  | checkpoint | Area clean & works signed off below
checklist-flat |  |  | checklist | Transplumb Pump / Plant Report |  |  |  |  | Yes | Transplumb Pump / Plant Report | 863a97ec-fbfa-4b1f-8c95-562faa8fc42c
checkpoint-status |  |  | checkpoint | Has a Take 5/SWMS been completed before works start
checkpoint-status |  |  | checkpoint | Pump / plant location and description
checkpoint-status |  |  | checkpoint | Control board clean and sealed from water ingress
checkpoint-status |  |  | checkpoint | Check operation of all controls
checkpoint-status |  |  | checkpoint | Check indicator and alarm light operations
checkpoint-status |  |  | checkpoint | Pump 1 working as intended including amp and motor continuity test
checkpoint-status |  |  | checkpoint | Pump 2 working as intended including amp and motor continuity test
checkpoint-status |  |  | checkpoint | Check system pipework, manifolds, hoses and related service lines
checkpoint-status |  |  | checkpoint | Pump well clean and free of foreign objects
checkpoint-status |  |  | checkpoint | Pump well access steps and pump guiderails in good condition
checkpoint-status |  |  | checkpoint | Comments
checkpoint-status |  |  | checkpoint | Area Clean
holdpoint |  |  | signoff | Final Sign off
checklist-flat |  |  | checklist | Transplumb Backflow Testing |  |  |  |  | Yes | Transplumb Backflow Testing | 926243c6-decc-4bee-a500-b91847d0f90b
checkpoint-status |  |  | checkpoint | Has a Take 5/SWMS been completed before works start
text | e03791a7-71f4-591a-a96e-5f0abe43f382 |  | textbox | Owner/Client
text | 1872454b-00bc-5496-af02-46cc8f0b1252 |  | textbox | Location Of Device (Insert Maps Location Screenshot)
text | bf510190-7344-5c5c-9803-01b944141fb4 |  | textbox | Meter Number
text | 825973cf-ccaf-56f9-b3fa-22cf7da12fda |  | textbox | Make/Size/Model/Serial No
text | edc2ec93-490a-53d3-a799-58b669a1db0a |  | textbox | Device Type (Rpzd, Double Check Valve,Single Check Valve)
checkpoint-status |  |  | checkpoint | Installation Complies With As/3500
checkpoint-status |  |  | checkpoint | Permission Received To Isolate Water
checkpoint-status |  |  | checkpoint | Strainer Installed And Cleaned
checkpoint-status |  |  | checkpoint | First Closed Test Result (Kpa)
checkpoint-status |  |  | checkpoint | Second Closed Test Result (Kpa)
checkpoint-status |  |  | checkpoint | Third Closed Test Result (Kpa)
checkpoint-status |  |  | checkpoint | Fourth Open Test Result (Kpa)
checkpoint-status |  |  | checkpoint | Test Equipment Used To Complete Results
checkpoint-status |  |  | checkpoint | Device Test Completed
holdpoint |  |  | signoff | Final Sign off
checklist-flat |  |  | checklist | Blank Canvas Checklist |  |  |  |  | Yes | ZSYS - Add Blank Canvas Checklist (old version) | bbd37744-dafb-44a3-993e-45ee67ef6b1d
checkpoint-no-status |  |  | checkpoint | Add Comments, Files or Signatures here
checklist-flat |  |  | checklist | Toolbox |  |  |  |  | Yes | Toolbox | bc9906e5-4bbd-4ccf-9a1c-2f4fa00cbe78
checkpoint-status |  |  | checkpoint | Details entered below
text | 2f52eb13-951c-5df7-927e-14d7c2bcb9d4 |  | textbox | Site foreman/supervisor
text | b7c60a2f-ef63-5f61-9654-9fb484ac5308 |  | textbox | Subject
text | 90ba9410-10e6-52d2-b09a-c39e7f80dbd7 |  | textbox | Comments and points raised
button | e772369a-93b1-51d0-a64f-f75ab39991a3 |  | button | Corrective action required | Yes,No
text | c9227d5c-6dc4-50b7-bb36-3c7dbc07ff83 |  | textbox | If yes, action by
checkpoint-status |  |  | checkpoint | Corrective action complete (if one was raised)
checkpoint-status |  |  | checkpoint | Persons present signatures below
checklist-flat |  |  | checklist | Plant Introduction |  |  |  |  | Yes | Plant Introduction | c0b1509a-850b-457f-aad3-987c0cae1038
checkpoint-status |  |  | checkpoint | Details entered below
text | 1644f4ea-eda1-58b9-9451-2ea940a77fe0 |  | textbox | Site representative
text | abf31ff5-cf2d-5812-b8ed-e03f7c7a2648 |  | textbox | Independent contractor
text | 3dc4ae3d-aef0-56fe-9dd9-59c94c03db58 |  | textbox | Item of plant
checkpoint-status |  |  | checkpoint | Hazard checklist been completed
checkpoint-status |  |  | checkpoint | Has a swms been provided and signed for the task
checkpoint-status |  |  | checkpoint | Log book provided
checkpoint-status |  |  | checkpoint | Maintenance log book provided
checkpoint-status |  |  | checkpoint | Operator's manual provided
checkpoint-status |  |  | checkpoint | Certification of operator provided
checkpoint-status |  |  | checkpoint | Noise level - operational
checkpoint-status |  |  | checkpoint | Final sign off attached below
checklist-flat |  |  | checklist | Transplumb Variations |  |  |  |  | Yes | Transplumb Variations | d8cdbdfe-e08e-4c38-9928-6d1a1420a4b4
checkpoint-status |  |  | checkpoint | Variation details entered below
text | 5b105197-095a-5b07-9e05-ac2d0484b1b6 |  | textbox | Variation Name
text | 1e848568-4553-55e6-bf24-b7a30e19c719 |  | textbox | Variation Description
checkpoint-status |  |  | checkpoint | Materials & Labour Breakdown - Names, Hours & Materials Quantities entered in comments below
checkpoint-status |  |  | checkpoint | Final signoff - any supporting docs and client signature attached below
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | SWMS Checklist |  |  |  |  | Yes | SWMS Checklist | e03c32a0-5cd8-4688-8a19-5821621c7cd9
checkpoint-status |  |  | checkpoint | Has a swms doc been uploaded
checkpoint-status |  |  | checkpoint | Do you agree to follow all procedures outlined within the attached swms
checkpoint-status |  |  | checkpoint | Are there any site specific additions or omissions to add to this swms
checkpoint-status |  |  | checkpoint | Have you signed into the attached swms
checklist-flat |  |  | checklist | Take 5 Checklist |  |  |  |  | Yes | Take 5 Checklist | e6f5920a-2c07-4425-9833-f57f0d914582
checkpoint-status |  |  | checkpoint | Task details entered below
text | 3044c2cd-3711-55c8-91c7-1dd0bd58ebd6 |  | textbox | Task
checkpoint-status |  |  | checkpoint | If any of the below are 'Fail' (no) - make yourself acquainted with site requirements before starting work
checkpoint-status |  |  | checkpoint | Have you completed a site induction?
checkpoint-status |  |  | checkpoint | Do you know the site’s health and safety rules?
checkpoint-status |  |  | checkpoint | Are you familiar with security arrangements and the system for reporting incidents, near misses and hazards?
checkpoint-status |  |  | checkpoint | Are you familiar with the emergency facilities and evacuation procedure/route for the site?
checkpoint-status |  |  | checkpoint | Do you have access to appropriate emergency and first aid equipment?
checkpoint-status |  |  | checkpoint | Have you asked the person in charge about all relevant hazards?
checkpoint-status |  |  | checkpoint | If any of the below are 'Fail' (no) - follow up with person in charge to ensure your safety
checkpoint-status |  |  | checkpoint | Has a safe work method statement or job safety analysis been completed?
checkpoint-status |  |  | checkpoint | Do you have the correct procedures, equipment and PPE to do the work safely?
checkpoint-status |  |  | checkpoint | Has equipment that requires a lock/tag-out and/or power that requires isolation/containment been completed?
checkpoint-status |  |  | checkpoint | Is there appropriate separation of vehicles and people during the proposed work?
checkpoint-status |  |  | checkpoint | Is all required electrical/mechanical equipment in a safe condition?
checkpoint-status |  |  | checkpoint | Are all hazardous and/or dangerous goods/substances used and stored according to their material safety data sheets?
checkpoint-status |  |  | checkpoint | Have you consulted with all fellow workers about the task to be completed and the safe way to do it?
checkpoint-status |  |  | checkpoint | Have you got a safe way of getting in and out of your work area?
checkpoint-status |  |  | checkpoint | Have any manual handling risks been identified and assessed?
checkpoint-status |  |  | checkpoint | Any additional site specific hazards or requirements commented below
button | 9bc068e1-305b-5d80-8d78-a499965d4595 |  | button | Additional site specific hazards? | Yes,No
checkpoint-status |  |  | checkpoint | Sign off attached below
checklist-flat |  |  | checklist | Transplumb Drainage BG ITP |  |  |  |  | Yes | Transplumb Drainage BG ITP | fc7edb0c-678f-4a7b-a44a-c4eae796840f
checkpoint-status |  |  | checkpoint | Working to an approved drawing
checkpoint-status |  |  | checkpoint | Setout is correct as per current approved drawings
checkpoint-status |  |  | checkpoint | Pipe bedding materials comply (as per AS 3500)
checkpoint-status |  |  | checkpoint | Grades, fittings & joints installed to standards
checkpoint-status |  |  | checkpoint | Inspection & Testing carried out prior to backfill
checkpoint-status |  |  | checkpoint | Sealed any open ends
checkpoint-status |  |  | checkpoint | Backfill & compact trenches to code requirements
checkpoint-status |  |  | checkpoint | CCTV on completion
checkpoint-status |  |  | checkpoint | Area clean & works signed off below