## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Precast Components ITP
section | Job Approval Documents/Construction Documents
checkpoint | Received Construction drawing from Client
checkpoint | Shop drawings Prepared, reviewed and updated. Issued "As For Construction"
label | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint-no-status | Formwork
checkpoint-no-status | Reinforcement (Reo)
checkpoint-no-status | Embedded Items and their placement
checkpoint-no-status | Lift Procedure
checkpoint-no-status | Concreting (mix design)
section | Test on Concrete (requests and approvals)
checkpoint-no-status | Request From Client
checkpoint-no-status | Test schedule and Test Results
section | Transport 01
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 02
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Other Documentations
checkpoint-no-status | Special Instructions
checkpoint-no-status | Other
section | Installation
checkpoint | All PPE and safety requirements in place. Machinery inspections complete.
checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location
bool | Set out
bool | Core Holes
bool | Install dowels
checkpoint | Installation of precast panels including back propping. Correct location, connections, finish confirmed against shop drawings.
checkpoint | Grouting and sealing
checkpoint | Remove back propping when instructed by consulting Engineers.
section | Final Inspection
checkpoint-no-status | Final Inspection
bool | PL1- 06 Nos
bool | PL2- 04 Nos
bool | ST1 - 14Nos
bool | ST2- 07Nos
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
checklist | Checkers Checklist | [5 empty] | Checkers Checklist - PL Panels
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item - Ferrules -M12-50mm - Position, Size, Orientation - NS / FS
dropdown | Embedded Item: | 4,7,other
checkpoint | Embedded Item - FF,NF Lifters Correct - Position,Size,Orientation -Foot Anchors Galvanised1.3T-65mm (Nexus P52165) 02 Nos
checkpoint | Concrete cover check
checkpoint | Panel Thickness check,allignment check (150mm)
checkpoint | Panel width double check 100% accuracy, alignment check
textbox | Panel width:
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Reinforcement (Reo) placed, cleaned, tightened
bool | Curing Procedure arranged
bool | Photo Taken
checklist | Installers Checklist | [5 empty] | Installers Checklist - PL Panels
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Embedded Item - FF,NF Lifters Correct - Position,Size,Orientation -Foot Anchors Galvanised1.3T-65mm (Nexus P52165) 02 Nos
checkpoint | Embedded Item - Ferrules -M12-50mm - Position, Size, Orientation - NS / FS
dropdown | Embedded Item: | 4,7,other
checkpoint-no-status | ID Plate
textbox | ID Plate:
section | Pre-Pour Check Approvals
checkpoint-no-status | Pre-Pour Check Approvals
bool | Formwork Check -Panel Dimensions & DOUBLE CHECK
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
bool | Concrete cover Check
checkpoint | Reinforcement Check
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals
bool | QA - Concrete N40 Panel Mix - Special Adjustments
bool | QA - All main & other requirement to do Concreting -DOUBLE CHECK
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
date | Pour Date:
checkpoint | CONCRETE TEST Procedure
checkpoint-no-status | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged Broom/ Sponge Finish)
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist | [5 empty] | Checkers Checklist - ST Panels (steps)
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item - Ferrules -M12-50mm - Position, Size, Orientation - NS / FS - 02 Nos
checkpoint | Embedded Item - FF,NF Lifters Correct - Position,Size,Orientation -Foot Anchors Galvanised1.3T-55mm (Nexus P52155) 02 Nos
checkpoint | Concrete cover check
checkpoint | Panel Thickness check,allignment check (150mm)
checkpoint | Panel width double check 100% accuracy, alignment check
textbox | Panel width:
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Reinforcement (Reo) placed, cleaned, tightened
bool | Curing Procedure arranged
checkpoint-no-status | Photo Taken
checkpoint | Chamfer the edges external and in selected 3 faces
checklist | Installers Checklist | [5 empty] | Installers Checklist - ST Panels (steps)
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Embedded Item - FF,NF Lifters Correct - Position,Size,Orientation -Foot Anchors Galvanised1.3T-55mm (Nexus P52155) 02 Nos
checkpoint | Embedded Item - Ferrules -M12-50mm - Position, Size, Orientation - NS / FS - 02 Nos
checkpoint-no-status | ID Plate
textbox | ID Plate:
section | Pre-Pour Check Approvals
checkpoint-no-status | Pre-Pour Check Approvals
bool | Formwork Check -Panel Dimensions & DOUBLE CHECK
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
bool | Lifters, Ferrules, Tubes Fixed Firm & aligned -Check
checkpoint | Reinforcement Check
checkpoint | Concrete cover Check - (top min cov30mm, Bottom Min Cov 25mm)
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals
bool | QA - Concrete N40 Panel Mix - Special Adjustments
bool | QA - All main & other requirement to do Concreting -DOUBLE CHECK
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | Panel width double check 100% accuracy, alignment check
date | Pour Date:
checkpoint | CONCRETE TEST Procedure
checkpoint-no-status | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged Broom/ Sponge Finish)
checkpoint | Curing Procedure arranged