## Master List Templates
Id | Type | Name | Values | Prompting Name
054ede44-8eb6-4e13-878e-4004cdbdc4e2 | checklist | ITP-002 - Cement Stabilisation | itp | ITP-002 - Cement Stabilisation
857405fa-85ca-48bc-809a-9bd1da8daf36 | section | Cement Stabilisation
211533ca-5805-4d71-b0d7-6792fc45bd60 | checkpoint | 1 - Mix Design
384fb554-cf0d-59eb-90bf-b6fb71af28cc | note | FREQUENCY - Prior to start
3747d49e-3a7b-5282-91ac-8ad2be9c21f0 | note | ACCEPTANCE CRITERIA - Mix design to be selected based on pavement material investigation. Binder application rates to be confirmed with client prior to start.
00628e39-730f-58fa-a3e3-112bbd4a6faf | note | REFERENCE DOCUMENTS - VR 307.05
8a535256-11e1-58cb-b799-c5503eb2436f | note | INSPECTION / TEST METHOD - Record
ea5f15e2-3aa6-5193-81e4-c0a092f2624e | note | RECORD OF CONFORMITY - Record
8bd7767d-ebcc-52d4-82dc-2bed99e3cafc | note | HP*
3d743550-9f10-5b89-8973-62aa79108fbf | note | RESPONSIBILITY - Project Engineer
7a85e3f7-b11a-584e-bc50-4aa201f36a92 | date | Date Completed:
9f3911a5-4f47-4aed-9fe4-13bf8764d9be | checkpoint | 2 - Preliminary level confirmation
ff60f601-c148-5ad6-865e-6e15a6df273b | note | FREQUENCY - Prior to start
47dd3d87-6faa-545c-9b8b-1432adb632b8 | note | ACCEPTANCE CRITERIA - The surface level of the area to be stabilised shall be confirmed to be within level tolerances prior to commencement of stabilisation. Unless otherwise specified, +15/-25mm.
cfba47b5-42ce-5e3b-82c2-78bd0b60accd | note | REFERENCE DOCUMENTS - VR 307.03(a)
3e4c02e1-3bd5-5847-877c-63876c6ac8ce | note | INSPECTION / TEST METHOD - Visual
b854368f-d066-54cf-b68e-960c327abea5 | note | RECORD OF CONFORMITY - Visual
c8e50bac-7d05-55f8-93bf-7f413e73cf32 | note | IP
882145fe-1483-5a40-969b-ec6fd593a72d | note | RESPONSIBILITY - Project Engineer
291853e0-f4f3-5ccf-b09d-2c3a6d896633 | date | Date Completed:
00d54696-f99b-422e-a4e7-92b5ee393315 | checkpoint | 3 - Binder Supply
4314f9c8-937c-52d6-a4be-78395e9c0939 | note | FREQUENCY - Each production day
be703c3e-6bde-5d42-a367-a8614a91bc75 | note | ACCEPTANCE CRITERIA - Quicklime & Hydrated Lime to meet requirements of AS1672. Cement supply to comply with AS 3972. ALI shown on delivery dockets.
63431d19-7f04-5275-b328-01d6c2c0b9f3 | note | REFERENCE DOCUMENTS - VR 307.04
dd137de7-7213-5ce5-8cfb-e3f303cd1c42 | note | INSPECTION / TEST METHOD - Test Report
886b7eb6-0a20-5ff0-8a27-507197a0bd8a | note | RECORD OF CONFORMITY - Test Report
a2fae1e3-07d8-501a-8bdc-18289ddcc3ad | note | IP
1a362821-71ab-5f57-ac45-3d8851abce12 | note | RESPONSIBILITY - Project Engineer
42fe5711-fbc1-58cb-b688-783194f68df2 | date | Date Completed:
234b66b2-9e36-4b87-aecd-5314e6bc8ef9 | checkpoint | 4 - Spreading of stabilising agent
5eb8c8ba-94d6-565d-8e3b-c07d43f00aef | note | FREQUENCY - Each Lot
a7c83163-734a-5a43-bb11-cf27fa89866e | note | ACCEPTANCE CRITERIA - Binder shall be spread at the specified rate. In passes not exceeding 15kg/m2. No traffic to be allowed after spreading other than construction traffic. Matt test & load cell outputs recorded for QA purposes.
17ea66b5-9f67-55e7-a63d-982c391529b4 | note | REFERENCE DOCUMENTS - VR 307.14
1d069a39-16af-5c76-818d-80b31ca96351 | note | INSPECTION / TEST METHOD - QA Report
99502a6e-6287-5f68-b48a-fc88df335496 | note | RECORD OF CONFORMITY - QA Report
29d85bdf-96e1-5c51-bc9d-c2fb87284596 | note | IP
f4126577-e218-533c-b299-0da63d056a05 | note | RESPONSIBILITY - Project Engineer
0bfc193c-9866-5ae9-b9ff-cc00a05432e4 | date | Date Completed:
11df4343-a2f8-4fcf-8d99-f5ae3086c484 | checkpoint | 5 - Slaking of Lime
689de229-9953-50cd-a7fc-3719119a48d2 | note | FREQUENCY - Each Run
e64fd0ca-f44c-513a-bb3c-6997920552a0 | note | ACCEPTANCE CRITERIA - If quicklime is used it shall be slaked with sufficient water to allow full slaking to take place prior to mixing. Full slaking will be deemed to have been achieved when all quicklime that has been spread has changed from a cream coloured granulate to a fine white powder and there is a cessation of rising vapours.
69b5e4d2-e046-5510-bfb7-99431304bfa5 | note | REFERENCE DOCUMENTS - VR 307.08 (c)
d4e17935-f15a-5986-b205-fcb1ec7e945f | note | INSPECTION / TEST METHOD - Visual
63699f4c-9ba0-5483-a167-0fcd1324d384 | note | RECORD OF CONFORMITY - Visual
abc4eed3-8d04-5651-9024-c9660992cc11 | note | IP
c12d786b-5867-5b6e-80c8-a7dbd9d18e2c | note | RESPONSIBILITY - Project Engineer
a1b36ae5-a2e3-5339-8498-978042f82172 | date | Date Completed:
95799c10-a35f-420f-a9fb-b026e36c660c | checkpoint | 6 - Mixing of stabilising agent
132c0357-59f9-58c4-92cf-47893713d041 | note | FREQUENCY - Each Run
0c162f02-8828-53e7-9221-592547e43113 | note | ACCEPTANCE CRITERIA - Mixing shall commence as soon as practical after spreading of the cementitious binder. Water to be added as required to achieve and maintain close to optimum moisture content. Mixing depth to be physically checked.
1914ca6e-9fe8-5a02-bc2c-cef9d5d2513e | note | REFERENCE DOCUMENTS - VR 307.08(e)
76f30061-b855-590d-bd7f-2857f706424b | note | INSPECTION / TEST METHOD - Visual/ QA report
21a16b57-d02f-52b8-a29f-08128e924330 | note | RECORD OF CONFORMITY - Visual/ QA report
de5435da-fa9d-5c1b-b8d1-1f7653c60491 | note | IP
cb5c192c-b3b2-5edf-9322-121cf79db2cc | note | RESPONSIBILITY - Project Engineer
f81eb0ca-2dbe-5780-8f0f-e25d036ad971 | date | Date Completed:
0922a61f-0aa9-4d6e-91b8-8035ee7356c7 | checkpoint | 7 - Compaction
e2dd7b21-32aa-5576-88b7-8881d10616c5 | note | FREQUENCY - Each Run
c0dcd38b-59c3-5d9e-8133-b792dc851266 | note | ACCEPTANCE CRITERIA - Compaction of the stabilised layer shall commence immediately after mixing.
a58ad524-b1bf-593b-ab93-00fe9b72126b | note | ○ All compaction shall be completed within the times specified in Table VR 307.052 after addition of the cementitious binder.
3d01408b-dce5-590d-810b-9b9591e639d8 | note | REFERENCE DOCUMENTS - VR 307.08(f)
032625a9-5c46-5e9c-834d-93eeddc95e00 | note | INSPECTION / TEST METHOD - Visual
07ef0049-c5db-54a3-826b-13aa632ec3ea | note | RECORD OF CONFORMITY - Visual
a1967668-8f94-554a-8a9a-12ba6c0affa2 | note | TP
3a7b0ca6-9f2d-5792-972d-6a7ba9fe57d8 | note | RESPONSIBILITY - Project Engineer
2e4d3d6e-cbd6-5d69-a87a-fa03b7ecd377 | date | Date Completed:
7f1669fd-991e-452f-982e-da1036b3efda | checkpoint | 8 - Trimming
e72c0e36-f4f6-5b58-8ba4-c5a07fcd550c | note | FREQUENCY - Each Lot
7dd8ab88-306f-5b30-a5ff-d1c77ddc4576 | note | ACCEPTANCE CRITERIA - On completion of initial rolling, the stabilised material shall be trimmed to the specified surface tolerances. Water may be applied during this operation to replace evaporated moisture.
3e37b5e4-b0bc-56e0-85e3-55f3394fe361 | note | REFERENCE DOCUMENTS - VR 307.08(g)
620a1526-adf8-5246-993b-ad4f9d697efa | note | INSPECTION / TEST METHOD - Visual
185f82f3-d9ce-595d-a82e-8c5be90c776f | note | RECORD OF CONFORMITY - Visual
9b192d14-67ef-5c8f-bac4-9ca024e3295f | note | IP
220194bd-e879-5ab5-b423-4cab8a2fbd69 | note | RESPONSIBILITY - Project Engineer
ed38ae14-636d-511f-bd58-cfec4d8d60f5 | date | Date Completed:
b62aa8d4-d01f-4451-b0ed-4bc8c75e6852 | checkpoint | 9 - Test Rolling
0f07b646-7dd3-5604-b1d2-3eb4e2d8ae18 | note | FREQUENCY - Each Lot
31203af8-29f9-591b-8b9b-88389900d9f2 | note | ACCEPTANCE CRITERIA - Stabilised layers shall pass test rolling in accordance with Section 173, prior to acceptance of the layer.
4ac80e37-bd42-5cfd-a218-688e5a3756af | note | REFERENCE DOCUMENTS - VR 307.10
5337b595-e3a0-521a-9886-11137dc059f4 | note | INSPECTION / TEST METHOD - Visual
b34708e6-945c-57d7-9573-012a94832280 | note | RECORD OF CONFORMITY - Visual
3b876763-2a72-5ff5-a4c7-fbf2a807c7e1 | note | HP, WP
c8fe3744-2c66-5b38-aede-483b034e7271 | note | RESPONSIBILITY - Project Engineer / DTP
86b292d8-967f-5192-9037-7387c0f61331 | date | Date Completed:
446662e0-2cbd-4d6b-b6e9-87f42b382e8e | signoff | AUTHORITY HOLDPOINT
b8230bd9-3c25-4f4c-87c4-a626ec0f10e1 | checkpoint | 10 - Compaction Testing
fff40d79-c68d-5832-adf7-4bff052991ea | note | FREQUENCY - Each Lot
d6ceb9b0-4a8c-5d8e-ad51-a8775c03fcbb | note | ACCEPTANCE CRITERIA - If required, density testing to be undertaken as per table 307.151 or otherwise specified
c014796f-6467-5535-944f-a2119eee4f88 | note | REFERENCE DOCUMENTS - VR 307.15
f7dbd2ad-70c3-507b-bb08-ed3c2a8acd8c | note | INSPECTION / TEST METHOD - Test Report
71b0c00d-0aff-5a88-bac4-7db11c566d54 | note | RECORD OF CONFORMITY - Test Report
1e1fba40-14e4-5882-9046-3a5e4b681cd7 | note | TP
4e793f49-f7dd-592b-a4fd-9f5629a9ad98 | note | RESPONSIBILITY - Project Engineer
f9e824d4-ce33-50ad-9a8e-3430912d5675 | date | Date Completed:
719f67f7-a2bb-4b5d-bb6e-1287188872c6 | checkpoint | 11 - Maintenance of Stabilised layer
ce86cc5b-3214-5a74-adbd-2f4cdd42b925 | note | FREQUENCY - Each Lot
77afaea5-2ed6-515e-97b5-76e6d1988d00 | note | ACCEPTANCE CRITERIA - Surface shall be kept moist and protected from damage by traffic and construction activities until further pavement layer is applied.
d1710ddb-4225-5f91-8d11-34cea298b2cb | note | REFERENCE DOCUMENTS - VR 307.11
f2cababd-5598-527a-a464-5c1a0d5d50b9 | note | INSPECTION / TEST METHOD - Visual
a61bb987-a201-54e5-aa93-f16f924c339a | note | RECORD OF CONFORMITY - Visual
39525603-82ff-5729-8ef0-049b053a4e5d | note | IP
7f62279c-845f-5bf9-ba10-39c77cd0c4df | note | RESPONSIBILITY - Project Engineer
cdee3857-4918-5cd5-9266-93c210cf44b0 | date | Date Completed:
8d41508b-d7b7-445c-a62c-ef47bcc0b43f | checkpoint | Final Inspection
a90427b8-034d-55db-9b7c-9859e00c27d9 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
a5e37654-341b-58fe-8d5c-c8794614a70a | textbox | Print Name:
d6770516-17fb-5f07-ba7e-09b5c3d48fca | textbox | Position:
c4b6b016-d4e2-5b46-b4a7-bcd5fb415363 | date | Date:
e174e8ac-105b-412c-96d1-2550f6fa80bf | signoff | Sign ITP
d475b86f-f799-5f15-9f50-f9ea507a9f6a | checklist | ITP-002 - Earthworks | itp | ITP-002 - Earthworks
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
78f2eb97-4d27-5397-9616-d0974c63c400 | checkpoint | 1.1 - Check for correct documentation
63ef06e4-2920-5a35-b5b9-535fc9e300ba | note | FREQUENCY: Prior to commencing any activity
975a3e51-9557-5498-a0e6-f409be88ad10 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
613e7170-9728-5570-9c31-94beb88c7c44 | note | – using the correct and complete set of drawings
8feb9044-c864-5b37-9c61-519e64230102 | note | – all drawings are the latest revision
7ef1083c-e883-5714-9b92-dd73a27abd47 | note | REFERENCE DOCUMENTS: IFC Drawings
c62d4720-bd30-52d5-8674-bf431547ccff | note | METHOD: Visual Inspection
661abbd6-eca8-532e-a3ff-1a64e77beb1b | note | RECORD: Signed ITP
9a9af3b3-4708-566d-a616-369ced59562c | note | IHP
72fb4da4-635e-5a66-ab2f-552827b9e2ba | note | RESPONSIBILITY: SWA Project Manager
51e49a8c-5445-526e-984b-423795089fd5 | date | Date Completed:
457fc29c-5478-51c3-a60f-061f5ba4ad0d | checkpoint | 1.2 - Implementation of all measures and controls
07d8c898-2208-523a-80f7-1387c0f63df8 | note | FREQUENCY: Prior to commencing any activity
0751365c-1d20-5c53-b1bb-3b51d00d3665 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
a8f70dba-46e3-5a26-95d6-26e96fae383e | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
1352caef-d602-554b-a7da-1423cabffbbb | note | METHOD: Visual Inspection
a0b75b41-f0dd-5860-96b6-6da3307d8ce6 | note | RECORD: Signed ITP
b53b50a3-f195-5159-859f-bc717daeffdb | note | IHP
06ed450d-b079-5465-9db2-0846a76be876 | note | RESPONSIBILITY: SWA Project Manager
7c543fa3-0593-5ec2-863a-f310fc8ca8f9 | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
8ca7bcd9-51c2-5af5-a939-2cb980971168 | checkpoint | 2.1 - Survey Set-Out
046dd51c-0175-5459-a6c5-f55a289e5f9f | note | FREQUENCY: Prior to commencement of excavation.
59adf8ec-c302-58b0-9358-84cc178503e2 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
f4ef093d-e2c1-520a-bcb4-4f73075c4346 | note | REFERENCE DOCUMENTS: Work Procedure
6cb1adab-fa85-5394-b96a-55d7a6d14d84 | note | METHOD: Verify
f4f4540d-46e7-5141-aded-2d93b7455cf6 | note | RECORD: Signed ITP
8ef72872-7802-5f59-bf65-b457024a33ac | note | IP
4357050c-8bee-5b9c-851a-a546b7d3e05b | note | RESPONSIBILITY: SWA Project Manager
4f7fa3db-aedc-5e1b-aadc-9eee1d7a7f47 | date | Date Completed:
4fa02bcf-128c-52b5-bef2-2b0ba5d23d06 | checkpoint | 2.2 - Excavation Permit
b66700e3-f3fb-5637-82da-e55576bdf4b2 | note | FREQUENCY: Each Lot
19e84c8b-81ad-5fc9-9c1c-2cf7de12c162 | note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
ce7a9b89-7a27-5c68-9149-9254a6ab0e3c | note | REFERENCE DOCUMENTS: Excavation Permit
1fcaa11d-5c25-529c-bc7a-fb66f002513e | note | METHOD: Verify
b940a2cc-622a-5268-b6d5-4174d5bfe926 | note | RECORD: Signed ITP
8d23f1bc-479e-5750-b0a8-4dc379f2e99d | note | IHP/IP
19cde785-dfd3-5089-a243-0103582f7314 | note | RESPONSIBILITY: SWA Project Manager/SWA SEQ Adviser
329413a2-cceb-5639-8216-500c4af30ad1 | date | Date Completed:
696a0b9e-a6bb-510b-9f82-a68874efa52d | checkpoint | 2.3 - Sub grade Material Properties
5fd83012-c466-593d-9c1a-748bded75184 | note | FREQUENCY: Each Lot
afe4b2e2-ed25-5b1b-9af5-d1e138adac8a | note | ACCEPTANCE CRITERIA: In situ material within 400mm of cut ﬂoor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
a1ffa119-4d34-5673-9c44-9dc6ea662460 | note | ○ If parameter met, rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
ad5e0754-0df5-5c5e-abad-2aae1ada4c77 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
8ae13c3c-13ac-50c2-8189-e50b75a74f02 | note | METHOD: Site Inspection/Test Report
6d2aaaa3-68de-5559-b12a-b31c9741aade | note | RECORD: Signed ITP & Test Report
07fd6496-84d5-54b1-b081-eab94ff926ce | note | TP/AP
10ab7e0c-4532-54d5-a31a-e33a6cd96b1d | note | RESPONSIBILITY: SWA Project Manager/External testing Company representative/RRV Superintendent
3e8552c4-a105-5534-846a-e1af640e3f76 | date | Date Completed:
cf0f983f-dec6-5c5c-b317-8e537435bfb7 | checkpoint | 2.4 - Inspection of Subgrade Material
fc2ff622-f8b0-5225-9a20-3b3fb6fdc287 | note | FREQUENCY: Each Lot
13024377-9a3c-5b23-84e9-ad46c0eb0d37 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to veriﬁcation by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
d2cc98f5-f540-50ae-8a5e-e3e548ef5835 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
0db4cef1-508a-5807-bef9-04f66542a0d3 | note | METHOD: Visual Inspection
76a001cd-1c60-595d-81ea-30fe6d7c513e | note | RECORD: Signed ITP
5b5cb03e-be09-5c3e-ae18-32be5d6e95ec | note | IHP/AP
c06704ae-32fe-5fa2-9cb1-3c0294866db3 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
d3926330-b65c-5374-aab5-5164629eeec9 | date | Date Completed:
ed73382c-33d9-5bab-a623-7ebe94daf695 | checkpoint | 2.5 - Material Classiﬁed as Silt
43018c9f-362c-57f1-a789-d614010c526d | note | FREQUENCY: Prior to commencing
762a0a86-0d34-5b1d-abfa-fa16440eb526 | note | ACCEPTANCE CRITERIA: Material classiﬁed as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent.
56b42410-7b7a-50f6-b7d5-89d80bb5a441 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (e)
68b0c69e-dc73-5f91-a426-5d5e86656bb2 | note | METHOD: Visual Inspection
5e98c672-e09a-5ac8-982a-016dbe24374d | note | RECORD: Signed ITP
cf5098b9-e705-5cac-a813-266e60de3dc5 | note | IHP/AP
b907f15a-9cc7-564b-8b66-da57e9316eb3 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
a0191669-b753-5b5a-a7a3-8c73f82bad58 | date | Date Completed:
1a64b919-5767-579b-b78d-b80a73f9f71f | checkpoint | 2.6 - Acceptance of Rock Subgrade (when applicable)
cb481af3-2357-5cbf-ad97-bc04aed2500c | note | FREQUENCY: Prior construction of the regulating layer.
51f0b093-c186-5f27-a8c3-ccabdfbfd53c | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
8ad4bf0a-5290-51af-a3e5-ee684a223608 | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
61cb11b6-7c28-56b9-8dc8-cf645c711174 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (f)
14a6497b-1d6f-5818-8481-9bf14cba7709 | note | METHOD: Site Inspection/ Document Review
d35e44fd-e587-5be6-a24f-718975f149ec | note | RECORD: Signed ITP
49338d4e-2a96-5325-800c-ad111c64dd75 | note | IHP/AP
12cb7c2b-36df-5553-ba6f-24e68e0207a8 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
2b1425cc-b454-5d77-98dd-96bd3b7aa072 | date | Date Completed:
6b5dbb08-09a3-59e4-9d78-56fe202c28ac | checkpoint | 2.7 - Unsuitable Material
db94795f-3834-5c1c-91f3-9fc4301600ab | note | FREQUENCY: Each lot as required
702af76c-3a00-56f1-9fd7-7ccc840360ca | note | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review
1b3e2ac5-48c1-5654-bd54-7761b3098b42 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (d)
36c5022f-b720-5452-8061-86025516a283 | note | METHOD: Visual Inspection
244ed7f3-e86b-5bac-9517-ea83524d8369 | note | RECORD: Signed ITP & Test Reports
f80bc235-fc80-596b-85fd-e33c182b9bd7 | note | IHP/AP/TP
f10559a8-06b7-5b31-8da5-5968ae7501a7 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representat ive
56094748-985f-5079-8f95-88fb28e47e3f | date | Date Completed:
85d203c2-ff88-5ee1-9095-c8f8c10eb8c6 | checkpoint | 2.8 - Groundwater
8e947778-8b84-5100-89f5-2f3fd0129bdf | note | FREQUENCY: Each lot as required
7673e185-bc79-53b7-bcb2-29c2e8a77f19 | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
516134ef-d6bb-59c1-8b17-ab08d4c1f88c | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (h)
d1271fbf-7904-518b-b1e7-07dbd73a020f | note | METHOD: Visual Inspection
5ea962a4-e35d-5646-9f69-39256bf464cd | note | RECORD: Signed ITP & Test Reports
3692b2d5-c7e4-55f3-90a5-cbebc233d986 | note | IHP/AP
cc609a62-4df2-51a4-b6b1-bc840724da7e | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
9e689064-6953-575d-8309-6c093fb7d00c | date | Date Completed:
591accc9-6902-5e5f-9757-29f5822dfa19 | checkpoint | 2.9 - Trimming and level conformity
61509124-0ebf-5b78-8745-f05a38c4eab4 | note | FREQUENCY: Each lot as required
a17b198b-f0c1-55dd-8a4a-d54afc2b9c1c | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
0d7a5745-75d9-57e4-9081-7b79048b2506 | note | ○ Level tolerances: Range x (Mean value of all measurements) (Scale A) x = +5, -25mm (Scale B )x = +5, -15mm
ad920ce8-f8b7-53b3-8743-60328344a9de | note | ○ Max S (Standard deviation of all readings) (Scale A) = 12 mm (Scale B) = 15 mm
5e252ff1-5950-54c6-bf76-db5a1f002010 | note | ○ No. measurements (Scale A) 80 per lot (Scale B) 40 per lot
87493cb0-d115-51c4-9d1f-759d71102d10 | note | REFERENCE DOCUMENTS: VcRoads Std 204.03 (f,g,h) Table 204.031
d04f4af3-fe8c-5e49-bcac-93f66a7ec19d | note | METHOD: Survey
311b327e-4037-5495-95d9-fdd693c1be25 | note | RECORD: Signed ITP & Survey Report
1018ec42-1b82-5abf-96e9-81d3440f82b4 | note | SCP
92e60c36-bee9-5e0c-8f85-d4a9bc691cf3 | note | RESPONSIBILITY: SWA Project Manager/External Surveyor
3b911a52-4913-54fd-8ba4-e6fcbb275574 | date | Date Completed:
6654a5b9-b49f-507b-92a0-605d8a01ad64 | section | 3 - Testing Requirements
a28580b2-c64c-594e-aa92-fe80a16a2976 | checkpoint | 3.1 - Test Rolling
d3a1bc80-faee-5112-bc75-bec68db18977 | note | FREQUENCY: Each lot as required
4e918e84-6387-53fd-91c4-0ca52044fde4 | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep. ( Cl 173) Plant to comply with requirements of Cl 173.03.
5aaa4854-fe7e-5cad-b4e1-74d41e8f3994 | note | ○ Pneumatic tyred plant nominated for test rolling procedures shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre.
4277ddd7-f14f-588f-b3b9-ea39086bd6ec | note | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Section173.03 173.03 (ii)
6ba8ef5c-35b4-5365-a45f-95d31a5cef58 | note | METHOD: Visual Inspection
1a0d1f68-b539-5451-b907-0976dddbb2e2 | note | RECORD: Signed ITP
9b6dc80f-3f74-52a8-8bd4-abfbdd979797 | note | IHP/WP
9ead8112-2025-5ed7-be9d-429f573ab070 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
b2ea547c-739f-5d7f-aa8f-212f732da151 | date | Date Completed:
a75a64bb-3d89-50ed-a9d6-5291bb034737 | checkpoint | 3.2 - Compaction Testing
f6a27ea9-f413-5e1c-9775-326bd9c2ee19 | note | FREQUENCY: Each lot as required
cb715b59-c134-524b-89fc-b956d96a3462 | note | ACCEPTANCE CRITERIA: Ripped and re- compacted material below Cut Floor Level = minimum compaction 98%.
e62dc0ef-1dae-5206-971f-c837806fad71 | note | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 98%.
5d92ffe2-2202-5931-b8a7-a03620b229c9 | note | ○ Type B material 400mm below the top of Type B material and Top 150mm of where ﬁll is to be constructed = minimum compaction 95%.
ce30c178-8296-5470-93d3-337682e65b40 | note | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Table 204.131
8cc9c55b-be60-5c5c-a496-fe978d289bd0 | note | METHOD: Compaction Test
1e3b7c0a-b2a1-539a-bacd-7cfd0f0697dc | note | RECORD: Signed ITP & Test Reports
56699200-6334-5d20-84a4-70d33c6231aa | note | IHP/AP/TP
a0e93b15-f5af-5c9a-8e7c-cf39d73bfe28 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representative
bfd3e807-29e4-5f56-ae7a-2ce38924e07a | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
dcd25591-fde7-5bcd-a09b-d3e6d47d71ec | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
16a05b1a-935d-5290-8681-c77a6eab76c0 | textbox | Print Name:
64743c84-a5c9-5c74-99f1-e395de6b42c8 | textbox | Position:
49bd4889-f620-5147-a465-3d6c08b91f49 | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
03b6dd15-6a8e-58af-86fe-27776b93d631 | checklist | ITP-004 - Underground Drainage | itp | ITP-004 - Underground Drainage
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
aa5b427d-339a-5d3d-b6c5-84f70f776c33 | checkpoint | 1.1 - Obtain MOA and Traﬃc Management Plans. Ensure Traﬃc Management Plan is adhered to.
ff7f771d-f196-5e94-89c0-d98ee7bccdc5 | note | FREQUENCY: Prior to commencing works
f1e48edd-754f-5254-98e2-0d81f4bf1295 | note | ACCEPTANCE CRITERIA: Refer to the VicRoads Traﬃc Management speciﬁcation 166
846dc3d1-3f0d-548b-88ce-ec81a4516cfc | note | REFERENCE DOCUMENTS: Traﬃc Mgmt. Plan
3b32932d-65ad-5802-8d9b-f12f832e80a9 | note | METHOD: Visual Inspection
9af47316-48b4-5e62-a789-d9cb5127c919 | note | RECORD: Signed ITP
09237390-a739-5faf-b772-8dade004f4a6 | note | IHP
7c013968-a164-5048-9bf4-0e39e513a1eb | note | RESPONSIBILITY: SWA Project Manager
30b0e11b-b6b1-5617-ae1d-0998085e5877 | date | Date Completed:
277ed93f-4550-5150-83c9-df642f820a8c | checkpoint | 1.2 - Purchase of pre-cast pits, pipes and end-walls
195669b0-1473-5494-a15a-ad3ec8a39b49 | note | FREQUENCY: Approval prior to placement of order
31a43218-3e13-5342-b183-b8ec49858bb2 | note | ACCEPTANCE CRITERIA: Refer to Construction Drawings
5700c480-85eb-5218-93a3-706a1f664619 | note | REFERENCE DOCUMENTS: Vic roads Standard drawings
dd1103a1-592e-5fa2-a1df-403df97b4a5e | note | METHOD: Review and approval of documentation, Visual inspection
b1ea887b-e0bf-56d9-9b74-1e58a173bb73 | note | RECORD: Signed ITP
87e90362-6a1a-532a-b98e-3458a3a56f01 | note | IHP
ef83053c-2695-53b4-b1cd-2a6e14967af3 | note | RESPONSIBILITY: SWA Project Manager
4eee7202-5202-5afd-a007-1628a7ce0d0f | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
3fc2718d-49ae-5211-b493-7b1d37994476 | checkpoint | 2.1 - CONFORMITY WITH DRAWINGS - The Contractor shall set out the drainage work in accordance with the drawings or as speciﬁed.
41bc5e39-ebc3-5862-ae41-6030e1febc70 | note | FREQUENCY: Each lot as required
8048936d-695b-5cdd-937b-b38056a05933 | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall conﬁrm the position of all culverts with the Superintendent.
44adf031-0957-5d70-9ecf-c9728a776289 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
2af47ceb-97b3-5f1e-8621-68cb1577ea32 | note | METHOD: Construction Drawings
4eb6ebae-de34-501e-b1c7-690696fc4379 | note | RECORD: Signed ITP
c1e9b9c5-bfe7-56fc-8315-e88f4513fc5d | note | IHP
0314b7e7-da94-50cc-96a9-00fc9f06bed8 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
b225dc7d-df7d-533f-8ab6-615287710640 | date | Date Completed:
2ef4dc01-6d04-55e0-b499-703d38ded273 | checkpoint | 2.2 - CONFORMITY WITH DRAWINGS – The culverts constructed shall be constructed true to line and level
2253bb94-74fd-544f-b1be-00da20521073 | note | FREQUENCY: Each Lot
d326f21e-5a8e-5f77-b41b-fd03ece16966 | note | ACCEPTANCE CRITERIA: Unless speciﬁed otherwise the tolerance on location of pipes compared to the design or a change to the design notiﬁed in accordance with this clause shall be:
91a11db4-0d59-5076-8514-b961491675e5 | note | (a) oﬀset of entry pits required to match lines of kerbs or barriers ±20 mm
7af79b61-d7d4-592d-b239-f1ea814f9603 | note | (b) plan location of pits other than oﬀsets to kerb lines or barriers ±100 mm
5ccb1813-f18a-572c-ad93-988c6e037d8b | note | (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
d89417c4-1dbd-54c6-a591-3542d3627404 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
6e29027b-260e-5746-8b1e-04e31e593e2a | note | METHOD: Construction Drawings
f646c043-e403-532e-bf52-ac5c9d1595e4 | note | RECORD: Signed ITP
5796186f-716a-5899-afe2-91ea32a06e83 | note | IHP
08433fe9-66f6-596e-b684-be188dd7aa3d | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
f4968ee5-7261-587f-a4c3-61303e64aad8 | date | Date Completed:
9229842c-f53c-55b8-95c3-6daceb99e979 | checkpoint | 2.3 - EXCAVATION
eb6a81b1-106b-5f34-acc5-de0ef1dc8f6b | note | FREQUENCY: Each Lot
d37c6318-756c-531a-b22b-17daa23f131a | note | ACCEPTANCE CRITERIA: For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm
5f543bae-e0ac-5b82-80d5-ad5d368ef555 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 701.14
239f74ed-19b8-5b33-a3e6-4f71c526e866 | note | METHOD: On-site Measurement
c5554e91-31f3-535b-a926-8a87cca0db04 | note | RECORD: Signed ITP & Drainage Checklist
a828992a-5878-5fea-a175-7d8ac53ec858 | note | WP
33b10b9d-3efd-5adc-aff9-bbe3d9ff2872 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
d8375f6f-ff33-5a15-b156-fb2952ca0d6e | date | Date Completed:
84b19f5b-5c46-57cf-a2f6-06554dc3aa79 | checkpoint | 2.4 - CULVERT BEDDING - Bedding material shall be provided and placed for the full width of the trench or, where the culvert is to be placed without trenching, to a width 0.8 m greater than the overall width of the culvert
25edea32-d970-5686-9c14-edca3b9efbfc | note | FREQUENCY: Each Lot
eb66c574-bb8f-5179-b2c3-6a00493b25af | note | ACCEPTANCE CRITERIA: The compacted thickness of bedding material following any shaping necessary shall be not less than:
3388aab4-97b7-511f-94a8-f344513ebbc7 | note | ○ 100 mm where D < 1500 mm
7d4a4a5d-71ea-55d7-af83-c565b0b0ecd2 | note | ○ 200 mm where D ≥ 1500 mm where D is the nominal pipe diameter or culvert width.
63c746b0-d9c2-53e3-82b2-3869e08c7f7f | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.15
1efcf702-d6c4-5fc2-b96a-28f08dfcd303 | note | METHOD: Site Inspection
18a937f2-a3e1-5bfd-80bd-dcaa997371f6 | note | RECORD: Signed ITP
cfb493f4-4784-5d48-844f-4e73bfc61023 | note | WP
bfa05788-6b45-5bad-ac25-11dc14849300 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
164537f7-8e27-51d7-84f9-89a18d28af18 | date | Date Completed:
9d74312e-086b-5ab1-b8fa-c13e8a502894 | checkpoint | 2.5 - PLACEMENT OF FILLING
c1c0360c-17a2-5ff3-bc82-281da7c28cc7 | note | FREQUENCY: Each lot as required
bd9a776e-abe2-546a-b401-bb87129b5561 | note | ACCEPTANCE CRITERIA: (a) Unless the culvert is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
160d80d9-ff77-5f51-b798-2054f70cd708 | note | (I) Culvert Under Area not to be Paved
0520f71c-d372-5b7a-915f-3b14a6e7c495 | note | ○ The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
288ada38-b0ab-508b-a609-231cf2a5eb01 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.18
c11628d9-8c2f-547c-a3d4-bd3c29584dbd | note | METHOD: Site Inspection
34d13068-7144-586d-9cb4-8dc1e9561164 | note | RECORD: Signed ITP
fa434381-2d8a-5b79-8a37-a56f27a08b6b | note | WP
95987a52-448a-5ad6-ad46-d0a13403a993 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
96f4d2af-c83c-5fea-88d4-62590757ddd1 | date | Date Completed:
3f774b8d-db9a-51be-a68e-24815f5896cb | checkpoint | 2.6 - INSPECTION OF DRAINAGE LINES BENEATH PAVEMENTS
138dc408-69fc-5f5a-8457-3469d3d95724 | note | FREQUENCY: Each lot as required
9a2feca4-3283-5092-bfd0-a4678f117675 | note | ACCEPTANCE CRITERIA: Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV).
4e9109f9-343f-5fbc-9da1-718231d95947 | note | ○ Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
87e7f08a-f96f-5d07-b90d-aa12b5d88b49 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.28
62e347ab-b426-508c-ae0c-1024c9cc5cfa | note | METHOD: Visual inspection
d7f8dc8d-3819-5d55-8f64-c2b409877f47 | note | RECORD: Signed ITP
8089c255-87cb-5470-a96e-b2c801bafb1d | note | HP/AP
c3e603f4-4c5b-53b7-8f4f-ee08d4470d78 | note | RESPONSIBILITY: Project Engineer/Clients Superinten dent
d5bd297f-9113-5a39-b980-f5e0b8f88b12 | date | Date Completed:
5d0bf3c2-9d31-5144-bcdd-4b712c1f0027 | signoff | AUTHORITY HOLDPOINT
554ac80d-3a13-5271-8a6f-e2f6eed39f0c | checkpoint | 2.7 - Where required installation of Geofabric or Jute matting and beaching material in swale drains
cd3f9388-74bb-5021-a6db-086733703b09 | note | FREQUENCY: After installation of pipes, pits, end-walls and placement of asphalt wearing coarse
bf175921-e803-564c-8f3d-1bf7d662556d | note | ACCEPTANCE CRITERIA: Rock used, should be an assortment of sizes where possible. The smallest rock size must be able to resist dislodgment in peak ﬂows. Rock shall be placed with a geo-textile liner.
a88ccc67-6170-5043-a577-bb75f2d995aa | note | REFERENCE DOCUMENTS: NIL
c4b9166f-c4a8-5869-8242-4ff325f26b11 | note | METHOD: Visual inspection
8d82beaf-77e0-5b9c-877d-eefb3b017b03 | note | RECORD: Signed ITP
bdadf9cc-a6a1-5f77-81ee-d96f0df941b1 | note | IHP
d4dafda0-0727-562c-994e-7c2f64c04999 | note | RESPONSIBILITY: Project Engineer/Si te Supervisor
aebf675d-db93-5925-94f6-6aaaedf55e39 | date | Date Completed:
6654a5b9-b49f-507b-92a0-605d8a01ad64 | section | 3 - Testing Requirements
d0124663-714e-56dc-8e0b-cd503b4b8a31 | checkpoint | 3.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION AND MOISTURE CONTENT - Bedding and backﬁll materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
38f7f3fd-186b-5a94-9d3c-d46cfddc8722 | note | FREQUENCY: 3 per Lot (A lot shall consist of one layer of bedding or backﬁll for a culvert length between adjacent pits or endwalls)
39406688-46e7-5934-88dd-11172fada3d6 | note | ACCEPTANCE CRITERIA: (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
fc9b0346-7df2-5e7c-8e79-36472f115322 | note | (b) Backﬁll
84515d71-0f2e-55eb-9c0a-e16782ff187a | note | (i) Material of Nominal Size 40 mm or Less After Compaction Backﬁll material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
73d39840-e6d7-5c0b-8fd4-8bafe562197f | note | (ii) Material of Nominal Size Greater than 40 mm After Compaction Backﬁll material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
396e2c2c-1b7b-578c-bd19-8bc8eb1b9057 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.19
b4b94626-f9df-5024-bf29-1e39dbd6c81e | note | METHOD: Lab Test
74d128c5-1452-5f90-beee-94ceb44c230b | note | RECORD: Signed ITP
3782413a-7cf5-5707-89ed-a514e9b0186e | note | IHP
020dfa56-df5b-5eee-81e0-d26e3b402d1a | note | RESPONSIBILITY: SWA Project Manager
1492241a-2e16-51e4-bc88-241b9eba531f | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
bd0e6189-8169-5e75-838d-b3124d3c7a13 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
0db37f49-dd06-5ab4-9403-1ca4a21edb57 | textbox | Print Name:
f9cbb62d-571f-5bfd-bb23-97eeb63cd4a6 | textbox | Position:
52ce646b-4fd7-5d88-bf27-a1d49b30da0a | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
676c0dc5-3d4c-4d0d-8c3d-cb430e079773 | checklist | ITP-005 - Crushed Rock Class 2 | itp | ITP-005 - Crushed Rock Class 2
a7c01852-e10f-4bbd-aedd-6f66b710dc41 | section | 1 - Preliminary Works
b8ff2abc-8817-464f-a7b6-584c55b03f47 | checkpoint | 1.1 - Crushed Rock Mix design
b893e869-4fea-5400-aef4-bd3a82fd8dc7 | note | FREQUENCY: Prior to Commencing Work
67a1cfd6-c73e-56f8-a9f6-2e053f32259e | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
3e86ac57-c71d-5ba6-90f9-ca14696ecb9c | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.812.09
f9e83717-2ba4-5d33-8cf6-d883fde8e7c4 | note | INSPECTION/TEST METHOD: Document Review
a8ff5066-85e7-5680-97ab-2f75724d7517 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
9d4219f5-9e18-58e6-9fe3-e67172c10dfd | note | HP*
ad577942-127e-5a92-8410-9be1f2e8f5f2 | note | RESPONSIBILITY: Project Engineer
a0880a7f-0855-5d3c-b945-86610cea2d0c | date | Date Completed:
1d41ea1f-fae0-4d58-aabd-ad265610043d | section | 2 - Placing Fill
62b23fe3-ef1b-4226-a0fa-193d962d3393 | checkpoint | 2.1 - Transverse Joints
99bb88ae-007d-5048-9a2c-5ec460cb096b | note | FREQUENCY: Check prior to placing material
ef8118c1-bcf5-51a2-87af-c9ace2201fb8 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsTransverse joints shall be offset from one layer to next by not less than 2 metres
513d9fe7-554c-5df5-8c83-7902aae5ed13 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (c)
ce711816-e815-59c4-a1b7-a239bd67b54f | note | INSPECTION/TEST METHOD: Site Inspection
bddf9f8b-454c-5c35-9ed1-91fa38c002dc | note | RECORD OF CONFORMITY: Signed ITP
d75e896d-9eec-57e8-b314-ccbdd8537d11 | note | IP
f586b5e7-0b4e-56d7-aefa-20152cc9c2ab | note | RESPONSIBILITY: Project Engineer
887b7376-711a-5fd6-8b9d-053f298f192f | date | Date Completed:
5509e709-c808-4199-95a1-ae8ff6225b45 | checkpoint | 2.2 - Longitudinal Joints
fbb0310c-9af1-5603-9687-8de821920689 | note | FREQUENCY: Check prior to placing material
eaf2e228-595c-50b5-8c27-ec0253790e0c | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mmLongitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
fcdb5ca4-b7fa-5770-832c-ab5719f8233e | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
d4ddedfc-bce5-57e1-bada-a02910b09773 | note | INSPECTION/TEST METHOD: Site Inspection
574d0f7d-1083-5251-8f97-f5db8827c0db | note | RECORD OF CONFORMITY: Signed ITP
73507be5-6e44-5ddf-a757-eaf129d3f3d3 | note | IP
631bcee7-5b63-5fd3-9736-dfe0750e8707 | note | RESPONSIBILITY: Project Engineer
b1b82ebf-6912-588e-94f8-737dad3086df | date | Date Completed:
ce405cb9-ac24-44b3-afda-0d4f4ca52ca2 | checkpoint | 2.3 - Lot Size
3aa867e1-dda0-5c81-89c6-0c8af05fe594 | note | FREQUENCY: Check prior to placing material
6aafaa08-1f0f-5648-a300-408bf1e2247a | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
d966c5bd-c1de-5d8d-993e-ef0b3e5ddc5e | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08 (b)(ii), Table 304.111
430e644e-1534-5f5e-814d-36fd5d921653 | note | INSPECTION/TEST METHOD: Site Inspection
6e063d09-2e39-5655-9615-da95d092240e | note | RECORD OF CONFORMITY: Signed ITP
517545a0-f6ff-5782-9046-0368a980a4bd | note | IP
d6adc4a8-2c74-5b51-bf7a-6691dd1dcfb8 | note | RESPONSIBILITY: Project Engineer
9fdf7d63-2128-5d29-ae66-7e5d3eaf5b22 | date | Date Completed:
fec62321-06cc-4b43-b613-d07f30dea7a4 | checkpoint | 2.4 - Proof Roll
98564637-b2a8-5c81-828c-92ecbfc88774 | note | FREQUENCY: After placing material
65742847-85c9-5bf5-90ca-f0eb0884d62d | note | ACCEPTANCE CRITERIA: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
14eb7bd1-1f96-5700-95b7-b36059300472 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08(b)(iv), Cl. 173
095f59d1-7069-509f-a14a-e5e641ddf06c | note | INSPECTION/TEST METHOD: Site Inspection
74149970-4aec-5e45-8e0d-4031673e3b5e | note | RECORD OF CONFORMITY: Signed ITP
a3107613-093c-55fd-be8b-1648b517d181 | note | HP
6a22060e-d6d8-537a-980a-51758196a342 | note | RESPONSIBILITY: Project Engineer / DTP / VIVA
a9901f72-1da7-57e6-9008-a3b637c8eda6 | date | Date Completed:
d392bc65-2cb9-4cca-8bf6-3b2cc505fb79 | signoff | AUTHORITY HOLDPOINT
702c65f0-5167-4d45-acb3-89fcfef6a9f5 | section | 3 - Testing Requirements
760c8a41-d630-46b3-ab1d-92c36a24881f | checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
aaa6f55f-6a82-5abe-ae03-58f08bcdc0dd | note | FREQUENCY: Prior to Testing
ef35cf70-4621-53cc-835b-7eeb1a7a767c | note | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
764eb108-3d66-54e9-86c8-3e33c977491a | note | ○ Scale B - Initially test every lot until 2 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
626562b0-88d3-59c8-893a-0e25990bca82 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.161
5302b1e4-f270-5089-abdb-922dd00733e7 | note | VicRoads Spec.
c1e874a4-3260-58c5-b842-780e1c112129 | note | ○ Cl.304.08 (a)
b0260730-334d-55df-9ff1-c0cb65fef98d | note | ○ Cl.304.11 (b)
11781de8-482c-5606-836a-5d1335d409f6 | note | ○ Cl.304.11 (c)(i)
7994d65e-7a67-5006-8dda-0cc760e016c4 | note | ○ Table 304.111
5b5b9f26-5857-5c87-ad58-4ffe02a7dfd8 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
7ce88dad-0b39-51e8-81fd-26050bfb83b4 | note | RECORD OF CONFORMITY: Signed ITP
2d2ea3ca-b76d-5c82-ad53-8723bbf6f13a | note | IP
d54e14a1-0b0c-5a38-9c58-eef4a72d5727 | note | RESPONSIBILITY: Project Engineer
ff89c13a-28d9-5533-934c-56e6026f5818 | date | Date Completed:
9ea74c3a-7990-458e-b9cc-ce7cc9b8712d | checkpoint | 3.2 - Modified Compactive Effort
6d520bd6-29c1-5ae8-a162-753bcc917cfd | note | FREQUENCY: As per 3.1
5e57f232-a612-57d4-932b-c1c097534ae7 | note | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 97.0% (Scale B) 1 per every lot
a9999452-9cf3-525f-9e20-70f38502c08e | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.081
95657a30-dce7-59b9-b63a-069c9c861a1e | note | INSPECTION/TEST METHOD: Site Inspection
239d06e7-3529-593c-b79d-f381437f1d33 | note | RECORD OF CONFORMITY: Test Records
41a83d58-832c-53b9-9937-2ffee8e40fde | note | TP
7757315f-f41c-5022-97ec-f1595ac55fec | note | RESPONSIBILITY: Project Engineer
a098d406-1906-5696-911b-2c290a6cdd66 | date | Date Completed:
4c893940-8d55-4c22-a1af-df2263507712 | checkpoint | 3.3 - Survey Level Conformity
035cdcca-8e35-5d04-a09f-b093faaa878d | note | FREQUENCY: At completion
b7cbba40-6394-5634-b412-5374a394c976 | note | ACCEPTANCE CRITERIA: Scale B:
3acb5a60-ef2f-5cda-94dd-a27222405eaf | note | – Minimum number of measurements per lot: 40 For Upper
72394234-7e74-5e89-91a0-a64060b67633 | note | – Upper Subbase: Mean + 6mm to – 12mm with a maximum Standard Deviation of 8mm
9c01780e-4115-5185-91f9-a2ee5b5e7c5f | note | – Lower Subbase: Mean +8mm to –16mm with a maximum Standard Deviation of 10mm.
bdfba48c-1b4d-58fb-b2e5-9b06e6e47786 | note | – Base: Mean ± 8mm with a maximum Standard Deviation of 8mm.
eaf70417-84af-506b-a947-e6a3cd3c137d | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.061, Table 304.062
421504d5-8526-552c-95fd-53a5766adddf | note | INSPECTION/TEST METHOD: Site Inspection
0b013088-c6f3-51e1-9b2c-750bdad5e150 | note | RECORD OF CONFORMITY: Test Records
d57dff8a-6f0c-5686-b5f1-bb61b0a3b9d7 | note | TP
b3100ef7-497e-50db-9caf-be5607ba9d2d | note | RESPONSIBILITY: Project Engineer
144331fe-4309-5dac-863b-e46b2a9518e7 | date | Date Completed:
a3e83dc3-be84-49cb-8790-bfa87923f394 | checkpoint | Final Inspection
a94cec0c-2c8a-5a22-953d-d34b2e63d92e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
531f55e5-cfe3-5e9b-95a2-491feb947bed | textbox | Print Name:
9fa74147-ab4d-52ef-9e47-0b67345c502c | textbox | Position:
f2cbc9f7-36db-502d-9f76-0f669cefa1a6 | date | Date:
ae6e6015-0b51-417a-a7e7-3f280d803298 | signoff | Sign ITP
fab90c11-a510-5a00-9cd8-8b3b9620cbf2 | checklist | ITP-005 - Flexible Pavement Construction | itp | ITP-005 - Flexible Pavement Construction
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
e0e726e1-03f5-5bd5-8794-646fdea2f249 | checkpoint | 1.1 - SET OUT OF WORKS
21a438d3-f799-5869-9ca0-65c3b2e95d5d | note | FREQUENCY: Each lot as required
1d06acbf-a00b-5e03-9db8-c71bc225cc9b | note | ACCEPTANCE CRITERIA: Ensure relevant construction drawing are being used to determine set-out of works.
e7ec4598-5998-59f4-a6da-3f7c62b4d1c4 | note | ○ Ensure all survey pegs are aligned max 40m apart and the oﬀset distances and heights are in accordance with relevant drawings
472ba5b7-b2fb-5b14-afce-13d6e376b05d | note | ○ Refence checking to be conducted with string lines
56cd3848-d046-5659-9cff-3b5220170d1e | note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
3c2d0e5c-ad3e-51fb-98da-f6b89fada6e6 | note | METHOD: Survey set-out
46d63712-60bf-5ace-98dd-1bb84e6dab98 | note | RECORD: Signed ITP
21f50034-22b9-5a3f-a7a2-09ceb5f4bd7e | note | SCP
703fbd8e-ae1f-50f0-8dd9-fd0f1075f13b | note | RESPONSIBILITY: SWA Project Manager
2c71cf9a-452c-5dba-96a4-f047f6c8fbae | date | Date Completed:
264a16ad-2e71-5132-a15f-6a71ca088ced | checkpoint | 1.2 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
e0c1e4c3-01ae-5a28-a97c-457c30e6c254 | note | FREQUENCY: Prior to commencing any activity
83cee339-0a84-599d-96a0-5475fb179165 | note | ACCEPTANCE CRITERIA: Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173 – Examination and Testing of Materials and Work (Roadworks). The number of measurements taken within each lot shall not be less than the number speciﬁed in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
77b93b7c-0603-5666-8f86-2d17e5e3bf3e | note | REFERENCE DOCUMENTS: Vicroads std sec 204.03
bb1ab119-fea3-5851-ae1a-f1ed4b3d8e0d | note | METHOD: Survey Report
f870a3d7-5a52-5e57-a3ad-fb8808c4ba5c | note | RECORD: Signed ITP
9a11a0fc-62d5-5c21-baed-7d41c3cfb678 | note | IHP
d54a04d6-e5f9-5007-a6a1-5f5743055cd1 | note | RESPONSIBILITY: SWA Project Manager
103858ec-6146-5004-8f4e-cc047cefe7fe | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
dbd9ce85-0c7a-550c-99ee-48caf50d3562 | checkpoint | 2.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (a) General
4f049f58-666a-5046-a5a3-8c374b9a2092 | note | FREQUENCY: Each lot as required
890cc7f0-2c5e-5912-a0df-e7880170454d | note | ACCEPTANCE CRITERIA: Material during compaction shall have a moisture content of not less than 85% of optimum. After completion of compaction of a layer, the moisture content of the material in the layer shall be maintained at a moisture content of not less than 85% of optimum until test rolling has been completed.
33ba4406-6891-5a3e-be9b-aeb2dd202059 | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
45aafbde-c218-53c8-ba9f-ec8067913673 | note | METHOD: Visual & Laboratory Report
21091960-9352-507b-9d8e-8277980a5e20 | note | RECORD: Signed ITP
6b7d5eae-9cf2-575f-ad7d-b90f11fad58e | note | IHP/AP
80f3b5fd-1d3f-5c4a-af15-dbc902752ec9 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
5b1c301b-eca4-5af8-918b-90a5383de1df | date | Date Completed:
c31cd46c-71a6-5377-9562-3f8dc0f6ef52 | checkpoint | 2.2 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (b) Material of Nominal Size 40 mm or Less
f0d761e5-1cf1-5154-9067-05b632345722 | note | FREQUENCY: Each Lot
73f4bc54-68aa-56d1-8e9f-b58949ad10f5 | note | ACCEPTANCE CRITERIA: The calculation of density ratio shall be based on tests performed using Modiﬁed compactive eﬀort. The work shall be assessed for compliance with Scale B requirements being not less than 97%. See table 304.081.
58ca41af-e55f-53c8-ac78-0969bd212cab | note | ○ For work to be tested for compliance with Scale B requirements, the number of tests per lot shall be six. See table 304.121.
7298ed6a-a8d2-5300-ad8c-a877189c71ff | note | ○ The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm.
673b97e8-f973-55cc-a012-7eff9d3dd982 | note | ○ The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
2d522158-75e2-5ada-b75c-c6d64e3633b6 | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
5a2a1a0f-8eb3-5562-985f-a06d6a3bd2ca | note | METHOD: Laboratory Test Report
38b38ded-4382-55a9-8321-91cce0bafc89 | note | RECORD: Signed ITP
fc050c64-6bbd-5fcc-a1d3-60db57ebc55a | note | IHP/IP/AP
aa41352b-a014-580f-a92f-f3367cc11c4d | note | RESPONSIBILITY: SWA Project Manager/SWA Site supervisor/RRV Superintendent
091e976c-11b3-5010-bec3-26cdfc39bcbf | date | Date Completed:
0ab143a2-e650-5576-bff5-9a365a7ead39 | checkpoint | 2.3 - TEST ROLL PAVEMENT LAYER
cf26d6d1-0a57-51a5-8998-6140e6be89af | note | FREQUENCY: Each Lot
7021f6a6-d397-5d7a-891b-d587e34330a3 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any ﬁll on the prepared areas until the area has been reviewed by the Superintendent. The Contractor shall provide for the Superintendent to be present during all test rolling.
b77690bb-91cb-57fc-89d4-7c8858b0d4ec | note | REFERENCE DOCUMENTS: VcRoads Std Specs 173.03 & 204.12
ddebae22-3f6e-5344-8a8a-847524cc851a | note | METHOD: Proof roll
5502962f-5656-5b8c-b4cc-be0affcca612 | note | RECORD: Signed ITP & Test Report
1d60d458-0615-5369-8e39-1fa82e4810bb | note | HP/AP
fb4f3192-b1fb-5ea8-99b9-42ab1d8acccb | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
35502628-900b-5e3a-81f1-cd8fab79ff54 | date | Date Completed:
dfb368da-a096-5427-ab0d-4219cac63f72 | signoff | AUTHORITY HOLDPOINT
30dd4d76-cf89-5bbf-94c3-44642a49aa5b | checkpoint | 2.4 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
dd9451ef-7628-5777-b511-8406baf71479 | note | FREQUENCY: Each Lot
b5517203-2972-5415-a154-7513e172b6f0 | note | ACCEPTANCE CRITERIA: The surface level of the pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet either Scale B requirements as speciﬁed in Clause 304.12.
93744061-4d1c-5633-81ff-e0fcad3646da | note | ○ Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
7ca6e396-4048-5fbb-a817-d7b9b6aec8eb | note | ○ Each level measurement shall be taken at random locations over the area of the lot in accordance with the VicRoads Test Method and the number of measurements taken within each lot shall not be less than the number speciﬁed in Table 304.061. Surface Level Tolerance as per Table 304.062
8e8eaa68-3058-5d05-bab8-40a44dbc94ad | note | REFERENCE DOCUMENTS: VcRoads Std Specs 304.06
1bb3836a-8681-55de-961b-4ea84c3730ab | note | METHOD: Survey report
c9b54e4d-138a-5902-a65d-40167a8a0199 | note | RECORD: Signed ITP
17e955f5-a405-5b78-9b63-88db0449b409 | note | IHP/WP
0ee07f49-db61-5573-aa0e-f85d91236efa | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
0e76f698-81d7-554d-acc6-0a5da44178f2 | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
7ac89bf9-222c-5771-bff6-eadc91bf12d7 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations
726d8fff-32d0-5a53-897e-89e54955aa0a | textbox | Print Name:
9fd2b4b9-a3d2-5ac2-ae5f-5981ed4b8a07 | textbox | Position:
2b92b7c0-85c8-53f5-8ecf-7a7cc9248cd9 | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
124e85ba-1427-56c6-9cc1-ef7db652307f | checklist | ITP-006 - Kerb & Channel | itp | ITP-006 - Kerb & Channel
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
78f2eb97-4d27-5397-9616-d0974c63c400 | checkpoint | 1.1 - Check for correct documentation
406918ce-3cdc-5bf1-b99b-1cc0ce3670a6 | note | FREQUENCY: Prior to commencing any activity
e011307f-87f3-5b57-afc6-849b34cae3d6 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
be8c534a-b509-5771-ac62-7b511d66b998 | note | – using the correct and complete set of drawings
c69f4138-b3f7-51db-b97d-ccc326af37c6 | note | – all drawings are the latest revision
822ffbea-10b5-5f82-8ab0-f8c159005040 | note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
34936628-eb58-5204-b959-a44867dbf91e | note | METHOD: Drawing Register
79444e64-5635-591e-91f8-b477547447c6 | note | RECORD: Signed ITP
d9bd5ac5-3489-5b71-9430-2ce1611cfa4d | note | IHP
add5cad4-344d-5ff9-9b01-f3492d8fa430 | note | RESPONSIBILITY: Site Supervisor
f8ea5604-b840-516b-b9b6-3986295a792a | date | Date Completed:
457fc29c-5478-51c3-a60f-061f5ba4ad0d | checkpoint | 1.2 - Implementation of all measures and controls
f1ed7616-4da5-594e-89ed-b752ad56207f | note | FREQUENCY: Prior to commencing any activity
897e971e-0b58-53da-ba2b-45c29e989652 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
a01e5185-92e6-5d8d-a6f3-c9eea4ec684c | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
c3a498a8-cfc9-5cf9-91bd-4bdad6bfba9d | note | METHOD: Visual Inspection
47148980-a363-51fc-aec0-5235296d4922 | note | RECORD: Signed ITP
bc3fe039-08d6-5b5e-a8c2-555746084963 | note | IP
e13d9d0a-b15d-5f8b-bd51-dc48258f1cb3 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
2a2f6067-9e00-575e-b431-248df43cc440 | date | Date Completed:
73920d7e-e2c5-5db3-bfa8-d36b7058a4c5 | checkpoint | 1.3 - Setting Out
f103293e-2257-5261-bc5c-72da2d09ed65 | note | FREQUENCY: Prior to commencing any activity
2fed43cc-312a-53e7-8a8e-f9ece4210455 | note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor. Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
31f53ffb-c188-501b-9f47-21af8c4b9fd6 | note | REFERENCE DOCUMENTS: Vicroads std sec 703.13
1688d011-d595-5d40-bfd1-813a57c0c5d8 | note | METHOD: Survey Setout
f132a59f-8e2b-5db4-ac00-1a50c25e51f6 | note | RECORD: Signed ITP
abe4a46c-5cab-59fd-919b-5f5eb81e9ca2 | note | IP
cf7c601a-6eea-58c4-92bf-cbcbc7a6625c | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
941f7e22-16ae-5d20-ab1b-03abed20d5b2 | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
b94cae42-558a-5a9a-960c-3da6f075764d | checkpoint | 2.1 - Excavation
fc4b5e5e-7efc-5785-b195-266e3c5e4d0b | note | FREQUENCY: Check prior to placing material
391c45c5-f8e1-5129-a718-7cde5ad901d0 | note | ACCEPTANCE CRITERIA: The base preparation for kerb and channel shall consist of a boxed out area to a depth of 355mm below FL and 1150mm wide. Excavation shall not extend more than 150mm from the edge of the adjacent face.
cd4e7867-48ed-52ef-8f01-7af0c0fe7913 | note | REFERENCE DOCUMENTS: Vicroads std sec 703.20
395c6ce3-2753-51a3-93ac-2c98f38853b7 | note | METHOD: Survey/Site Inspection
b6a9d6b7-6aa3-5b2d-9e12-f998914f0c63 | note | RECORD: Signed ITP
3851b852-2945-58a2-b5e1-49e85c93b11c | note | IP
2748247b-269e-5276-8976-c1df5a2cb9ee | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
275a27df-78e2-54bb-beba-bccd1405ef56 | date | Date Completed:
230b1f2d-ae16-5865-84cf-631a67835520 | checkpoint | 2.2 - Subgrade Inspection
7419fe17-5292-5f9b-af6e-6ab9f3ed0a53 | note | FREQUENCY: Check prior to placing material
b448cca9-b6ce-5da8-b0e3-7d05f86ef3be | note | ACCEPTANCE CRITERIA: Test roll subgrade to check for No visual deformation or springing. Where deformation is exhibited, the Engineer or Superintendent is to be notiﬁed immediately.
0728161c-0c6a-5ff6-b941-64cfbc2b7da1 | note | REFERENCE DOCUMENTS: Vicroads std sec 173.03, 173.03 (ii)
f39ed3b9-079b-58c8-9755-6fb9aba9ef11 | note | METHOD: Visual Inspection
e468e85e-66dc-585b-991d-a6061a47cd52 | note | RECORD: Signed ITP
68dbdd3b-1e7b-591b-9528-31a809df4c41 | note | IP
ba0308c4-4a24-5f91-9915-59aa7615f963 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
86650319-7ccf-5b27-a073-c105b613572c | date | Date Completed:
5b4520ab-04b3-50db-ac15-158652020b73 | checkpoint | 2.3 - Bedding Preparation
e59e6c97-83db-5648-ac91-397818f406a7 | note | FREQUENCY: Each lot as required
7ba6e700-5771-54d0-8877-7f24e9b6b106 | note | ACCEPTANCE CRITERIA: Bedding material to be used for base preparation shall consist of size 20mm Class 3 or Class 4 crushed rock at a minimum of 100mm compacted thickness. Preparation of ﬁnished base shall be 190mm below lip of kerb as per survey marks.
3f13d882-6cd5-5b8c-977a-a1143ab675b9 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21
41f35c2c-a05f-520f-a7ec-6ec733bf708f | note | METHOD: Site Inspection
fbe9548a-bbbd-542c-8d90-54fc5c63104e | note | RECORD: Signed ITP
ddd43e43-3217-5d2f-b08d-63fe96bf5a7a | note | IP
fdc53d79-8c28-5630-813c-dcc3012d51a1 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
55becea8-8fc6-5e8f-9292-936708566548 | date | Date Completed:
5f2a781c-c5ee-551d-9de8-efbb77367502 | checkpoint | 2.4 - Kerb Concrete Mixture/Strength
1a135d14-44b7-59ab-abdf-e5d70cf31fbd | note | FREQUENCY: Each lot as required
3f26fb6f-256e-598e-b9e6-32f4e8b8994e | note | ACCEPTANCE CRITERIA: Traﬃc routes a minimum of or equivalent to 320kg of cementitious binder material or geopolymer binder per m3 of concrete – VR 330/32
7b5cdbee-30f5-5e93-891b-da9cfc6152a2 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.05, 703.11
65ecbc29-e2f8-5f0c-9b01-3b2f4a5cf809 | note | METHOD: Delivery Dockets
257a7f1c-f457-59cb-8c77-b6d58c927c89 | note | RECORD: Signed ITP
87154659-50e1-5da3-a1fe-e622c69d60d0 | note | IP
3593b420-23e2-5fba-aa66-ea5339877f43 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
0655ebfd-b77c-57fd-9155-b251f8b36dbe | date | Date Completed:
b9296863-da55-50ca-b3a4-74c6b40da96f | checkpoint | 2.5 - Tolerances on Line, Level & Shape
8e4afeb6-97d5-5635-ad08-b6d52ddb3959 | note | FREQUENCY: Each lot as required
d8372740-cf9d-51c8-aef2-29373cca4e95 | note | ACCEPTANCE CRITERIA: All surfaces shall be ﬁnished in conformity with the lines, grades, thicknesses and cross sections shown on the drawings or as speciﬁed. Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10mm. Except on curves or in shaped areas, the deviation of the ﬁnished work from a 3m straight edge shall not exceed 5mm at any point.
9a5ffbb5-5164-51dd-b467-84c02f5bad84 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
6158c054-13b7-53b6-8521-4c14420bbc7b | note | METHOD: Visual Inspection
ba02012e-f3de-5cee-947a-ccc94dab95a8 | note | RECORD: Signed ITP
8bc8d6a9-f2df-5f9f-9f39-9ee3ee69107b | note | IHP
7d102f00-ae1b-5335-bdd7-2293953dcd21 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
fbf4435c-3c54-5df9-91a3-a82a670999a0 | date | Date Completed:
5b03b7b4-4b8c-5fae-b01d-c6a211250c9e | checkpoint | 2.6 - Kerb and Channel Finish
152a4c81-2200-58c7-8846-475a98e97122 | note | FREQUENCY: Each lot as required
710f7d21-3cbf-56cd-8d40-0e5b7b49ca9e | note | ACCEPTANCE CRITERIA: All edging shall consist of a smooth, uniformed and of a trowel ﬁnish. The mortar used shall consist of two parts of ﬁne aggregate, one part cement and suﬃcient water to produce a mix of suitable consistency. Thickness of the rendering shall not exceed 3mm.
efff80fd-0242-5e39-80b8-c9f8160181d1 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21 (a)
d850c6d3-a71c-5054-84ea-71aeafd4b346 | note | METHOD: Visual Inspection
76ab2fe7-1bdf-5321-b5f0-3284d7615a29 | note | RECORD: Signed ITP
53219070-0f0e-5f92-92bc-22136a46688c | note | IHP
57dd1aee-e3f5-572b-a8dc-2d732d48fef2 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
394a1dec-5c62-5a2c-8294-8922811baf6e | date | Date Completed:
dbc95655-357b-5db7-8376-fa2faa5ef7c2 | checkpoint | 2.7 - Kerb Backﬁll
c74426ba-4f22-5b05-9f10-30fcfc2e71d4 | note | FREQUENCY: Each lot as required
7ca14e0d-b321-5913-b323-51a9714edbf0 | note | ACCEPTANCE CRITERIA: Once concrete has cured, topsoil which is free from perishable matter, shall be placed ﬁrmly compacted in layers less than 150mm thick and to a width of no less than 300mm behind the edging to the top of the edging.
53f8edff-f0ea-5e80-bed1-59c7560088b6 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.29
7bc19819-ca2e-5e79-894d-e29bd539afa5 | note | METHOD: Visual Inspection
080fb305-c66f-556d-a03a-33861058893c | note | RECORD: Signed ITP
2d9a91b8-51ff-5edb-b545-a8456e4f6752 | note | IHP
df133037-dd9a-5711-96ad-bf48ac9a8097 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
6bb7c0a6-e316-5ac0-94bc-a436be1504c3 | date | Date Completed:
6654a5b9-b49f-507b-92a0-605d8a01ad64 | section | 3 - Testing Requirements
b893228a-c23a-5236-a21c-016fbf1f0b68 | checkpoint | 3.1 - Compaction Testing
b307cbbb-e0f3-54c8-a277-335031719f5e | note | FREQUENCY: Each lot as required
2f6160d1-c830-5bc1-b0c3-4f14ddd3bb97 | note | ACCEPTANCE CRITERIA: For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six. A small lot is classed as an area equivalent to or less than 500m2 and requires only 3 individual tests. Compaction testing for crushed rock material shall be no less than 98%.
b9b69829-6d11-5e75-9067-7720b2b6557b | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08 (b) Table 304.081, 173.04 (d)
6adc21e0-8da3-58ab-aefd-8685be89e42b | note | METHOD: Test Point
a92a55bc-a934-53b1-90dd-41b857704a5e | note | RECORD: Signed ITP
55bcf49e-48ab-5bbe-9874-4ef19631138f | note | TP/HP/AP
c3d35af1-f2f2-529e-bd5e-850d1d7fa0be | note | RESPONSIBILITY: External Geo tester/SWA Project Manager/RRV Superintendent
ccbb13b1-06f1-5589-940d-1c78307f3d56 | date | Date Completed:
95f4b835-9bd7-53a6-af27-329bf209b2e3 | signoff | AUTHORITY HOLDPOINT
2d7b071f-cd97-5d39-b004-e1989e93ef82 | checkpoint | 3.2 - Conformance Testing for concrete strength & consistency.
3f41a8b5-9b84-545e-a8f7-47afadee5d0b | note | FREQUENCY: Each lot as required
64bce072-3844-521b-a3a0-5dd2b3a16ba7 | note | ACCEPTANCE CRITERIA: The minimum compression strength requirements for each strength grade shall be as shown in Table 703.111
e6dbae4c-ba22-505f-9712-e8ae967f620b | note | REFERENCE DOCUMENTS: Vicroads std sec Table 703.111
c07a8be1-b11d-51db-9679-f6b7058ac38c | note | METHOD: Survey Report
a73228ac-bee6-5e95-a53a-30015f0e35a9 | note | RECORD: Signed ITP & Test Reports
e0effab5-22c2-5331-abf3-391f5ddfa888 | note | TP/HP/AP
fb96dc8c-7e23-5fe2-9ae0-dfdbcf9b46db | note | RESPONSIBILITY: External Surveyor/SWA Project Manager/RRV Superintendent
bc9f3d1f-b1b4-541c-8f87-805c1d330bcc | date | Date Completed:
e1586d20-1767-5b9a-969b-680a4a731b41 | signoff | AUTHORITY HOLDPOINT
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
8138864d-4a3b-5bda-986f-6aa83420317b | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
873f6803-4544-5ef3-a4f4-c6a4310767ef | textbox | Print Name:
db859f22-cc9e-5287-af0c-cf55b244179c | textbox | Position:
751dba85-2a55-5a4e-a2b7-ea4dee9eefbc | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
850ee71d-d2df-5dad-a93c-b836182b2248 | checklist | ITP-007 - Hot Mix Asphalt | itp | ITP-007 - Hot Mix Asphalt
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
26d5d62f-8773-5d6d-81f7-d3753ca4498e | checkpoint | 1.1 - Site Inspection and Base Conditions
d688b9be-5b87-57c4-9401-8e4ee3044ced | note | FREQUENCY: Prior to commencing paving.
77fe2bc8-1442-5be1-96e4-22b2b5e30898 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from surface water. All manhole and valve covers have been raised or lowered to the new surface level of the pavement.
5db3395a-5a33-563d-af34-17c90380b207 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.1
9f664117-1f46-5641-8a55-271a2941339d | note | METHOD: Visual Inspection
f6b9ce53-7b0e-55f5-bf58-2190378470f2 | note | RECORD: Signed ITP
3149520a-eadf-5e65-84c7-25d8c44897df | note | WP
62204960-fdca-5390-8706-6d46b6c16a02 | note | RESPONSIBILITY: Site supervisor
7a542c34-35be-501d-bef9-f7c96b21f6bf | date | Date Completed:
4977d416-cdc2-5db9-a0a9-9fa87c56ca6a | checkpoint | 1.2 - Ambient Conditions for Asphalt Placement
0a2ecb52-16f0-520a-a241-548c9b5501b7 | note | FREQUENCY: Prior to commencing paving.
58b668e8-a984-5f99-847e-f7f7849aa2ec | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed if the majority of the surface area is below:
21a4db70-16bd-5874-b125-c5d207382d63 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
e74390b4-ae7a-5952-85e9-f515b4722f5a | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs.
c975c47b-f504-5bc5-af6d-5fc2f3139d57 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.13
b5ace85e-d10c-5e83-8616-5240a88f8e00 | note | METHOD: Calibrated thermometer
05794ef6-1210-5f5e-988c-9e216f5d1c6e | note | RECORD: Signed ITP
1fa6e8b4-45b7-5c03-9bd0-ad631acac909 | note | IP
b320e086-223b-5c4d-a615-12e62920d7f4 | note | RESPONSIBILITY: Project Engineer/Site supervisor
cc06b2f3-d3c5-5b1b-8572-83b09a446a34 | date | Date Completed:
258a39b8-19ff-5418-829d-82c7f06ce5e9 | checkpoint | 1.3 - Surface Preparation
4e54f265-bace-5007-9924-59ff70e7ba9d | note | FREQUENCY: Prior to commencing paving.
3ca451bd-60bc-5aa8-82ff-2fb8f95d4ae6 | note | ACCEPTANCE CRITERIA: The area to be paved is free of all loose and deleterious material
d7bca43d-b98f-5a72-b645-801e4af922e9 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.3
b7150c70-7401-5f10-a71c-de2898c7e3a7 | note | METHOD: Sweep Clean and Inspect
6deba588-d573-5826-8f7d-5cf57d2a7308 | note | RECORD: Signed ITP
4f8547f4-8f39-585e-846f-eb93a72dee5f | note | WP
97ac1dbb-d171-51cc-b773-9def1a760570 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
05dbeb64-1a43-5b0f-ab97-a2a9299cfea7 | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
3d8767f9-be0b-5aac-8f8d-8d8d30576afc | checkpoint | 2.1 - Application of Tack Coat
2bc89cc0-05fd-5d39-8173-cf3ac73aea87 | note | FREQUENCY: Prior to commencing paving
984a04d0-36e7-50cd-8190-d10f5be69ef0 | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform ﬁlm over the surface area at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
b126fdc9-f32a-5128-a548-41a431071e21 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.15, AS2150 11
a513f9de-8a20-5afb-8cdb-fe7b7bf868e4 | note | METHOD: Visual Inspection & photo evidence
819b6f4c-677c-5939-bf3e-385c4c9c3ddf | note | RECORD: Signed ITP/Spray Record
085a77d8-e12c-5d16-97d2-38661c7775e2 | note | WP
db648bc6-04a9-5f5c-ac17-0872310e84da | note | RESPONSIBILITY: Project Engineer/Site Supervisor
9524c87e-3988-520f-8b62-836e7879ac95 | date | Date Completed:
d22d01c7-b271-511d-bf41-2fff8ae5a522 | checkpoint | 2.2 - Planned Joints
ba46facf-a072-5cc6-93b1-8ddeca9a627d | note | FREQUENCY: Prior to commencing paving
22cc8efb-d9e3-5cfa-9255-9ae523d70f8a | note | ACCEPTANCE CRITERIA: A site speciﬁc paving plan shall be generated by the contractor prior to asphalt commencement to adhere to the following: Transverse Joints: Oﬀset from layer to layer by at least 2m Longitudinal Joints: Oﬀset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines. Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an oﬀset from layer to layer of not less than 150mm.
ab9a16a0-8110-5e82-9f33-bbb12b923d13 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.17 (b) & (c)
95996cce-9371-5937-9658-016a41201d7a | note | METHOD: Measure and mark out runs and submit Paving Plan to Client if requested
3d58eaf1-61e9-5cc6-b381-2f3448a26604 | note | RECORD: Signed ITP/Job Sheet
00d39b2f-424d-567f-bfa5-6a0decd08391 | note | WP
9ec50226-d017-515d-846c-a3e479e4b999 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
dbb35a21-e66d-5201-a4d2-1dff79c94fad | date | Date Completed:
6661068e-fea7-5cf6-8f24-87de51d674b3 | checkpoint | 2.3 - Commencement of Placing
cca105be-6bd6-5600-ac6f-65bcc11a3079 | note | FREQUENCY: Prior to commencing Paving
683db6f9-07e7-55cd-8bb3-bdaa06b97f49 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub- base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Vicroads Superintendent.
068e27e3-051d-572c-8924-d5b1ea8f3f4a | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.18
b511a1d6-2391-58b3-a195-d66345ed525d | note | METHOD: Visual Inspection
53a5f474-6809-567f-bcda-a795f9214c82 | note | RECORD: Signed ITP
63aeb9c7-da48-5ccd-8879-363cd0e982d5 | note | HP
a51be06b-60e3-5c7c-91e1-0b8ed01b9320 | note | RESPONSIBILITY: SWA Project Engineer
2feae5b8-a61c-5937-9a35-e1a01f92a36d | date | Date Completed:
34e18449-c3fd-51e1-b56f-ccf521a5d073 | signoff | AUTHORITY HOLDPOINT
6011a022-02be-59a2-94b2-a549f045b1b4 | checkpoint | 2.4 - Delivery of Mix
35c6435e-3596-510a-ab77-9fe4f8e7b182 | note | FREQUENCY: Each Load
8dac07ce-4df2-5efe-83be-bf1ba1081dc2 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
9ef15b20-6680-5bdb-9cfb-9fa375011ac0 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.16, Table 407.081
ed145bdc-d3cd-59b4-a60d-32e90a0175ef | note | METHOD: Visual Inspection & Delivery Docket
31350090-570c-5cb2-8a93-d05f68c8ecf7 | note | RECORD: Signed ITP & Production Dockets
01d78e9e-b9b9-5b71-bbd4-212c346d7d27 | note | WP
bec095f5-a796-55ca-b444-42f5b4d59bea | note | RESPONSIBILITY: Project Engineer/Site Supervisor
19cc829a-5c9e-5a21-8524-84978ad9bf59 | date | Date Completed:
df52cdfd-6140-55da-9bdb-919ccff3ef0e | checkpoint | 2.5 - Traceability
82c1addb-3683-5b4c-93c1-01ea48344802 | note | FREQUENCY: Each Load
e1f1bbfe-0d5f-5c7f-83bc-c2f11703b555 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, oﬀset/lane and layer
7b7f2e40-84a3-555e-8ae0-489a7049337d | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
ee9c3476-6420-55a6-9993-a2d1de3442f4 | note | METHOD: Project Engineer/Site Supervisor
23c11b58-21bc-500e-a1c6-850486660080 | note | RECORD: Signed ITP & Traceability
e70ee5c4-d130-52b6-a5d5-7af94576eccc | note | IP
9adf5571-8d0c-5fdf-b3ae-6535c2707fa5 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
44a30b4e-f09a-5f2b-bfae-62dff848ba35 | date | Date Completed:
c2ae29b9-5806-569e-9a2b-c426503dac7f | checkpoint | 2.6 - Layer Thickness and Level Control
ff96ea57-e6b4-5e2f-b266-c33d5fc970c0 | note | FREQUENCY: Regularly during paving
b8b4c9e2-2100-5327-a3a9-c2ab0e694095 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or speciﬁcations
5a70b30b-e11f-5018-bb87-4345416cb836 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20
08d03c8b-a82b-5ccf-8737-a66353e78fcb | note | METHOD: Dips, string line, measurements oﬀ kerb
ad93486a-b761-59b7-8a32-3da121a65202 | note | RECORD: Signed ITP & Traceability
73b78505-8b06-529d-b7e6-0c4856c4aca5 | note | WP
34ac231a-8cb8-5f66-a3c2-d0bf25788dad | note | RESPONSIBILITY: Project Engineer/Site Supervisor
33018af0-6960-5889-8c7c-7c828282672d | date | Date Completed:
36fd9b7a-b6e8-5247-b9fc-beb7b3b74a89 | checkpoint | 2.7 - Paver Stoppages
002feb29-adaf-5658-ae69-f5df46cafaf1 | note | FREQUENCY: If paver stops
3e721a1b-0f43-56cf-805a-523cb54c3fba | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
942ba5fa-42f6-5275-9f04-0f4ea0d094da | note | Asphalt should be ramped down by constructing a temporary wedge of dense graded or cold mixed asphalt. Max ramp grade:
a00ce693-9716-5d75-b53b-2000b9676a84 | note | ○ 40km/h – 20-1
d42553af-6974-50c2-90d8-9801971de2bf | note | ○ 60km/h – 30-1
cac18e2c-74bf-5902-8668-cfd79548b07f | note | ○ 80km/h – 40-1
b5595fd4-381d-5048-8c44-8b281365a04f | note | ○ >80km/h – 50-1
81117fe2-cc8b-5f28-91ac-5bc494815aca | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20 (c)
b2bc6f2f-ff8b-514c-8300-32611bfa4ad0 | note | METHOD: Thermometer
e73f5314-0277-5e7e-b7d9-f0cf640711b4 | note | RECORD: Signed ITP & Traceability
8a42da44-1238-560a-ad9a-d42ac4ae2cb9 | note | WP
1e0101a2-201b-53fd-bb91-8a1a1ca37140 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
8ccf48ab-72e6-5fba-bf7d-c5a8ec70a402 | date | Date Completed:
7b5f6175-7f46-5e8e-9ee6-408a701b92a1 | checkpoint | 2.8 - Surface Finish of Wearing Course
4dfcca4d-6cd9-5059-96c5-7f49ee738a46 | note | FREQUENCY: During paving and after ﬁnal roll
69febd5b-5b7e-5aaa-8709-463fd2426c24 | note | ACCEPTANCE CRITERIA: The ﬁnished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
150e0736-0b04-54a4-8e7a-7931c1c79df7 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (i)
df87ffeb-c1aa-56b5-83c7-41217ac9ccdf | note | METHOD: Visual Inspection
9fea420f-2c0a-5f15-ba5e-3302a9a34645 | note | RECORD: Signed ITP & Traceability
984f1f0d-073b-5547-9c56-1bad2e6177d0 | note | WP
29c20c6b-d274-509f-bafb-d926f20bdb16 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
ad523783-fc01-5bf0-a6ee-655ee901c821 | date | Date Completed:
10f33595-9d77-50f4-8495-2fa4d6875210 | checkpoint | 2.9 - Kerb and Channel
07ca60f3-ee52-57e6-b0dd-5cb66e9cc014 | note | FREQUENCY: During paving and after ﬁnal roll
8645ebc8-f881-5f69-8a08-46d7a3097f08 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either ﬂush with or not more than 5 mm above the lip of the channel unless otherwise speciﬁed
8dd06cfd-fb12-53a9-8ad4-f0e267ff66ff | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (ii)
767fd6b1-2d01-5b59-84fe-65c38d519d41 | note | METHOD: Visual Inspection & Measurement
ccbd261d-642c-5fbb-887f-4c9d8bd42bbb | note | RECORD: Signed ITP & Traceability
d7fce216-ea7a-573d-b611-c9e33c6889d4 | note | WP
accfc560-ed8b-54d2-a681-96c53a9c120b | note | RESPONSIBILITY: Project Engineer/Site Supervisor
8429c875-5a5e-5cce-ae99-b0f6f2a50ad8 | date | Date Completed:
d4973271-760f-5b31-af74-2ebb3b7ab3b1 | checkpoint | 2.10 - Alignment of layers not placed against concrete edge
627dfba2-fac7-556e-9e93-8665eddfa9ab | note | FREQUENCY: During paving and at completion of work
9f42c967-3d8b-50e2-b03a-b701b4fbb12b | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed oﬀset from centreline or design line. The rate of change of oﬀset of the edge of layer shall not be greater than 25mm in 10m
cb25d7fe-dae1-5e4a-946c-f9075c8adc68 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (iv)
93f531db-bdf6-5972-91cb-a8bcc1019e4c | note | METHOD: Alignment as marked by Surveyor and measured
263cd0dd-a3b4-55bc-b476-0f0d7811254b | note | RECORD: Survey Report
7ad599ca-07d1-5ee5-9751-8cf7ecdc9b38 | note | SCP
7db19754-8f98-5056-befa-eb8448c94030 | note | RESPONSIBILITY: Client Surveyor, Project Engineer, Site Supervisor
be21af9a-dbbb-5d73-923b-ce2e4ed1d78b | date | Date Completed:
26d72225-2718-546d-bfad-44cc023633ba | checkpoint | 2.11 - Width of layers not placed against concrete edge
4a9a14be-2086-57b2-9593-b9bf91e5b5b0 | note | FREQUENCY: During paving and at completion of work
b081645d-0eff-5ff6-94da-c8c81aba66a7 | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or speciﬁed width of layer by more than 50mm or greater than the design or speciﬁed width by more than 100mm.
5682dcc8-6286-5be5-9903-fe928cd88306 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
e182e220-7601-562e-bf1d-b783541a2e5a | note | METHOD: Measurement
576e1c36-cb82-5e07-add9-c30db9da78dd | note | RECORD: Survey Report
7e12bf87-ce19-57c7-a3cd-c48f136371db | note | IP
701fd94e-b617-5779-a62e-9088f361468c | note | RESPONSIBILITY: Project Engineer/Site Supervisor
e05f32b5-a38f-5191-b348-2b4e005ae60a | date | Date Completed:
d7d138dc-b209-5f3f-9e52-54a34e093893 | checkpoint | 2.12 - Traﬃcking of Asphalt & Paving of multiple layers
297135e5-ed13-5bf2-b6b3-60822e7847e5 | note | FREQUENCY: During paving and at completion of work
8d32ab87-f6d9-51a3-8e39-5ddb6e23cb82 | note | ACCEPTANCE CRITERIA: Traﬃcking of asphalt or placement of asphalt over freshly laid asphalt layer is not permitted unless the majority of the asphalt has a surface temperature lower than 50°C
d9f9b24e-9138-5594-8bf9-8d9afacda926 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
08f0e70b-8783-508a-a289-8e3212659fc3 | note | METHOD: Measurement or suﬃcient time has lapsed
68f2edb5-423d-58f6-880b-ffe22f7d8951 | note | RECORD: This ITP
1a9d1188-0fef-5f2d-b2ce-39a176b42ce6 | note | IP
7f4e2eb8-984e-5863-aa73-35bf680251cf | note | RESPONSIBILITY: Project Engineer/Site Supervisor
c0ea7700-500e-5ee0-81ff-63d8cd2a82fc | date | Date Completed:
6654a5b9-b49f-507b-92a0-605d8a01ad64 | section | 3 - Testing Requirements
6a8c7900-a2b5-5b4c-a9f2-c7a3c37ec233 | checkpoint | 3.1 - Compaction
3ea01a93-90b8-5aad-ab52-1f0ad5c4630d | note | FREQUENCY: Per Lot (6 shot test)
f36c22c2-771b-518e-9f9f-2e96e8204641 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
df530418-75cf-5498-a9e5-98a12f1077d2 | note | ○ 95.0% or greater Accept lot
a885aa2a-d150-5ded-be97-e54e3a8180ee | note | ○ 94.9% to 93.0% Lot may be accepted at reduced rate
8722fdb1-40ee-5b6c-abb6-5c54ceeb6058 | note | ○ 92.9% or less Remove and replace asphalt
7b0a66d6-9185-5c93-ad10-be01dcf44c4b | note | For layers ≥50mm, if characteristic thickness is:
4c3f1e16-ed84-5603-936e-2256cef26004 | note | ○ 96.0% or greater Accept lot
960a15fd-97c4-5533-bd6b-de6cc1e8d086 | note | ○ 95.0% to 94.0% Lot may be accepted at reduced rate.
1ba6fd39-3ae3-5145-8d5c-44343953e3dd | note | ○ 93.9% or less Remove and replace asphalt
e43ae737-0256-515e-8077-48ee79a67f65 | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.221
85937a4b-7422-55a2-b459-567d8e37a27f | note | METHOD: Compaction Testing
48296b9b-c05b-522a-8bdf-b1b3e3e1d468 | note | RECORD: Asphalt Field Compaction Report
c9314ccd-99a3-56e3-99d9-ad7ee2ee0c09 | note | TP
2f032d04-b346-521b-a1d8-8762ffc48592 | note | RESPONSIBILITY: Fulton Hogan Laboratory Technician Veriﬁed by Project Engineer
ed7eab13-91ea-5ca6-93e8-5c612059edcf | date | Date Completed:
cbc56fa7-00d7-56ad-8ff1-adc73e4f310b | checkpoint | 3.2 - Surface Levels
a3b57793-0945-5ea8-9026-0401d2e010c9 | note | FREQUENCY: Each lot as required
c97caed1-4c69-5de5-813f-f2b9636177e1 | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
56a92c5a-65bf-53fe-9336-974dfc6b8971 | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.222
d96e15c5-222a-5ebb-9cfc-9599336885ad | note | METHOD: Survey
b93cd5ab-2182-52e5-9651-43d28c3e9ba9 | note | RECORD: Signed ITP & Survey Reports
14cf22b7-2397-5b6a-903e-3f50db452276 | note | SCP
fa364c43-4d29-58d2-9f4a-d9e17cc7dac5 | note | RESPONSIBILITY: External Surveyor Project Engineer to verify
d05db9ed-8783-5625-8556-9a307514c7ca | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
17776558-95c5-52a4-b43c-e734ad34c2d6 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
12075917-4f55-5e71-a2da-d7268412a15a | textbox | Print Name:
59b83e06-98fd-57f0-a0b3-0202a69fc95c | textbox | Position:
58008f9d-4619-5f03-a977-6d42d33a406f | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
1da3da15-df67-53b8-8391-08ce244460db | checklist | ITP-008 - Line Marking | itp | ITP-008 - Line Marking
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
5cef2364-fc9a-55b3-897e-5719fb07fa24 | checkpoint | 1.1 - Line marking Conformance
6decc52f-f238-5406-ab45-b16481be0a0b | note | FREQUENCY: Prior to commencing any activity
7c288dfd-04f6-552e-b391-cad67fc8e389 | note | SPECIFICATION REFERENCE: 721.A05
0eed24db-71c4-56d9-8c7a-215ae2ec8619 | note | ACCEPTANCE CRITERIA: Materials to be used conform with speciﬁcation
fa4c2060-243b-501c-8e2f-27a76b3071ef | note | METHOD: Record Review
6433e9d9-b4ff-5fb3-90fa-e39d594a5687 | note | RECORDS: Material sheet
abe5d130-c2eb-59cf-932e-10707b24b6f6 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
a6bb2cbf-0d23-52b0-b090-753f9c10c343 | date | Date Completed:
c5e3f47c-1aa8-52ad-8554-cf927bf34df6 | checkpoint | 1.2 - Site preparation
d18fc51f-9df8-57ee-b89e-384f6558a56e | note | FREQUENCY: Prior to commencing any activity
d66cd9af-99fe-503e-b88f-bec56f029177 | note | SPECIFICATION REFERENCE: 721.A06
c4e4e470-6b2e-5cbb-b3a3-fb2a6752d2b4 | note | ACCEPTANCE CRITERIA: Removal of any existing unsound, obsolete or redundant pavement markings. Removal of any foreign material or debris.
94a82f71-9f08-575c-9f6c-bdbbbe4ed1bd | note | METHOD: Visual and photos
b39132fc-055b-52d3-8708-1e0fd0fa57a5 | note | RECORDS: Photos
c9307376-374c-5ff1-b4c2-6f24de01fc24 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
14672bcf-16ca-5aa0-a5d7-8cfe11bb7f1c | date | Date Completed:
10e8df30-8e3b-5e45-9098-f3d33006ff0a | checkpoint | 1.3 - Set-out of Pavement Markings
7bde258e-74c2-5c81-bf6b-35ad7ddc6081 | note | FREQUENCY: Prior to commencing any activity
de495b17-2a23-56c0-ad33-f7afc9581f62 | note | SPECIFICATION REFERENCE: 721.A09
6e1c40b2-5fcd-51d6-b2b3-7fb4bff75f4c | note | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings
29c9a0d7-fe06-53d9-a7d2-a1303ed045e4 | note | METHOD: Visual and photos
c558960a-0248-57f7-90b1-384e21ba49ad | note | RECORDS: Photos
f1b399a1-dea7-51e6-87f2-19eb06a93111 | note | RESPONSIBILITY: IP - Contractor Representative, HP - SWA Representative
08893043-6dba-527a-9b46-af7ef49a05f5 | date | Date Completed:
42ac8a73-53d5-50a4-af62-d62c56b9c160 | signoff | AUTHORITY HOLDPOINT
4d771e39-83c7-5f41-a79c-a877901269cc | section | 2 - Installation
53d345a3-b074-53be-9960-4c84b68ad956 | checkpoint | 2.1 - Line marking Installation
c216f09e-e64f-5289-90ff-ea17db6088ce | note | FREQUENCY: During Construction
7b41ef96-e45e-5b58-8eba-c45bf7e440a0 | note | SPECIFICATION REFERENCE: 721.E01
1fbb8408-bf5f-5a16-a62c-f142b6eaf5bb | note | ACCEPTANCE CRITERIA: Line marking installed as per IFC Drawings
c7f74a36-d531-5906-8184-1de2656be786 | note | METHOD: Visual and photos
2de447ee-5a6f-56df-822b-09690da6d889 | note | RECORDS: Photos
83888801-2031-57f3-9d6e-cf2df5ddddfa | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
ecf7e8c7-cd15-594e-b258-61d9a4262581 | date | Date Completed:
d7536392-f7f1-5cf6-a9e1-10ecb3aafac4 | checkpoint | 2.2 - Glass bead Install
5455461d-d578-5fef-9098-a807025a435f | note | FREQUENCY: During line marking works
129c5718-be6b-5fc0-91c6-c9e6c29be098 | note | SPECIFICATION REFERENCE: 721.E01
ce56130a-5110-595a-aec7-42c6ca9abcef | note | ACCEPTANCE CRITERIA: Glass beads sprinkled/sprayed on to line marking while in a ﬂuid state to ensure embedment. Glass beads to have uniform distribution.
351b2f21-f74a-5d7f-b7a2-9715036c0f93 | note | METHOD: Visual and photos
e9e028e9-191f-54b7-80e9-a5bf175842e5 | note | RECORDS: Photos
6d897b20-0225-53cb-9378-5dd5cfdc8b15 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
66e6e253-8acf-59ac-ae0d-5e39d27d0b8f | date | Date Completed:
92b4b64a-0442-5ccf-809c-1df2c0c9fc2b | section | 3 - Compliance
2e11042d-a62c-5dff-b90b-fcb515194edd | checkpoint | 3.1 - Completion Inspection
a78cba1d-391d-5576-b565-d7c818c9ae63 | note | FREQUENCY: Upon Construction
eca57be0-f036-5a9c-bdf8-e25656d8747b | note | SPECIFICATION REFERENCE: 721.E01
c016ebed-7ed6-50d5-901b-0940617d2880 | note | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, streats, overlaps, unbeaded areas, tyre marks or other defects.
d3cc0d09-3bbe-5fda-a526-1c56c0b925f3 | note | ○ Edges and cuts-oﬀs shall be neat and sharp, and there shall be no visible run-oﬀ, overspray, dribbles,splash or spiliage on to the surrounding area, or on to parked or passing vehicles
89a29f29-226a-5cf8-a981-41a43db99235 | note | METHOD: Visual and photos
e7353a58-a06a-51aa-8a5e-2b88791f02b0 | note | RECORDS: Photos
2139db14-7aa0-5b72-8de0-a3783d940be8 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
453e1ff4-6428-5952-a42b-9d525c515a66 | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
5d9c743b-b1d0-566a-9dda-72569b99b130 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
2275156b-b27e-564c-83c7-e53642e4cd9e | textbox | Print Name:
6b1dd9bd-aca6-522f-9252-6caa596d6f13 | textbox | Position:
3320fbd0-ce9f-544f-b805-702c0f697824 | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
41b1572e-b2fb-53b0-8c57-7655a1fefb56 | checklist | ITP-009 - Road Signage Checklist | itp | ITP-009 - Road Signage Checklist
1b96c8c3-d3cb-5511-bdc0-8ad038818b89 | checkpoint | Inspection Checklist Items
dc9b7c6f-a3ed-5493-8998-dbc970ea3834 | textbox | Sign Code & Dimensions
a917188f-ab1a-5f77-b82e-144aef0167e9 | textbox | Chainage Location
c5198dd8-98c3-59ae-a1b4-113408481183 | textbox | Number & Post per Assembly
2477ad5e-17d6-5890-b4ad-005a3ffec528 | textbox | Mounting Height (H) (mm) & Spacing b/w post(S) (mm)
98565e99-e225-56ba-bf92-09385b9da396 | textbox | Post Hole Depth (D) (mm)
64db3e30-c50c-5fe8-8663-c497b25407f1 | textbox | Fitting Type and Number of Fitting
dd0678d8-3635-54eb-bb12-b59c577f0e13 | date | Footing and Sign Installation Date
9600558b-1bcf-560a-b940-10cd212b3d9d | note | Photos
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
4c619913-70b2-59b9-8e85-7aa07009facc | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
7c9377e4-e5f8-5220-be1f-c2b39c3c57de | textbox | Print Name:
f6476e10-3a1a-5684-898c-a073d3a3fdf6 | textbox | Position:
bd7fa19e-daa1-5a8b-9ef3-03c4d76e0e2f | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
981e7153-3854-5c45-8bbb-2905670016f0 | checklist | ITP-010 - Guardrail | itp | ITP-010 - Guardrail
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
78f2eb97-4d27-5397-9616-d0974c63c400 | checkpoint | 1.1 - Check for correct documentation
0ec57c45-86f2-5bdc-b58b-a216f96427bf | note | FREQUENCY: Prior to commencing any activity
086cb6b8-35d8-503d-979c-02b0754ff62e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
ab817a45-c92b-5e09-af6c-7c7e05ebd0bf | note | – using the correct and complete set of drawings
0e87b665-1836-5f00-8bd9-0aff94e5fb43 | note | – all drawings are the latest revision..
aa50f204-8caf-51f3-b943-d67d410f8d74 | note | REFERENCE DOCUMENTS: Design Drawings
4a0abe65-ea75-56fc-871d-5432bf3fb90c | note | METHOD: Visual Inspection
251f8e93-1153-5553-8544-9e01118b4ab8 | note | RECORD: Signed ITP
03256eb2-10f7-5eb2-acbc-768daed6ab0d | note | IP
82c51713-01e0-5753-b05a-f8bc425c1a90 | note | RESPONSIBILITY: Project Manager/ Site Supervisor
6dcf91aa-ca4f-5cd5-bded-9751eee20558 | date | Date Completed:
457fc29c-5478-51c3-a60f-061f5ba4ad0d | checkpoint | 1.2 - Implementation of all measures and controls
5afcc918-dc4a-558f-aa76-735dfd2c28bb | note | FREQUENCY: Prior to commencing any activity
663cff31-6696-5aa8-af87-521b6453cf31 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS
6a2336c7-2787-58be-84c1-3df28befa56c | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
c37a8318-8c2d-5a69-8c75-a83252fb4bc3 | note | METHOD: Visual Inspection
f341f913-15fa-54c4-97bd-e055ff085002 | note | RECORD: Signed ITP
5742e225-b980-5fa7-b89e-fd6a8e25bfc2 | note | IP
12c453ab-0f00-53a1-9a99-d7a762d45f9b | note | RESPONSIBILITY: Project Manager/ Site Supervisor
179b0df0-6817-59e8-83a9-f173c1ad472a | date | Date Completed:
73920d7e-e2c5-5db3-bfa8-d36b7058a4c5 | checkpoint | 1.3 - Setting Out
4c70ffe9-0fd7-59db-aade-198edbbb95fa | note | FREQUENCY: Prior to commencing any activity
8dd0c908-2af4-5773-b10c-1cdd07379690 | note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor.
caac9424-8219-5a49-be8c-0b27d7d96fdf | note | ○ Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
f0a37273-72f2-5e02-a92c-218a38f5abef | note | REFERENCE DOCUMENTS: Drawings 708.08
a0b2264e-1557-5811-a657-fa658781abaf | note | METHOD: Document Review
25ba3632-56f1-5b5b-b635-2d5d334c04af | note | RECORD: Signed ITP
f9e669d5-a8fc-5868-88b2-85fd11d2861b | note | IP
5f22be86-56b4-51c7-a4f6-77db6d3b4243 | note | RESPONSIBILITY: Project Manager/ Site Supervisor Superintendent
540fad9a-8918-51a5-bfb3-689327283865 | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
9579dbba-7fbc-5ddf-a026-c6bd5bf26814 | checkpoint | 2.1 - Supply of materials
07311716-27c3-59bc-8c66-34ff2ec8f1e8 | note | FREQUENCY: Each Delivery
41fd03e0-71a3-5cf0-8d71-d65231baead1 | note | ACCEPTANCE CRITERIA: All materials are to be on VicRoads current accepted products list and conform with the detailed design
8e743b2d-c7ea-5d17-8f27-b941961e81bb | note | REFERENCE DOCUMENTS: 708.04, 708.05 Detailed design
65b15744-9046-51d6-9b49-9c0cb11e31e5 | note | METHOD: Visual Inspection
70bdaa8e-43b7-5dea-8b64-f89f86506728 | note | RECORD: Signed ITP
1e7a1bf2-e8a9-5d1c-bb3b-ec9a92bfb1d2 | note | IP
d5b348f3-513f-539d-9466-d8c71722ef26 | note | RESPONSIBILITY: Project Manager/ Site Supervisor
0c0c4c74-906d-528e-b904-8c78909e065c | date | Date Completed:
a11c7727-374c-58fe-ae54-aad72e43d297 | checkpoint | 2.2 - Installation
85a5de76-58b8-5d60-aee8-b55099377790 | note | FREQUENCY: Each lot as required
8db5e8bf-9e53-5d1f-a2c4-2912b045a9c6 | note | ACCEPTANCE CRITERIA: The oﬀset, height and post spacing is to conform with VicRoads speciﬁcations and the detailed design
88f58727-1259-5f70-9b1b-a724f725415a | note | ○ Where the face of guardrail is less that 1m behind back of kerb, the mounting height should be measured from lip of kerb. Otherwise measure from ground level Fasteners are to be snug tightened to AS4100
c5f6a30b-5ebc-515c-b4c2-7a399533416b | note | REFERENCE DOCUMENTS: Detailed design 708.08 SD3661 AS4100
5f83d83c-6406-5083-9409-db6c8a43b72d | note | METHOD: Visual Inspection
fe660ed2-bef8-5c2e-9d8f-c860f088952e | note | RECORD: Signed ITP
b2c24674-080a-5153-8c78-959dfae3b2bb | note | IP
01ba80f2-36ab-5720-b70e-1c3e7a2f224c | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
cd466e90-8a5b-5335-b067-d55ed355d4d9 | date | Date Completed:
1a622dd6-72db-5c53-b748-bd2deb588d9c | checkpoint | 2.3 - End Treatments
51b415f8-bb9e-5625-823b-01f660682781 | note | FREQUENCY: Each lot as required
57c5859d-5b20-5d54-8805-88afb2bad015 | note | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed to VicRoads speciﬁcations
0bbb2739-8a95-53a2-ace1-5e372d6aed4b | note | REFERENCE DOCUMENTS: Detailed design 708.08
6ea32cbc-291c-531d-b0a3-17bcdbd44c54 | note | METHOD: Visual Inspection
370fc108-8336-590c-b227-ef32a7bac163 | note | RECORD: Signed ITP
623b922e-10a0-5aee-bbb3-be120111e4dd | note | IP
edfa7fad-f9b0-59fe-badc-78506f6adf76 | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
c070f63d-cad9-520d-a077-313ac75e4be6 | date | Date Completed:
7d961610-33b0-5075-8b0b-29fcab9d6e50 | checkpoint | 2.4 - Motorcycle rub rail
4d5697fd-9c4c-5f8f-a59d-ac37aa7b95a5 | note | FREQUENCY: Each lot as required
a748f548-eee9-5b61-873c-7ce62cbd9938 | note | ACCEPTANCE CRITERIA: Where speciﬁed, motorcycle rub rail is to be installed on the new length of guardrail
237b6204-7728-5f89-802a-f6314a444077 | note | REFERENCE DOCUMENTS: Detailed design 708.09
7509c32b-e1e2-562b-b3f5-6ad6425f2f4d | note | METHOD: Visual Inspection
e6c525e7-02f8-56aa-83bc-8a3ea15886d5 | note | RECORD: Signed ITP
54c65d0e-d8a3-539d-a84c-45b0a1bc4744 | note | IP
6ac946d1-567f-5d9d-8b3d-0ce869d45aaf | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
29a00349-f5ee-5795-8f98-7a256ef90ccf | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
6ca108b5-1937-510e-89f1-beae553f2df9 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
68028ba3-22e7-5c2e-bfd6-3aaf14cc3eb5 | textbox | Print Name:
d1dbdee0-8b8e-5e3e-80e4-a67262f3bc1a | textbox | Position:
59922202-9206-54e2-84fd-08300ad09ec6 | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
071f267e-65d6-5ec1-ae3e-4fd51de41713 | checklist | ITP-015 - Drainage Checklist | itp | ITP-015 - Drainage Checklist
13f7ffd1-5e39-5df6-8ea1-5ca3fe37ae75 | checkpoint | Pit Details
afd16bda-97e3-5754-8cbb-5ee0a29304bc | textbox | Pit No.
bb7ea087-37fb-5cd4-a859-16092d3bfe5f | textbox | Pit Type
3700b52b-7d10-594f-95f2-b8e9dab30909 | textbox | Dimension
41e518d5-d2c6-5512-b24c-a7bc2898354f | textbox | Inlet Level
2ab54a67-4535-5730-b9c8-a8be2f5c6bb4 | textbox | Outlet Level
c1384ddb-1ec4-550c-bd3c-4778cc89c5c9 | textbox | FSL
290caf0d-9fba-5a85-a0dd-73e9cb030aad | textbox | Pit Depth
f5136021-0cd5-516d-b858-1c4ccd860983 | checkpoint | Checklist Items
ac624d40-08bc-5426-9b5b-c423dd5c0b32 | textbox | Drainage Line Number
daa29e46-8508-5a48-b08d-f361bd3ae10f | textbox | Pipe Size
e4639f21-6947-5345-a311-15e53939e1f9 | textbox | Trench Width (mm)
499ecc76-afc3-516c-88d2-3c7a49542bfe | textbox | Minimum Cover (mm)
d2056b63-946c-5f28-b703-ec88f0006d41 | textbox | Beading Depth (mm)
ffd080c2-bbf6-53a0-9d39-930b9730536f | date | Start Date
515a47c7-7afb-50ee-b28d-2539758af222 | date | Finish Date
5fafde7d-7fad-516a-aec6-4672c04f8451 | checkpoint | Pipe/Pits/End Walls
3cfaf860-9b55-5617-b805-a33a0edf6914 | note | Pipes/Pits/End Wall in sound condition?
d4d0a798-2bbd-5bd2-86b0-698bcc3f625c | date | Start Date
829e1b3b-f075-58d3-bfe4-8c32bdbba046 | date | Finish Date
0eac159f-b12f-5d66-8d10-01cc4f217314 | checkpoint | Laying Direction
870fdf83-eae7-550c-8b8f-51b95043010a | note | The direction of Laying Satisfactory i.e Collar on Upstream?
ff9b4f1b-9a73-5a34-be7c-4fbdaac7d65d | date | Start Date
a56660c3-2851-551b-b087-3dbea48313df | date | Finish Date
66cf5018-577f-5abd-a910-ac97cbd0a061 | checkpoint | Rubber Joint
f90311b1-ba4f-5fec-b632-b87d0bcff459 | note | Rubber Joints in Satisfactory condition?
c4ef5e28-032f-5e32-96aa-dea191a1df86 | date | Start Date
3399d266-167e-5a7e-960e-a90cefa99f68 | date | Finish Date
284d6a6b-59fe-5706-b0ab-0ca0e8f7f5ad | checkpoint | Gap Filling
97d086c1-dac2-5af5-8835-2f81a6f7f8bc | note | All the holes have been mortared to satisfactory condition?
2d35c2c4-4f3d-540a-b840-2305de4e50f9 | date | Start Date
9d077d7d-e1de-5a54-b9ca-c5dc9f487873 | date | Finish Date
1e3d31a3-16a4-5503-92f7-d36c6b0d7d2e | checkpoint | Step Irons
6448d217-65bd-5977-b378-0e887266a884 | note | Step Irons Installed in the Pit greater than 1000mm?
1a6d2c1e-2d63-5ae4-aa0c-ccdb11fc4325 | date | Start Date
4334c58c-5249-5bd2-82b0-431bad66f96a | date | Finish Date
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
4e42773f-3821-5e50-a586-f0f5f566380c | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
6db91f04-ea88-5494-894e-9f5a266a884d | textbox | Print Name:
2d884928-1d04-5d03-b9a2-196391ae2f4d | textbox | Position:
85dc6342-20eb-5e07-af92-556a8c64f6fc | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
8fe6a39f-e81d-5b67-af95-beb08e12de40 | checklist | ITP-045 - General Concrete Paving | itp | ITP-045 - General Concrete Paving
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
78f2eb97-4d27-5397-9616-d0974c63c400 | checkpoint | 1.1 - Check for correct documentation
eee305db-0ad2-5699-b288-4788c2b43125 | note | FREQUENCY: Prior to commencing any activity
c8d7bea0-57cc-583c-9fd9-b621043824cf | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
6b9c67dd-4cb9-5f4b-9744-4e7527ee10ca | note | – using the correct and complete set of drawings
3efe8d84-93fb-583e-bc2b-451f4118c0b7 | note | – all drawings are the latest revision
31b372e6-c70b-5e8e-b17b-8f237045cce6 | note | REFERENCE DOCUMENTS: IFC Drawings
38ee64f2-e227-5668-bfab-9ec0daf653ba | note | METHOD: Visual Inspection
7f692d85-cf72-5493-8c74-aaef275660b4 | note | RECORD: Signed ITP
45436503-1205-5db6-96ee-9a9e0dfc19a0 | note | IHP
fdd44d80-f5cd-5032-bfb5-8f806677d98e | note | RESPONSIBILITY: SWA Project Manager
8f7436cd-24d0-54e5-af47-eaeee43eef71 | date | Date Completed:
457fc29c-5478-51c3-a60f-061f5ba4ad0d | checkpoint | 1.2 - Implementation of all measures and controls
9f91c3b5-48be-5d37-85a0-8256be9ca02d | note | FREQUENCY: Prior to commencing any activity
93c0e39a-a5f8-5024-8170-a9a032969438 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
0d4b03c9-0adb-53ab-befb-105153d6be76 | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
03b7fbd0-c5c4-5500-a36e-404816c634db | note | METHOD: Visual Inspection
0e717617-a77c-522a-8569-c6d075d69eab | note | RECORD: Signed ITP
88dddc8f-70a7-5945-a81b-4cb883b91b85 | note | IHP
2dab62d2-2af2-541a-baa5-45ecddeaafad | note | RESPONSIBILITY: SWA Project Manager
0c45d27c-a007-5bf8-8f0c-28f42159517f | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
8ca7bcd9-51c2-5af5-a939-2cb980971168 | checkpoint | 2.1 - Survey Set-Out
abae3e05-7160-545e-a830-bc34f458e2b8 | note | FREQUENCY: Prior to commencement of excavation.
b4301f2d-b7b3-5195-ad81-984de74540b5 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
02d60dce-893c-51bf-a329-de97b920bb44 | note | REFERENCE DOCUMENTS: Work Procedure
97460939-0a43-504b-87a3-7e7a2c0a03e2 | note | METHOD: Verify
f09ee51f-e536-52c2-9ac9-de3e2305bacb | note | RECORD: Signed ITP
12b8d6be-108e-5097-a66e-99ebd8a9eca4 | note | IP
d8157272-ebae-54db-a99c-80b3065efb5e | note | RESPONSIBILITY: SWA Project Manager
02b04572-69a8-53d1-818b-757e80e6a654 | date | Date Completed:
4fa02bcf-128c-52b5-bef2-2b0ba5d23d06 | checkpoint | 2.2 - Excavation Permit
03252232-fe2e-5a4d-b036-738dad4895a7 | note | FREQUENCY: Each Lot
8af09b81-6abb-5249-a7bb-ab137bc4f8cb | note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
c07e38af-35e2-5e79-b28e-0fc068c3c13e | note | REFERENCE DOCUMENTS: Excavation Permit
4a361387-65a4-5272-b5ec-4388fde85aaf | note | METHOD: Verify
856122d7-7ff0-5172-91bd-85e294e46ccd | note | RECORD: Signed ITP
97cbc96f-7798-5c85-a32b-0160f8864d66 | note | IHP/IP
45a8e1bc-177e-530b-8779-e42edbb64f42 | note | RESPONSIBILITY: SWA Project Manager/SWA SEQ Adviser
ab6dfcee-9cc6-5b21-bec3-6a58e2b39ce4 | date | Date Completed:
77bda8d2-d871-5513-9609-54c06848553d | checkpoint | 2.3 - Formwork
b3b985c0-28db-545c-8d82-3d36a4cfa80e | note | FREQUENCY: Each Lot
9ee77081-b54e-5159-bcb7-ea45c4ac6a7d | note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
b760cfe0-e69e-511f-8e5e-33a77b7c533f | note | REFERENCE DOCUMENTS: AS 3610
89f51154-a6d6-5e74-8575-0ab43c80eb8e | note | METHOD: Site Inspection
84f7f7fe-b106-520f-8f37-4718d9860513 | note | RECORD: Signed ITP
e7d3d7a3-84e2-57cf-8274-2b32d9c52d50 | note | IP
ba5a65f5-ec86-5068-a12f-628344a3522f | note | RESPONSIBILITY: SWA Project Manager
43b7d9d1-2223-565c-8c60-93cfb407a4c2 | date | Date Completed:
0637ccf6-215a-5e75-ab68-744fb1bff0e1 | checkpoint | 2.4 - Reinforcement
d977ed63-365a-5784-8115-9cb77129d6b8 | note | FREQUENCY: Each Lot
9fbdaaf1-a7a8-5a80-a574-d0f94a16fe47 | note | ACCEPTANCE CRITERIA: Steel reinforcement shall comply with the requirements of AS/NZS 4671. Minimum cover of 50mm.
deed33a2-cf34-5341-b812-33d94defdda1 | note | REFERENCE DOCUMENTS: AS/NZS 4671
bb66d9c4-36e8-5292-a3fb-894b1e131ce7 | note | METHOD: Visual Inspection
ab682694-8311-5184-8de8-d53d35473aa8 | note | RECORD: Signed ITP
b7836cc6-a210-5599-aefc-3a2b6b85f24e | note | IP
50cb1299-6081-5559-93fd-20d8e6674e5a | note | RESPONSIBILITY: SWA Project Manager
923e47b5-5730-54a5-aef7-ac426c05fb6c | date | Date Completed:
e20bed31-8e3d-5851-a8a1-9872e4a3742b | checkpoint | 2.5 - Temporary Drainage Provisions
24f4c914-4947-5a8f-8ec7-2ecca6acae77 | note | FREQUENCY: Prior to commencing
3169cfbd-1019-5fc7-a713-0752a938f562 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place. Obtain written approval from relevant waterway authority.
a5994913-35dc-5e73-8d0d-3af76faf0e42 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
fa7ae607-c8e0-51db-8357-442afacae9ea | note | METHOD: Visual Inspection
3952a518-6b38-5987-9d53-9f2618de5399 | note | RECORD: Signed ITP
6a994837-f953-506c-b73a-23444f4627ea | note | IHP
b295128c-a848-5bda-828d-6927061ea0f0 | note | RESPONSIBILITY: SWA Project Manager
247db84d-0562-5b5f-b1c7-aadaf6b5769d | date | Date Completed:
c90b11c3-dfbd-5a48-abf1-a184be14e804 | checkpoint | 2.6 - Bedding
b86142db-7ed2-506c-8022-12f89d4cfec4 | note | FREQUENCY: Each lot as required
19ccc43e-9e69-5614-8486-9250ae584e49 | note | ACCEPTANCE CRITERIA: Crushed rock bedding material as per drawings
f9b52c92-bf19-5eca-a988-d11736b9bb1c | note | ○ Bedding trimmed, moistened, and compacted as necessary
4150a687-4a52-5cb5-9ddf-29e55bdcd3b6 | note | ○ Bedding compacted thickness: Footpaths and other surfacing ≥ 50mm
58cfa338-2c0a-5856-9c01-9fa94cae0523 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.18 IFC Drawings
8a81b5ba-6e5e-562a-b6e7-285e246fd04d | note | METHOD: Site Inspection/ Document Review
fc1ed9dd-34c1-5b3c-abb1-78b58b4fe61c | note | RECORD: Signed ITP
dbd7fe59-b8af-5708-bbd9-5d0d59c7e813 | note | IHP/AP
9424fe40-9803-541f-a6a3-27aa14256388 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
874afa84-ec5a-54d4-8a36-ee27ac2b52a5 | date | Date Completed:
dafeadec-2220-59e3-bbc5-78238f26162c | checkpoint | 2.7 - Concrete Placement
4f7d565d-7f57-5453-b26a-93912bc3bd78 | note | FREQUENCY: Each lot as required
acc00d4e-8e07-599d-a0fd-1db87aff3296 | note | ACCEPTANCE CRITERIA: Concrete strength as per drawing speciﬁcation
a663f449-dcd3-5701-bddf-3ba323dabc69 | note | ○ Comply with requirements of AS1379
665753b3-3f85-5bc6-9053-cd7aab90e78f | note | ○ Aggregates to comply with Table 703.051
1d6965d9-4404-563d-822a-7be694dfb7ac | note | ○ Extrusion machines cement content ≥ 320kg/m3
fad3e71a-cc88-5f5f-acc7-f5b89e5181d0 | note | ○ Surface pitting < 5mm diameter
9858029a-694f-585c-9191-dd273623ecd9 | note | ○ Concrete to be satisfactorily compacted. Proﬁle transitions between 10-20mm per metre.
2d590dc3-87de-56f6-98c5-7ae19cd651e3 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.04(b), VicRoads Std Specs 703.20, VicRoads Std Specs 703.21 IFC Drawings AS 1379
f6bee428-7f17-5475-aa09-5cfc7aad58e6 | note | METHOD: Visual Inspection
c09aa0fe-5e05-5d2e-9d3d-d1463ffac490 | note | RECORD: Signed ITP & Test Reports
d6565033-d887-5731-ad83-91bb7cb2a0b9 | note | IHP/AP/TP
cd559b5b-f877-5455-b216-12021ee4b89e | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representat ive
de0c3ad5-15ba-5d22-acab-0dc1ea949d0e | date | Date Completed:
3c8951bc-fb1d-55dd-9ffd-3a7869dd5df0 | checkpoint | 2.8 - Finish Surfaces
97d1d49e-0650-5d7a-a283-fe6beac811b7 | note | FREQUENCY: Each lot as required
2458e28b-0d1d-55df-bf30-2fd7e5864265 | note | ACCEPTANCE CRITERIA: Footpaths and other Surfacing: Wooden ﬂoat ﬁnish
01554e45-55e2-573e-8714-8a9355e842ad | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.22
e383673f-a8cf-5bbc-8153-de67e5b615ec | note | METHOD: Visual Inspection
a9b975bf-17ce-5878-b1d3-1130035dbc29 | note | RECORD: Signed ITP & Test Reports
d787be7c-1b20-5e06-b37a-a68c9f3e271a | note | IHP/AP
9b3c965a-a117-5631-95d7-940e51cba2e9 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
0d0ba586-677c-5291-8567-6edcec752a21 | date | Date Completed:
f0a3cd2b-c8ba-5f2a-bd8c-0bb6b423c27f | checkpoint | 2.9 - Tolerances
7e1f213e-c927-5e3a-bb54-588ffee96534 | note | FREQUENCY: Each lot as required
0039b4cc-3463-5e3d-9747-203a1732f40b | note | ACCEPTANCE CRITERIA: Match existing surfaces ± 5mm
c6d108b4-31ec-58dd-a1c9-0fdaf1cdb20e | note | Section dimensions:
76921a82-71b7-50fa-87ca-eb95f7c7e047 | note | ○ Within 5mm and 15mm for width; and
2f686c82-3021-5e91-86dc-383081391768 | note | ○ Within ±3mm for dimensions less than 25mm.
823267a9-7e77-531f-b955-7c5996bd3df5 | note | Concrete footpath:
423372ed-8a34-59a6-bb01-bacb34bc7c0a | note | ○ 150mm thick
1ac7b9db-405b-5a4b-9c53-d41690d3f1d5 | note | ○ SL72 reinforcement
2a0eae66-1f89-55b8-89cd-aca1468ee7b6 | note | Concrete Surfacing:
bd278de7-ae77-531c-8e6a-f98576d30908 | note | ○ Type 1 100mm
6a9a005c-a671-5582-88bc-e979a7ad5656 | note | ○ Type 2 150mm
59281743-6354-57b8-9065-4eb789c31dd4 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.13 IFC Drawings
fce9109c-59a6-57b8-a526-a376140eb285 | note | METHOD: Visual Inspection
cfca9fed-4e1f-5b37-ac15-be65df065258 | note | RECORD: Signed ITP
62a919a0-fbce-5427-bb9b-b5a2305a2328 | note | IHP
4f5590ec-c453-5983-b09d-f0a68b59cc58 | note | RESPONSIBILITY: SWA Project Manager
8b537dfe-da43-5a13-906f-d5e10c4d52d7 | date | Date Completed:
91c41ed5-0ba5-5b7e-b34b-7afbac17d4e2 | checkpoint | 2.10 - Joints
c0eda2c0-4fdb-5684-a781-2574ebefbc25 | note | FREQUENCY: Each lot as required
a1d0afd5-e008-5fe7-9428-81a406c1d340 | note | ACCEPTANCE CRITERIA: Footpaths and other surfacing:
00367f8a-f964-588f-ad0e-9aece009add2 | note | ○ Expansion joints at 12.5m regular intervals
c7bb1a40-deab-58bd-a61d-eaff096da0d4 | note | ○ Control joints at 2.5m regular intervals
3b81d342-8743-502f-8d9b-d1fef036eafe | note | ○ 20mm deep and 5mm wide
6890dbdb-92eb-5c26-9d1f-694580d3c34e | note | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
28b948a1-deba-5b69-86f0-ce86f3b2389d | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.23
9dc6f66e-636b-5095-8f59-286d7cd20127 | note | METHOD: Visual Inspection
2c38b942-8492-52a6-861e-c17e97ea07ab | note | RECORD: Signed ITP
242f470e-e1d3-5f64-9745-98a9bb169abc | note | IHP
a8a79afc-d754-595c-a364-ffc1cd16cfb3 | note | RESPONSIBILITY: SWA Project Manager
398720d9-0b29-530a-9002-bd63a7e02063 | date | Date Completed:
dc2a1895-a01d-5fee-9752-491b58cbbe20 | checkpoint | 2.11 - Backﬁlling
f2fea800-ab53-551b-8af7-686702f2bbeb | note | FREQUENCY: Each lot as required
a9e9f3e1-8090-57d3-89ab-f537973b7684 | note | ACCEPTANCE CRITERIA: Topsoil compacted in layers < 150mm
7bff6008-e82e-5e36-923d-bb08df9da072 | note | ○ Width ≥ 300mm behind edging to top of edging
00c16956-63fb-5a9f-95b5-38084361c3e7 | note | ○ Topsoil placed after 3 days of concrete placement
c4bb5253-c4e9-57f6-9cb7-12ababf9993d | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.26
cb708d60-148c-5c77-b55b-8c03917beea2 | note | METHOD: Visual Inspection
a52af329-6691-5041-b433-630a748bddb0 | note | RECORD: Signed ITP
c6d14f8b-b636-5e39-bd6c-45c1d8bcbb50 | note | IHP
eb384a0c-84cf-5b91-acb2-e9ce86be90b0 | note | RESPONSIBILITY: SWA Project Manager
8d7ea636-fc0d-536a-8d62-d1c00989f915 | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
b61cd3df-1245-58d3-98da-582d5d4fb73e | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
ca92968e-fd7d-596f-b881-5c495579f796 | textbox | Print Name:
7536c187-d446-55b3-a24c-2c06c642217f | textbox | Position:
b45b5b7b-c0f3-5fb7-92e9-46c8c6e8a06c | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
03f66bb4-f5f3-461d-b781-a49c242883f1 | checklist | SWA-004 - Sprayed Bituminous Surfacing | itp | SWA-004 - Sprayed Bituminous Surfacing
93fa33f8-7709-4651-a627-7b7c9e2c601b | section | Details
61445f3d-639c-4a8c-8504-0d21de680733 | checkpoint | 1 - Preparation of sealing
cff9242f-fbf8-5414-a073-7c24f2147ca9 | note | SPECS REFERENCE: VR 408.02
d7002269-39bb-5c18-8acb-7d67cb836944 | note | DOCUMENTATION OR ACTION: Constructed to meet specified shape and level requirements Homogeneous and consistent with the material in the pavement base layer
03e69ba4-7cfd-5e10-a787-fc76737e851d | note | ○ Uniform in texture
997ca655-6d14-5f63-ae43-deefda2fe657 | note | ○ Free of tearing and scabbing Free of lamination on or within 75 mm of the finished surface
ee5eb2d6-c6e0-54ac-bd58-9dff98adee76 | note | ○ Level with adjacent sealed areas and edgings at the Joints
07fa5320-f833-52ca-a4d8-56e1d5423a70 | note | ○ A hard dense and tight surface capable of being swept with a rotary road broom or similar
22bec890-726e-545b-869f-9fe06789423a | note | ○ Free of looses and foreign materials
c96b2033-e4df-546e-bac8-fbb7867b0095 | note | ○ Dried back to the moisture content and embedment requirements specified in Clause 310.03
97c6f657-3ea3-5663-a1ba-4581d6e97bba | note | RESPONSIBILITY: Subcontractor
e9f9a715-c5a1-5aa8-b0d9-8eba4fdf9cc0 | date | Date:
53907519-1ab6-4476-9938-2962499da213 | checkpoint | 2 - Preparation Testing
7c634490-6015-538a-a348-f9d2cfe61861 | note | SPECS REFERENCE: VR 408.03
c56e711e-aff9-5a3d-b1ed-07ff2b29065a | note | DOCUMENTATION OR ACTION: Testing Scale B
44652329-ef93-515f-8534-88c1cd58a165 | note | ○ Maximum lot size 4000m2
8644e199-81a1-50c7-ae3b-880e86303553 | note | RESPONSIBILITY: Subcontractor
de0a892a-c892-5f26-b12e-41d9d924a6d9 | date | Date:
65490af4-83a4-4c27-aef5-6be9b8b7fdef | checkpoint | 3 - Commencement of Work
fef1d9b1-725a-5e37-96a4-f394d2fc4cf2 | note | SPECS REFERENCE: VR 408.03
a25ddcf7-7c52-5924-8844-b95750a8813e | note | DOCUMENTATION OR ACTION: HP - Work shall not commence until the contractor and the Superintendent have agreed that the road or pavement surface is fit and ready for surfacing no more than 24 prior to the work occurring.
1d32c36a-8ed9-5339-8a45-3d003584a501 | note | RESPONSIBILITY: HP VR Rep. AP
ff6d0caa-d896-5f33-8d7a-59f94181363d | note | ○ Site Eng
3b6e8706-a439-5fa4-badd-caae6bf1deea | note | ○ Superintendent
7782d94d-6c9f-564b-b7c9-10c4bd99bf72 | date | Date:
839c7d89-ca80-4cb2-bd8f-cef957b74b57 | signoff | AUTHORITY HOLDPOINT
b4a40e44-a39d-43e3-bf76-36129bdc832f | checkpoint | 4 - Limits of Work
e18accc4-2d19-5919-930f-f409a1b99a0e | note | SPECS REFERENCE: VR 408.04
7e243a63-d5e4-5050-aa9d-5db4b0edc39c | note | DOCUMENTATION OR ACTION: Limits of works shall be marked out as per drawing and table 408.161
2cce2553-e5cf-5d81-8814-5f1f40a8ee4f | note | RESPONSIBILITY: Subcontractor
387ae2b0-c89d-51a1-ba02-f295ab0bb789 | date | Date:
563edd87-7324-4f54-9e4f-fb1fa2a3cee5 | checkpoint | 5 - Materials
6db03085-d758-5c99-a3a4-a58934548ce5 | note | SPECS REFERENCE: VR 408.06 & 408.07
891f46eb-3c91-590e-91f2-325a15392390 | note | DOCUMENTATION OR ACTION: Materials to comply with specification, contractor to confirm materials to be used
64781f3f-a6ac-5604-a58a-f9a8ac13d58e | note | RESPONSIBILITY: Subcontractor
df73da13-cfa5-507a-b8d5-f3fd861f0aa5 | date | Date:
45b6c6a6-c68a-4e35-a8f2-c510f0620819 | checkpoint | 6 - Application
8f6b9b7f-0b2f-518a-a972-5bb9dd0cf155 | note | SPECS REFERENCE: VR 408.10
1a7e132d-8708-59b9-b608-c7a77e215fef | note | DOCUMENTATION OR ACTION: Supply Seal design to superintendent for review prior to application of seal and application rate not to be less than 0.1L/m2 for design
5ff11baa-48fd-572f-9990-0ce0ae2ffbad | note | ○ Minimum air and pavement temperature to e not less than 15 degree C
bf3a2abd-ad0f-559e-825e-5708f3e46793 | note | RESPONSIBILITY: HP Subcontractor
222ce37d-b482-598d-85d0-f9d23d9ab337 | note | ○ HP VR Rep. AP
bc32dd88-2348-57d0-ad19-95308a7838d4 | note | ○ Site Eng
57a265c7-a187-54d0-be46-3cef9c455607 | note | ○ Superintendent
e0022086-b80f-58a5-8ea7-c7ffa8f4bf63 | date | Date:
eeca1da1-4600-4fc1-8b3d-9b7029bf1987 | signoff | AUTHORITY HOLDPOINT
da74c6f9-4421-4d05-a8d4-c06a4df50890 | checkpoint | 7 - Removal of Loose Aggregate
79365212-2431-5aa9-af12-628355a4dd65 | note | SPECS REFERENCE: VR 408.11
eb58a75d-62c5-53eb-8e06-84bc5864fc28 | note | DOCUMENTATION OR ACTION: Aggregate to be removed within 48 hours of application.
11ba391d-064e-5d05-98a4-e0d9439ee920 | note | ○ Road to remain appropriately signed until aggregate is removed.
3a0ba5ad-9765-52d3-9646-aab916ec96ac | note | RESPONSIBILITY: Subcontractor
c9ee018a-9160-5029-9b7f-3344f79d7c27 | date | Date:
a7862975-0bb7-4178-9932-8669feafa809 | checkpoint | 8 - Acceptance of Loose Aggregate
6cdcba82-98f3-5cb4-ae57-8152ab7eb73a | note | SPECS REFERENCE: VR 408.12
93dde1d9-04d7-53ff-8580-4edafe0b6426 | note | DOCUMENTATION OR ACTION: ACCEPTANCE OF SEAL
7c66ee3b-9bd8-5e5d-94d1-0561220aee67 | note | ○ Accepted application rate shall not be 0.1L/m2 less than seal design rate
a9496df0-d14a-50ad-8ead-72b15f418dad | note | ○ Surface texture shall be based on visual assessment
97b29395-f65b-5e70-8a52-19d5e89bb215 | note | ○ Aggregate retention shall be based on visual assessment
acc827c7-f818-5b09-98ea-0c3e99ee1942 | note | ○ The seal shall appear visually uniform.
7e93cd0b-3a5f-5386-8179-375e0355db1a | note | RESPONSIBILITY: HP Subcontractor
48645473-3fca-5301-8600-9dbe96a446af | note | ○ HP VR Rep. AP
9a8b9bae-fc69-535f-8f39-29b0afcaba3e | note | ○ Site Eng
fde1ea6d-a8d3-5e63-a71a-21e8ea979b64 | note | ○ Superintendent
a359a989-ace0-54d9-a870-609bb7380fd8 | date | Date:
729f4191-3252-4a0e-bc0b-a5205e8e1d72 | signoff | AUTHORITY HOLDPOINT
4bbbd276-1409-4b7e-8cc3-003929e7fe06 | checkpoint | 9 - Maintenance of Seals (Repairs to Seal)
5c3eae87-5151-5708-9019-90ba14fcbfc7 | note | SPECS REFERENCE: VR 408.14
37ddc42b-f785-56b9-bfed-9e9f3f88e1cd | note | DOCUMENTATION OR ACTION: HP - Superintenden t to approve the proposed treatment to effect the above work before undertaking the work.
55c29598-be38-5343-ae21-2ba328f3f1cf | note | ○ HP - Where the treatment for protection or repair of a seal involves the application of a further seal coat the Superintenden t shall approve prior.
c2b7714b-6c69-5c9b-8e9d-623eb1cbb504 | note | RESPONSIBILITY: HP Subcontractor
6842f207-63a1-52b3-8781-affd1675d053 | note | ○ HP VR Rep. AP
15f70d05-08aa-5d97-9878-9eb73d7d720a | note | ○ Site Eng
92f41fee-4a70-532b-b1ce-dbad34bbdda3 | note | ○ Superintendent
cd1b0a17-c7fd-5944-b209-f82c5d70fd20 | date | Date:
a282a80b-0bb9-4165-a879-c6c00e36851b | signoff | AUTHORITY HOLDPOINT
0f4d7f4a-48ec-4de1-93ed-bba1db217d39 | checkpoint | Final Inspection
00d6ecf3-5858-5420-94a9-5dbf1851a393 | note | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
35eaab8e-8b45-586c-ac1d-4c6fb0f8f6ba | textbox | Print Name:
96576342-c889-57f0-8c40-42beab02b0d3 | textbox | Position:
fe9f077d-c8a5-556a-b72b-6bbacf73c5a4 | date | Date:
e55d43e2-7d63-4b95-acde-9602d72b45bd | signoff | Sign ITP
606be79f-221c-5b48-9dca-bcec2e8b79ed | checklist | SWA-013 - Pre - Construction | itp | SWA-013 - Pre - Construction
b2d83159-08e6-5c9d-a961-c21cb4456f84 | section | 1.0 - Pre-Construction Checklist
4fc3e0ad-f977-54c6-81dd-7b08502bf136 | checkpoint | 1.1 - Communication (1)
6ac75fb9-74e2-5fb2-85a3-84c4b8008c39 | note | ACTIVITY / DESCRIPTION: Community and emergency services
c678d74b-a672-592b-b979-1c99b7f696d5 | date | Date:
bb15b43f-69a0-5735-aba3-d508dc3c1dfc | checkpoint | 1.1 - Communication (2)
e55c5068-9fa4-5a1b-aa0a-6de36cbc5bf4 | note | ACTIVITY / DESCRIPTION: Emergency response plan
bda3f06a-3c3c-5018-af54-e0aff08de424 | date | Date:
b3859a9c-fc33-5200-ba37-62c016e88edb | checkpoint | 1.2 - Approved Construction Documentation (1)
9628d657-61bb-5a84-9ad5-12752bc1064a | note | ACTIVITY / DESCRIPTION: IFC drawings (PDF, hardcopy)
0d71f2f0-26f9-5995-bc5f-ccfbf607e17b | date | Date:
62496475-0e5e-5735-9b2d-ff3d2c818f3e | checkpoint | 1.2 - Approved Construction Documentation (2)
f343ec02-718c-59db-ab3a-25e80837e2df | note | ACTIVITY / DESCRIPTION: Digital (CAD) files (Surveyor)
60cef747-332a-5e37-80d6-c09065e0a958 | date | Date:
3cc842ef-03f0-5ce3-a3cf-d70a2ee247c0 | checkpoint | 1.2 - Approved Construction Documentation (3)
6486ac0a-36f4-5647-8cc9-8c58b9fc2796 | note | ACTIVITY / DESCRIPTION: Budget / Resource arrangement POs (incl. sub-contract agreements)
0951336e-809c-5108-957b-34c50eb0e7de | date | Date:
169fc211-abc1-565b-b02e-2123113df383 | checkpoint | 1.2 - Approved Construction Documentation (4)
a291999a-7702-54be-a784-596df5954215 | note | ACTIVITY / DESCRIPTION: Quantities / Specifications
aee31bd7-4cde-5a8f-a5ba-9514c271b1c7 | date | Date:
0c1abebb-8bd3-52d3-8cde-700416aaa7ad | checkpoint | 1.3 - Dilapidation Report (records and photographs) (1)
03636c61-da3d-5862-9ef7-a0e61d9ba316 | note | EXTERNAL REFERENCE: Hold Point (HP)
79639933-4198-5797-be20-6f279137add8 | note | ACTIVITY / DESCRIPTION: Residential (ie: structures, access/gate, letterbox, fence)
76df2442-44de-52f2-a7ee-9e1b2db476fd | date | Date:
ca372360-d710-5770-88f9-f083b3e9f62f | signoff | AUTHORITY HOLDPOINT
9a6352b0-50e1-5e4b-b6a5-3e7811e4b73a | checkpoint | 1.3 - Dilapidation Report (records and photographs) (2)
6e875f2f-1f6d-54b8-ad88-e8bac65328d1 | note | EXTERNAL REFERENCE: Hold Point (HP)
ad5b0201-e292-57e1-b0be-3814d7cd5e6f | note | ACTIVITY / DESCRIPTION: Business (ie: structures, access/fence/gate, signs/letterbox)
8118ed5e-26cf-5d2f-a5e1-25503267f92e | date | Date:
3a93edef-590b-5176-94a0-397633c9d559 | signoff | AUTHORITY HOLDPOINT
123d6bf2-c8b3-599b-94ec-15e82d53874d | checkpoint | 1.3 - Dilapidation Report (records and photographs) (3)
1825af1f-9911-5784-b310-f67d99f16c75 | note | EXTERNAL REFERENCE: Hold Point (HP)
34872f6b-7c88-59d7-8915-8ea569094049 | note | ACTIVITY / DESCRIPTION: Agricultural (ie: access, livestock, fence/gate)
b9ca6609-db0a-5eaa-9c75-18e375ab6eb3 | date | Date:
2e14c651-fc80-5b4a-bd29-3512017a1157 | signoff | AUTHORITY HOLDPOINT
363f3d0d-5dd8-5649-a38e-a0bddbd4c51f | checkpoint | 1.4 - Heritage / Cultural listed areas: (1)
67ed8b4e-48f9-57f8-a600-390c9bdd29c2 | note | EXTERNAL REFERENCE: Hold Point (HP)
fa5dd48c-18b6-528b-a52f-0ec372b0b2c3 | note | ACTIVITY / DESCRIPTION: "No Go Zone"
255ffa41-0fb6-50b0-be8a-005e04fba535 | date | Date:
733c6df6-42e2-5657-961b-1024edf89599 | signoff | AUTHORITY HOLDPOINT
52d14d69-fa07-5162-a859-1821c1f33c83 | checkpoint | 1.4 - Heritage / Cultural listed areas: (2)
aa5e5762-73d7-5990-869a-eae524283d11 | note | EXTERNAL REFERENCE: Hold Point (HP)
c0716d5a-f08e-5685-94f9-d746f9de8103 | note | ACTIVITY / DESCRIPTION: Tourist attraction
fb3f411a-7165-5bd9-81c8-65d0947b8412 | date | Date:
aee433d7-f9d4-5a4f-902c-18a076f853ea | signoff | AUTHORITY HOLDPOINT
a298a41a-792b-5625-a33c-1452f9cb50bd | checkpoint | 1.5 - Protected Environment (1)
c3537a7b-f353-5fa5-9655-321eb8f210b2 | note | EXTERNAL REFERENCE: Hold Point (HP)
d36c54d2-7b0e-55a0-96df-a1570770f991 | note | ACTIVITY / DESCRIPTION: Flora
63416b39-c036-5c4f-9cdd-9efbf878ddc8 | date | Date:
949e8670-1ad1-5759-9628-d18b3962f15b | signoff | AUTHORITY HOLDPOINT
14b01889-e344-5ade-881d-9527443df828 | checkpoint | 1.5 - Protected Environment (2)
e374ec65-344d-5f55-9163-0363f1fc82c8 | note | EXTERNAL REFERENCE: Hold Point (HP)
6874e82f-7eb2-55a8-a9e5-dca3b0fb7d8d | note | ACTIVITY / DESCRIPTION: Fauna
5628aec3-4ec4-5365-a8b6-d9c417458b93 | date | Date:
a806cca3-0da1-5f3e-9137-e49511e13742 | signoff | AUTHORITY HOLDPOINT
9628fbb0-5e58-51a7-9e83-e306352b1d2e | checkpoint | 1.5 - Protected Environment (3)
ab221c3f-e8c1-5fcc-9705-0d3c8e189157 | note | EXTERNAL REFERENCE: Hold Point (HP)
f016b3a2-6fac-5fc4-8857-7be2cfcc15e3 | note | ACTIVITY / DESCRIPTION: Water bodies
07f39192-f364-5554-8b65-d980b885953a | date | Date:
23d31775-434a-5394-a319-b2592be213ab | signoff | AUTHORITY HOLDPOINT
630240bb-14e8-5749-b2d2-8954a78b695c | checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (1)
e0f4292e-52b6-5e42-a758-b0de3e089e54 | note | ACTIVITY / DESCRIPTION: Dial Before You Dig
1e1eb03f-76ab-5ba0-855e-bcb622315ec9 | date | Date:
f80fb2ce-63a3-5385-8539-29badaf7c2ff | checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (2)
2e00c3ff-cbe8-5c74-af86-841465f410a7 | note | ACTIVITY / DESCRIPTION: Excavation Permit
2aec04a3-0aad-5ac9-b793-83d1ef151c2b | date | Date:
d73a1703-5ab5-59f1-80c1-317204987232 | checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (3)
7533acb9-6cc7-596c-a296-26e31d51c11a | note | ACTIVITY / DESCRIPTION: Assess and arrange for Service location
13f705f3-bf35-53d8-8ca7-e84941343889 | date | Date:
09e8a0bd-1f3d-57f6-803b-0f48aba10250 | section | 2.0 - Pre-Commencement Checklist
09a2b3de-027a-5601-938e-5db460546be8 | checkpoint | 2.1 - Traffic Items (1)
55c62a7f-b4ab-5f3c-8def-280e4c917421 | note | ACTIVITY / DESCRIPTION: VMS boards
6ac3d201-2c28-52a7-a8b2-90c414058ae2 | date | Date:
931e4db6-fa85-551c-872e-381357d7b596 | checkpoint | 2.1 - Traffic Items (2)
5b9dd624-ae8f-581b-8874-6c737a56c425 | note | ACTIVITY / DESCRIPTION: TGS/TMP, MoA
ec18bf29-de58-576d-aabb-a088bed6a4ad | date | Date:
3e705a2f-43de-56c5-aae9-2a8b1cd1a773 | checkpoint | 2.2 - Site marks / references (1)
502435bf-bca4-55cb-b6da-3dd2a6dd1dcf | note | ACTIVITY / DESCRIPTION: Limit of Works
1705a55f-e283-55eb-a225-cf0b20ff39c8 | date | Date:
bf5a2eb1-6f6d-5986-969f-ed0f8c70bb23 | checkpoint | 2.2 - Site marks / references (2)
ce62becc-d90c-520d-97b2-d9ebc15c1536 | note | ACTIVITY / DESCRIPTION: Survey control point
1477e2f0-75ce-520a-97a9-db697eb6aa70 | date | Date:
7819aa13-83a6-56e0-82dc-67161b9a9b76 | checkpoint | 2.3 - Services, inspect/identify clash points: (1)
1de60d9c-e7ab-5885-a3f6-0366865fff98 | note | ACTIVITY / DESCRIPTION: Sewer, Water
f335f453-2ac9-58b4-b6b4-18bc46f26df7 | date | Date:
7296f66a-8e76-5871-9283-a9a21e7e8d25 | checkpoint | 2.3 - Services, inspect/identify clash points: (2)
c6d0efd6-f8c1-556b-9d3d-ae7f2b631821 | note | ACTIVITY / DESCRIPTION: Gas, Electricity
102be5f6-8768-518c-93a3-a2c773473a8f | date | Date:
9a0fcc69-3668-5c15-a6ca-91ededf6fc07 | checkpoint | 2.3 - Services, inspect/identify clash points: (3)
75076475-3b85-5121-ac0c-03db0e1eef54 | note | ACTIVITY / DESCRIPTION: Telecommunication
14f8a3e3-f9ec-5544-b28d-605ec91d8327 | date | Date:
a24228fa-78b8-5c90-88b4-ffc9700be614 | checkpoint | 2.3 - Services, inspect/identify clash points: (4)
5f3060bb-3bb1-5591-b921-d4f59a6a92a6 | note | ACTIVITY / DESCRIPTION: Drainage (ie: council/shire, Other state authority)
de24c3b0-6b49-5f90-8428-2c576569d3e0 | date | Date:
b48da278-70f9-5760-8050-ae93342082fa | checkpoint | 2.3 - Services, inspect/identify clash points: (5)
5cd070f3-4bc2-5d15-82ac-70e37c344a84 | textbox | ACTIVITY / DESCRIPTION: Other specify:
50d772c2-4165-5d56-8320-9c86a7d20b54 | date | Date:
9f5df32c-0781-554e-ab01-a593e7fcb3b0 | checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (1)
74683223-37ac-5f0b-9dc8-c59bbbb49457 | textbox | ACTIVITY / DESCRIPTION: O/H and U/G services flagged "No Go Zone"
082b5cea-cbd9-5d32-b47a-12a91485a800 | date | Date:
e3efc0a8-16a5-5596-84a1-1e66adf6bd04 | checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (2)
2d9b5ac8-2932-551d-afe9-cce406feb1b8 | textbox | ACTIVITY / DESCRIPTION: Trees(s) marked and approved for trimming or removal
6ddf181a-e8b1-5fc9-ab3d-1f6b4ab98b3e | date | Date:
68a4a80a-b84c-5ad0-bb9b-33814848d601 | checkpoint | 2.5 - SWMSs reviewed: (1)
91edcc50-d584-52ff-9a80-5cf97676facd | textbox | ACTIVITY / DESCRIPTION: Site-specific
f484d58c-c0a0-5b74-9e0c-44d3b5f26fef | date | Date:
14fc9cb2-1963-5087-af52-96411e05c1d0 | checkpoint | 2.5 - SWMSs reviewed: (2)
b108d9a3-d755-5fe7-a3ce-9b4c144ed150 | textbox | ACTIVITY / DESCRIPTION: Spotter required / arranged
241f3d92-8abd-5760-a197-07485a7903e6 | date | Date:
4bbdbbcd-53e6-582b-9ebf-412a8a2c384b | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (1)
000ad7b0-a0b3-5691-adc5-5fdb50559397 | textbox | ACTIVITY / DESCRIPTION: Sight and Clearance Distances:
49c34f83-a82c-5d2d-99ae-76a827d686e7 | date | Date:
4fb3fe3d-2615-531c-894d-134d05fa9e44 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (2)
845fa20d-5809-53bd-a769-4e8cf144dca5 | textbox | ACTIVITY / DESCRIPTION: Stop-slow areas, spotter, slips, confined space/work at height
8d29808c-5f6e-5d17-ab5d-12701fcc7f8a | date | Date:
07c218e2-d218-5982-b0c6-77b42e57d30e | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (3)
da8e0f5e-1206-53be-ae77-1b48e2a2c06f | textbox | ACTIVITY / DESCRIPTION: Vehicle access to properties
42516fb7-f459-51b6-a80b-3d181e45b9cf | date | Date:
5f33f279-b1ef-5404-a4c7-074c9bcea778 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (4)
5e983dd6-62b6-5c14-abdf-4a9d516d310a | textbox | ACTIVITY / DESCRIPTION: Proximity to Services: clearance requirements
78bb6672-239a-5d14-9e90-b6fff32dfc28 | date | Date:
81b2c664-740d-5448-bd1a-fdae47df441c | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (5)
e5327478-ff3b-525b-9d22-e123465c38a6 | textbox | ACTIVITY / DESCRIPTION: Proximity to Water: supply point, watertable/dam/river/coast/port
73da7c40-9c91-5b8e-8574-8dfb3ce76381 | date | Date:
abb4d79d-c3ff-5250-bffc-b4ead813a58b | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (6)
9b5ae601-5c84-5742-862a-02d344119001 | textbox | ACTIVITY / DESCRIPTION: Site compound/Plant parking, material stockpile area, "dumpsite"
de3f3c7e-21fa-52b6-8b20-c9dea9d405fa | date | Date:
d7be73a1-96ee-543f-9d6a-da9f3eb56961 | section | 3.0 - Construction
04c6e6f5-8a7c-53ba-8fb8-508a095038bb | checkpoint | 3.1 - Vegetation Removal (1)
c4f91f9b-460b-5bf7-9724-1d68269b5fd8 | note | EXTERNAL REFERENCE: Hold Point (HP)
9a06f88c-d3ba-509b-94eb-73443c6aa6a3 | note | ACTIVITY / DESCRIPTION: Spotter, Traffic Control
24caba61-85bc-5159-b0ec-72a77a683fad | date | Date:
91426355-0c6c-5b3d-8fc1-c9d9c1668208 | signoff | AUTHORITY HOLDPOINT
a473aca8-8c79-5fdf-b4fe-14896a29f1ac | checkpoint | 3.1 - Vegetation Removal (2)
2440ce69-0b95-549f-bf60-60b1909778d8 | note | EXTERNAL REFERENCE: Hold Point (HP)
87e8fdf3-58d0-5c59-bdc3-c912e2382397 | note | ACTIVITY / DESCRIPTION: Equipment, Access
9b81ac8f-b070-5323-9dca-acfbdb427325 | date | Date:
eb97adb4-1c8a-5365-8fd4-42fdba865a40 | signoff | AUTHORITY HOLDPOINT
56872da4-6472-5b90-9b0f-7b3c2c13ff4a | checkpoint | 3.1 - Vegetation Removal (3)
ccf59e41-4ab4-5852-a208-c13193b332ce | note | EXTERNAL REFERENCE: Hold Point (HP)
d042cc4b-aab0-544a-85f7-80f1ce6852a5 | note | ACTIVITY / DESCRIPTION: Soil erosion / water contamination
c63da54d-4452-5d56-aa26-80f408262e25 | date | Date:
5d04e02c-f31d-5f78-8848-826fc6d3d926 | signoff | AUTHORITY HOLDPOINT
d175339a-b6c9-5d40-82f7-b0bd4fa0651d | checkpoint | 3.2 - Contaminated Materials
f1271195-0f83-5568-b48c-aea50c41dd87 | note | ACTIVITY / DESCRIPTION: Contaminated Materials
ffafd4b5-54da-5bfe-801d-00e309038cf1 | date | Date:
4905149c-6cd5-553c-aa53-f8dd9f9209f8 | checkpoint | 3.3 - Traffic Items (1)
d3430d21-a698-50e9-8359-dc7188cd9a6e | note | EXTERNAL REFERENCE: Hold Point (HP)
52a94787-19b2-56c7-bb15-816a2990cbb0 | note | ACTIVITY / DESCRIPTION: External review: Road Safety Audit
70f42a74-ee1e-5d54-b8b0-1cde5b68b86f | date | Date:
857609ba-bcdd-52e5-9966-247a1e7ab2bd | signoff | AUTHORITY HOLDPOINT
4353c527-d5de-5bc4-8839-7a2a00fb9a79 | checkpoint | 3.3 - Traffic Items (2)
ec7ce81c-2ad7-50f3-9cbc-9f01a126af9d | note | EXTERNAL REFERENCE: Hold Point (HP)
580d0e38-7fdd-5696-a5d5-495e0cc60140 | note | ACTIVITY / DESCRIPTION: Internal review: adjust hold-time (traffic lights / traffic controller), flowbias, identify peak-hour period(s) / public transport / rubbish collection
c346f444-f86f-59e7-8e38-9f9909100dbd | date | Date:
18c5c9bc-dbb1-50b3-b62a-b4a9a6c31ec6 | signoff | AUTHORITY HOLDPOINT
023cd8e3-0a57-5f46-ab79-677a60bbcaea | checkpoint | 3.4 - Trenching works (1)
941db789-7b82-594b-bb6b-fcef0d6edb67 | note | ACTIVITY / DESCRIPTION: Review escape plan (routes)
6d62af35-d0f5-5ef6-b239-b452fd3decb6 | date | Date:
61f48a8a-fa99-5641-bbfe-b6f60ea0f347 | checkpoint | 3.4 - Trenching works (2)
b4ecbe1d-c4f4-56b2-aeff-6efdc65fdd2b | note | ACTIVITY / DESCRIPTION: Review ground / water conditions
619cc4c2-86a0-5d57-897a-31c5d6c53318 | date | Date:
50b067dd-e199-593f-948b-da80c5a99b37 | checkpoint | 3.4 - Trenching works (3)
540cea3b-7a41-5fa6-9f28-8540567fd217 | note | ACTIVITY / DESCRIPTION: Indentify Shoring / Benching requirements
12f019cc-0473-5500-a16e-4c48b4fd9135 | date | Date:
6e76b710-f980-5558-8431-29ac043efdf9 | checkpoint | 3.5 - Drainage Works (1)
206c1000-b617-500b-9644-e5b5617da94c | note | ACTIVITY / DESCRIPTION: Assess surface-water impact – flow-path / catchment / outlet
70024a33-18da-5be1-9e03-818c3b557391 | date | Date:
29c04c64-77ba-5d73-8906-4be090479ace | checkpoint | 3.5 - Drainage Works (2)
d8430f2c-7145-59d6-b01b-4d49402c154c | note | ACTIVITY / DESCRIPTION: Surface drainage (swale drain)
1e06ce8b-b227-5e32-b27a-c39c24c7bb90 | date | Date:
167a25d9-c42d-5c43-97ff-75a7dd8e647d | checkpoint | 3.5 - Drainage Works (3)
4cce8002-4d20-5487-8f39-429bf484f752 | note | ACTIVITY / DESCRIPTION: Sub-surface drain pipe and aggregate (agricultural drains / "agi pipe")
33acb2dc-5580-585c-86fc-a0d62281f5ab | date | Date:
0fbcb240-f41b-5f68-8c33-171bac159531 | checkpoint | 3.5 - Drainage Works (4)
ea0ce010-f16e-5655-b25a-79d53b30ded2 | note | ACTIVITY / DESCRIPTION: Review confined space entry
f6040a37-cd0a-5d2b-b12f-5777b19c46ac | date | Date:
3726bf23-5745-5680-8666-551d87ab6950 | checkpoint | 3.5 - Drainage Works (5)
055373e2-fcd2-5867-bae6-c62a3c9a7c4e | note | ACTIVITY / DESCRIPTION: Review lifting methods (load / equipment / plant / crane)
f396fea9-8948-5986-a2e1-3320dc2bbc80 | date | Date:
cfbebd2d-684d-51d0-9413-db270416aa3f | checkpoint | 3.5 - Drainage Works (6)
e5e82d46-11a8-5768-bb45-772759095f7e | note | ACTIVITY / DESCRIPTION: Levels
00326889-24e1-507e-9670-084aaf6e1b9c | date | Date:
7a26beac-4d87-59a2-a1e4-9fa8e1ed4230 | checkpoint | 3.5 - Drainage Works (7)
4398c1aa-7394-5b74-b0bf-a13b96671e33 | note | ACTIVITY / DESCRIPTION: Pit covers / Grates
e659082f-e4d6-5e1d-a61b-b6414277833e | date | Date:
9d8eb224-efef-5f72-bfe3-0050bdec094e | checkpoint | 3.6 - Structural Items (1)
3b525321-4f28-5639-add6-31ec82bc5df6 | note | EXTERNAL REFERENCE: Hold Point (HP)
be017c29-8f47-5668-bdae-a8405425460c | note | ACTIVITY / DESCRIPTION: Crown units / culvert
395b34ca-3ed7-5d85-be46-515ca8a56d07 | date | Date:
103f0129-b32e-57c2-af8b-a3f7add75fec | signoff | AUTHORITY HOLDPOINT
18eff7e7-e534-53e5-b1b2-f8c8a887abee | checkpoint | 3.6 - Structural Items (2)
caeee054-0a9f-552c-80b4-84f23d4ffd26 | note | EXTERNAL REFERENCE: Hold Point (HP)
43028459-d569-558f-948f-38217645075c | note | ACTIVITY / DESCRIPTION: Retaining structure works
807220dc-dd15-50c5-a8fc-c003c6fae476 | date | Date:
981296d4-9984-5161-a3ec-e5b6a05eedaa | signoff | AUTHORITY HOLDPOINT
a3537f1a-55ea-5962-bff5-bd495d5b3602 | checkpoint | 3.6 - Structural Items (3)
0df10fa0-c833-55e1-9193-0d7a4569cbd7 | note | EXTERNAL REFERENCE: Hold Point (HP)
303a4d60-fb15-5276-81ad-fab2e818ecb3 | note | ACTIVITY / DESCRIPTION: Bridge works
a8c8c7d3-a0f9-557d-86f0-ec9e894e650e | date | Date:
35993f22-ecb4-5eab-a0ae-5e4ce3edbe9f | signoff | AUTHORITY HOLDPOINT
4a190e24-251a-540e-82fd-c505ec372a23 | checkpoint | 3.7 - Concrete kerb works: (1)
85ba550e-6b28-5857-bc5e-ccbab8a99472 | note | ACTIVITY / DESCRIPTION: Alignment / level
ad6260d7-5ed9-59c9-acbc-d5ce0a530454 | date | Date:
afca6eb2-42e9-5871-a25d-9b2186c4710a | checkpoint | 3.7 - Concrete kerb works: (2)
196e60b1-5cf7-5548-a2a2-2f21dce71563 | note | ACTIVITY / DESCRIPTION: profile / finish
81cc87f6-e6c0-5e62-bc6d-46af70cb2f8e | date | Date:
7e73f34b-3b8d-56ba-85f1-8b0acbff2d39 | checkpoint | 3.8 - Concrete Works (1)
401cdf12-25f0-5fd8-9ee9-30975c3b2303 | note | EXTERNAL REFERENCE: Hold Point (HP)
12a4338e-180e-5542-ae61-a968ebe17b5a | note | ACTIVITY / DESCRIPTION:
30e9d4f6-b44a-5cd4-9e38-c9188dca2b01 | date | Date:
c47414f3-fa1c-50a3-8a33-3606072f8375 | signoff | AUTHORITY HOLDPOINT
02765cad-de6e-46a3-9a1b-e3f0c5053b0d | checkpoint | 3.8 - Concrete Works (1)
50a1f3c8-852d-5f7d-a90f-bbe760fbedbf | note | EXTERNAL REFERENCE: Hold Point (HP)
b8b5e787-b8a9-522f-bc42-7971fc89dbbd | note | ACTIVITY / DESCRIPTION: (in-situ & pre-cast) - Bedding material / blinding material
c90c15f0-ebc6-556f-a851-79e244f671c9 | date | Date:
9c56dcf1-b717-5818-a50f-ccce242b4a1c | signoff | AUTHORITY HOLDPOINT
0c625859-86f9-5ab1-8026-930a4904a79f | checkpoint | 3.8 - Concrete Works (2)
3d269fdf-cde3-5045-b197-b495c7bf1264 | note | EXTERNAL REFERENCE: Hold Point (HP)
1f8d3ea8-ab2f-5a5a-8252-be864ae88514 | note | ACTIVITY / DESCRIPTION: (in-situ) - Formwork, duct-work
8f5b6cbd-ad5a-5282-b1f1-8450ee22c61c | date | Date:
2371a583-9885-5764-b61b-e0237cf48e85 | signoff | AUTHORITY HOLDPOINT
6ef3bea8-ad11-53ff-87b1-4cead0bd366b | checkpoint | 3.8 - Concrete Works (3)
f8c6660a-0b26-5d62-98ea-ddc73be56ed4 | note | EXTERNAL REFERENCE: Hold Point (HP)
e1f3c380-ce16-557f-9480-15d08544bce7 | note | ACTIVITY / DESCRIPTION: (pre-cast) Alignment/dimensions
f7e3ff3c-d599-5193-8553-3425282b40b2 | date | Date:
993f861b-8184-575d-a544-05aa52939e09 | signoff | AUTHORITY HOLDPOINT
c1dbc150-73c9-5965-80c0-2f873810e14c | checkpoint | 3.8 - Concrete Works (4)
538b3710-fbf1-576a-9efb-9cda272d4314 | note | EXTERNAL REFERENCE: Hold Point (HP)
14e24089-3285-5a04-be40-c2f11bbf4886 | note | ACTIVITY / DESCRIPTION: (in-situ) - Rebar layout
b1c808e3-525b-5745-880b-ed644c29343e | date | Date:
e6bfc1c5-771c-5a8e-9052-3af4acdb8bc2 | signoff | AUTHORITY HOLDPOINT
942dfb61-1ce6-5e95-8cfc-77270dad5ca4 | checkpoint | 3.8 - Concrete Works (5)
4362a75c-8d17-58f2-a2b9-37e835138dc9 | note | EXTERNAL REFERENCE: Hold Point (HP)
517c09cb-52a7-55c1-af1d-c19b4061c574 | note | ACTIVITY / DESCRIPTION: (in-situ) - Concrete mix / Compaction / Placement method(s)
ba98caf0-cd34-5675-a817-86ab1e308f91 | date | Date:
311b0aa1-f9bc-5a84-a199-e568fd5128ba | signoff | AUTHORITY HOLDPOINT
01d97373-6e1a-5d6e-a4f2-840588cfd4c7 | checkpoint | 3.8 - Concrete Works (6)
bab3caaf-3e29-5150-9f97-102d3d7e3f11 | note | EXTERNAL REFERENCE: Hold Point (HP)
b0f820c0-a955-5788-bfbb-884b9b202c56 | note | ACTIVITY / DESCRIPTION: (pre-cast) - Lift points / placement method
2088c290-f00d-5619-969f-6f3235b7382d | date | Date:
9d766382-17f8-52ba-9eee-e55f692560e3 | signoff | AUTHORITY HOLDPOINT
7d7720d5-504d-5ab0-b356-0cd8ce894f2c | checkpoint | 3.8 - Concrete Works (7)
dfe49555-ae54-5b30-b62e-f56301f61a2c | note | EXTERNAL REFERENCE: Hold Point (HP)
d03928cd-fe9d-5ac9-b157-dcd34632c6ea | note | ACTIVITY / DESCRIPTION: (in-situ & precast) - Pre-stress works (where applicable)
ed14191b-2a26-5984-b326-bb45015ed9c3 | date | Date:
51f5e363-c5b1-50af-a638-b352658a5b58 | signoff | AUTHORITY HOLDPOINT
bedaf76c-4d8b-5d5e-8d2f-fa65048a13a4 | checkpoint | 3.8 - Concrete Works (8)
8884b095-83d5-5ce6-8d8d-80eaf4306d63 | note | EXTERNAL REFERENCE: Hold Point (HP)
17cf4daa-0a6f-5fb4-9b7c-5f129acf634d | note | ACTIVITY / DESCRIPTION: (in-situ & precast) Finish
6e271065-4fde-52f2-8ee8-97b76b48f1f6 | date | Date:
354cc997-dc12-595c-9a05-016bebf4b960 | signoff | AUTHORITY HOLDPOINT
93698472-379c-5500-a64d-b7a3cb16f38e | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (1)
e73589a9-ec36-54cd-9029-5ee29ce1deec | note | EXTERNAL REFERENCE: Hold Point (HP)
1b3a26cc-7010-5158-ab72-bbdbee1bd096 | note | ACTIVITY / DESCRIPTION: Require in-situ testing / laboratory report (where required)
75b4e119-6301-5b94-b8ce-839b4666ce1f | date | Date:
6bc4eedf-e450-520b-bfaf-d5317605fe58 | signoff | AUTHORITY HOLDPOINT
dcb10286-482f-510a-982d-dfd99d52eddb | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (2)
8b2306d3-92b6-5476-83a2-281a1b1190f1 | note | EXTERNAL REFERENCE: Hold Point (HP)
e70bb6c6-d7ea-5908-a5dd-e5a62cd09130 | note | ACTIVITY / DESCRIPTION: Material dockets (ie: Lime / Cement)
f937da68-feb6-5804-b46e-17e5c22c049a | date | Date:
12e36667-97e2-5e02-aefe-014aab282531 | signoff | AUTHORITY HOLDPOINT
53406d98-ee22-59ae-8672-fac588b98ff4 | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (3)
90496a06-77d2-58e8-a89d-fb4b7d1f7ecf | note | EXTERNAL REFERENCE: Hold Point (HP)
6bce577a-706e-5a14-aafe-da3385ac4755 | note | ACTIVITY / DESCRIPTION: Density results
c1445df0-8e52-5f7f-96e1-74811d8d9e30 | date | Date:
8b042285-4fe9-5d5a-b6ad-5abf9e9e0d5a | signoff | AUTHORITY HOLDPOINT
5a27f415-647a-5b80-8931-502afee8cc56 | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (4)
e51627c3-a02b-5a2c-867d-795095cde3c8 | note | EXTERNAL REFERENCE: Hold Point (HP)
fd110d90-715a-5e18-9914-c7a94602cd50 | note | ACTIVITY / DESCRIPTION: Proof-roll
f3628880-a322-519a-a4fb-4d030a922d59 | date | Date:
5a9332b9-2fb9-5487-9b70-34c59a2f3316 | signoff | AUTHORITY HOLDPOINT
aae52039-2989-5bd7-9b81-6683ad24c2ea | checkpoint | 3.10 - Pavement Works (1)
b0e21f3b-781c-567f-9184-cedcd7dba172 | note | EXTERNAL REFERENCE: Hold Point (HP)
5b32bd42-1cfa-5ce5-b6d4-e6b7b8432557 | note | ACTIVITY / DESCRIPTION: Density results
981e0eb1-3b86-5839-a78d-f4ca87dddfb8 | date | Date:
3ca88ab2-46fa-5c97-8abb-c033f56603d6 | signoff | AUTHORITY HOLDPOINT
1ac8e438-da3c-51af-a12d-c6c12c6d4be1 | checkpoint | 3.10 - Pavement Works (2)
de3488c1-cb69-51df-9b46-9083c7620eb3 | note | EXTERNAL REFERENCE: Hold Point (HP)
4460a507-b9c6-5ecf-94c7-151aeee07db0 | note | ACTIVITY / DESCRIPTION: Proof-roll / Test Rolling
13da7516-ddc1-5ea8-864c-3925ea208098 | date | Date:
842111af-844a-5ca6-b2df-690c4ede6adf | signoff | AUTHORITY HOLDPOINT
5b55a4f2-7c30-57f3-928c-f1d66d85f6ee | checkpoint | 3.10 - Pavement Works (3)
7f373744-f16a-59ab-8365-8d1b2626e0d1 | note | EXTERNAL REFERENCE: Hold Point (HP)
ebf648f9-2a90-524a-9a17-27d3e7fcc4ed | note | ACTIVITY / DESCRIPTION: Dryback results (NB: required prior to sealing works)
447c7ffb-ccd8-547d-8638-4bf69813c694 | date | Date:
19b8ffce-c57c-5d26-8996-ccd499fa3e7d | signoff | AUTHORITY HOLDPOINT
0c75ec88-90e7-5b67-91ca-be734b9d492e | checkpoint | 3.10 - Pavement Works (4)
3fef4dd5-2ef3-59f8-927a-73fce94b43d5 | note | EXTERNAL REFERENCE: Hold Point (HP)
cf83917c-4162-5eb0-8ed4-456ddbf42093 | note | ACTIVITY / DESCRIPTION: Ball Penetration Test
7f10fe4e-729a-547e-a479-92f014ea1436 | date | Date:
7bf6d8fa-9777-541d-8864-153db73b402b | signoff | AUTHORITY HOLDPOINT
3518b0fc-b416-527c-82c1-27c1de20e1e9 | checkpoint | 3.11 - Utility Services, Traffic / Public lights (1)
d038a06b-3e2a-5e9c-bf71-de2b832e1b7f | note | ACTIVITY / DESCRIPTION: Level & Location (ie: clearance requirement)
43daad50-b548-5b48-a1ad-7365ecc21eef | date | Date:
735aab93-d698-5845-afa5-724bacfe6674 | checkpoint | 3.11 - Utility Services, Traffic / Public lights (2)
575b00ff-78d5-57f8-a161-2d17d6d112c3 | note | ACTIVITY / DESCRIPTION: Approved equipment for installation
765441c7-7694-5c75-a283-4c365041838c | date | Date:
42559c48-cc6d-5a80-9fd0-9a5d9976d007 | checkpoint | 3.11 - Utility Services, Traffic / Public lights (3)
a46320d2-7f1e-5097-a48d-6447073a73da | note | ACTIVITY / DESCRIPTION: Pit and conduit (ie: clearance requirement)
561ad1d9-de3b-57fe-9f7f-e9a880990643 | date | Date:
279cfb92-5524-5ca3-9b73-71d938404b24 | checkpoint | 3.11 - Utility Services, Traffic / Public lights (4)
25963336-1eba-572e-b0e9-e5b299512e7c | note | ACTIVITY / DESCRIPTION: Audits by relevant authority / hand-over procedure
3e25cae7-33e3-5629-9827-724e49802f46 | date | Date:
22d5166f-e1df-58fd-992e-efada75e8532 | checkpoint | 3.12 - Pavement Surface Works (1)
b6eaf2b8-9418-57ed-b6c3-2eacb3f58fb4 | note | EXTERNAL REFERENCE: Hold Point (HP)
0ab970b0-5923-5246-afca-a41d27053472 | note | ACTIVITY / DESCRIPTION: Seal (ie: suitable material, spray-sheet details)
b377244e-049f-565e-b5ab-9b6c17b108f6 | date | Date:
bdd95225-7f71-5084-a039-d89b440aac6c | signoff | AUTHORITY HOLDPOINT
951b0751-eecd-5a60-8068-307cf2f4f0ed | checkpoint | 3.12 - Pavement Surface Works (2)
b846e4a9-d9b0-5d0f-8d23-23db84ef0d0c | note | EXTERNAL REFERENCE: Hold Point (HP)
9bf5d3da-5e55-5f80-8075-102e2cd4bdbd | note | ACTIVITY / DESCRIPTION: Asphalt (ie: material dockets)
96810742-a4c1-5113-a84e-f2d7a6584165 | date | Date:
e89a9cc3-79c2-5186-8847-3e0b1bbc5103 | signoff | AUTHORITY HOLDPOINT
97379716-9c47-5d54-812d-47cf5b06c392 | checkpoint | 3.13 - Landscape (1)
398e27fa-a911-566f-a856-c1ead55abbe6 | note | ACTIVITY / DESCRIPTION: Seed / Grass
2afa04d7-980a-5c03-b9a5-80f631a38a8f | date | Date:
7b886802-0d02-5a9f-9ad8-da4205e6e194 | checkpoint | 3.13 - Landscape (2)
087d861a-ac33-5a99-9133-2da489077fdb | note | ACTIVITY / DESCRIPTION: Hydro-seed / Hydromulch
ced50251-08f1-5808-a1b4-ff6e82306766 | date | Date:
cf35ef9b-77b8-5179-9be8-dc768c2d627e | checkpoint | 3.13 - Landscape (3)
851c9681-9923-5889-8551-1992519214c2 | note | ACTIVITY / DESCRIPTION: Street furniture
52496859-46bb-5845-886a-71886ad7d6ba | date | Date:
906c7998-319d-50c7-bb07-c155bca1e8b3 | checkpoint | 3.13 - Landscape (4)
307cf2ee-fa00-58a1-8d27-d9f5b40676fe | note | ACTIVITY / DESCRIPTION: Maintenance arrangement / period: 3 / 6 / 12 / 18 / 24 months
3d76ca1d-49f4-530b-ae11-4b845347c14c | date | Date:
6617e321-c217-5ab8-9c71-9bd7fc26c64b | section | 4.0 - Practical Completion
6fb7bb23-6dc6-5cc1-b38f-5d21fc3731e0 | checkpoint | 4.1 - Road Fixtures (1)
a78b448f-3d6b-5115-bf91-68755dbd1d50 | note | EXTERNAL REFERENCE: Hold Point (HP)
491ff107-7508-5ded-bcd7-46dc66d1889c | note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
c3234fb8-5a01-54b2-8c31-df4d3772bb61 | date | Date:
ed95d064-cbff-54e7-a314-1d9a50b260ce | signoff | AUTHORITY HOLDPOINT
cda61ea7-d8bf-531b-93e6-b76ccc167a28 | checkpoint | 4.1 - Road Fixtures (2)
68e0deb5-ff03-5ad4-a55e-aa978e856497 | note | EXTERNAL REFERENCE: Hold Point (HP)
4c2e81e9-4907-5868-b8d1-d123752e8ef6 | note | ACTIVITY / DESCRIPTION: Signs
2b632d02-8e86-56ae-9497-1942b780189c | date | Date:
0d76150a-4665-56d4-b923-0760dac6a411 | signoff | AUTHORITY HOLDPOINT
a18bf6e9-148e-5c29-8561-db6238147f98 | checkpoint | 4.1 - Road Fixtures (3)
8460d55e-5f83-5331-ab37-22230156ea0b | note | EXTERNAL REFERENCE: Hold Point (HP)
88345f33-bc9b-505b-98a5-80a9327974ed | note | ACTIVITY / DESCRIPTION: Guide posts
30bfad2f-388f-5f9b-92ba-6d644b77d9e8 | date | Date:
1cd99bde-61ac-5002-9398-3902940ed822 | signoff | AUTHORITY HOLDPOINT
c5695b91-8cf4-572e-9c57-e58004694939 | checkpoint | 4.2 - Safety Barrier Works (1)
45a477e3-6218-5f97-9aec-324bc41f1015 | note | EXTERNAL REFERENCE: Hold Point (HP)
f7ea3589-d893-5f22-8fb1-b84637152666 | note | ACTIVITY / DESCRIPTION: Guardrail
f44c2698-72a0-5bb0-9da0-24d0e9af787d | date | Date:
bf5b8e40-7255-5a5a-9db0-6401fbe79e5a | signoff | AUTHORITY HOLDPOINT
30a71c59-ad05-53e3-a7f9-1e1c56e4a846 | checkpoint | 4.2 - Safety Barrier Works (2)
5816b8bc-7785-502f-93d7-b22dd3287534 | note | EXTERNAL REFERENCE: Hold Point (HP)
6d99b1d0-3c0e-52c2-b183-fbdcf96608c4 | note | ACTIVITY / DESCRIPTION: Wire-rope
d834a3c0-472e-5f71-a98c-db0213e7605a | date | Date:
0d3e1168-a42c-5219-bba7-8cee3a7a2f5c | signoff | AUTHORITY HOLDPOINT
791b0a0c-dbb3-540d-a589-69fa39a4913c | checkpoint | 4.2 - Safety Barrier Works (3)
95c4c178-aad0-5b49-958e-e6d0d0d481b1 | note | EXTERNAL REFERENCE: Hold Point (HP)
2d487db0-bf78-5a7f-ad16-57cea40f5505 | note | ACTIVITY / DESCRIPTION: Motorcycle-safe fixtures
c650ada4-30b7-578a-b8e5-f31b1ba00970 | date | Date:
15999a7a-3d03-5469-a6db-913beb6374ff | signoff | AUTHORITY HOLDPOINT
85c5688a-3665-525a-8f0b-51ce1c8ce4ba | checkpoint | 4.3 - Fences and Gates
8912adce-b3ab-5d7e-8c53-a6455556f9c2 | note | ACTIVITY / DESCRIPTION: Fences and Gates
da41faa5-b8d9-57fb-b5a4-91fce97a9ed7 | date | Date:
aeb9f816-a3f8-52f0-b67c-c44686b0b735 | checkpoint | 4.4 - Quality Ride Test
6930f8cd-1a69-5aeb-8223-009d731a03c5 | note | EXTERNAL REFERENCE: Hold Point (HP)
b7076034-b179-54d3-a933-b8d5ceb054f0 | note | ACTIVITY / DESCRIPTION: Quality Ride Test
1284124b-0fc7-5008-9461-e2d2bf5cf373 | date | Date:
b7b7d7d0-bf51-5cf5-a92d-4a6fe712f993 | signoff | AUTHORITY HOLDPOINT
329676c7-e061-5a56-a75d-10d228394296 | section | 5.0
c4fa4f04-e0ab-56b5-a9a3-67111a83ef99 | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (1)
dff99e57-221f-5d1e-8fb6-c9aafa0555bf | note | EXTERNAL REFERENCE: Hold Point (HP)
8eedd16b-1f11-57f6-9019-0bdbc003a50b | note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
09948306-f65b-5d5a-a0b7-328132f80554 | date | Date:
1e0a1d0e-6302-5136-a54b-bb75dad8852a | signoff | AUTHORITY HOLDPOINT
e3e6566b-2b7c-598a-ab84-5aec11baa9d3 | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (2)
4bb23012-1b28-5815-847a-52fce7be4eac | note | EXTERNAL REFERENCE: Hold Point (HP)
de297435-d6a4-5eab-9aaa-3271b9fbf73a | note | ACTIVITY / DESCRIPTION: Signs, guide posts
503f7189-fc53-5a4d-86b7-2acb91f9cf01 | date | Date:
779aaedb-5d89-5b6f-bed1-d17c91bd2048 | signoff | AUTHORITY HOLDPOINT
b9dc7589-ae80-5f70-9e0d-40e0324e2287 | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (3)
39ec032c-277e-50b6-b1aa-1447b14abf8f | note | EXTERNAL REFERENCE: Hold Point (HP)
91679e6d-2a25-531d-9495-cb4792238201 | note | ACTIVITY / DESCRIPTION: Seal / Asphalt surface
136e4b81-c14c-55b1-91b7-266d280b636a | date | Date:
7292b3de-8ed0-5de7-ad30-40502dd9d94c | signoff | AUTHORITY HOLDPOINT
aae25a75-f669-5e45-8fa4-48bcb753eec5 | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (4)
fbce7819-e701-5581-a44f-36c502e9a0d9 | note | EXTERNAL REFERENCE: Hold Point (HP)
4d3ba9f5-d460-5173-b974-75d6edf1a06f | note | ACTIVITY / DESCRIPTION: Landscape (where applicable)
e560aa7e-540e-5ad9-9d8b-16f7d9db106c | date | Date:
7221322e-81a1-5f8e-9f03-5fd99ff21a58 | signoff | AUTHORITY HOLDPOINT
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
30e35763-5253-53b3-a77e-c12431fd0cb6 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
cb9f02e9-9908-55ca-8cd9-4341da118c0d | textbox | Print Name:
d84717bd-2a80-5c3a-b881-8158314def49 | textbox | Position:
0f7b88f2-0a7d-540b-889a-2ecfe760bed4 | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP