## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-146-CIV-BRUNT-Cement Treated Crushed Rock Layer
ITP Description: |  | Cement Treated Crushed Rock Layer
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2024-04-04
ITP created by: |  | Jason Lee
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | ITP for Brunt Road Project Only
Inspection & Test Plan - Cement Treated Crushed Rock Layer
|  |  | Doc Ref No. ITP-146-CIV-BRUNT-Cement Treated Crushed Rock Layer | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-04-04
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 204 (Dec 2015) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 173 (Oct 2008) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | VicRoads Section 306 (Feb 2023) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries-Materials
2.1 | Material Conformance | Section 306.04 Section 815.04 IFC Drawings | Cementitious Treated material shall comply with the requirements of Section 815. CTCR mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each material type prior to start of works | HP | Nominated Authority | ConQA HP Release
3 | Preliminaries-Documentations
3.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP Signed-off
4 | Pre-construction / Pre-installation Activities
4.1 | Survey Set-Out | IFC Drawings | Area has been set out in accordance with the IFC Drawings. ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP): | Verify | Prior to commencement | HP* | SE/Surveyor | This ITP Signed-off
4.2 | Pre-Commencement of Fill | Section 204.10 (b) | "Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor. The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority. No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority Reference: Previous Layer Lot Number | Visual inspection | Prior to commencement | HP* | SE/PE | This ITP Signed-off
5 | Construction / Installation Activities
5.1 | Test Roll | Section 306.10 Table 306.091 | Shall be test rolled in accordance with Section 173 within maximum allowable working time for the relevant binder and time of year as specified in Table 306.091 Table 306.091 Type GP - 2 hrs (Oct to Apr), 3 hrs (May to Sep) Type GB - 3 hrs (Oct to Apr), 5 hrs (May to Sep) Slag/Lime Blend - 8 hrs (Oct to Apr), 12 hrs (May to Sep) | Testing | Each Lot/Layer | HP | Nominated Authority | ConQA Hold Point Release
5.2 | Compaction Testing | Section 306.09 Table 306.091 | Characteristic Value of Density Ratio Scale A - Not less than 96% Mean Density Ratio Scale B - Not Less than 96% Attach Compaction Test Report | Review Document | Scale A - 6 per lot Scale B - 3 per Lot | IP | SE/Site Supervisor Superintendent | This ITP Signed-off
6 | Post Construction Activities
6.1 | Survey Conformance | VicRoads Section 306.03 | Level tolerances Scale A: Range x = +4, -8mm Max S = 8 mm 80 measurements per lot Level tolerances Scale B: Range x = +6, -12mm Max S = 13 mm 40 measurements per lot Level tolerances Scale C: No point on the subbase surface shall be more than 10 mm above or 25 mm below the specified level. Attach: Survey Conformance Report/Data | Document Review | Each lot | HP* | SE/Surveyor | This ITP Signed-off
6.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed-off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /