## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-147-RAIL-BRUNT-Track Drainage
ITP Description: |  | Track Drainage
Project: |  | Brunt Rd
Discipline (e.g. CIV/STR/RAIL: |  | RAIL
Revision Number: |  | 0
Revision Date: |  | 2024-03-28
ITP created by: |  | Mac Cameron
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | ITP to be used at Brunt Rd Project Only
Inspection & Test Plan - Track Drainage
|  |  | Document Title: ITP-147-RAIL-BRUNT-Track Drainage | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-03-28
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Drawing Pack - Rail Track and Civil | GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | MTM Type Approval Product Register | A9402 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | MTM Track Drainage Standard | L1-CHE-STD-030 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.4 | VicRoads Section 701 | VicRoads Section 701 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.5 | VicRoads Section 705 | VicRoads Section 705 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries - Materials
2.1 | Supply of: - HDPE Slotted Pipe - Geofabric | A9402 L1-CHE-STD-030 Section 701 | To be type approved by MTM. Drainage Pipes to be supplied in accordance to Section 701 To be inspected upon delivery to have no damage. | Visual Measure Document Review | Prior to works commencing | HP | SE/PE | This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets
2.2 | Supply of: - LDPE Liner - Clean Stone - Bedding Sand - Beaching Rock | L1-CHE-STD-030 Section 701 | To meet L1-CHE-STD-030 requirements. Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 & Table 701.092 To be inspected upon delivery to have no damage. | Visual Measure Document Review | Prior to works commencing | HP | SE/PE | This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets
2.3 | Supply of: - Riser - Standard Headwall - Class D Pit Cover | L1-CHE-STD-030 Section 705 | To meet L1-CHE-STD-030 requirements. To be supplied in accordance to Section 705 To be inspected upon delivery to have no damage. | Visual Measure Document Review | Prior to works commencing | HP | SE/PE | This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets
3 | Preliminaries - Procedures & Documentation
3.1 | Primary Documentations | A4263 PTDT Form B - Track Certifier Booking Form | Approved PTDT | Document review and approval | Prior to works commencing | HP | SE/PE | This ITP Signed Off Attach: Approved Permit
3.2 | Pre-Commencement of Work | ITP, Quality Checklist, SWMS | All approved by relevant representative. | Document review and approval | Once (Prior to Works) | HP | SE/PE | This ITP Signed Off Attach: Approved Templates
4 | Pre-Construction Activities
4.1 | Approval of IFC drawings | GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Approved IFC Drawings | Document review and approval | Prior to works commencing | HP | SE/PE | This ITP Signed Off
5 | Construction Activities
5.1 | Survey Track Drainage Alignment & Pits | IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation. | Visual Inspection Survey / Measure | As Task Progresses | HP | SE/PE Supervisor Surveyor | This ITP Signed Off Attach: Survey Records & Photos on site
5.2 | Grade Existing Open Cess Drain | IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Grade through existing cess drain alignment to depth indicated on design documentation. | Visual Inspection Survey / Measure | As Task Progresses | HP | SE/PE Supervisor | This ITP Signed Off Attach: Photos on site
5.3 | Excavate Slotted Pipe Drainage Trench | IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Excavation shall be to the depth indicated on the design documentation | Visual Inspection Survey / Measure | As Task Progresses | HP | SE/PE Supervisor | This ITP Signed Off Attach: Photos on site
5.4 | Place the Following and Compact: - Bedding Sand - Geofabric - Slotted Pipe - Stone | IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Bedding conforming to to Section 701.09 shall be supplied, placed and compacted. Compaction and moisture content testing to be in accordance with Section 701.20 (where applicable). Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three (3). A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. (b) Backfill (i) Material of nominal size 40 mm or less after compaction - Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. (ii) Material of nominal size greater than 40 mm after compaction - Backfill material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. - Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. Trench to be wrapped with geotextile in accordance with the manufacturers specifications and design documentation. Attach: Compaction Test Reports | Visual Inspection Survey / Measure | As Task Progresses | HP | SE/PE Supervisor | This ITP Signed Off Attach: Photos on site Compaction Test Reports
5.5 | Pit, Headwall & Beaching Rock Installation | IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | All stormwater pits shall be provided with a lockable minimum Class D pit lid, grate or ballast cage in accordance with MTM L1-CHE-STD-030 | Visual Inspection Measure | As Task Progresses | HP | SE/PE Supervisor | This ITP Signed Off Attach: Photos on site
6 | Post-Construction Activities
6.1 | Track Certification | MTMF020000-1 – Track Form A T MTMF020000-2 – Track Form B A4549: MAINTAINING TRACK INTEGRITY PROCEDURE | - Track Geometry Conformance Certificate - Track System and Component | Visual Measure Document Review | Once (upon completion of occupation works) | HP | Nominated Authority (MTM Infrastructure Track Certifier) Project Cert III Rail Infrastructure | This ITP Signed Off Attach: Relevant Conformance Certs as per acceptance criteria
6.2 | As-Built Drawings | As-Built Drawing Management Procedure (A8197) Section 701 | IFC drawings (including cables, patches and labels) are marked up with redlines if applicable and supplied the Project and MTM. Provide record of dimensional measurements to demonstrate the drainage is within the tolerances specified in 701.10 | Document review and approval | Once | HP | SE/PE Supervisor | This ITP Signed Off Attach: As-Built Survey Pickup
6.3 | Non-conformance Report (NCR) Closure | MTM Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP | SE/PE | This ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /