## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-146-CIV-BRUNT-Cement Treated Crushed Rock Layer Rev.0 | itp |  |  |  |  | ITP-146-CIV-BRUNT-Cement Treated Crushed Rock Layer Rev.0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-146-CIV-BRUNT-Cement Treated Crushed Rock Layer
label | ITP Description: Cement Treated Crushed Rock Layer
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 4/04/2024
label | ITP created by: Jason Lee
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
label | Reference - VicRoads Section 204 (Dec 2015)
checkpoint | 1.2 - Non Dependent
label | Reference - VicRoads Section 173 (Oct 2008)
checkpoint | 1.3 - Non Dependent
label | Reference - VicRoads Section 306 (Feb 2023)
checkpoint | 1.4 - Non Dependent
label | Reference - IFC Drawings
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Material Conformance
label | Reference - Section 306.04, Section 815.04 IFC Drawings
label | Acceptance Criteria - Cementitious Treated material shall comply with the requirements of Section 815.
label | ○ CTCR mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each material type prior to start of works
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA HP Release
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries-Documentations
checkpoint | 3.1 - IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | Method - Document Review
label | Frequency - Prior to starting Works and at regular intervals
label | Category - HP*
label | Responsibility - All
label | Verifying Documents - This ITP Signed-off
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Survey Set-Out
label | Reference - IFC Drawings
label | Acceptance Criteria - Area has been set out in accordance with the IFC Drawings.
label | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | Method - Verify
label | Frequency - Prior to commencement
label | Category - HP*
label | Responsibility - SE/Surveyor
label | Verifying Documents - This ITP Signed-off
checkpoint | 4.2 - Pre-Commencement of Fill
label | Reference - Section 204.10 (b)
label | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
label | Reference: Previous Layer Lot Number
label | Method - Visual inspection
label | Frequency - Prior to commencement
label | Category - HP*
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed-off
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Test Roll
label | Reference - Section 306.10 Table 306.091
label | Acceptance Criteria - Shall be test rolled in accordance with Section 173 within maximum allowable working time for the relevant binder and time of year as specified in Table 306.091
label | – Table 306.091 –
label | ○ Type GP - 2 hrs (Oct to Apr), 3 hrs (May to Sep)
label | ○ Type GB - 3 hrs (Oct to Apr), 5 hrs (May to Sep)
label | ○ Slag/Lime Blend - 8 hrs (Oct to Apr), 12 hrs (May to Sep)
label | Method - Testing
label | Frequency - Each Lot/Layer
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Compaction Testing
label | Reference - Section 306.09 Table 306.091
label | Acceptance Criteria - Characteristic Value of Density Ratio
label | ○ Scale A - Not less than 96%
label | Mean Density Ratio
label | ○ Scale B - Not Less than 96%
label | Attach Compaction Test Report
label | Method - Review Document
label | Frequency - Scale A - 6 per lot, Scale B - 3 per Lot
label | Category - IP
label | Responsibility - SE/Site Supervisor, Superintendent
label | Verifying Documents - This ITP Signed-off
section | 6. Post Construction Activities
checkpoint | 6.1 - Survey Conformance
label | Reference - VicRoads Section 306.03
label | Acceptance Criteria - Level tolerances Scale A:
label | ○ Range x = +4, -8mm
label | ○ Max S = 8 mm
label | ○ 80 measurements per lot
label | Level tolerances Scale B:
label | ○ Range x = +6, -12mm
label | ○ Max S = 13 mm
label | ○ 40 measurements per lot
label | Level tolerances Scale C:
label | ○ No point on the subbase surface shall be more than 10 mm above or 25 mm below the specified level.
label | Attach: Survey Conformance Report/Data
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - SE/Surveyor
label | Verifying Documents - This ITP Signed-off
checkpoint | 6.2 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed-off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP